## PMO Project Financials
[31 empty] | Report ID: |  | ServiceDelivery-RS-001
| PMO Project Financials | [29 empty] | Execution: |  | 2025-06-17 10:57
| Summary 2025 - All Customers | [29 empty] | Executed By: |  | NETSYNC\lmcchesney
| Status: Open, Closed | [29 empty] | Data Refresh: |  | 2025-06-16 20:00
Alert Level: 0,1,2,3,4
| Abiodun David Babasola, Ali Al-Haddad, Brian Willery, Brittney Antoinette Hickman, Christina Rice, Jason Esry, Jason Matthew Davis, Jennifer Soliz, Jim Blackwell, Joanna Herrera, Joaquin Marroquin, Karyn Hubbard, LaQisha Marshall, Lauren Lanzini Coffey, Marco Lish, Marshall Chuck Pugh, Michelle Duenes, Richard Keith Arnst, Robert McIver, Ryan Scott, Shannon Marie Alvarado, Summer Abunaja, Tray Giddens, Walter Clay Knight, William Chris Roome, Inactive |  |  |  |  | On-Budget |  | 1% - 10% | 11% - 20% |  | 21% - 30% | +30%
Start Date |  | End Date | Job Status | Project Manager | Solution Architect |  | Resources Assigned |  |  | Resources Engaged |  |  | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt |  | Total Amt Posted |  | Hardware Rev | Services Rev | Services GP | Services GP %
07/05/20 |  | 07/05/20 | Open | Reihana Abdelmaksoud | Bryan Geoghan, Christopher Garcia, David Watkins, Jacob Parks, Jeffrey Holman, Joshua Adam Engle, Michael Brett Beggs, Pedro Cantu |  | David Watkins, Michael Brett Beggs |  |  | Darrell Walton, Joel Hubbard, Moises Rodriguez, Vitalii Stepanchenko, William Chris Roome |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00007932 | 1045085 | N/A | 0% | 1050% | 1 | -8 | 30 | 770 | -800% | 30 | 1.5 | 10.5 | 695 | 0 |  | 770 |  | 8419692.49 | 0 | -770 | 0%
05/24/21 |  | 09/30/22 | Open | Brian Willery | Billy Pearson, Firas Abood, Wyley Johnson |  | Brian Willery, Larry Noble, Susan Richardson |  |  | Aaron Abshire, Cory Bradfield, Felipe Waterwall, Luis Alvarez, Victor Estrada |  |  | Susan Richardson | TX-HOU | Klein ISD | J00010667 | UCS and FortiSiem (Fortinet third party) | Training/Knowledge Transfer/Documentation | 95% | 222.9% | 38.8 | -37.7 | 4017.7 | 7522 | -97.16% | 4017.7 | 10 | 86.5 | 6638 | 0 |  | 7522 |  | 437100.6 | 5547.2 | -1974.8 | -35.6%
04/18/22 |  | 04/28/23 | Open | Brian Willery | Charles Brown, David Escamilla |  | Osazee Eweka |  |  | Brian Willery, Charles Brown, Osazee Eweka |  |  | N/A | N/A | Amazon Web Services | J00012911 | AWS Migration Evaluator - Work Order | Closed | 100% | 0% | 24.75 | 24.75 | 2895.75 | 0 | 100% | 2895.75 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 3958.8 | 3958.8 | 100%
04/18/22 |  | 04/28/23 | Open | Brian Willery | Charles Brown, David Escamilla |  | Osazee Eweka |  |  | Brian Willery, Charles Brown, Osazee Eweka |  |  | Susan Richardson | TX-HOU | Amazon Web Services | J00012911 | AWS Migration Evaluator - Work Order | Closed | 0% | 0% | 0 | -43 | 0 | 5475 | 0% | 0 | 0 | 43 | 5475 | 0 |  | 5475 |  | 0 | 3958.8 | -1516.2 | -38.3%
05/22/23 |  | 05/22/23 | Open | Jim Blackwell | Firas Abood |  | Firas Abood, Jim Blackwell, Khalid Abunaja, Meredith A Richardson |  |  | Andy Pham, Jaime Flores, Jim Blackwell, Joshua Hubbard, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio |  |  | N/A | N/A | Houston ISD | J00015369 | Synology Video Storage | Closed | 100% | 40% | 43.75 | 29 | 5781.25 | 1505 | 66.29% | 5781.25 | 2.75 | 17.5 | 1340 | 10.4 |  | 1505 |  | 48323.52 | 4950 | 3434.6 | 69.39%
08/15/22 |  | 05/26/23 | Open | Brian Willery | Matthew Duncan |  | Brian Willery, Charles Brown, Matthew Duncan, Steve J Rodriguez, Xavier A Trevino |  |  | Brian Willery, Charles Brown, Juan Saenz, Osazee Eweka |  |  | N/A | N/A | Amazon Web Services | J00013506 | AWS Cybersecurity Migration | Closed | 100% | 0% | 114.4 | 114.4 | 13156 | 0 | 100% | 13156 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 21218 | 21218 | 100%
08/15/22 |  | 05/26/23 | Open | Brian Willery | Matthew Duncan |  | Brian Willery, Charles Brown, Matthew Duncan, Steve J Rodriguez, Xavier A Trevino |  |  | Brian Willery, Charles Brown, Juan Saenz, Osazee Eweka |  |  | Xavier A Trevino | TX-SOUT | Amazon Web Services | J00013506 | AWS Cybersecurity Migration | Closed | 0% | 0% | 0 | -181 | 0 | 24155 | 0% | 0 | 0 | 181 | 24155 | 0 |  | 24155 |  | 0 | 21218 | -2937 | -13.84%
07/28/23 |  | 08/18/23 | Open | Tray Giddens | David Escamilla |  | Dustin Huffman, Kathleen Brown, Kurt Sell, Luis Ovalles, Tray Giddens |  |  | Brian Willery, Carlo Enriquez, Dionisio Oscar Medina-Marcelino, Luis Ovalles, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Chevron Phillips Chemical | J00014755 | Nutanix cluster for Bartlesville | Closed | 100% | 188.5% | 71.1 | -47.9 | 9950.5 | 17297.5 | -67.37% | 9950.5 | 15 | 134 | 15272.5 | 929.93 |  | 17297.5 |  | 187618.05 | 14050.8 | -4176.63 | -29.73%
02/08/22 |  | 09/15/23 | Open | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Jim Blackwell, Larry Noble |  |  | Cory Bradfield, Craig St. Rose, Jeff Ogbor, Jim Blackwell, Jose R. Duarte, Justin Higgins, Kord Mullins, Luis Alvarez, Victor Estrada |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00011958 | DELL EMC Implementation | Closed | 100% | 257.6% | 53.76 | -68.24 | 5480.45 | 12360.5 | -126.9% | 5480.45 | 16.5 | 138.5 | 10543.5 | 45.84 |  | 12360.5 |  | 1022368.6 | 26001.2 | 13594.86 | 52.29%
09/29/23 |  | 10/27/23 | Open | Jim Blackwell | Firas Abood, Jeremy R Freeman |  | Firas Abood, Jeremy R Freeman, Jim Blackwell |  |  | Ali Al-Haddad, Cory Bradfield, Devon LeMoine, James Adams, Jim Blackwell, Jose R. Duarte, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Truong Nguyen |  |  | N/A | N/A | Houston ISD | J00013099 | UCSX MDS Refresh - Option1 | Closed | 100% | 149.4% | 167.63 | -42.67 | 20144.5 | 29796.25 | -25.45% | 20144.5 | 40.2 | 250.5 | 24526.75 | 20.15 |  | 29796.25 |  | 2139728.68 | 32152 | 2335.6 | 7.264%
09/01/23 |  | 12/15/23 | Open | Jim Blackwell | Firas Abood |  | Cory Bradfield, Cory Bradfield, Jim Blackwell, Kurt Sell, Monica Johnson |  |  | Cory Bradfield, Jaime Flores, Jim Blackwell, Julio C Montoya, Justin Smallwood, Mohammed Al-Shaikhli |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00015034 | Compute Refresh | Closed | 100% | 0% | 89.39 | 89.39 | 11366.85 | 0 | 100% | 11366.85 | 0 | 0 | 0 | 135.41 |  | 0 |  | 162945.49 | 14930.8 | 14795.39 | 99.09%
09/01/23 |  | 12/15/23 | Open | Jim Blackwell | Firas Abood |  | Cory Bradfield, Cory Bradfield, Jim Blackwell, Kurt Sell, Monica Johnson |  |  | Cory Bradfield, Jaime Flores, Jim Blackwell, Julio C Montoya, Justin Smallwood, Mohammed Al-Shaikhli |  |  | Monica Johnson | TX-HOU | Harris County Auditor | J00015034 | Compute Refresh | Closed | 0% | 0% | 0 | -103 | 0 | 14471.25 | 0% | 0 | 14.75 | 117.75 | 12630 | 135.41 |  | 14471.25 |  | 162945.49 | 14930.8 | 324.14 | 2.171%
11/10/22 |  | 01/05/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Baq Alsaedi, Cory Bradfield, Jose R. Duarte, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Central Bank | J00014299 | Cohesity Deployment | Closed | 0% | 0% | 0 | -83.75 | 0 | 11501.25 | 0% | 0 | 8 | 91.75 | 10421.25 | 88.73 |  | 11501.25 |  | 179107.62 | 19417.6 | 7827.62 | 40.31%
11/10/22 |  | 01/05/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Baq Alsaedi, Cory Bradfield, Jose R. Duarte, Tray Giddens |  |  | N/A | N/A | Central Bank | J00014299 | Cohesity Deployment | Closed | 100% | 0% | 93.94 | 93.94 | 12427.5 | 0 | 100% | 12427.5 | 0 | 0 | 0 | 88.73 |  | 0 |  | 179107.62 | 19417.6 | 19328.87 | 99.54%
05/18/23 |  | 01/08/24 | Open | Karyn Hubbard | George Edwin Jacob |  | Alexander Gutman, Arcangelo Fanelli, Beau C. Devillier, Bryan Mullen, Eric Rodriguez, George Edwin Jacob, Juan Pomares, Karyn Hubbard, Tony Dean Skipworth |  |  | Bryan Mullen, Karyn Hubbard, Lauren Lanzini Coffey, Tabais Prater, Tony Dean Skipworth |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | J00015128 | Data Center Core Refresh | Closed | 100% | 276.2% | 80.8 | -134.4 | 9705 | 29342.5 | -166.3% | 9705 | 8 | 223.2 | 28262.5 | 416.54 |  | 29342.5 |  | 208001.68 | 12302.4 | -17456.64 | -141.9%
04/03/23 |  | 01/18/24 | Open | Tray Giddens | David Escamilla |  | David Escamilla, Dustin Huffman, Kathleen Brown, Kurt Sell, Luis Ovalles, Tray Giddens |  |  | Carlo Enriquez, Luis Ovalles, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Chevron Phillips Chemical | J00015266 | Sweeny Nutanix Cluster | Closed | 100% | 50.09% | 121.79 | 72.79 | 14077.75 | 7835 | 59.77% | 14077.75 | 12 | 61 | 6215 | 704.05 |  | 7835 |  | 374682.47 | 21000 | 12460.95 | 59.34%
11/10/22 |  | 01/19/24 | Open | Marco Lish | David Escamilla |  | Cory Bradfield, Cory Bradfield, Larry Noble, Marco Lish, Neel Shah |  |  | Jorge Ortiz Cardozo, Lauren Lanzini Coffey, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Airport System | J00014307 | AWS- Control Tower, Dir Connect & Veem | Closed | 100% | 48.21% | 29.25 | 15.15 | 3836.25 | 1762.5 | 51.79% | 3836.25 | 0 | 14.1 | 1762.5 | 0 |  | 1762.5 |  | 0 | 55542 | 53779.5 | 96.83%
10/16/23 |  | 02/02/24 | Open | Summer Abunaja | Michael Brett Beggs |  | Garrett Curran, Summer Abunaja, Yong Kim |  |  | N/A |  |  | N/A | N/A | Amazon Web Services | J00016683 | AWS Control Tower | Closed | 100% | 0% | 13.5 | 13.5 | 1728 | 0 | 100% | 1728 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 6032.49 | 6032.49 | 100%
07/28/23 |  | 02/02/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, James Adams, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Central Bank | J00015894 | HPE DL380 Gen11 | Closed | 0% | 0% | 0 | -57.25 | 0 | 9361.25 | 0% | 0 | 21.25 | 78.5 | 6605 | 15.68 |  | 9361.25 |  | 62113.32 | 13699.6 | 4322.67 | 31.55%
07/28/23 |  | 02/02/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, James Adams, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Paul Serres, Tray Giddens |  |  | N/A | N/A | Central Bank | J00015894 | HPE DL380 Gen11 | Closed | 100% | 0% | 70 | 70 | 8710 | 0 | 100% | 8710 | 0 | 0 | 0 | 15.68 |  | 0 |  | 62113.32 | 13699.6 | 13683.92 | 99.89%
06/27/22 |  | 03/21/24 | Open | Brian Willery | Jacob Parks, Jeffrey Holman, Kenneth Dieter |  | Beau C. Devillier, Brian Willery, Lauren J Kennewell |  |  | Brian Willery, James Elmore, Juan Saenz, Mohaymen Sodi, Ron Loge, Tony Dean Skipworth |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00013362 | Net-Pro-Srvc - ACI Configurations | Closed | 100% | 56.29% | 1133.13 | 520.29 | 151009.25 | 85537.5 | 45.92% | 151009.25 | 25 | 637.84 | 72023.75 | 258.81 |  | 85537.5 |  | 0 | 49989 | -35807.31 | -71.63%
10/02/23 |  | 03/29/24 | Open | Gena Robbins | Michael Brett Beggs |  | Beau C. Devillier, Gena Robbins, Jeffery Giles, Joshua Osgood, Kristy L Dice, Luis Ovalles |  |  | Austen Howard, Cory Bradfield, Gena Robbins, Jeffery Giles, Joshua Osgood, Luis Ovalles, Raymond Phan, Saravanan Lakshmanan |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00016505 | ISE - HX Compute Nodes | Closed | 100% | 242.4% | 41.25 | -54.25 | 4998.75 | 11087.5 | -131.5% | 4998.75 | 4.5 | 100 | 10817.5 | 501.08 |  | 11087.5 |  | 159523.88 | 11419.8 | -168.78 | -1.478%
02/06/24 |  | 04/01/24 | Open | Summer Abunaja | Steven Walker |  | David Monasmith, David Monasmith, Larry Noble, Luis Ovalles, Steven Walker, Summer Abunaja |  |  | Luis Ovalles |  |  | David Monasmith | TX-HOU | Texas A&M Health Science Center | J00017459 | SQL Support Work Order | Closed | 100% | 44.44% | 9 | 5 | 1180 | 540 | 55.56% | 1180 | 0 | 4 | 540 | 0 |  | 540 |  | 0 | 1795 | 1255 | 69.92%
03/05/24 |  | 04/02/24 | Open | LaQisha Marshall | Firas Abood, Michael Brett Beggs |  | Firas Abood, Kurt Sell, LaQisha Marshall, Michael Brett Beggs, Thomas McClanahan |  |  | Adam Felix, Grayson Rigsby, LaQisha Marshall, Michael Steven Foster, Oscar Gonzalez, Richard Shea, Robert Jones, Steven Shipmon, Tabais Prater, Taylor Poole |  |  | Thomas McClanahan | TX-CEN | Samsung Austin Semiconductor, LLC (SAS) | J00017764 | Uninstall Project | Closed | 100% | 64.75% | 239.4 | 96.4 | 15105 | 8575 | 40.27% | 15105 | 12 | 155 | 7855 | 752.5 |  | 8575 |  | 0 | 19822 | 10494.5 | 52.94%
04/03/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla, Kenneth Dieter, Kinton Connelly |  | Camille Elizabeth Taber, Jeff Barker, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | Aaron Abshire, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | Camille Taber | FL | St. Johns River Water Management District | J00011917 | DC Network Redesign | Closed | 0% | 0% | 0 | -68.25 | 0 | 9056.25 | 0% | 0 | 0 | 68.25 | 9056.25 | 0 |  | 9056.25 |  | 56504.8 | 2781.2 | -6275.05 | -225.6%
05/23/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla |  | Camille Elizabeth Taber, David Escamilla, Jeff Barker, LaQisha Marshall, Tony Dean Skipworth |  |  | LaQisha Marshall |  |  | Camille Taber | FL | St. Johns River Water Management District | J00015630 | Phase 2 | Closed | 0% | 0% | 0 | -18 | 0 | 2250 | 0% | 0 | 0 | 18 | 2250 | 0 |  | 2250 |  | 58048.57 | 0 | -2250 | 0%
04/03/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla, Kenneth Dieter, Kinton Connelly |  | Camille Elizabeth Taber, Jeff Barker, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | Aaron Abshire, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | N/A | N/A | St. Johns River Water Management District | J00011917 | DC Network Redesign | Closed | 100% | 0% | 16.26 | 16.26 | 1840.6 | 0 | 100% | 1840.6 | 0 | 0 | 0 | 0 |  | 0 |  | 56504.8 | 2781.2 | 2781.2 | 100%
05/23/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla |  | Camille Elizabeth Taber, David Escamilla, Jeff Barker, LaQisha Marshall, Tony Dean Skipworth |  |  | LaQisha Marshall |  |  | N/A | N/A | St. Johns River Water Management District | J00015630 | Phase 2 | Closed | 100% | 0% | 30.85 | 30.85 | 5771.25 | 0 | 100% | 5771.25 | 0 | 0 | 0 | 0 |  | 0 |  | 58048.57 | 0 | 0 | 0%
08/14/23 |  | 05/15/24 | Open | LaQisha Marshall | David Watkins, Firas Abood, Michael Brett Beggs |  | Kurt Sell, LaQisha Marshall, Lori Endsley, Romar Roca, Ron Loge, Thomas McClanahan, Tony Dean Skipworth |  |  | LaQisha Marshall, Ron Loge, Tony Dean Skipworth |  |  | Thomas McClanahan | TX-CEN | Samsung Austin Semiconductor, LLC (SAS) | J00016213 | ACI Network refresh | Closed | 100% | 73.72% | 648.74 | 188.49 | 84856.2 | 74426.25 | 29.05% | 84856.2 | 18 | 478.25 | 71676.25 | 310.41 |  | 74426.25 |  | 0 | 127285 | 52548.34 | 41.28%
01/30/24 |  | 05/24/24 | Open | LaQisha Marshall | Amanda Barney, Jacob Parks, Jeffrey Holman |  | Alexander Gutman, Amanda Barney, Ashutosh Patel, Beau C. Devillier, Ibrahim Altaweel, Jacob Sennett, Joshua Osgood, LaQisha Marshall, Rogelio Morgado-Perez, Sean Cowhey, Tavis Jackson |  |  | Ashutosh Patel, Conner MacDonnell, Jacob Sennett, Joshua Osgood, LaQisha Marshall |  |  | Alex Gutman | TX-DAL | Vantage Financial, LLC Division of Peoples Bank | J00017392 | 2023 Palo Alto Renewal | Closed | 100% | 110.3% | 128.75 | -13.25 | 17858.75 | 19820 | -10.29% | 17858.75 | 0 | 142 | 19820 | 0 |  | 19820 |  | 656872.6 | 35360.8 | 15540.8 | 43.95%
07/14/21 |  | 06/10/24 | Open | Robert McIver | David Pena, Edward Padron, Firas Abood, Jose Padilla Jr., Wyley Johnson |  | Christopher Prado, Cory Bradfield, Cory Bradfield, Eric Rodriguez, Felix Martinez, Francisco Medrano, Ivan Uribe, Mario Sanchez, Michael Hilton, Robert McIver |  |  | Alexander Reyes, Carlos Carrillo, Christopher Prado, Cory Bradfield, Erasmo Ramos, Eric Firestone, Felix Martinez, Francisco Medrano, Ivan Uribe, Juan Saenz, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Matthew D'Ambrosio, Michael Hilton, Robert McIver, Sophia Quinter |  |  | Eric Rodriguez | TX-SOUT | McAllen ISD | J00011019 | Multiple PIRs - Multiple PSEs | Closed | 0% | 0% | 0 | -735.52 | 0 | 78832.25 | 0% | 0 | 68.07 | 803.59 | 71528.75 | 2450 |  | 78832.25 |  | 796612.16 | 126433.6 | 45151.35 | 35.71%
07/14/21 |  | 06/10/24 | Open | Robert McIver | David Pena, Edward Padron, Firas Abood, Jose Padilla Jr., Wyley Johnson |  | Christopher Prado, Cory Bradfield, Cory Bradfield, Eric Rodriguez, Felix Martinez, Francisco Medrano, Ivan Uribe, Mario Sanchez, Michael Hilton, Robert McIver |  |  | Alexander Reyes, Carlos Carrillo, Christopher Prado, Cory Bradfield, Erasmo Ramos, Eric Firestone, Felix Martinez, Francisco Medrano, Ivan Uribe, Juan Saenz, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Matthew D'Ambrosio, Michael Hilton, Robert McIver, Sophia Quinter |  |  | N/A | N/A | McAllen ISD | J00011019 | Multiple PIRs - Multiple PSEs | Closed | 100% | 0% | 1120.2 | 1120.2 | 100578.14 | 0 | 100% | 100578.14 | 0 | 0 | 0 | 2450 |  | 0 |  | 796612.16 | 126433.6 | 123983.6 | 98.06%
03/01/23 |  | 06/17/24 | Open | Robert McIver | Steven Walker, Timothy Ramsey |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Ibrahim Altaweel, Robert McIver, Rogelio Morgado-Perez, Ronan Empig, Tom Magboo |  |  | Christopher Brown, Patrick Shea Thompson, Robert McIver |  |  | Eric Rodriguez | TX-SOUT | Edinburg CISD | J00014974 | Active Directory and Azure Audit | Closed | 0% | 0% | 0 | -85 | 0 | 10675 | 0% | 0 | 0 | 85 | 10675 | 229.55 |  | 10675 |  | 0 | 6926.8 | -3977.75 | -57.43%
03/01/23 |  | 06/17/24 | Open | Robert McIver | Steven Walker, Timothy Ramsey |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Ibrahim Altaweel, Robert McIver, Rogelio Morgado-Perez, Ronan Empig, Tom Magboo |  |  | Christopher Brown, Patrick Shea Thompson, Robert McIver |  |  | N/A | N/A | Edinburg CISD | J00014974 | Active Directory and Azure Audit | Closed | 100% | 0% | 40.25 | 40.25 | 5381.25 | 0 | 100% | 5381.25 | 0 | 0 | 0 | 229.55 |  | 0 |  | 0 | 6926.8 | 6697.25 | 96.69%
05/17/24 |  | 06/21/24 | Open | Jennifer Soliz | David Escamilla |  | Cory Bradfield, Cory Bradfield, Diana Berger, Jennifer Soliz, Juan Saenz, Xavier A Trevino |  |  | Cory Bradfield, Jennifer Soliz, Juan Saenz |  |  | Xavier A Trevino | TX-SOUT | Xcell Orthopaedics Physical Therapy | J00018336 | Small Backup Solution | Closed | 100% | 96.99% | 29.9 | 0.9 | 4141.49 | 3845 | 3.01% | 4141.49 | 0 | 29 | 3845 | 0 |  | 3845 |  | 3415.55 | 6296 | 2451 | 38.93%
04/08/24 |  | 06/28/24 | Open | Tray Giddens | David Escamilla |  | Ashley F Freeman, Juan Saenz, Larry Noble, Tray Giddens |  |  | Juan Saenz, Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Amazon Web Services | J00018008 | VMC on AWS POC | Closed | 0% | 0% | 0 | -8.5 | 0 | 1107.5 | 0% | 0 | 0 | 8.5 | 1107.5 | 0 |  | 1107.5 |  | 0 | 10000 | 8892.5 | 88.92%
04/08/24 |  | 06/28/24 | Open | Tray Giddens | David Escamilla |  | Ashley F Freeman, Juan Saenz, Larry Noble, Tray Giddens |  |  | Juan Saenz, Tray Giddens |  |  | N/A | N/A | Amazon Web Services | J00018008 | VMC on AWS POC | Closed | 100% | 0% | 36 | 36 | 4788 | 0 | 100% | 4788 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 10000 | 10000 | 100%
02/26/24 |  | 06/28/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Galveston County | J00017664 | Data Center (DC) Expansion | Closed | 100% | 88.21% | 109.11 | 21.61 | 14112.45 | 12883.75 | 19.81% | 14112.45 | 8.75 | 96.25 | 11702.5 | 0 |  | 12883.75 |  | 302015.22 | 20437.6 | 7553.85 | 36.96%
04/29/24 |  | 07/05/24 | Open | Marco Lish | Michael Brett Beggs |  | Beau C. Devillier, Kirk O'Guinn, Kristy L Dice, Luis Ovalles, Marco Lish, Michael Brett Beggs, Tavis Jackson |  |  | Conner MacDonnell, Dante Torres, Eric Mitchell Frisby, Luis Ovalles, Marco Lish, Sebastian Stanislaw Salata |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00018263 | Additional Video Surveillance Server Install | Closed | 100% | 363.1% | 32.5 | -82.5 | 3347.5 | 9310 | -253.8% | 3347.5 | 3 | 118 | 6970 | 0 |  | 9310 |  | 81293.01 | 5272.32 | -4037.68 | -76.58%
07/03/23 |  | 07/08/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs |  | Amy Martinez-Nagy, Daniel Saenz, David Avila, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Ivan Uribe, Mario Sanchez, Michael Brett Beggs, Robert McIver, Ruben Cantu, Steve J Rodriguez |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Edgar Gonzalez, Felix Martinez, Francisco Hernandez, Francisco Rosa, Jorge Robert Rangel, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Mark Rosa, Matthew D'Ambrosio, Moises Rodriguez, Robert McIver, Roger Guerra, Ruben Cantu, William Brown |  |  | Eric Rodriguez | TX-SOUT | La Joya ISD | J00014847 | E-Rate 25 (2022-2023) Category 2 | Closed | 0% | 0% | 0 | -872.75 | 0 | 81999 | 0% | 0 | 73.4 | 946.15 | 77010 | 8895.92 |  | 81999 |  | 2083295.29 | 299827.53 | 208932.61 | 69.68%
07/03/23 |  | 07/08/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs |  | Amy Martinez-Nagy, Daniel Saenz, David Avila, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Ivan Uribe, Mario Sanchez, Michael Brett Beggs, Robert McIver, Ruben Cantu, Steve J Rodriguez |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Edgar Gonzalez, Felix Martinez, Francisco Hernandez, Francisco Rosa, Jorge Robert Rangel, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Mark Rosa, Matthew D'Ambrosio, Moises Rodriguez, Robert McIver, Roger Guerra, Ruben Cantu, William Brown |  |  | N/A | N/A | La Joya ISD | J00014847 | E-Rate 25 (2022-2023) Category 2 | Closed | 100% | 0% | 1176.06 | 1176.06 | 93868.09 | 0 | 100% | 93868.09 | 0 | 0 | 0 | 8895.92 |  | 0 |  | 2083295.29 | 299827.53 | 290931.61 | 97.03%
03/25/24 |  | 07/12/24 | Open | Joaquin Marroquin | Michael Brett Beggs |  | Cory Bradfield, Cory Bradfield, Joaquin Marroquin, Larry Noble, Lonnie Owens |  |  | An Le, Cory Bradfield, Daniel Quade, Joaquin Marroquin, Luis Ovalles, Michael Torres |  |  | Lonnie Owens | TX-CEN | Boerne ISD | J00017856 | Pure Storage FlashArray Installation | Closed | 100% | 50.68% | 166.25 | 93 | 21612.75 | 10216.25 | 55.94% | 21612.75 | 11 | 84.25 | 8881.25 | 0 |  | 10216.25 |  | 238441.2 | 33326.4 | 23110.15 | 69.34%
01/18/24 |  | 07/12/24 | Open | Marco Lish | George Edwin Jacob |  | George Edwin Jacob, Jeff Barker, Jonathan Pendrich, Luis Ovalles, Marco Lish |  |  | Luis Ovalles, Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Oncor Electric Delivery Company LLC | J00017315 | Nutanix Upgrade | Closed | 100% | 48.38% | 146.25 | 85.5 | 19411.25 | 9363.75 | 58.46% | 19411.25 | 10 | 70.75 | 8013.75 | 0 |  | 9363.75 |  | 0 | 28346.8 | 18983.05 | 66.97%
01/10/24 |  | 07/26/24 | Open | Christina Rice | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Christina Rice, Christina Rice, Mark Forehand, Michael Brett Beggs, Ron Loge, William Davenport |  |  | Christina Rice, Jarshawn Newsome, Ron Loge |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | J00016982 | UTSW: ARDC DMZ to ACI | Closed | 100% | 40.58% | 128.75 | 77.5 | 17123.75 | 8086.25 | 60.19% | 17123.75 | 1 | 52.25 | 7911.25 | 0 |  | 8086.25 |  | 0 | 25171.6 | 17085.35 | 67.88%
08/25/23 |  | 08/05/24 | Open | Joaquin Marroquin | Steven Walker |  | Christopher Brown, Christopher Brown, Joaquin Marroquin, Xavier A Trevino |  |  | Christopher Brown, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Del Mar College | J00014476 | Work Order - Microsoft Endpoint Manager | Closed | 100% | 127.8% | 45 | -12.5 | 6025 | 7702.5 | -27.78% | 6025 | 0 | 57.5 | 7702.5 | 0 |  | 7702.5 |  | 0 | 7534.8 | -167.7 | -2.226%
05/12/23 |  | 08/09/24 | Open | Christina Rice | George Edwin Jacob |  | Beau C. Devillier, Christina Rice, Christina Rice, George Edwin Jacob, Kristy L Dice, Ron Loge |  |  | Christina Rice, Ron Loge |  |  | Kristy L Dice | TX-DAL | UT Southwestern Medical Center | J00015440 | UTSW: Integration of VMWare to ACI | Closed | 0% | 0% | 0 | -88.75 | 0 | 13418.75 | 0% | 0 | 0 | 88.75 | 13418.75 | 0 |  | 13418.75 |  | 0 | 33480.8 | 20062.05 | 59.92%
05/12/23 |  | 08/09/24 | Open | Christina Rice | George Edwin Jacob |  | Beau C. Devillier, Christina Rice, Christina Rice, George Edwin Jacob, Kristy L Dice, Ron Loge |  |  | Christina Rice, Ron Loge |  |  | N/A | N/A | UT Southwestern Medical Center | J00015440 | UTSW: Integration of VMWare to ACI | Closed | 100% | 0% | 181.25 | 181.25 | 24106.25 | 0 | 100% | 24106.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 33480.8 | 33480.8 | 100%
04/10/24 |  | 08/09/24 | Open | Jennifer Soliz | David Escamilla |  | Jennifer Soliz, Joseph Redford Scowden, Larry Noble, Luis Ovalles |  |  | Jennifer Soliz, Luis Ovalles |  |  | Joseph Scowden | TX-HOU | DDI Leasing Inc dba DDI Capital | J00017661 | Revision One - UCS | Closed | 0% | 0% | 0 | -141.5 | 0 | 18927.5 | 0% | 0 | 0 | 141.5 | 18927.5 | 0 |  | 18927.5 |  | 517363.31 | 37229.84 | 18302.34 | 49.16%
04/10/24 |  | 08/09/24 | Open | Jennifer Soliz | David Escamilla |  | Jennifer Soliz, Joseph Redford Scowden, Larry Noble, Luis Ovalles |  |  | Jennifer Soliz, Luis Ovalles |  |  | N/A | N/A | DDI Leasing Inc dba DDI Capital | J00017661 | Revision One - UCS | Closed | 100% | 0% | 206.25 | 206.25 | 27693.5 | 0 | 100% | 27693.5 | 0 | 0 | 0 | 0 |  | 0 |  | 517363.31 | 37229.84 | 37229.84 | 100%
10/09/23 |  | 08/14/24 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Graylon Hampton, Steven Walker, Timothy Rosser, William Birdsong, Wyley Johnson |  | Camille Elizabeth Taber, Christopher Butler, Graylon Hampton, Kreshnik Memaj, Shannon Marie Alvarado, Steven Walker |  |  | Hamzeh Tahat, Kevin Curtis, Kolawole Ayeni, Kreshnik Memaj, Matthew D'Ambrosio, Ryan Scott, Shannon Marie Alvarado |  |  | Camille Taber | FL | Polk County Sheriffs Office | J00016072 | Backend Network for VVS | Closed | 100% | 105.1% | 304.51 | -11.49 | 39026.55 | 35732.5 | -3.773% | 39026.55 | 4 | 320 | 35232.5 | 13627.5 |  | 35732.5 |  | 333965.89 | 0 | -49360 | 0%
02/20/23 |  | 08/28/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs, Timothy Ramsey, Wyley Johnson |  | David Avila, Diana Berger, Eric Rodriguez, Ivan Uribe, Robert McIver, Romar Roca, Ruben Cantu |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Conner MacDonnell, Felix Martinez, Francisco Hernandez, Francisco Rosa, Ivan Uribe, Jesus Angel Cantu, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Mark Rosa, Oscar Garcia, Robert McIver, Roger Guerra, Romar Roca, Ruben Cantu, William Brown |  |  | David Avila | TX-SOUT | Rio Grande City Grulla ISD | J00013577 | x15 Campus - Network Upgrades | Closed | 0% | 0% | 0 | -680.04 | 0 | 68816.3 | 0% | 0 | 161.87 | 841.91 | 57679.8 | 1430.08 |  | 68816.3 |  | 885850.85 | 28782.6 | -41463.78 | -144.1%
02/20/23 |  | 08/28/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs, Timothy Ramsey, Wyley Johnson |  | David Avila, Diana Berger, Eric Rodriguez, Ivan Uribe, Robert McIver, Romar Roca, Ruben Cantu |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Conner MacDonnell, Felix Martinez, Francisco Hernandez, Francisco Rosa, Ivan Uribe, Jesus Angel Cantu, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Mark Rosa, Oscar Garcia, Robert McIver, Roger Guerra, Romar Roca, Ruben Cantu, William Brown |  |  | N/A | N/A | Rio Grande City Grulla ISD | J00013577 | x15 Campus - Network Upgrades | Closed | 100% | 0% | 470.88 | 470.88 | 40630.5 | 0 | 100% | 40630.5 | 0 | 0 | 0 | 1430.08 |  | 0 |  | 885850.85 | 28782.6 | 27352.52 | 95.03%
09/06/24 |  | 09/06/24 | Open | Richard Keith Arnst | Steven Walker |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Richard Keith Arnst |  |  | Christopher Brown, Richard Keith Arnst, Ron Loge |  |  | Eric Rodriguez | TX-SOUT | Great Hearts Texas | J00015293 | MS O365 & AD Migration | Closed | 0% | 0% | 0 | -472 | 0 | 63455 | 0% | 0 | 0 | 472 | 63455 | 99.74 |  | 63455 |  | 14700 | 55249.2 | -8305.54 | -15.03%
09/06/24 |  | 09/06/24 | Open | Richard Keith Arnst | Steven Walker |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Richard Keith Arnst |  |  | Christopher Brown, Richard Keith Arnst, Ron Loge |  |  | N/A | N/A | Great Hearts Texas | J00015293 | MS O365 & AD Migration | Closed | 100% | 0% | 316.25 | 316.25 | 42061.25 | 0 | 100% | 42061.25 | 0 | 0 | 0 | 99.74 |  | 0 |  | 14700 | 55249.2 | 55149.46 | 99.82%
09/10/24 |  | 09/10/24 | Open | Tray Giddens | David Escamilla, Mark J Chambliss |  | Christopher Ceykovsky, Jaime B Flores, Jaime Flores, John Stephen Kurkjian, Justin Cornish , Larry Noble, Susan Richardson, Tray Giddens |  |  | Bryant Bush, Hector Rivera, Jaime Flores, John Stephen Kurkjian, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Tray Giddens |  |  | Susan Richardson | TX-HOU | University of Houston Clear Lake | J00016300 | VMware and VoIP upgrades | Closed | 100% | 122.9% | 156.25 | -24.25 | 21246.25 | 24800 | -15.52% | 21246.25 | 11.5 | 192 | 24110 | 0 |  | 24800 |  | 67677.74 | 29881.52 | 5081.52 | 17.01%
07/17/24 |  | 10/01/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Jaclyn Pias, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, Tray Giddens |  |  | Jaclyn Pias | TX-HOU | Houston Federal Credit Union | J00018673 | 2024 VDI Project Extension SSO Adjustment | Closed | 100% | 109.6% | 33.75 | 13.75 | 4688.75 | 4935 | 40.74% | 4688.75 | 17 | 37 | 2640 | 0 |  | 4935 |  | 0 | 6288.96 | 1353.96 | 21.53%
01/08/24 |  | 10/11/24 | Open | Jennifer Soliz | Emilio Carrillo, George Edwin Jacob, Timothy Ramsey, Wyley Johnson |  | Emilio Carrillo, George Edwin Jacob, Hannah Paul, Jennifer Soliz, Larry Noble, Mohammed Almoola, Raul Velazquez, Timothy Ramsey, Tony Dean Skipworth, Wyley Johnson |  |  | An Le, Angel Alicea, Angel Alicea-Torres, Anthony Lange, Daniel Quade, Hector Rivera, James Danner, Jennifer Soliz, John Senkulics, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Michael Torres, Mohammed Almoola, Paul Serres, Raul Velazquez, Ron Loge, Tony Dean Skipworth |  |  | Hannah Edmunds | TX-CEN | Comal ISD | J00016474 | DC Nexus Equipment | Closed | 100% | 178.1% | 347.78 | -208.47 | 40978.53 | 71836.25 | -59.94% | 40978.53 | 63 | 619.25 | 67081.25 | 0 |  | 71836.25 |  | 469327.71 | 56983.6 | -14852.65 | -26.06%
08/28/24 |  | 10/31/24 | Open | Walter Clay Knight | George Edwin Jacob |  | Jeff Barker, Joseph Boglino |  |  | Juan Saenz, Osazee Eweka, Walter Clay Knight |  |  | Joseph Boglino | US-FED | Amazon Web Services | J00018897 | AWS POC | Cancelled | 0% | 0% | 0 | -12.25 | 0 | 1591.25 | 0% | 0 | 0 | 12.25 | 1591.25 | 0 |  | 1591.25 |  | 0 | 23584.9 | 21993.65 | 93.25%
08/28/24 |  | 10/31/24 | Open | Walter Clay Knight | George Edwin Jacob |  | Jeff Barker, Joseph Boglino |  |  | Juan Saenz, Osazee Eweka, Walter Clay Knight |  |  | N/A | N/A | Amazon Web Services | J00018897 | AWS POC | Cancelled | 5% | 0% | 109.25 | 109.25 | 14606.25 | 0 | 100% | 14606.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 23584.9 | 23584.9 | 100%
02/07/24 |  | 11/01/24 | Open | Shannon Marie Alvarado | Matthew Duncan |  | Jamie Lewis, Juan Saenz, Kathryn Santoni Menza, Matthew Duncan, Osazee Eweka, Shannon Marie Alvarado, William Isaac Sears |  |  | Juan Saenz, Osazee Eweka, Shannon Marie Alvarado |  |  | Jamie Lewis | US-SP | Amazon Web Services | J00017464 | Amazon Web Services (AWS) | Closed | 0% | 0% | 0 | -120.5 | 0 | 15997.5 | 0% | 0 | 0 | 120.5 | 15997.5 | 0 |  | 15997.5 |  | 0 | 123456.79 | 107459.29 | 87.04%
02/07/24 |  | 11/01/24 | Open | Shannon Marie Alvarado | Matthew Duncan |  | Jamie Lewis, Juan Saenz, Kathryn Santoni Menza, Matthew Duncan, Osazee Eweka, Shannon Marie Alvarado, William Isaac Sears |  |  | Juan Saenz, Osazee Eweka, Shannon Marie Alvarado |  |  | N/A | N/A | Amazon Web Services | J00017464 | Amazon Web Services (AWS) | Closed | 100% | 0% | 382.91 | 382.91 | 50911.75 | 0 | 100% | 50911.75 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 123456.79 | 123456.79 | 100%
12/13/21 |  | 11/29/24 | Open | Brian Willery | Michael Brett Beggs |  | Brian Willery, Jason Osuna, Larry Noble |  |  | Brian Willery |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00011889 | New Shelf - ESeries 12x12 TB Drives | Closed | 100% | 1.736% | 14.4 | 14.15 | 1596 | 23.75 | 98.26% | 1596 | 0 | 0.25 | 23.75 | 0 |  | 23.75 |  | 25127.9 | 2709 | 2685.25 | 99.12%
12/13/21 |  | 11/29/24 | Open | Brian Willery | Michael Brett Beggs |  | N/A |  |  | Brian Willery |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00011890 | New Shelf - ESeries 12x12 TB Drives | Closed | 100% | 5.208% | 14.4 | 13.65 | 1596 | 71.25 | 94.79% | 1596 | 0 | 0.75 | 0 | 0 |  | 71.25 |  | 59785.1 | 2709 | 2637.75 | 97.37%
06/03/24 |  | 11/29/24 | Open | Marco Lish | Firas Abood |  | Cory Bradfield, Cory Bradfield, Larry Noble, Marco Lish, Neel Shah |  |  | Cory Bradfield, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00018457 | Moving GIS Cluster | Closed | 100% | 39.73% | 98.15 | 64.65 | 13090.75 | 5215 | 65.87% | 13090.75 | 5.5 | 39 | 4472.5 | 0 |  | 5215 |  | 0 | 20617.2 | 15402.2 | 74.71%
07/28/23 |  | 12/02/24 | Open | LaQisha Marshall | Kenneth Dieter, Naveed Hussain |  | Cory Bradfield, Cory Bradfield, Hannah Paul, LaQisha Marshall, Naveed Hussain, Steve J Rodriguez |  |  | Cory Bradfield, Hector Rivera, Jaime Flores, Justin Cornish, LaQisha Marshall, Sarah Beatrice Williamson |  |  | Hannah Edmunds | TX-CEN | Texas Department of Transportation | J00010567 | PO 601330000075694 - Houston Transtar VDI | Closed | 100% | 136% | 352.29 | -51.71 | 38676.45 | 61727.5 | -14.68% | 38676.45 | 75 | 479 | 51665 | 42.09 |  | 61727.5 |  | 464234.12 | 54362.4 | -7407.19 | -13.63%
01/30/24 |  | 12/06/24 | Open | Marco Lish | Firas Abood |  | Cory Bradfield, Cory Bradfield, Jaime B Flores, Jaime Flores, Larry Noble, Marco Lish, Neel Shah |  |  | Cory Bradfield, Hector Rivera, Jaime Flores, Kenneth Stevenson, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00017295 | HITS Enterprise HX Expansion | Closed | 100% | 70.45% | 87.3 | 36.55 | 10430.4 | 7570 | 41.87% | 10430.4 | 10.75 | 61.5 | 6156.25 | 35.1 |  | 7570 |  | 19182.2 | 16427.6 | 8822.5 | 53.71%
05/01/24 |  | 12/13/24 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Karen Grant-Dennison, William Davenport |  |  | Austen Howard, Carlo Enriquez, Cason Spencer, Jason Esry, Joan Brito, Joshua Osgood, Kebret Eshetu, Luis Ovalles, Patrick Shea Thompson, Quy Le, Remijio Hernandez, William Chris Roome |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00018256 | Data Centers Modernization Project | Closed | 100% | 0% | 418.38 | 418.38 | 47059.1 | 0 | 100% | 47059.1 | 0 | 0 | 0 | 0 |  | 0 |  | 1538061.88 | 72866 | 72866 | 100%
05/01/24 |  | 12/13/24 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Karen Grant-Dennison, William Davenport |  |  | Austen Howard, Carlo Enriquez, Cason Spencer, Jason Esry, Joan Brito, Joshua Osgood, Kebret Eshetu, Luis Ovalles, Patrick Shea Thompson, Quy Le, Remijio Hernandez, William Chris Roome |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00018256 | Data Centers Modernization Project | Closed | 0% | 0% | 0 | -307.5 | 0 | 37342.5 | 0% | 0 | 3 | 310.5 | 37162.5 | 0 |  | 37342.5 |  | 1538061.88 | 72866 | 35523.5 | 48.75%
10/09/24 |  | 12/17/24 | Open | LaQisha Marshall | David Goss |  | Christi D Hubbard, David Goss, LaQisha Marshall, Larry Noble |  |  | Cory Bradfield, David Goss, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Pflugerville ISD | J00019162 | ESXi Hosts Upgrade | Closed | 100% | 62.22% | 22.5 | 8.5 | 2992.5 | 1825 | 37.78% | 2992.5 | 0 | 14 | 885 | 0 |  | 1825 |  | 0 | 4398.8 | 2573.8 | 58.51%
12/29/23 |  | 12/20/24 | Open | Jennifer Soliz | Kenneth Dieter |  | Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Andrew G Wagenhofer, Christopher Knipe, Jennifer Soliz, Michael Hilton, Ron Loge, Sarah Beatrice Williamson |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00009890 | 2194850 - ACI NERC | Cancelled | 95% | 48.44% | 398.42 | 215.42 | 45052.12 | 32855 | 54.07% | 45052.12 | 10 | 193 | 31105 | 279.63 |  | 32855 |  | 860337.8 | 74726 | 41591.37 | 55.66%
03/18/24 |  | 12/27/24 | Open | Shannon Marie Alvarado | Amanda Barney, David Watkins |  | Beau C. Devillier, Bryan Mullen, David Watkins, Jeffery Alan Jorzig, Jeffery Jorzig, Katharine McCarley, Katherine McCarley, Shannon Marie Alvarado |  |  | Bradley Buchanan, Bryan Mullen, Carlo Enriquez, Jeffery Alan Jorzig, Kebret Eshetu, Quentin Sowels, Quy Le, Shannon Marie Alvarado, William Chris Roome |  |  | Katie McCarley | TX-DAL | Winstead PC | J00017832 | SD-WAN Advice, Implementation & Migration MT&E | Closed | 0% | 0% | 0 | -519.25 | 0 | 64021.25 | 0% | 0 | 1 | 520.25 | 63961.25 | 0 |  | 64021.25 |  | 53701.2 | 0 | -64021.25 | 0%
03/18/24 |  | 12/27/24 | Open | Shannon Marie Alvarado | Amanda Barney, David Watkins |  | Beau C. Devillier, Bryan Mullen, David Watkins, Jeffery Alan Jorzig, Jeffery Jorzig, Katharine McCarley, Katherine McCarley, Shannon Marie Alvarado |  |  | Bradley Buchanan, Bryan Mullen, Carlo Enriquez, Jeffery Alan Jorzig, Kebret Eshetu, Quentin Sowels, Quy Le, Shannon Marie Alvarado, William Chris Roome |  |  | N/A | N/A | Winstead PC | J00017832 | SD-WAN Advice, Implementation & Migration MT&E | Closed | 100% | 0% | 0 | -4.5 | 244.27 | 562.5 | 0% | 244.27 | 0 | 4.5 | 0 | 0 |  | 562.5 |  | 53701.2 | 0 | -562.5 | 0%
12/08/23 |  | 01/31/25 | Open | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Jim Blackwell, Larry Noble |  |  | Ali Al-Haddad, Andy Pham, Anthony Lange, Bryant Bush, Cory Bradfield, David Dobbs, Hector Rivera, Jerald Garner, Jim Blackwell, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nicolas Garakani, Paul Serres |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016827 | Dell Powerscale Deployment | Closed | 100% | 87.09% | 182.2 | 70.03 | 21839.6 | 15891.45 | 38.44% | 21839.6 | 46.5 | 158.67 | 9928.95 | 136.5 |  | 15891.45 |  | 2758826.44 | 35341.2 | 19313.25 | 54.65%
04/15/24 |  | 01/31/25 | Open | Jim Blackwell | Aman Khan, Firas Abood |  | Aman Khan, Ashley F Freeman, Jim Blackwell, Jorge Ortiz Cardozo, Larry Noble, Moe Izaks, Mohaymen Sodi |  |  | Jim Blackwell, Jorge Ortiz Cardozo, Mohaymen Sodi, Nicolas Garakani |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018027 | Cisco Core Network Refresh | Closed | 100% | 53.33% | 236.25 | 110.25 | 26411.25 | 15587.5 | 46.67% | 26411.25 | 0 | 126 | 14462.5 | 0 |  | 15587.5 |  | 306255.45 | 39640.64 | 24053.14 | 60.68%
11/20/23 |  | 02/18/25 | Open | Shannon Marie Alvarado | David Watkins, Kenneth Dieter |  | Beau C. Devillier, Mohammad Jilani, Mohaymen Sodi, Ron Loge, Saravanan Lakshmanan, Shannon Marie Alvarado, Shawn Sutton |  |  | Carlo Enriquez, Christina Rice, Mohammad Jilani, Mohaymen Sodi, Moises Rodriguez, Ron Loge, Saravanan Lakshmanan, Shannon Marie Alvarado |  |  | Shawn Sutton | TX-DAL | Ector County ISD | J00013551 | ECISD: DC Stretch & Move - Option 1 w\ WLCs (BBT) | Closed | 100% | 113.8% | 292.16 | -40.34 | 43309 | 46072.5 | -13.81% | 43309 | 0 | 332.5 | 33523.75 | 0 |  | 46072.5 |  | 284981.9 | 44741.24 | -1331.26 | -2.975%
10/22/24 |  | 02/21/25 | Open | Marco Lish | Michael Brett Beggs |  | Beau C. Devillier, Kristy L Dice, Marco Lish |  |  | Joshua Hubbard, Luis Ovalles, Marco Lish, Phillip Ma Lim |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00019260 | Video Surveillance Server Deployment | Closed | 100% | 80% | 27.5 | 8.5 | 2982.5 | 2463.75 | 30.91% | 2982.5 | 3 | 22 | 1530 | 0 |  | 2463.75 |  | 32551.47 | 4697.44 | 2233.69 | 47.55%
07/22/24 |  | 02/21/25 | Open | Marco Lish | Michael Brett Beggs |  | Beau C. Devillier, Joshua Parker, Marco Lish, Michael Brett Beggs |  |  | Marco Lish |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00018693 | Dell ME for Video | Closed | 100% | 64.39% | 26.4 | 9.4 | 3340 | 2125 | 35.61% | 3340 | 0 | 17 | 1406.25 | 0 |  | 2125 |  | 483334.92 | 5260.4 | 3135.4 | 59.6%
05/06/24 |  | 02/27/25 | Open | Abiodun David Babasola | Steven Walker |  | Abiodun David Babasola, Beau C. Devillier, Christopher Brown, Christopher Brown, David Babasola, Liberty Reyes Tumibay, Mark Forehand, Steven Walker |  |  | Abiodun David Babasola, Christopher Brown, Liberty Reyes Tumibay |  |  | Mark Forehand | TX-DAL | City of Richardson | J00018287 | Active Directory (AD) Assessment Remediation | Closed | 100% | 112.1% | 70 | -8.5 | 9310 | 10457.5 | -12.14% | 9310 | 0 | 78.5 | 8125 | 0 |  | 10457.5 |  | 0 | 23885.68 | 13428.18 | 56.22%
10/02/23 |  | 03/07/25 | Open | Brian Willery | Joshua Adam Engle, Michael Brett Beggs |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Ron Loge |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00016545 | ACI Tenant Builds With Optics | Closed | 100% | 11.87% | 113.75 | 100.25 | 15128.75 | 1987.5 | 88.13% | 15128.75 | 0 | 13.5 | 1518.75 | 0 |  | 1987.5 |  | 3730.32 | 23792.8 | 21805.3 | 91.65%
12/09/24 |  | 03/10/25 | Open | Abiodun David Babasola | Steven Walker |  | Abiodun David Babasola, Christopher Brown, Christopher Brown, David Babasola, Joshua Parker |  |  | Abiodun David Babasola, Christopher Brown |  |  | Joshua Parker | TX-DAL | Richardson ISD | 200000271 | N/A | Closed | 100% | 80% | 43.75 | 8.75 | 5818.75 | 4635 | 20% | 5818.75 | 0 | 35 | 0 | 0 |  | 4635 |  | 0 | 9150.8 | 4515.8 | 49.35%
09/26/24 |  | 03/10/25 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Luis Ovalles, Michael Brett Beggs, William Davenport |  |  | Caleb Henry, Jason Esry, Luis Ovalles, Noah Trump |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00019064 | Veeam Repository Server Installation | Closed | 100% | 83.54% | 23.94 | 5.94 | 2584 | 2242.5 | 24.81% | 2584 | 2 | 20 | 120 | 0 |  | 2242.5 |  | 20750.4 | 4286.8 | 2044.3 | 47.69%
09/26/24 |  | 03/10/25 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Luis Ovalles, Michael Brett Beggs, William Davenport |  |  | Caleb Henry, Jason Esry, Luis Ovalles, Noah Trump |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00019064 | Veeam Repository Server Installation | Closed | 0% | 0% | 0 | -3 | 0 | 395 | 0% | 0 | 0 | 3 | 395 | 0 |  | 395 |  | 20750.4 | 4286.8 | 3891.8 | 90.79%
12/09/24 |  | 03/28/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Tray Giddens |  |  | Christopher Brown, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200000254 | N/A | Closed | 100% | 96.47% | 42.5 | 1.5 | 5652.5 | 5460 | 3.529% | 5652.5 | 0 | 41 | 0 | 0 |  | 5460 |  | 0 | 7426 | 1966 | 26.47%
06/26/23 |  | 04/01/25 | Open | Joanna Herrera | David Escamilla |  | David D Tijerina, David Escamilla, Joanna Herrera, Juan Saenz, Kurt Sell |  |  | Joanna Herrera, Juan Saenz |  |  | David D Tijerina | TX-CEN | Bexar County | J00015835 | AWS PinPoint deployment WO 220050892 | Closed | 100% | 96.43% | 17.63 | 0.63 | 2353.75 | 2285 | 3.573% | 2353.75 | 0 | 17 | 877.5 | 0 |  | 2285 |  | 0 | 3843.2 | 1558.2 | 40.54%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, LaQisha Marshall, Tony Dean Skipworth, Yong Kim |  |  | LaQisha Marshall, Nick Varga, Tony Dean Skipworth |  |  | Jay Bucsa | CA-LAX | Chaffey Joint Union High School District | J00017862 | Nexus 9336C-FX2-E Deployment | Closed | 0% | 0% | 0 | -87.25 | 0 | 11541.25 | 0% | 0 | 0 | 87.25 | 11541.25 | 0 |  | 11541.25 |  | 152510.72 | 19856.72 | 8315.47 | 41.88%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, Jeff Barker, Juan Pomares, Karl Houston, Karyn Hubbard, LaQisha Marshall, Luis Ovalles, Yong Kim |  |  | Juan Pomares, LaQisha Marshall, Luis Ovalles |  |  | Jay Bucsa | CA-LAX | Chaffey Joint Union High School District | J00017864 | Cisco Unified Computing System (UCS) | Closed | 0% | 0% | 0 | -178.75 | 0 | 24823.75 | 0% | 0 | 20 | 198.75 | 23023.75 | 0 |  | 24823.75 |  | 587800.38 | 39652.88 | 14829.13 | 37.4%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, LaQisha Marshall, Tony Dean Skipworth, Yong Kim |  |  | LaQisha Marshall, Nick Varga, Tony Dean Skipworth |  |  | N/A | N/A | Chaffey Joint Union High School District | J00017862 | Nexus 9336C-FX2-E Deployment | Closed | 100% | 20.79% | 93.78 | 74.28 | 12172.7 | 2617.5 | 79.21% | 12172.7 | 0 | 19.5 | 0 | 0 |  | 2617.5 |  | 152510.72 | 19856.72 | 17239.22 | 86.82%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, Jeff Barker, Juan Pomares, Karl Houston, Karyn Hubbard, LaQisha Marshall, Luis Ovalles, Yong Kim |  |  | Juan Pomares, LaQisha Marshall, Luis Ovalles |  |  | N/A | N/A | Chaffey Joint Union High School District | J00017864 | Cisco Unified Computing System (UCS) | Closed | 100% | 29.54% | 222.6 | 156.85 | 33488.09 | 8813.75 | 70.46% | 33488.09 | 0 | 65.75 | 0 | 0 |  | 8813.75 |  | 587800.38 | 39652.88 | 30839.13 | 77.77%
05/10/24 |  | 04/04/25 | Closed | LaQisha Marshall | Steven Walker |  | Christi D Hubbard, LaQisha Marshall, Larry Noble, Lori Endsley, Luis Ovalles |  |  | LaQisha Marshall, Luis Ovalles, Sophia Quinter |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00018043 | PKI Environment Reconfiguration | Closed | 100% | 55% | 116.36 | 52.36 | 1437.5 | 8597.5 | 45% | 1437.5 | 0 | 64 | 7048.75 | 0 |  | 8597.5 |  | 0 | 11527.6 | 2930.1 | 25.42%
10/04/23 |  | 04/07/25 | Open | Christina Rice | Michael Brett Beggs |  | Austen New LN: Howard Cockerham, Beau C. Devillier, Christina Rice, Christina Rice, Cory Bradfield, Cory Bradfield, Devin Moreno, Gena Robbins, Jeffery Giles, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Michael Brett Beggs, Shawn Sutton |  |  | Austen Howard, Christina Rice, Conner MacDonnell, Cory Bradfield, Devin Moreno, Gena Robbins, Jackory Nash, Jeffery Giles, Jhon Genao, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Tony Dean Skipworth |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00016590 | Denton ISD: UCS-X & Dell - DC Refresh | Training/Knowledge Transfer/Documentation | 90% | 102.6% | 409.89 | 9.64 | 50465.25 | 51603.75 | 2.352% | 50465.25 | 20.5 | 420.75 | 46758.75 | 0 |  | 51603.75 |  | 727494.38 | 66283.56 | 14679.81 | 22.15%
03/04/25 |  | 04/09/25 | Open | Abiodun David Babasola | George Edwin Jacob |  | Abiodun David Babasola, Alexander Gutman, David Babasola |  |  | Abiodun David Babasola, Jacob Hill, Noah Trump, Tavis Jackson |  |  | Alex Gutman | TX-DAL | Tyler Junior College | 200002215 | N/A | Closed | 100% | 55% | 20 | 12 | 0 | 887.5 | 60% | 0 | 3 | 11 | 180 | 0 |  | 887.5 |  | 0 | 2606 | 1718.5 | 65.94%
12/08/23 |  | 04/09/25 | Closed | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Eric Firestone, Firas Abood, Jim Blackwell, Larry Noble |  |  | Cory Bradfield, Eric Firestone, Jim Blackwell, Justin Cornish |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016828 | ISE Deployment | Closed | 100% | 63.24% | 578.75 | 230.5 | 83918.75 | 54146.25 | 39.83% | 83918.75 | 17.75 | 366 | 41497.5 | 0 |  | 54146.25 |  | 165785.6 | 0 | -54146.25 | 0%
01/06/25 |  | 04/18/25 | Open | Shannon Marie Alvarado | George Edwin Jacob, Michael Brett Beggs |  | Camille Elizabeth Taber, Cory Bradfield, Cory Bradfield, George Edwin Jacob, Michael Brett Beggs, Shannon Marie Alvarado |  |  | Cory Bradfield, Diego Asencio, Shannon Marie Alvarado |  |  | Camille Taber | FL | Hillsborough County Public Schools | 200000304 | N/A | Closed | 100% | 48.28% | 207.13 | 135.13 | 27051.05 | 12560 | 65.24% | 27051.05 | 28 | 100 | 3780 | 0 |  | 12560 |  | 1212759 | 44171.24 | 31611.24 | 71.57%
02/19/25 |  | 04/29/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Steven Walker, Tray Giddens |  |  | Christopher Brown, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200002088 | N/A | Closed | 100% | 111.8% | 27.5 | -3.25 | 0 | 4101.25 | -11.82% | 0 | 0 | 30.75 | 0 | 0 |  | 4101.25 |  | 0 | 5760.4 | 1659.15 | 28.8%
05/02/24 |  | 05/01/25 | Open | Shannon Marie Alvarado | Firas Abood, Mark J Chambliss |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Hamzeh Tahat, Karyn Hubbard, Leonid G Kamenker, Leonid Kamenker, Samuel Newland, Shannon Marie Alvarado |  |  | Cory Bradfield, Hamzeh Tahat, Michael Garcia, Osazee Eweka, Samuel Newland, Shannon Marie Alvarado |  |  | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00017292 | UC Infra Installation & Apps Upgrade | Closed | 100% | 57.41% | 592.25 | 260.25 | 81565.25 | 45447.5 | 43.94% | 81565.25 | 8 | 340 | 25967.5 | 3277.5 |  | 45447.5 |  | 387306.6 | 73499.4 | 24774.4 | 33.71%
10/02/24 |  | 05/02/25 | Open | Jason Esry | Steven Walker |  | Jason Esry, Jeff Barker, Steven Walker, William Davenport |  |  | Jason Esry, Luis Ovalles |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00019133 | SQL Physical to Virtual Migration | Closed | 100% | 389% | 36.25 | -104.75 | 4821.25 | 18975 | -289% | 4821.25 | 0 | 141 | 0 | 0 |  | 18975 |  | 0 | 7087.2 | -11887.8 | -167.7%
10/02/24 |  | 05/02/25 | Open | Jason Esry | Steven Walker |  | Jason Esry, Jeff Barker, Steven Walker, William Davenport |  |  | Jason Esry, Luis Ovalles |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00019133 | SQL Physical to Virtual Migration | Closed | 0% | 0% | 0 | -10 | 0 | 1330 | 0% | 0 | 0 | 10 | 1330 | 0 |  | 1330 |  | 0 | 7087.2 | 5757.2 | 81.23%
07/16/24 |  | 05/02/25 | Open | Joaquin Marroquin | David Escamilla |  | David D Tijerina, Joaquin Marroquin, Juan Saenz, Larry Noble |  |  | Joaquin Marroquin, Juan Saenz |  |  | David D Tijerina | TX-CEN | Amazon Web Services | J00018667 | AWS DRS Migration & Control Tower Deployment | Implementation/Deployment | 0% | 0% | 0 | -16.5 | 0 | 2147.5 | 0% | 0 | 0 | 16.5 | 2147.5 | 0 |  | 2147.5 |  | 0 | 15710.4 | 13562.9 | 86.33%
07/16/24 |  | 05/02/25 | Open | Joaquin Marroquin | David Escamilla |  | David D Tijerina, Joaquin Marroquin, Juan Saenz, Larry Noble |  |  | Joaquin Marroquin, Juan Saenz |  |  | N/A | N/A | Amazon Web Services | J00018667 | AWS DRS Migration & Control Tower Deployment | Implementation/Deployment | 70% | 13.53% | 77.63 | 67.13 | 10393.75 | 1407.5 | 86.47% | 10393.75 | 0 | 10.5 | 0 | 0 |  | 1407.5 |  | 0 | 15710.4 | 14302.9 | 91.04%
07/01/24 |  | 05/02/25 | Open | Lauren Lanzini Coffey | Amanda Barney |  | Amanda Barney, Lauren Lanzini Coffey, Neel Shah |  |  | Lauren Lanzini Coffey, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00018603 | SecureLogix | Training/Knowledge Transfer/Documentation | 95% | 42.14% | 35 | 20.25 | 4935 | 1881.25 | 57.86% | 4935 | 0 | 14.75 | 718.75 | 0 |  | 1881.25 |  | 0 | 7772.4 | 5891.15 | 75.8%
03/11/25 |  | 05/02/25 | Closed | Walter Clay Knight | Jeremy Williams |  | Camille Elizabeth Taber, Jeremy Williams, Walter Clay Knight |  |  | Tony Dean Skipworth, Walter Clay Knight |  |  | Camille Taber | FL | Mainline | 200002359 | N/A | Closed | 100% | 48.91% | 18.4 | 9.4 | 0 | 1190 | 51.09% | 0 | 0 | 9 | 0 | 0 |  | 1190 |  | 0 | 4254.1 | 3064.1 | 72.03%
03/27/25 |  | 05/09/25 | Open | Christina Rice | Jacob Parks, Jeffrey Holman, Michael Brett Beggs |  | Christina Rice, Christina Rice, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Shawn Sutton, Sophia Quinter |  |  | Christina Rice, Joshua Osgood, Luis Ovalles, Sophia Quinter |  |  | Shawn Sutton | TX-DAL | Denton ISD | 200002157 | N/A | Training/Knowledge Transfer/Documentation | 95% | 134.3% | 17.5 | -4 | 0 | 2970 | -22.86% | 0 | 2 | 23.5 | 120 | 0 |  | 2970 |  | 138843.78 | 3660.32 | 690.32 | 18.86%
01/24/22 |  | 05/16/25 | Open | Lauren Lanzini Coffey | Billy Pearson, Firas Abood |  | Firas Abood, Lauren Lanzini Coffey, Michael Hilton, Neel Shah, Ron Loge, Tony Dean Skipworth |  |  | Andy Pham, Devon LeMoine, Justin Cornish, Lauren Lanzini Coffey, Michael Hilton, Ron Loge, Tony Dean Skipworth |  |  | N/A | N/A | Sam Houston State University | J00011651 | ACI Deployment | Training/Knowledge Transfer/Documentation | 95% | 2.946% | 288.56 | 280.06 | 32286.7 | 980.5 | 97.05% | 32286.7 | 0 | 8.5 | 0 | 643.98 |  | 980.5 |  | 956677.52 | 94815.2 | 93190.72 | 98.29%
01/24/22 |  | 05/16/25 | Open | Lauren Lanzini Coffey | Billy Pearson, Firas Abood |  | Firas Abood, Lauren Lanzini Coffey, Michael Hilton, Neel Shah, Ron Loge, Tony Dean Skipworth |  |  | Andy Pham, Devon LeMoine, Justin Cornish, Lauren Lanzini Coffey, Michael Hilton, Ron Loge, Tony Dean Skipworth |  |  | Neel Shah | TX-HOU | Sam Houston State University | J00011651 | ACI Deployment | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -269.6 | 0 | 32092 | 0% | 0 | 21 | 290.6 | 29954 | 643.98 |  | 32092 |  | 956677.52 | 94815.2 | 62079.22 | 65.47%
01/10/25 |  | 05/23/25 | Open | Brittney Antoinette Hickman | David Goss |  | Brittney Antoinette Hickman, David Goss, Luis Ovalles, Rusty Bryan |  |  | Brittney Antoinette Hickman, David Goss, Jacob Hill, Luis Ovalles, Noah Trump |  |  | Rusty Bryan | TX-DAL | Region 17 Education Service Center | 200001587 | N/A | Planning/Design/Staging | 85% | 116.9% | 197.8 | -7.45 | 23159.04 | 28383.75 | -3.766% | 23159.04 | 26 | 231.25 | 1560 | 0 |  | 28383.75 |  | 732573.72 | 0 | -28383.75 | 0%
01/30/23 |  | 05/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | Garrett Curran | CA-LAX | Amazon Web Services | J00014741 | AWS Funded - Control Tower Setup | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -14 | 0 | 1890 | 0% | 0 | 0 | 14 | 1890 | 0 |  | 1890 |  | 0 | 10000 | 8110 | 81.1%
01/30/23 |  | 05/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | Garrett Curran | CA-LAX | Amazon Web Services | J00014746 | WORK ORDER - AWS Funded Migration Evaluator | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -4 | 0 | 540 | 0% | 0 | 0 | 4 | 540 | 0 |  | 540 |  | 0 | 4800 | 4260 | 88.75%
01/30/23 |  | 05/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | N/A | N/A | Amazon Web Services | J00014741 | AWS Funded - Control Tower Setup | Training/Knowledge Transfer/Documentation | 95% | 4.179% | 41.88 | 40.13 | 4866.5 | 218.75 | 95.82% | 4866.5 | 0 | 1.75 | 0 | 0 |  | 218.75 |  | 0 | 10000 | 9781.25 | 97.81%
01/30/23 |  | 05/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | N/A | N/A | Amazon Web Services | J00014746 | WORK ORDER - AWS Funded Migration Evaluator | Training/Knowledge Transfer/Documentation | 95% | 9.352% | 24.06 | 21.81 | 2795.75 | 281.25 | 90.65% | 2795.75 | 0 | 2.25 | 0 | 0 |  | 281.25 |  | 0 | 4800 | 4518.75 | 94.14%
12/09/24 |  | 05/30/25 | Open | Joaquin Marroquin | Daniel Snyder, David Goss, Wyley Johnson |  | Amy Martinez-Nagy, Daniel Snyder, David D Tijerina, David Goss, Joaquin Marroquin, Sophia Quinter, Wyley Johnson |  |  | Cory Bradfield, Joaquin Marroquin, Kevin Curtis, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Sophia Quinter |  |  | David D Tijerina | TX-CEN | Leander ISD | 200000177 | N/A | Implementation/Deployment | 25% | 25.31% | 593.75 | 443.5 | 84633.75 | 19421.25 | 74.69% | 84633.75 | 0 | 150.25 | 0 | 0 |  | 19421.25 |  | 239314.87 | 135009.72 | 115588.47 | 85.61%
08/23/22 |  | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs |  |  | Gena Robbins, Luis Ovalles, Ron Loge |  |  | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012888 | SaaS/Parking NO HDWR - AAAQ361562 | Closed | 100% | 184% | 96.6 | -81.15 | 12915 | 24048.75 | -84.01% | 12915 | 0 | 177.75 | 24048.75 | 64.29 |  | 24048.75 |  | 0 | 0 | -24113.04 | 0%
07/11/22 |  | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Cory E Hopf, Cory Hopf, Joshua Adam Engle, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs |  |  | Gena Robbins, Luis Ovalles, Ron Loge |  |  | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012890 | HX Nodes for SAAB - AAAQ361558 | Closed | 100% | 196.6% | 38.78 | -35.47 | 4752.5 | 10301.25 | -91.46% | 4752.5 | 2 | 76.25 | 8681.25 | 0 |  | 10301.25 |  | 67944 | 0 | -10301.25 | 0%
03/18/25 |  | 05/30/25 | Open | Richard Keith Arnst | Steven Walker |  | Daniel Saenz, Eric Rodriguez, Richard Keith Arnst, Steven Walker |  |  | Christopher Brown, Richard Keith Arnst |  |  | Daniel Saenz | TX-SOUT | Great Hearts Texas | 200002434 | N/A | Planning/Design/Staging | 25% | 112% | 43.75 | -5.25 | 0 | 6510 | -12% | 0 | 0 | 49 | 0 | 0 |  | 6510 |  | 473 | 7187.84 | 677.84 | 9.43%
03/04/25 |  | 06/03/25 | Open | Jennifer Soliz | Steven Walker |  | Garrett Curran, Jennifer Soliz, Steven Walker |  |  | Jennifer Soliz |  |  | Garrett Curran | CA-LAX | San Bernardino County ERA | 200002270 | N/A | Closed | 100% | 115% | 5 | -0.75 | 0 | 718.75 | -15% | 0 | 0 | 5.75 | 0 | 0 |  | 718.75 |  | 27523.56 | 0 | -718.75 | 0%
07/29/24 |  | 06/05/25 | Closed | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Michael Brett Beggs, Phillip Ma Lim, Tavis Jackson , William Davenport |  |  | Carlo Enriquez, Jason Esry, Jay Daniel De Leon, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Kendall Walls, Luis Ovalles, Phillip Ma Lim, Quy Le, Tavis Jackson, Yonathan Fadel |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00018726 | Data Center Network Refresh | Closed | 100% | 48.32% | 305.23 | 157.73 | 36770.62 | 16992.5 | 51.68% | 36770.62 | 0 | 147.5 | 0 | 0 |  | 16992.5 |  | 570092.93 | 42659.36 | 25666.86 | 60.17%
07/29/24 |  | 06/05/25 | Closed | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Michael Brett Beggs, Phillip Ma Lim, Tavis Jackson , William Davenport |  |  | Carlo Enriquez, Jason Esry, Jay Daniel De Leon, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Kendall Walls, Luis Ovalles, Phillip Ma Lim, Quy Le, Tavis Jackson, Yonathan Fadel |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00018726 | Data Center Network Refresh | Closed | 0% | 0% | 0 | -74 | 0 | 7527.5 | 0% | 0 | 0 | 74 | 7527.5 | 0 |  | 7527.5 |  | 570092.93 | 42659.36 | 35131.86 | 82.35%
02/03/25 |  | 06/05/25 | Open | Richard Keith Arnst | Steven Walker |  | Richard Keith Arnst, Steven Walker, Susan Richardson |  |  | Richard Keith Arnst |  |  | Susan Richardson | TX-HOU | Howard Hughes Management Co., LLC | 200001810 | N/A | Closed | 100% | 20.13% | 202.4 | 161.65 | 5300 | 5093.75 | 79.87% | 5300 | 0 | 40.75 | 0 | 0 |  | 5093.75 |  | 0 | 81870 | 76776.25 | 93.78%
10/28/24 |  | 06/06/25 | Open | Jennifer Soliz | Steven Walker |  | Hannah Paul, Jennifer Soliz, Larry Noble, Lori Endsley, Steven Walker |  |  | Jennifer Soliz |  |  | Hannah Edmunds | TX-CEN | Edgewood ISD | J00019243 | VM Migration to Azure | Closed | 100% | 105% | 10 | -0.5 | 0 | 1312.5 | -5% | 0 | 0 | 10.5 | 0 | 0 |  | 1312.5 |  | 20047.25 | 1630.24 | 317.74 | 19.49%
04/25/25 |  | 06/06/25 | Open | LaQisha Marshall | David D Tijerina, David Goss |  | David D Tijerina, David Escamilla, David Goss, LaQisha Marshall, Tony Dean Skipworth |  |  | LaQisha Marshall, Tony Dean Skipworth |  |  | David D Tijerina | TX-CEN | Travis County | 200002593 | N/A | Planning/Design/Staging | 5% | 10.61% | 33 | 29.5 | 0 | 447.5 | 89.39% | 0 | 0 | 3.5 | 0 | 0 |  | 447.5 |  | 89560.52 | 19724 | 19276.5 | 97.73%
03/10/25 |  | 06/13/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, David Escamilla, Jaclyn Pias |  |  | Brian Willery, Cory Bradfield |  |  | Jaclyn Pias | TX-HOU | US Legal Support | 200002361 | N/A | Implementation/Deployment | 95% | 62.64% | 66.25 | 24.75 | 0 | 5467.5 | 37.36% | 0 | 0 | 41.5 | 0 | 0 |  | 5467.5 |  | 0 | 13856.84 | 8389.34 | 60.54%
06/03/25 |  | 06/13/25 | Open | Joanna Herrera | Michael Brett Beggs |  | Arcangelo Fanelli, Joanna Herrera, Juan Saenz, Michael Brett Beggs |  |  | Joanna Herrera, Juan Saenz |  |  | Arcangelo Fanelli | TX-DAL | Cook Children's Health Care System | 200003046 | N/A | Training/Knowledge Transfer/Documentation | 95% | 47.39% | 10.55 | 5.55 | 0 | 665 | 52.61% | 0 | 0 | 5 | 0 | 0 |  | 665 |  | 0 | 1585 | 920 | 58.04%
07/17/24 |  | 06/13/25 | Open | Lauren Lanzini Coffey | Christopher Ceykovsky, Jacob Parks, Jeffrey Holman, Kenneth Dieter, William Birdsong |  | Beau C. Devillier, Bryan Mullen, Christopher Ceykovsky, Jacob Parks, Jeffrey Holman, Joshua Parker, Kenneth Dieter, Lauren Lanzini Coffey, William Birdsong |  |  | Anthony Towsley, Bryan Mullen, Lauren Lanzini Coffey |  |  | Joshua Parker | TX-DAL | Collin County - Texas | J00018662 | Cisco Equipment Assessment | On HOLD | 100% | 22.46% | 569.85 | 441.85 | 69351.25 | 16832.5 | 77.54% | 69351.25 | 0 | 128 | 10447.5 | 0 |  | 16832.5 |  | 0 | 169792.84 | 152960.34 | 90.09%
10/07/24 |  | 06/16/25 | Open | Walter Clay Knight | Aman Khan, David Escamilla, Eduardo Chavez, Jacob Parks, Jeffrey Holman |  | Aman Khan, Carmen Isela Brandt, David Escamilla, Eduardo Chavez, Jacob Parks, Jeffrey Holman, Yong Kim |  |  | Luis Ovalles, Nick Varga, Walter Clay Knight |  |  | Carmen Brandt | CA-LAX | City of Manhattan Beach | J00019153 | Network Refresh and NetApp | Implementation/Deployment | 65% | 68.13% | 198.15 | 63.15 | 29446.73 | 16895 | 31.87% | 29446.73 | 0 | 135 | 125 | 0 |  | 16895 |  | 0 | 45340.08 | 28445.08 | 62.74%
02/10/25 |  | 06/18/25 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Tray Giddens |  |  | Cory Bradfield, Craig St. Rose, James Adams, Jose R. Duarte, Kord Mullins, Miguel Reed, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Galveston County | 200001831 | N/A | Closed | 100% | 73.12% | 218.13 | 98.63 | 23386.25 | 12895 | 45.22% | 23386.25 | 40 | 159.5 | 2400 | 0 |  | 12895 |  | 0 | 30708 | 17813 | 58.01%
08/01/23 |  | 06/19/25 | Open | Tray Giddens | David Escamilla |  | Aman Khan, Austen New LN: Howard Cockerham, Bradley Buchanan, Conner MacDonnell, Dante Torres, David Escamilla, Devin Moreno, Dustin Huffman, Frank Jaimes, Jeffery Giles, Jhon Genao, Juan Pomares, Kirk O'Guinn, Kurt Sell, Mohaymen Sodi, Noah Castleberry, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Ron Loge, Sean Cowhey, Tabais Prater, Tavis Jackson, Tray Giddens |  |  | Austen Howard, Carlo Enriquez, Devin Moreno, Jhon Genao, Justin Mitchell, Kanoa Parman, Kebret Eshetu, Kevin Curtis, Kirk O'Guinn, Kolawole Ayeni, Matthew D'Ambrosio, Mohaymen Sodi, Nicolas Garakani, Noah Trump, Patrick Shea Thompson, Phillip Ma Lim, Quy Le, Ron Loge, Sean Cowhey, Tabais Prater, Tray Giddens, William Chris Roome, Yonathan Fadel |  |  | Dustin Huffman | TX-HOU | Apache Corporation | J00016147 | Nexus Refresh | Implementation/Deployment | 50% | 130.4% | 373.4 | -93.85 | 49610.75 | 58677.5 | -25.13% | 49610.75 | 19.5 | 486.75 | 47760 | 20 |  | 58677.5 |  | 866896 | 78495 | 19797.5 | 25.22%
06/20/22 |  | 06/20/25 | Open | Jason Esry | Emilio Carrillo, Firas Abood, Kenneth Dieter, Mark J Chambliss, Timothy Ramsey |  | David D Tijerina, Jaime Cortez, Jason Esry, Larry Noble, Robert Kelly, Robert Kelly, Timothy Ramsey, Tony Dean Skipworth |  |  | Abdulrahman Farhan, Eric Firestone, Ernesto Gonzalez, Isaiah Covington, Jaime Cortez, James Danner, Jason Esry, Jeffrey Charles Primeaux, Kyle Linder, Micah Rendon, Mohammed Almoola, Ron Loge, Tony Dean Skipworth, Trevor Youngman |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00013237 | DC \ ACI \ Core Router and FW Work | Implementation/Deployment | 95% | 86.73% | 474.48 | 82.98 | 58472.5 | 50840 | 17.49% | 58472.5 | 20 | 411.5 | 43967.5 | 473.32 |  | 50840 |  | 637580.65 | 83092 | 31778.68 | 38.25%
03/06/25 |  | 06/27/25 | Open | Jennifer Soliz | Steven Walker |  | Garrett Curran, Jennifer Soliz, Meray Doughly, Steven Walker |  |  | Jennifer Soliz |  |  | Garrett Curran | CA-LAX | San Bernardino County ERA | 200002312 | N/A | Implementation/Deployment | 0% | 0% | 0 | -7 | 0 | 875 | 0% | 0 | 0 | 7 | 0 | 0 |  | 875 |  | 0 | 150 | -725 | -483.3%
05/23/25 |  | 06/27/25 | Open | Jim Blackwell | Firas Abood |  | Cory Bradfield, Cory Bradfield, Firas Abood, Jeremy R Freeman, Jim Blackwell, Meredith A Richardson |  |  | Cory Bradfield, Jim Blackwell |  |  | N/A | N/A | Houston ISD | 200002987 | N/A | Planning/Design/Staging | 5% | 9.452% | 79.35 | 71.85 | 0 | 992.5 | 90.55% | 0 | 0 | 7.5 | 0 | 0 |  | 992.5 |  | 0 | 11000 | 10007.5 | 90.98%
10/15/24 |  | 06/27/25 | Open | Ryan Scott | Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, Darrell Walton, Darrell Walton, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Ryan Scott, Taylor Leger |  |  | Darrell Walton, Devin Moreno, Jose Gutierrez, Noah Castleberry, Ryan Scott |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00019060 | WAN Processor and AMP Refresh | Training/Knowledge Transfer/Documentation | 95% | 54.67% | 56.25 | 26 | 7481.25 | 3102.5 | 46.22% | 7481.25 | 0.5 | 30.75 | 311.25 | 0 |  | 3102.5 |  | 0 | 15710.4 | 12607.9 | 80.25%
03/12/25 |  | 06/27/25 | Open | Tray Giddens | Aman Khan, David Escamilla |  | Aman Khan, Dustin Huffman, Tray Giddens |  |  | Caleb Henry, Cory Bradfield, Craig St. Rose, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio, Noah Trump, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Gulf Capital Bank | 200002327 | N/A | Planning/Design/Staging | 5% | 83.97% | 98.55 | 31.05 | 0 | 9468.75 | 31.51% | 0 | 15.25 | 82.75 | 1721.25 | 0 |  | 9468.75 |  | 527907.68 | 15272 | 5803.25 | 38%
05/12/25 |  | 06/30/25 | Closed | Brian Willery | David Goss, Steven Walker |  | Brian Willery, David Goss, Jason Osuna, Steven Walker |  |  | N/A |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | 200002958 | N/A | Not started | 0% | 0% | 46.78 | 46.78 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 124583.8 | 9514.92 | 9514.92 | 100%
02/16/24 |  | 06/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Cory Bradfield, Cory Bradfield, Jaime B Flores, Jaime Flores, Larry Noble, Maria De Kanter, Mohaymen Sodi, Susan Richardson |  |  | Abdalsattar Albaghdadi, Anthony Lange, Brian Willery, Bryant Bush, Cory Bradfield, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Luis Ovalles, Matthew D'Ambrosio, Mohaymen Sodi, Nathan Dao, Nicolas Garakani, Paul Serres |  |  | Susan Richardson | TX-HOU | Klein ISD | J00017378 | Datacenter Compute, Storage & Network Electronics | Training/Knowledge Transfer/Documentation | 95% | 396.9% | 346.13 | -925.17 | 46690.64 | 168352.8 | -267.3% | 46690.64 | 102.33 | 1373.63 | 102875.5 | 32.5 |  | 168352.8 |  | 6806687.42 | 164198.28 | -4187.02 | -2.55%
01/30/25 |  | 06/30/25 | Open | Brittney Antoinette Hickman | Steven Walker |  | Brittney Antoinette Hickman, Christopher Brown, Christopher Brown, Luis Ovalles, Mark Forehand, Steven Walker |  |  | Brittney Antoinette Hickman, Christopher Brown, Luis Ovalles |  |  | Mark Forehand | TX-DAL | City of Richardson | 200001737 | N/A | Planning/Design/Staging | 55% | 93.39% | 140 | 9.25 | 18620 | 17373.75 | 6.607% | 18620 | 0 | 130.75 | 0 | 0 |  | 17373.75 |  | 19743.14 | 30078.44 | 12704.69 | 42.24%
04/29/24 |  | 06/30/25 | Open | Jim Blackwell | David Escamilla, Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, David Escamilla, Firas Abood, Jim Blackwell, Larry Noble, Luis A Alvarez, Luis Alvarez |  |  | Andy Pham, Cory Bradfield, Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018235 | UCSC Server Implementation | Training/Knowledge Transfer/Documentation | 95% | 49.9% | 105.2 | 56.2 | 1387.5 | 6512.5 | 53.42% | 1387.5 | 3.5 | 52.5 | 1537.5 | 0 |  | 6512.5 |  | 167484.44 | 19506.8 | 12994.3 | 66.61%
05/09/25 |  | 06/30/25 | Open | Jim Blackwell | Firas Abood |  | Firas Abood, Jesus Escobedo, Jim Blackwell, Juan Saenz, Meredith A Richardson |  |  | Jim Blackwell, Juan Saenz |  |  | N/A | N/A | Houston ISD | 200002956 | N/A | Planning/Design/Staging | 0% | 0% | 0 | -20.5 | 0 | 2747.5 | 0% | 0 | 0 | 20.5 | 0 | 0 |  | 2747.5 |  | 0 | 4500 | 1752.5 | 38.94%
03/04/25 |  | 06/30/25 | Open | Marco Lish | Matthew Duncan |  | Marco Lish, Matthew Duncan, Neel Shah |  |  | Erick Nunez , Juan Saenz, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Public Works | 200002286 | N/A | Planning/Design/Staging | 45% | 49.27% | 161.85 | 82.1 | 0 | 10546.25 | 50.73% | 0 | 0 | 79.75 | 0 | 0 |  | 10546.25 |  | 0 | 33830.4 | 23284.15 | 68.83%
11/08/22 |  | 06/30/25 | Open | Marco Lish | Michael Brett Beggs |  | Jeff Barker, Jonathan Pendrich, Marco Lish, Michael Brett Beggs |  |  | Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | J00014358 | Staff Aug Backlog | Training/Knowledge Transfer/Documentation | 100% | 573.1% | 52 | -246 | 6500 | 37250 | -473.1% | 6500 | 0 | 298 | 37250 | 0 |  | 37250 |  | 750440.34 | 0 | -37250 | 0%
07/11/24 |  | 06/30/25 | Open | Summer Abunaja | Matthew Duncan |  | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja |  |  | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja |  |  | N/A | N/A | Amazon Web Services | J00018637 | AWS AppStream POC | Implementation/Deployment | 90% | 72.08% | 148.8 | 41.55 | 19660.5 | 13988.75 | 27.92% | 19660.5 | 0 | 107.25 | 0 | 0 |  | 13988.75 |  | 0 | 31024 | 17035.25 | 54.91%
07/11/24 |  | 06/30/25 | Open | Summer Abunaja | Matthew Duncan |  | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja |  |  | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja |  |  | Neel Shah | TX-HOU | Amazon Web Services | J00018637 | AWS AppStream POC | Implementation/Deployment | 0% | 0% | 0 | -90 | 0 | 11922.5 | 0% | 0 | 0 | 90 | 11922.5 | 0 |  | 11922.5 |  | 0 | 31024 | 19101.5 | 61.57%
05/09/24 |  | 06/30/25 | Open | Summer Abunaja | George Edwin Jacob |  | Joseph Boglino, Larry Noble, Summer Abunaja, Tony Dean Skipworth |  |  | Summer Abunaja, Tony Dean Skipworth |  |  | Joseph Boglino | US-FED | U.S. Peace Corps | J00018290 | APIC Cluster Project | Implementation/Deployment | 20% | 76.67% | 30 | 7 | 4050 | 3070 | 23.33% | 4050 | 0 | 23 | 3070 | 0 |  | 3070 |  | 140008.68 | 6075 | 3005 | 49.47%
04/03/25 |  | 07/02/25 | Open | Abiodun David Babasola | George Edwin Jacob |  | Abiodun David Babasola, David Babasola, George Edwin Jacob, Lauren J Kennewell, Ron Loge, Timothy Fain |  |  | Abiodun David Babasola, Austen Howard, Brycen Dimas, Dante Torres, Remijio Hernandez, Ron Loge |  |  | Lauren J Kennewell | TX-DAL | Duncanville ISD | 200002471 | N/A | Planning/Design/Staging | 25% | 27.47% | 242.97 | 180.72 | 0 | 8551.25 | 74.38% | 0 | 4.5 | 66.75 | 442.5 | 0 |  | 8551.25 |  | 992618.73 | 50096.3 | 41545.05 | 82.93%
04/04/25 |  | 07/04/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Steven Walker, Tray Giddens |  |  | Christopher Brown, Tray Giddens |  |  | Dustin Huffman | TX-HOU | City of League City | 200002600 | N/A | Planning/Design/Staging | 5% | 39.09% | 55 | 33.5 | 0 | 2832.5 | 60.91% | 0 | 0 | 21.5 | 0 | 0 |  | 2832.5 |  | 0 | 11520.8 | 8688.3 | 75.41%
04/24/25 |  | 07/11/25 | Open | Marco Lish | Michael Brett Beggs |  | Jonathan Pendrich, Marco Lish, Michael Brett Beggs |  |  | Luis Ovalles, Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Coblentz Patch Duffy & Bass LLP | 200002887 | N/A | Planning/Design/Staging | 0% | 16.77% | 77.5 | 64.5 | 0 | 1715 | 83.23% | 0 | 0 | 13 | 0 | 0 |  | 1715 |  | 0 | 16209.92 | 14494.92 | 89.42%
05/31/24 |  | 07/11/25 | Open | Richard Keith Arnst | Ahmed Al-Zubaidi, David Escamilla, Joshua Adam Engle, Wyley Johnson |  | Ashutosh Patel, Christopher Butler, Maria De Kanter, Randy Schamberger, Raul Velazquez, Richard Keith Arnst, Tony Dean Skipworth |  |  | Ashutosh Patel, Kreshnik Memaj, Raul Velazquez, Richard Keith Arnst, Romar Roca, Tony Dean Skipworth |  |  | Randy Schamberger | FL | Charlotte County Clerk of the Circuit Court | J00014845 | Core Upgrade & Net-Pro-3rd Party Srvcs | Implementation/Deployment | 85% | 120% | 548.85 | -77.65 | 87146.41 | 88672.5 | -14.15% | 87146.41 | 32 | 658.5 | 65992.5 | 50 |  | 88672.5 |  | 271377.04 | 112684.24 | 23961.74 | 21.26%
04/22/25 |  | 07/18/25 | Open | Summer Abunaja | Jeremy Williams |  | Garrett Curran, Jeremy Williams, Summer Abunaja |  |  | Juan Saenz, Summer Abunaja |  |  | Garrett Curran | CA-LAX | Santa Ana Unified School District | 200002778 | N/A | On HOLD | 15% | 2.775% | 144.12 | 140.12 | 0 | 435 | 97.22% | 0 | 0 | 4 | 0 | 0 |  | 435 |  | 0 | 33348 | 32913 | 98.7%
03/14/25 |  | 07/25/25 | Open | Jason Esry | David Goss |  | David D Tijerina, David Goss, Jason Esry |  |  | Cory Bradfield, Jason Esry |  |  | David D Tijerina | TX-CEN | Leander ISD | 200002407 | N/A | Planning/Design/Staging | 25% | 17.99% | 130.63 | 107.13 | 0 | 3042.5 | 82.01% | 0 | 0 | 23.5 | 0 | 0 |  | 3042.5 |  | 547590.15 | 29141.2 | 26098.7 | 89.56%
02/26/24 |  | 07/25/25 | Open | Jason Esry | David Escamilla, Michael Brett Beggs |  | Cory Bradfield, Cory Bradfield, David D Tijerina, David Escamilla, Jason Esry, Larry Noble, Michael Brett Beggs, Ron Loge |  |  | Cory Bradfield, Jason Esry, Ron Loge |  |  | David D Tijerina | TX-CEN | University of Texas - Austin | J00017214 | UT Austin VXRail Apex DC Refresh | Implementation/Deployment | 65% | 32.53% | 474.88 | 328.38 | 65336.87 | 23472.5 | 69.15% | 65336.87 | 8 | 154.5 | 15172.5 | 0 |  | 23472.5 |  | 2059242.16 | 110000 | 86527.5 | 78.66%
11/07/22 |  | 07/25/25 | Open | Richard Keith Arnst | David Escamilla |  | Alexander Gutman, Beau C. Devillier, Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge, Shawn Sutton |  |  | Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge |  |  | Shawn Sutton | TX-DAL | City of Dallas | J00014229 | AWS - DRaaS Implementation | Implementation/Deployment | 75% | 55.71% | 880.08 | 389.83 | 101771 | 66318.75 | 44.29% | 101771 | 0 | 490.25 | 59935 | 1005.53 |  | 66318.75 |  | 0 | 225027.68 | 157703.4 | 70.08%
01/15/25 |  | 07/25/25 | Open | Robert McIver | Firas Abood |  | Cory Bradfield, Cory Bradfield, Firas Abood, Robert McIver, Xavier A Trevino |  |  | Cory Bradfield, Francisco Hernandez, Jonathan Pina, Robert McIver, Roger Guerra |  |  | Eric Rodriguez | TX-SOUT | McAllen ISD | 200001640 | N/A | Planning/Design/Staging | 35% | 16.25% | 144.58 | 122.33 | 18622.04 | 2535 | 84.61% | 18622.04 | 1.25 | 23.5 | 75 | 0 |  | 2535 |  | 205113.02 | 25656.4 | 23121.4 | 90.12%
02/12/24 |  | 07/25/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Kurt Sell, Luis Ovalles, Steven Walker, Tray Giddens |  |  | Christopher Brown, Luis Ovalles, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Houston Federal Credit Union | J00017474 | Domain Upgrade & O365 Migration | Implementation/Deployment | 0% | 0% | 0 | -139 | 0 | 18570 | 0% | 0 | 0 | 139 | 18570 | 0 |  | 18570 |  | 0 | 47282.8 | 28712.8 | 60.73%
02/12/24 |  | 07/25/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Kurt Sell, Luis Ovalles, Steven Walker, Tray Giddens |  |  | Christopher Brown, Luis Ovalles, Tray Giddens |  |  | N/A | N/A | Houston Federal Credit Union | J00017474 | Domain Upgrade & O365 Migration | Implementation/Deployment | 70% | 12.98% | 238.75 | 207.75 | 31753.75 | 4065 | 87.02% | 31753.75 | 0 | 31 | 0 | 0 |  | 4065 |  | 0 | 47282.8 | 43217.8 | 91.4%
05/22/25 |  | 07/31/25 | Open | Abiodun David Babasola | Steven Walker |  | Abiodun David Babasola, Christopher Brown, Christopher Brown, David Babasola, Kristy L Dice, Steven Walker |  |  | Abiodun David Babasola, Christopher Brown |  |  | Kristy L Dice | TX-DAL | Prestonwood Baptist Church | 200002988 | N/A | Planning/Design/Staging | 5% | 12% | 37.5 | 33 | 0 | 602.5 | 88% | 0 | 0 | 4.5 | 0 | 0 |  | 602.5 |  | 0 | 7470 | 6867.5 | 91.93%
04/04/25 |  | 07/31/25 | Open | Christina Rice | Matthew Duncan, Michael Brett Beggs |  | Christina Rice, Christina Rice, Juan Saenz, Matthew Duncan, Michael Brett Beggs, Shawn Sutton |  |  | Christina Rice, Juan Saenz |  |  | Shawn Sutton | TX-DAL | Denton ISD | 200002612 | N/A | Not started | 0% | 21.65% | 151.25 | 118.5 | 0 | 4326.25 | 78.35% | 0 | 0 | 32.75 | 0 | 0 |  | 4326.25 |  | 0 | 24667.24 | 20340.99 | 82.46%
01/06/25 |  | 07/31/25 | Open | Jennifer Soliz | David Goss, Matthew Duncan |  | Carmen Isela Brandt, David Goss, Jennifer Soliz, Matthew Duncan |  |  | Jennifer Soliz |  |  | Carmen Brandt | CA-LAX | Marin County | 200000552 | N/A | Planning/Design/Staging | 40% | 47.5% | 20 | 10.5 | 2500 | 1187.5 | 52.5% | 2500 | 0 | 9.5 | 0 | 0 |  | 1187.5 |  | 0 | 176468.22 | 175280.72 | 99.33%
05/20/25 |  | 07/31/25 | Open | LaQisha Marshall | Ahmed Al-Zubaidi, Steven Walker |  | Ahmed Al-Zubaidi, Ashutosh Patel, David Monasmith, David Monasmith, Ibrahim Altaweel, Jerome Tanyag Mara, LaQisha Marshall, Mohammad Arman, Rogelio Morgado-Perez, Steven Walker, Tom Magboo |  |  | Ashutosh Patel, LaQisha Marshall |  |  | David Monasmith | TX-HOU | College Station ISD | 200002989 | N/A | Planning/Design/Staging | 5% | 1.901% | 263 | 258 | 0 | 675 | 98.1% | 0 | 0 | 5 | 0 | 0 |  | 675 |  | 0 | 33990 | 33315 | 98.01%
08/25/23 |  | 07/31/25 | Open | Marshall Chuck Pugh | Steven Walker |  | Beau C. Devillier, Christopher Brown, Christopher Brown, Lauren J Kennewell, Lee McChesney, Marshall Chuck Pugh , Steven Walker |  |  | Christopher Brown, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Carroll ISD | J00014805 | Microsoft Office 365 Migration | Implementation/Deployment | 85% | 116.5% | 46.13 | -7.62 | 6022.35 | 7208.75 | -16.52% | 6022.35 | 0 | 53.75 | 7208.75 | 0 |  | 7208.75 |  | 0 | 8128 | 919.25 | 11.31%
08/25/23 |  | 07/31/25 | Open | Marshall Chuck Pugh | Steven Walker |  | Beau C. Devillier, Christopher Brown, Christopher Brown, Lauren J Kennewell, Lee McChesney, Marshall Chuck Pugh , Steven Walker |  |  | Christopher Brown, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Carroll ISD | J00014807 | Microsoft Office 365 Migration | Implementation/Deployment | 85% | 31.21% | 105.75 | 72.75 | 13806.25 | 4345 | 68.79% | 13806.25 | 0 | 33 | 1375 | 0 |  | 4345 |  | 0 | 18635 | 14290 | 76.68%
05/05/25 |  | 07/31/25 | Open | Robert McIver | David Escamilla |  | Arpine Ramirez, Daniel Saenz, David Escamilla, Juan Saenz, Robert McIver, Ron Loge |  |  | Juan Saenz, Robert McIver, Ron Loge |  |  | Daniel Saenz | TX-SOUT | City of Mission | 200002941 | N/A | Implementation/Deployment | 60% | 50% | 127.5 | 63.75 | 0 | 9546.25 | 50% | 0 | 0 | 63.75 | 0 | 0 |  | 9546.25 |  | 0 | 11672.56 | 2126.31 | 18.22%
05/27/25 |  | 07/31/25 | Open | Walter Clay Knight | David Goss |  | David D Tijerina, David Goss, Walter Clay Knight |  |  | Walter Clay Knight |  |  | David D Tijerina | TX-CEN | Williamson County | 200003014 | N/A | Planning/Design/Staging | 5% | 1.547% | 64.63 | 63.63 | 0 | 125 | 98.45% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 59519.92 | 8772.88 | 8647.88 | 98.58%
06/05/25 |  | 08/01/25 | Closed | Brian Willery | Amanda Barney, George Edwin Jacob, Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | 200003058 | N/A | Not started | 0% | 0% | 123.75 | 123.75 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 206853.5 | 20165.6 | 20165.6 | 100%
04/10/25 |  | 08/01/25 | Closed | Brian Willery | Jeremy Williams, Michael Brett Beggs |  | Brian Willery, Camille Elizabeth Taber, Jeremy Williams, Michael Brett Beggs |  |  | N/A |  |  | Camille Taber | FL | Lake County School Board | 200002580 | N/A | Not started | 0% | 0% | 188.88 | 188.88 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 938041.19 | 42461.52 | 42461.52 | 100%
04/25/25 |  | 08/01/25 | Open | Brittney Antoinette Hickman | Matthew Duncan |  | Brittney Antoinette Hickman, Carmen Isela Brandt, Garrett Curran, Juan Saenz, Matthew Duncan, Osazee Eweka |  |  | Brittney Antoinette Hickman, Juan Saenz, Osazee Eweka |  |  | Garrett Curran | CA-LAX | Los Angeles Community College District | 200002640 | N/A | Planning/Design/Staging | 25% | 24.71% | 109.25 | 82.25 | 0 | 3510 | 75.29% | 0 | 0 | 27 | 0 | 0 |  | 3510 |  | 0 | 22598.8 | 19088.8 | 84.47%
04/09/25 |  | 08/01/25 | Open | Joanna Herrera | Steven Walker |  | Jason Osuna, Joanna Herrera, Steven Walker |  |  | Christopher Brown, Joanna Herrera |  |  | Jason Osuna | TX-CEN | Cobre Consolidated School District | 200002613 | N/A | Implementation/Deployment | 45% | 30% | 75 | 52.5 | 0 | 2972.5 | 70% | 0 | 0 | 22.5 | 0 | 0 |  | 2972.5 |  | 0 | 14663.2 | 11690.7 | 79.73%
09/26/24 |  | 08/01/25 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Galveston County | J00019097 | VMware Services | Implementation/Deployment | 50% | 76.24% | 106.25 | 25.25 | 14981.25 | 10800 | 23.76% | 14981.25 | 0 | 81 | 800 | 0 |  | 10800 |  | 0 | 23711.6 | 12911.6 | 54.45%
04/14/25 |  | 08/01/25 | Closed | William Chris Roome | George Edwin Jacob |  | George Edwin Jacob, Jonathan Pendrich, William Chris Roome, William Roome |  |  | N/A |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | 200002653 | N/A | Not started | 0% | 0% | 84 | 84 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2894478.68 | 1812972.64 | 1812972.64 | 100%
06/09/25 |  | 08/08/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, David Escamilla, Jaclyn Pias |  |  | Brian Willery |  |  | Jaclyn Pias | TX-HOU | AIS Portfolio Services | 200003066 | N/A | Planning/Design/Staging | 5% | 2.286% | 43.75 | 42.75 | 0 | 125 | 97.71% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 251413.55 | 11000 | 10875 | 98.86%
03/24/25 |  | 08/08/25 | Open | Walter Clay Knight | David Escamilla |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, David Escamilla, Moe Izaks, Walter Clay Knight |  |  | Cory Bradfield, Craig St. Rose, Walter Clay Knight |  |  | Ashley F Freeman | TX-HOU | Harris County Toll Road Authority | 200002488 | N/A | Implementation/Deployment | 60% | 16.67% | 296.94 | 247.44 | 0 | 6392.5 | 83.33% | 0 | 0 | 49.5 | 0 | 0 |  | 6392.5 |  | 2498811.16 | 61174 | 54781.5 | 89.55%
10/23/24 |  | 08/11/25 | Open | Ryan Scott | Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Ryan Scott, Tony Dean Skipworth |  |  | Bryan Mullen, Devin Moreno, Noah Castleberry, Ryan Scott, Tony Dean Skipworth |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00019061 | DC: ACI - APIC Refresh | On HOLD | 20% | 43.33% | 67.5 | 39.25 | 7575.69 | 3676.25 | 58.15% | 7575.69 | 1 | 29.25 | 247.5 | 0 |  | 3676.25 |  | 0 | 16532.8 | 12856.55 | 77.76%
05/16/25 |  | 08/15/25 | Open | Brian Willery | David Goss, Steven Walker |  | Brian Willery, David Goss, Jason Osuna, Steven Walker |  |  | Brian Willery |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | 200002979 | N/A | Planning/Design/Staging | 5% | 3.296% | 106.2 | 102.7 | 0 | 437.5 | 96.7% | 0 | 0 | 3.5 | 0 | 0 |  | 437.5 |  | 349374.3 | 153470.56 | 153033.06 | 99.71%
05/21/24 |  | 08/29/25 | Open | LaQisha Marshall | George Edwin Jacob |  | Alexander Gutman, Beau C. Devillier, George Edwin Jacob, Jeffery Giles, LaQisha Marshall, Luis Ovalles |  |  | LaQisha Marshall, Luis Ovalles |  |  | Alex Gutman | TX-DAL | Dallas College | J00018375 | UCS FI Migration | On HOLD | 20% | 23.68% | 57 | 43.5 | 6868.5 | 1747.5 | 76.32% | 6868.5 | 0 | 13.5 | 1747.5 | 0 |  | 1747.5 |  | 4530.18 | 11332.8 | 9585.3 | 84.58%
02/28/25 |  | 08/29/25 | Open | Marshall Chuck Pugh | George Edwin Jacob |  | George Edwin Jacob, Lauren J Kennewell, Marshall Chuck Pugh , Ron Loge |  |  | Marshall Chuck Pugh, Ron Loge |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | 200002216 | N/A | Planning/Design/Staging | 40% | 64.5% | 50 | 17.75 | 0 | 5543.75 | 35.5% | 0 | 0 | 32.25 | 0 | 0 |  | 5543.75 |  | 0 | 10458 | 4914.25 | 46.99%
01/29/24 |  | 08/29/25 | Open | Ryan Scott | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Mullen, Michael Brett Beggs, Ron Loge, Ryan Scott, Taylor Leger, Tony Dean Skipworth |  |  | Bryan Mullen, Ron Loge, Ryan Scott |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00017306 | 2023 DC Core ACI Optimization | Implementation/Deployment | 60% | 77.97% | 541.25 | 119.25 | 71986.25 | 53000 | 22.03% | 71986.25 | 0 | 422 | 28000 | 0 |  | 53000 |  | 0 | 168369.6 | 115369.6 | 68.52%
03/25/25 |  | 09/26/25 | Open | Marco Lish | David Escamilla |  | Dennis Odneal, Marco Lish |  |  | Juan Saenz, Marco Lish |  |  | Dennis Odneal | TX-HOU | University of Nevada Las Vegas | 200002508 | N/A | Planning/Design/Staging | 45% | 39.2% | 99.5 | 60.5 | 0 | 5130 | 60.8% | 0 | 0 | 39 | 0 | 0 |  | 5130 |  | 0 | 18200 | 13070 | 71.81%
01/20/25 |  | 09/26/25 | Open | Tray Giddens | Ahmed Al-Zubaidi, David Escamilla, Mark J Chambliss, Saif Qaissi, Wyley Johnson |  | Abdulrahman Farhan, Ahmed Al-Zubaidi, Cory E Hopf, Cory Hopf, David Escamilla, Haley Glasscock, Ibrahim Altaweel, Lindie Lorraine Lamar, Mark J Chambliss, Rogelio Morgado-Perez, Romar Roca, Saif Qaissi, Tray Giddens, Wyley Johnson |  |  | Abdalsattar Albaghdadi, Abdulrahman Farhan, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Stafford MSD | 200001658 | N/A | Planning/Design/Staging | 5% | 9.578% | 485.5 | 439 | 69717.5 | 6525 | 90.42% | 69717.5 | 0 | 46.5 | 0 | 0 |  | 6525 |  | 0 | 92047.48 | 85522.48 | 92.91%
01/27/25 |  | 09/26/25 | Open | Tray Giddens | Ahmed Al-Zubaidi, David Escamilla, Mark J Chambliss, Saif Qaissi, Wyley Johnson |  | Ahmed Al-Zubaidi, Cory Bradfield, Cory Bradfield, David Escamilla, Lindie Lorraine Lamar, Mark J Chambliss, Saif Qaissi, Tray Giddens, Wyley Johnson |  |  | Cory Bradfield, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Stafford MSD | 200001723 | N/A | Planning/Design/Staging | 5% | 2.042% | 146.88 | 143.88 | 18485 | 380 | 97.96% | 18485 | 0 | 3 | 0 | 0 |  | 380 |  | 0 | 24280.2 | 23900.2 | 98.43%
06/16/25 |  | 09/30/25 | Open | LaQisha Marshall | Ahmed Al-Zubaidi, Steven Walker |  | Ahmed Al-Zubaidi, David Monasmith, David Monasmith, LaQisha Marshall, Steven Walker |  |  | LaQisha Marshall |  |  | David Monasmith | TX-HOU | College Station ISD | 200003091 | N/A | Not started | 0% | 0.322% | 155.25 | 154.75 | 0 | 62.5 | 99.68% | 0 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 0 | 29995 | 29932.5 | 99.79%
06/04/25 |  | 10/03/25 | Open | Joaquin Marroquin | Ahmed Al-Zubaidi, David Escamilla, Steven Walker, Wyley Johnson |  | Ahmed Al-Zubaidi, Christopher Brown, Christopher Brown, Cory Bradfield, Cory Bradfield, David Escamilla, Joaquin Marroquin, Steven Walker, Wyley Johnson, Xavier A Trevino |  |  | Cory Bradfield, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | 200003048 | N/A | Planning/Design/Staging | 5% | 2.275% | 351.66 | 343.66 | 0 | 1040 | 97.73% | 0 | 0 | 8 | 0 | 0 |  | 1040 |  | 2515824.14 | 94653.6 | 93613.6 | 98.9%
02/14/25 |  | 10/31/25 | Open | William Chris Roome | George Edwin Jacob |  | Gearld Stanley McNiel, George Edwin Jacob, Jonathan Pendrich, Katharine McCarley, Katherine McCarley, Ron Loge, Stan McNiel, William Chris Roome, William Roome |  |  | Bradley Buchanan, Carlo Enriquez, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jalen Vecchitto, Joshua Hubbard, Joshua Osgood, Justin Mitchell, Lauren Lanzini Coffey, Noah Castleberry, Remijio Hernandez, Ron Loge, William Chris Roome |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | 200001912 | N/A | Planning/Design/Staging | 10% | 36.99% | 740 | 466.25 | 66900 | 23258.75 | 63.01% | 66900 | 0 | 273.75 | 0 | 0 |  | 23258.75 |  | 1636652.22 | 953120 | 929861.25 | 97.56%
04/09/25 |  | 11/28/25 | Open | Shannon Marie Alvarado | David Watkins, Michael Brett Beggs |  | Arcangelo Fanelli, David Watkins, Michael Brett Beggs, Shannon Marie Alvarado |  |  | Jeffery Alan Jorzig, Jorge Ortiz Cardozo, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Baptist Hospitals of Southeast Texas | 200002598 | N/A | Planning/Design/Staging | 30% | 5.152% | 1669.25 | 1586.75 | 0 | 10750 | 95.06% | 0 | 3.5 | 86 | 437.5 | 0 |  | 10750 |  | 1393666.9 | 366314.8 | 355564.8 | 97.07%
03/03/25 |  | 12/31/25 | Open | Jason Matthew Davis | Amanda Barney, Chad Hart, David Watkins, Kristian Martell, Mark J Chambliss |  | Amanda Barney, Christine A Hupe, David Laurence Fine, Jason Matthew Davis, Kristian Martell, Lauren Lanzini Coffey, Neel Shah, Taylar Hansen, Tim Losee |  |  | Carlos Montalvo, David Laurence Fine, Jason Matthew Davis, Kristian Martell, Lauren Lanzini Coffey, Tim Losee |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200002160 | N/A | Planning/Design/Staging | 10% | 6.992% | 14801.65 | 13766.65 | 0 | 185326.25 | 93.01% | 0 | 0 | 1035 | 0 | 0 |  | 185326.25 |  | 0 | 4006141.2 | 3820814.95 | 95.37%
02/05/25 |  | 12/31/25 | Open | Shannon Marie Alvarado | Steven Walker |  | Arcangelo Fanelli, Christopher Brown, Christopher Brown, Shannon Marie Alvarado, Steven Walker |  |  | Christopher Brown, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | 200001852 | N/A | Implementation/Deployment | 75% | 55.68% | 46.25 | 20.5 | 6151.25 | 3416.25 | 44.32% | 6151.25 | 0 | 25.75 | 0 | 0 |  | 3416.25 |  | 0 | 9042 | 5625.75 | 62.22%
05/12/25 |  | 01/30/26 | Open | Brittney Antoinette Hickman | David Watkins, Michael Brett Beggs |  | Alexander Liu, Arcangelo Fanelli, Bradley Buchanan, Brittney Antoinette Hickman, Bryan Mullen, Brycen Dimas, Caleb Henry, Conner MacDonnell, David Watkins, Devin Moreno, Erick Sanchez, Frank Jaimes, Jalen Vecchitto, Jayden Colon, John Johnson, Joshua Osgood, Michael Brett Beggs, Noah Castleberry, Noah Trump, Quan Tran, Riley Jezek, Sean Cowhey, Tavis Jackson, Taylor Poole |  |  | Abiodun David Babasola, Alexander Liu, Bradley Buchanan, Brittney Antoinette Hickman, Bryan Mullen, Brycen Dimas, Caleb Henry, Carlo Enriquez, Devin Moreno, Erick Sanchez, Frank Jaimes, Gabriel Lantigua, Jacob Hill, Jalen Vecchitto, John Johnson, Jonathan Weir, Joshua Osgood, Justin Mitchell, Justin Thompson, Kendall Walls, Noah Castleberry, Noah Trump, Quy Le, Remijio Hernandez, Ryan Frankeberger, Samuel Gonzalez, Sean Cowhey, Tavis Jackson, Tony Dean Skipworth, Yonathan Fadel |  |  | Arcangelo Fanelli | TX-DAL | Fort Worth ISD | 200002923 | N/A | Planning/Design/Staging | 45% | 24.71% | 4965.41 | 3745.16 | 0 | 100817.5 | 75.42% | 0 | 6.5 | 1226.75 | 390 | 0 |  | 100817.5 |  | 6539213.1 | 417179.5 | 316362 | 75.83%
12/22/22 |  | 04/17/26 | Open | Robert McIver | Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Hugh Miller, Michael Brett Beggs, Wyley Johnson |  | Abdalsattar Albaghdadi, Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Cory Bradfield, Cory Bradfield, Daniel Hernandez, Daniel R Hernandez, David Monasmith, David Monasmith, Dhulfiqar Al Hashimi, Ernesto Gonzalez, Fadi Ashour, Mark Lynd, Michael Brett Beggs, Mohammed Almoola, Quoc Nguyen, Robert McIver, Romar Roca, Timothy Sean Marcyes, Wyley Johnson |  |  | Abdalsattar Albaghdadi, Albert Bernal, Cory Bradfield, Craig St. Rose, David Dobbs, Dhulfiqar Al Hashimi, Erick Nunez , Ernesto Gonzalez, James Adams, Jose R. Duarte, Justin Smallwood, Kendric Mamou, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Mohammed Almoola, Mohaymen Sodi, Moises Rodriguez, Mustafa Al-Tamimi, Paul Serres, Rafael Rodriguez-Vargas, Robert McIver, Timothy Sean Marcyes |  |  | David Monasmith | TX-HOU | Texas A&M System | J00014492 | Rellis Campus - Core Network Refresh | Planning/Design/Staging | 40% | 72.92% | 2440.44 | 761.11 | 279798.13 | 232226.75 | 31.19% | 279798.13 | 100.25 | 1779.58 | 133933 | 1154.69 |  | 232226.75 |  | 4123249.95 | 632171.96 | 398790.52 | 63.08%
[21 empty] | 50296.76 | 26946.11 | 3023542.3 | 3024436.05 | 53.57% | 3023542.3 | 1305.12 | 24655.77 | 1967410.75 | 52126.54 |  | 3024436.05 |  | 79179197.71 | 14551765.65 | 11475203.06 | 78.86%