## PMO Project Financials
[31 empty] | Report ID: |  | ServiceDelivery-RS-001
| PMO Project Financials | [29 empty] | Execution: |  | 2025-07-02 14:45
| Summary 2025 - All Customers | [29 empty] | Executed By: |  | NETSYNC\lmcchesney
| Status: Open, Closed | [29 empty] | Data Refresh: |  | 2025-07-01 20:00
Alert Level: 0,1,2,3,4
| Abiodun David Babasola, Ali Al-Haddad, Brian Willery, Brittney Antoinette Hickman, Christina Rice, Jason Esry, Jason Matthew Davis, Jennifer Soliz, Jim Blackwell, Joanna Herrera, Joaquin Marroquin, Karyn Hubbard, LaQisha Marshall, Lauren Lanzini Coffey, Marco Lish, Marshall Chuck Pugh, Michelle Duenes, Richard Keith Arnst, Robert McIver, Ryan Scott, Shannon Marie Alvarado, Summer Abunaja, Tray Giddens, Walter Clay Knight, William Chris Roome, Inactive |  |  |  |  | On-Budget |  | 1% - 10% | 11% - 20% |  | 21% - 30% | +30%
Start Date |  | End Date | Job Status | Project Manager | Solution Architect |  | Resources Assigned |  |  | Resources Engaged |  |  | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt |  | Total Amt Posted |  | Hardware Rev | Services Rev | Services GP | Services GP %
07/27/15 |  | 09/30/15 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J001335 | cascade project | N/A | 0% | 0% | 3000 | 3000 | 105000 | 0 | 100% | 105000 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
01/05/16 |  | 01/04/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J002287 | 8000106462 | Closed | 100% | 0% | 2 | 2 | 70 | 0 | 100% | 70 | 0 | 0 | 0 | 0 |  | 0 |  | 1406 | 0 | 0 | 0%
01/05/16 |  | 01/04/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J002288 | AAAQ12399 | Closed | 100% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 608.94 | 225 | 225 | 100%
01/05/16 |  | 01/04/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J002289 | AAAQ12458 | Closed | 100% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 164.25 | 50 | 50 | 100%
12/13/16 |  | 01/13/17 | Open | Muhammad Mukhtar | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J004863 | 8000212097 | N/A | 0% | 0% | 480 | 480 | 48000 | 0 | 100% | 48000 | 0 | 0 | 0 | 22100 |  | 0 |  | 0 | 22100 | 0 | 0%
03/30/16 |  | 03/29/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | Jake Sinclair |  |  | N/A | N/A | Houston ISD | J003937 | HOUSTON ISD VALUEADD | N/A | 0% | 550% | 1 | -4.5 | 35 | 522.5 | -450% | 35 | 0 | 5.5 | 522.5 | 0 |  | 522.5 |  | 0 | 0 | -522.5 | 0%
06/01/16 |  | 05/31/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J003777 | AAAQ14079 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 188 | 0 | 0 | 0%
07/14/16 |  | 07/13/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J003944 | AAAQ19627 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 159 | 50 | 50 | 100%
10/27/16 |  | 10/26/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J004559 | 0000283062 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 16.05 |  | 0 |  | 272.35 | 20 | 3.95 | 19.75%
12/01/16 |  | 11/30/17 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J004781 | 0000285912 | Closed | 100% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 528.37 | 20 | 20 | 100%
02/06/17 |  | 02/05/18 | Open | John Cone | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J003888 | 8000118670 | N/A | 0% | 0% | 480 | 480 | 16800 | 0 | 100% | 16800 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 16152 | 16152 | 100%
02/23/17 |  | 02/22/18 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J005282 | 0000292824 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 425 | 20 | 20 | 100%
04/06/17 |  | 04/05/18 | Open | Charles Ryan | N/A |  | N/A |  |  | N/A |  |  | Kristy L Dice | TX-DAL | Trinity River Authority | J005640 | CONTRACT#5090432 | N/A | 0% | 0% | 10 | 10 | 950 | 0 | 100% | 950 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 5600 | 5600 | 100%
06/05/17 |  | 06/04/18 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J006477 | 0000303096 | N/A | 0% | 0% | 2 | 2 | 70 | 0 | 100% | 70 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 20 | 20 | 100%
07/20/17 |  | 07/19/18 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J006453 | 0000305081 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 425 | 20 | 20 | 100%
07/21/17 |  | 07/20/18 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J006461 | AAAQ34336 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 50 | 50 | 100%
08/18/17 |  | 08/17/18 | Open | Crystal Gentry | N/A |  | N/A |  |  | N/A |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J006648 | 0000308012 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 425 | 20 | 20 | 100%
09/14/17 |  | 09/13/18 | Open | Anthony Thurman | N/A |  | N/A |  |  | N/A |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J006804 | BPO 4500267165-0 | N/A | 0% | 0% | 64 | 64 | 3200 | 0 | 100% | 3200 | 0 | 0 | 0 | 0 |  | 0 |  | 36801.27 | 10985 | 10985 | 100%
09/07/18 |  | 10/05/18 | Open | Ben Reyes | N/A |  | N/A |  |  | N/A |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00001078 | 0000338105 | Closed | 100% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 381 | 20 | 20 | 100%
01/21/19 |  | 02/21/19 | Open | Ben Reyes | N/A |  | N/A |  |  | John Velez |  |  | N/A | N/A | Houston ISD | J00003362 | NET-PRO-EU | Closed | 0% | 0% | 0 | -1 | 0 | 35 | 0% | 0 | 0 | 1 | 35 | 0 |  | 35 |  | 96.9 | 50 | 15 | 30%
02/05/19 |  | 02/05/20 | Open | Ben Reyes | N/A |  | N/A |  |  | John Velez |  |  | N/A | N/A | Houston ISD | J00003493 | NET-PRO-EU | Closed | 100% | 100% | 1 | 0 | 30 | 35 | 0% | 30 | 0 | 1 | 35 | 2.32 |  | 35 |  | 153.44 | 50 | 12.68 | 25.36%
02/05/19 |  | 02/05/20 | Open | Ben Reyes | N/A |  | N/A |  |  | John Velez |  |  | N/A | N/A | Houston ISD | J00003501 | NET-PRO-EU | Closed | 0% | 0% | 0 | -1 | 0 | 35 | 0% | 0 | 0 | 1 | 35 | 0 |  | 35 |  | 379.31 | 100 | 65 | 65%
02/05/20 |  | 02/05/20 | Open | Jim Blackwell | Chad Hart |  | Chad Hart |  |  | Jim Blackwell, Kevin Curtis, Luis Alvarez, Victor Estrada |  |  | Ashley F Freeman | TX-HOU | Greater Harris County 911 Emergency Network | J00006777 | PO 20-3510 - DNA - Admin Switch Refresh | Training/Knowledge Transfer/Documentation | 0% | 150.7% | 25.88 | -11.12 | 2368.6 | 3032.5 | -42.97% | 2368.6 | 2 | 39 | 2972.5 | 19.76 |  | 3032.5 |  | 397153.1 | 0 | -3052.26 | 0%
02/13/19 |  | 02/13/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Netsync Network Solutions | J00003557 | 2019-DAL OFFICE | N/A | 0% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
03/07/19 |  | 03/09/20 | Open | Ben Reyes | N/A |  | N/A |  |  | John Velez |  |  | N/A | N/A | Houston ISD | J00003789 | 8000288890 | Closed | 100% | 200% | 1 | -1 | 30 | 70 | -100% | 30 | 0 | 2 | 70 | 0 |  | 70 |  | 146.55 | 50 | -20 | -40%
03/07/19 |  | 03/09/20 | Open | Ben Reyes | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00003790 | 8000289032 | Closed | 100% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 348.22 | 75 | 75 | 100%
03/07/19 |  | 03/09/20 | Open | Ben Reyes | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00003791 | 8000289314 | Closed | 100% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 89.91 | 50 | 50 | 100%
03/25/19 |  | 03/25/20 | Open | Ben Reyes | N/A |  | N/A |  |  | John Velez |  |  | N/A | N/A | Houston ISD | J00003876 | AAAQ65674 | Closed | 100% | 100% | 1 | 0 | 30 | 35 | 0% | 30 | 0 | 1 | 35 | 0 |  | 35 |  | 328.42 | 50 | 15 | 30%
03/26/19 |  | 03/26/20 | Open | Ben Reyes | N/A |  | N/A |  |  | Thai Hong |  |  | N/A | N/A | Houston ISD | J00003888 | NET-PRO-EU | Closed | 100% | 933.3% | 6 | -50 | 0 | 1960 | -833.3% | 0 | 0 | 56 | 1960 | 62 |  | 1960 |  | 0 | 0 | -2022 | 0%
03/27/19 |  | 03/27/20 | Open | Ben Reyes | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00003899 | AAAQ67912 | Closed | 100% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 130.13 | 50 | 50 | 100%
03/28/19 |  | 03/30/20 | Open | Ben Reyes | N/A |  | N/A |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00003913 | AAAQ65561 | Closed | 100% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 90.6 | 0 | 0 | 0%
04/24/19 |  | 04/24/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004187 | 482116 | N/A | 0% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 2693.54 | 100 | 100 | 100%
05/21/19 |  | 05/21/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004493 | 487775 | N/A | 0% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 1529.9 | 100 | 100 | 100%
05/28/19 |  | 05/28/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004557 | 488538 | N/A | 0% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 1853.06 | 100 | 100 | 100%
06/03/19 |  | 06/03/20 | Open | Scott Guse | N/A |  | N/A |  |  | Andrew Adikwu, Charles Phillips, Darrell Walton, Deon Branish , Juan Pomares, Julio Cerrato, Matthew Kennewell, Robert Reid, Tabais Prater, William Chris Roome, Zachary Newman |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004594 | 488686 | N/A | 0% | 18.38% | 800 | 655 | 24000 | 8090 | 81.88% | 24000 | 2 | 147 | 7990 | 77.14 |  | 8090 |  | 0 | 80000 | 71832.86 | 89.79%
06/03/19 |  | 06/03/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004595 | 488686 | N/A | 0% | 0% | 800 | 800 | 24000 | 0 | 100% | 24000 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 19200 | 19200 | 100%
06/03/19 |  | 06/03/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004597 | 488782 | N/A | 0% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 2226.82 | 100 | 100 | 100%
06/04/19 |  | 06/04/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004604 | 488916 | N/A | 0% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 2049.29 | 100 | 100 | 100%
06/07/19 |  | 06/07/20 | Open | Scott Guse | N/A |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00004703 | 489115 | N/A | 0% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 0 |  | 0 |  | 1593.23 | 100 | 100 | 100%
07/05/20 |  | 07/05/20 | Open | Reihana Abdelmaksoud | Bryan Geoghan, Christopher Garcia, David Watkins, Jacob Parks, Jeffrey Holman, Joshua Adam Engle, Michael Brett Beggs, Pedro Cantu |  | David Watkins, Michael Brett Beggs |  |  | Darrell Walton, Joel Hubbard, Moises Rodriguez, Vitalii Stepanchenko, William Chris Roome |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00007932 | 1045085 | N/A | 0% | 1050% | 1 | -8 | 30 | 770 | -800% | 30 | 1.5 | 10.5 | 695 | 0 |  | 770 |  | 8419692.49 | 0 | -770 | 0%
08/06/20 |  | 08/06/20 | Open | Marco Lish | Christopher Puyear |  | Beau C. Devillier, Joshua Parker, Marco Lish |  |  | Adam Ko, Benjamin Brooks, Chase Davis, Ezekiel Obeisun, Juan Pomares, Julio Cerrato, Kairo Sauceda, Sean Cowhey, Tavis Jackson, Thai Truong, Zachary Newman |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00008059 | Phone Extension Reprogramming | On HOLD | 0% | 89.74% | 97.5 | 12 | 11368.5 | 5275 | 12.31% | 11368.5 | 2 | 87.5 | 5175 | 118.192 |  | 5275 |  | 0 | 14253.68 | 8860.488 | 62.16%
08/13/20 |  | 08/13/20 | Open | Ali Al-Haddad | Mark J Chambliss |  | Mark J Chambliss |  |  | Ahmed Jameel, Enea Muskaj, Hector R. Rivera, Hector Rivera, Jose R. Duarte, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Mohammed Al-Shaikhli, Muthanna Alameri, Rogelio Morgado-Perez, Sean Clay, Syed Zaidi, Zaid Alameen |  |  | N/A | N/A | Houston ISD | J00008083 | PO 8000326116 - QTY249 - C9K-PWR-650WAC-R/2 ERATE | Implementation/Deployment | 0% | 0% | 0 | -726.5 | 0 | 34549.75 | 0% | 0 | 10 | 736.5 | 34049.75 | 574.11 |  | 34549.75 |  | 209160 | 0 | -35123.86 | 0%
10/30/20 |  | 10/30/20 | Open | Tray Giddens | N/A |  | N/A |  |  | Abel Abraham, Aboobiada Aliabdalla, Adeline Tidjon, Ahmed Alkutel, Ahmed Hamad, Aide Guadian, Ana Morales, Brianna Johnson, Darrick Bonner, David Gonzalez, Desmond Thomas, Ekpenyong Otu, Eleazar Guzman, Eliana Guzman, Felipe Ajche, Gerardo Guzman, Gregory Clark, Gregory Posey, Harold Mauricio Gomez, Hugo Gutierrez, Jaylen Morgan, Jennifer Mares, Jesus Guadian, Joan Elmore, John Silva, Jose E. Duarte Jr, Joseph Eneremadu, Juan Mendoza, Kai Rose , Kenia Dimas, Miguel Campos, Moses Mwamba |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00008064 | 0000391611 - Student 14000 | Closed | 100% | 35.25% | 14000 | 9065.08 | 420000 | 163067.6 | 64.75% | 420000 | 0 | 4934.92 | 163067.6 | 3246.38 |  | 163067.6 |  | 8223180 | 458260 | 291946.02 | 63.71%
06/19/20 |  | 11/20/20 | Open | Marshall Chuck Pugh | Joshua Adam Engle |  | Anthony Towsley, Charles Ryan, Joshua Parker, Marshall Chuck Pugh |  |  | Charles Ryan , Conner MacDonnell, Juan Pomares, Keiaudra Parker, Marshall Chuck Pugh , Matthew Veach, Orlando Francis, Sean Cowhey, Thai Truong, Vitalii Stepanchenko |  |  | Joshua Parker | TX-DAL | Carrollton-Farmers Branch ISD | J00007833 | ERATE CAT 2 - x32 location Switches & APs | On HOLD | 15% | 17.29% | 1327.14 | 1098.64 | 83197.8 | 13477.5 | 82.78% | 83197.8 | 1 | 229.5 | 13427.5 | 78.9 |  | 13477.5 |  | 936971.1 | 147188.1 | 133631.7 | 90.79%
11/09/20 |  | 12/04/20 | Open | Ali Al-Haddad | N/A |  | Ali Al-Haddad |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Ali Al-Haddad, Andrew Adikwu, Andy Alvarenga, Andy Pham, Baq Alsaedi, Bryant Bush, Daniel Hernandez, David Dobbs, David Neal Gravatt, Devinn Anthony Campbell, Devon LeMoine, Dueart Barton, Enea Muskaj, Hector Rivera, Jackory Nash, Jaime Flores, James Adams, Jeff Ogbor, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Jose R. Duarte, Julio C Montoya, Justin Higgins, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenia Dimas, Kenneth Stevenson, Kevi |  |  | N/A | N/A | Houston ISD | J00009095 | ERATE 20 - ES | Implementation/Deployment | 95% | 0% | 0 | -13271.86 | 756.23 | 933437.5 | 0% | 756.23 | 1243.44 | 14515.3 | 870815.5 | 13416.161 |  | 933437.5 |  | 514408.06 | 123175 | -823678.661 | -668.7%
11/02/20 |  | 12/04/20 | Open | Ali Al-Haddad | N/A |  | Ali Al-Haddad |  |  | Abdalsattar Albaghdadi, Ali Al-Haddad, Andy Alvarenga, Andy Pham, Baq Alsaedi, Devinn Anthony Campbell, Devon LeMoine, Dueart Barton, Enea Muskaj, Hector Rivera, James Adams, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Jose R. Duarte, Julio C Montoya, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kendric Mamou, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Nicolas Garakani, Paul Serres, Rob |  |  | N/A | N/A | Houston ISD | J00009096 | ERATE 20 - MS | Implementation/Deployment | 95% | 0% | 0 | -6159.1 | 378.72 | 458547.75 | 0% | 378.72 | 330.28 | 6489.38 | 441665 | 5539.758 |  | 458547.75 |  | 224647.55 | 78045 | -386042.508 | -494.6%
11/02/20 |  | 12/04/20 | Open | Ali Al-Haddad | Robert V Eubanks |  | Ali Al-Haddad |  |  | Aleksei Lavrushenkov, Ali Al-Haddad, Andy Alvarenga, Andy Pham, Baq Alsaedi, Bryant Bush, Daniel Hernandez, David Dobbs, Devon LeMoine, Dueart Barton, Enea Muskaj, Hector Rivera, Jackory Nash, Jaime Flores, James Adams, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Jose R. Duarte, Julio C Montoya, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Paul Serres, Robert |  |  | N/A | N/A | Houston ISD | J00009097 | ERATE 20 - HS | Implementation/Deployment | 95% | 0% | 0 | -4127.46 | 113.9 | 274968.5 | 0% | 113.9 | 458.41 | 4585.87 | 252020.5 | 4067.782 |  | 274968.5 |  | 1749084.14 | 48975 | -230061.282 | -469.8%
01/07/21 |  | 01/07/21 | Open | Jeremy Johns | N/A |  | N/A |  |  | Crespin Guerrero, Roland Hernandez |  |  | Ashley F Freeman | TX-HOU | Harris County - Texas | J00006423 | P332069 - x15 SMART-UPS 1500VA | Not started | 0% | 0% | 0 | -5 | 0 | 300 | 0% | 0 | 2.5 | 7.5 | 175 | 0 |  | 300 |  | 13189.8 | 1875 | 1575 | 84%
01/28/21 |  | 01/28/21 | Open | Sarah Morrison | N/A |  | N/A |  |  | Steven Walker |  |  | Taylor Leger | TX-DAL | Wynne Transportation | J00006535 | WD01132020YS | Not started | 0% | 59.17% | 23.66 | 9.66 | 2646.7 | 1890 | 40.83% | 2646.7 | 0 | 14 | 1890 | 0 |  | 1890 |  | 10805 | 4000 | 2110 | 52.75%
08/21/20 |  | 04/30/21 | Open | Jim Blackwell | Albert H Nguyen |  | N/A |  |  | Aaron Abshire, Aaron Johns, Darrell Walton, Dionisio Oscar Medina-Marcelin, Donald Muskaj, Felipe Waterwall, Jaime Flores, Jim Blackwell, Kevin Kunimoto, William Chris Roome |  |  | Joseph Boglino | US-FED | GMC Tek, LLC | J00008347 | RITM155370 GMCO1737 - Martinsburg, WV - DOM POD A | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -144 | 0 | 15452.5 | 0% | 0 | 32 | 176 | 13652.5 | 3529.58 |  | 15452.5 |  | 32102.3 | 22900 | 3917.92 | 17.11%
08/21/20 |  | 04/30/21 | Open | Jim Blackwell | Albert H Nguyen |  | N/A |  |  | Aaron Abshire, Aaron Johns, Darrell Walton, Dionisio Oscar Medina-Marcelin, Donald Muskaj, Felipe Waterwall, Jaime Flores, Jim Blackwell, Kevin Kunimoto, William Chris Roome |  |  | N/A | N/A | GMC Tek, LLC | J00008347 | RITM155370 GMCO1737 - Martinsburg, WV - DOM POD A | Training/Knowledge Transfer/Documentation | 95% | 0% | 45.03 | 45.03 | 5258.5 | 0 | 100% | 5258.5 | 0 | 0 | 0 | 3529.58 |  | 0 |  | 32102.3 | 22900 | 19370.42 | 84.59%
05/05/21 |  | 05/05/21 | Open | Michael Burk | Mark J Chambliss |  | Mark J Chambliss |  |  | Ali John, Ashley Stewart, Craig St. Rose, Crespin Guerrero, David Dobbs, Enea Muskaj, Hector Rivera, Justin Cornish, Justin Smallwood, Kord Mullins, Luis Alvarez, Mohammed Al-Shaikhli, Mustafa Husni, Truong Nguyen, Victor Estrada |  |  | N/A | N/A | Houston ISD | J00006634 | PO 8000317870 - x50 SMART ONLINE UPS 2200VA-Test | Not started | 0% | 0% | 0 | -129.25 | 0 | 6167.5 | 0% | 0 | 11 | 140.25 | 5697.5 | 82.69 |  | 6167.5 |  | 122295 | 7400 | 1149.81 | 15.54%
10/02/21 |  | 10/02/21 | Open | Michelle Duenes | Andrew Wells |  | N/A |  |  | Felipe Ajche, Gregory Posey, Harold Gomez, Harold Mauricio Gomez, Jesus Guadian, Lorenzo Hernandez, Oscar Nunez, Samsoni Jean Claude, Zaidoon Al Ani |  |  | Grant Jacobs | CA-LAX | Tekion Corp | J00011335 | NO PO AAAQ338436-02 | N/A | 0% | 0% | 0 | -73.5 | 0 | 2205 | 0% | 0 | 0 | 73.5 | 2205 | 0 |  | 2205 |  | 0 | 9558.39 | 7353.39 | 76.93%
10/02/21 |  | 10/02/21 | Open | Michelle Duenes | Andrew Wells |  | N/A |  |  | Felipe Ajche, Gregory Posey, Harold Gomez, Harold Mauricio Gomez, Jesus Guadian, Lorenzo Hernandez, Oscar Nunez, Samsoni Jean Claude, Zaidoon Al Ani |  |  | N/A | N/A | Tekion Corp | J00011335 | NO PO AAAQ338436-02 | N/A | 0% | 1.327% | 452 | 446 | 15820 | 180 | 98.67% | 15820 | 0 | 6 | 0 | 0 |  | 180 |  | 0 | 9558.39 | 9378.39 | 98.12%
02/21/22 |  | 04/08/22 | Open | Brian Willery | Andrew Wells |  | Brian Willery, Larry Noble, Susan Richardson |  |  | Ana Morales, Antonio Acosta, Darrick Bonner, Dedric Bowens, Enrique Valdes, Felipe Ajche, Harold Mauricio Gomez, Ishmeal Vaughn, Jesus Guadian, Lorenzo Hernandez, Maria Rivera, Quint Charvis, William Van der Voort |  |  | Susan Richardson | TX-HOU | Aldine ISD | J00012023 | PC Imaging Etching & Install | Not started | 5% | 114% | 182 | -25.5 | 6370 | 6250 | -14.01% | 6370 | 0 | 207.5 | 6250 | 81.28 |  | 6250 |  | 332745.14 | 10621.52 | 4290.24 | 40.39%
12/20/21 |  | 07/01/22 | Open | Brian Willery | Christopher Puyear |  | Brian Willery, Christopher Puyear, Jonathan Pendrich |  |  | Henry Pugsley |  |  | Jonathan Pendrich | TX-DAL | Army Airforce Exchange Services (AAFES) | J00011964 | SIP Analog Modem Server for Lab | On HOLD | 0% | 1.891% | 26.44 | 25.94 | 3054.3 | 67.5 | 98.11% | 3054.3 | 0 | 0.5 | 67.5 | 0 |  | 67.5 |  | 26983.83 | 3541.56 | 3474.06 | 98.09%
06/26/20 |  | 07/29/22 | Open | Karyn Hubbard | Joshua Adam Engle, Timothy Rosser |  | N/A |  |  | Charles Ryan , Karyn Hubbard, Ryan Scott |  |  | Rusty Bryan | TX-DAL | Midland ISD | J00007871 | PO 9342000165 - Network HW for Fiber WAN | Cancelled | 50% | 11.05% | 847.13 | 753.48 | 88784.85 | 8896.75 | 88.95% | 88784.85 | 0 | 93.65 | 8896.75 | 0 |  | 8896.75 |  | 0 | 0 | -8896.75 | 0%
05/09/22 |  | 09/09/22 | Open | Brian Willery | Joshua Adam Engle |  | Beau C. Devillier, Brian Willery, Jean Pierre Obenda, Lauren J Kennewell, Vitalii Stepanchenko |  |  | Brian Willery, Carlo Enriquez, Chase Davis, Conner MacDonnell, Daniel Hernandez, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelin, Dylan Pittsinger, Jean Pierre Obenda, Jhon Genao, Joel Fleming, Joel Hubbard, Jordan Newman, Juan Pomares, Kanoa Parman, Luis Hernandez, Orlando Francis, Patrick Thompson, Sean Cowhey, Taylor Poole, Thai Truong, Timothy Mitchell, Vitalii Stepanchenko |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00012957 | Burks-Webb-Johnson Schools - Network PS | Closed | 100% | 214.1% | 486.34 | -517.96 | 38892.5 | 89975 | -106.5% | 38892.5 | 37 | 1041.3 | 86877.5 | 2790.53 |  | 89975 |  | 0 | 58797 | -33968.53 | -57.77%
05/24/21 |  | 09/30/22 | Open | Brian Willery | Billy Pearson, Firas Abood, Wyley Johnson |  | Brian Willery, Larry Noble, Susan Richardson |  |  | Aaron Abshire, Cory Bradfield, Felipe Waterwall, Luis Alvarez, Victor Estrada |  |  | Susan Richardson | TX-HOU | Klein ISD | J00010667 | UCS and FortiSiem (Fortinet third party) | Training/Knowledge Transfer/Documentation | 95% | 222.9% | 38.8 | -37.7 | 4017.7 | 7522 | -97.16% | 4017.7 | 10 | 86.5 | 6638 | 0 |  | 7522 |  | 437100.6 | 5547.2 | -1974.8 | -35.6%
03/07/22 |  | 09/30/22 | Open | Karyn Hubbard | Joshua Adam Engle, Timothy Rosser |  | N/A |  |  | N/A |  |  | Rusty Bryan | TX-DAL | Midland ISD | J00008163 | 9342000165 - Fiber WAN | Not started | 50% | 0% | 1 | 1 | 30 | 0 | 100% | 30 | 0 | 0 | 0 | 40.83 |  | 0 |  | 0 | 0 | -40.83 | 0%
10/12/20 |  | 10/11/22 | Open | Marco Lish | N/A |  | N/A |  |  | Carlo Enriquez, Darrell Walton, Dionisio Oscar Medina-Marcelin, Dionisio Oscar Medina-Marcelino, James Danner, Jonathan Plante, Kanoa Parman, Tevin Beanum, William Chris Roome |  |  | Jonathan Pendrich | TX-DAL | United Services Automobile Association | J00008441 | Logistics Services | Planning/Design/Staging | 0% | 0% | 0 | -97.5 | 0 | 7472.5 | 0% | 0 | 0 | 97.5 | 7472.5 | 0 |  | 7472.5 |  | 78212 | 0 | -7472.5 | 0%
11/04/22 |  | 12/30/22 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014187 | 23111782 | Closed | 100% | 12.76% | 3.92 | 3.42 | 154.3 | 62.5 | 87.24% | 154.3 | 0 | 0.5 | 62.5 | 0 |  | 62.5 |  | 0 | 237.84 | 175.34 | 73.72%
11/04/22 |  | 12/30/22 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - Laredo | J00014180 | 23011002 | Closed | 100% | 4.931% | 10.14 | 9.64 | 398.1 | 62.5 | 95.07% | 398.1 | 0 | 0.5 | 62.5 | 0 |  | 62.5 |  | 0 | 579.6 | 517.1 | 89.22%
11/04/22 |  | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | N/A |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - Laredo | J00014181 | 23011059 | Closed | 100% | 0% | 1.05 | 1.05 | 41.25 | 0 | 100% | 41.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 55.12 | 55.12 | 100%
11/04/22 |  | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Eleazar Guzman, Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - Odessa | J00014182 | 23041034 | Closed | 100% | 51.02% | 2.94 | 1.44 | 115.5 | 92.5 | 48.98% | 115.5 | 0 | 1.5 | 92.5 | 0 |  | 92.5 |  | 0 | 277.8 | 185.3 | 66.7%
11/04/22 |  | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Austin | J00014188 | 23130658 | Closed | 100% | 47.62% | 2.1 | 1.1 | 82.5 | 125 | 52.38% | 82.5 | 0 | 1 | 125 | 0 |  | 125 |  | 0 | 110.24 | -14.76 | -13.39%
11/04/22 |  | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Eleazar Guzman, Eliana Guzman, Oscar Nunez, Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Houston | J00014186 | 23080907 | Closed | 100% | 303.9% | 1.81 | -3.69 | 71.45 | 212.5 | -203.9% | 71.45 | 0 | 5.5 | 212.5 | 0 |  | 212.5 |  | 0 | 144.2 | -68.3 | -47.36%
06/27/22 |  | 02/10/23 | Open | Brian Willery | N/A |  | Abdulrahman Farhan, Brian Willery, Jason Osuna, Larry Noble, Romar Roca |  |  | Abdulrahman Farhan, Brian Willery, Romar Roca |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00012741 | ASA Refresh | Closed | 100% | 89.23% | 365.34 | 57.34 | 53786.25 | 48637.5 | 15.69% | 53786.25 | 18 | 326 | 45937.5 | 112.01 |  | 48637.5 |  | 0 | 0 | -48749.51 | 0%
06/13/22 |  | 02/17/23 | Open | Brian Willery | Wyley Johnson |  | N/A |  |  | Brian Willery |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00012044 | ASA Refresh | Closed | 100% | 5.187% | 365.34 | 346.39 | 45748.8 | 2368.75 | 94.81% | 45748.8 | 0 | 18.95 | 2368.75 | 0 |  | 2368.75 |  | 44540.58 | 68440.4 | 66071.65 | 96.54%
01/13/23 |  | 03/23/23 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Isaac Brown, Abiodun David Babasola, Aboobiada Ali Abdalla, Andrew Comeaux, Anthony Balogun, David Lenihan, Dedric Bowens, Devante Humphrey, Eliana Guzman, Enrique Valdes, Gregory Posey, Kai Rose , Kaustuv Ghosh |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00014580 | Chromebook Install | Closed | 0% | 0% | 0 | -483.75 | 0 | 14702.5 | 0% | 0 | 0 | 483.75 | 14702.5 | 952.99 |  | 14702.5 |  | 1083000 | 234000 | 218344.51 | 93.31%
02/28/23 |  | 03/24/23 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Adam Ko, Chase Davis, David Gonzalez, Enrique Medina Valdes, Gregory Posey, Harold Gomez, Joel Hubbard, Pablo Bernal, Zachary Newman |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00014430 | 02309382 | Closed | 100% | 31.92% | 250 | 170.2 | 8750 | 3378 | 68.08% | 8750 | 0 | 79.8 | 3378 | 21.84 |  | 3378 |  | 494313.12 | 60000 | 56600.16 | 94.33%
02/28/23 |  | 03/28/23 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Adam Ko, Anthony Balogun, Chase Davis, David Gonzalez, David Lenihan, Enrique Medina Valdes, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, Joel Hubbard, Oscar Nunez, Pablo Bernal, Samsoni Jean Claude, Zachary Newman |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00014432 | 02308970 | Closed | 100% | 34.69% | 670 | 437.6 | 23450 | 9084 | 65.31% | 23450 | 0 | 232.4 | 9084 | 0 |  | 9084 |  | 532234.6 | 160800 | 151716 | 94.35%
12/21/22 |  | 03/28/23 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Abiodun David Babasola, Adam Ko, Chase Davis, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, Joel Hubbard, Juan Pomares, Pablo Bernal, Samsoni Jean Claude, Zachary Newman |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00014442 | 02309383 | Closed | 100% | 23.69% | 359 | 273.95 | 12565 | 4460.5 | 76.31% | 12565 | 0 | 85.05 | 4460.5 | 0 |  | 4460.5 |  | 350664.57 | 86640 | 82179.5 | 94.85%
11/04/22 |  | 03/29/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Lorenzo Hernandez |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Sugarland | J00014183 | 23080891 | Closed | 100% | 208.3% | 0.48 | -0.52 | 18.6 | 30 | -108.3% | 18.6 | 0 | 1 | 30 | 0 |  | 30 |  | 0 | 29.92 | -0.08 | -0.2674%
11/09/22 |  | 03/31/23 | Open | Brian Willery | Bryan Geoghan |  | Brian Newman, Brian Newman, Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Newman |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014067 | Collaboration Upgrade to 14 | Closed | 100% | 83.95% | 101.25 | 16.25 | 14006.25 | 11900 | 16.05% | 14006.25 | 0 | 85 | 11900 | 0 |  | 11900 |  | 0 | 13726.4 | 1826.4 | 13.31%
08/31/22 |  | 03/31/23 | Open | Tray Giddens | N/A |  | Ashley F Freeman, Larry Noble, Tray Giddens |  |  | Isaac Brown, Andrew Comeaux, David Gonzalez, David Lenihan, Dedric Bowens, Devante Humphrey, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, John Silva, Kaustuv Ghosh, Oscar Nunez, Samsoni Jean Claude, Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00013827 | FBISD AV classroom and carts | Closed | 100% | 85.41% | 606.99 | 88.59 | 27314.25 | 21442 | 14.59% | 27314.25 | 0 | 518.4 | 21442 | 0 |  | 21442 |  | 1500931.7 | 39150 | 17708 | 45.23%
12/19/22 |  | 03/31/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | N/A |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014385 | 23112109 | Closed | 100% | 0% | 2.84 | 2.84 | 112 | 0 | 100% | 112 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 334.04 | 334.04 | 100%
12/19/22 |  | 03/31/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | N/A |  |  | Monica Johnson | TX-HOU | Harmony Public Schools San Antonio | J00014390 | 23011107 | Closed | 100% | 0% | 1.05 | 1.05 | 41.25 | 0 | 100% | 41.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 55.12 | 55.12 | 100%
02/28/23 |  | 04/13/23 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Adam Ko, David Gonzalez, Enrique Medina Valdes, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, Joel Hubbard, Samsoni Jean Claude |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00014429 | 02308971 | Closed | 100% | 61.6% | 125 | 48 | 4375 | 2910 | 38.4% | 4375 | 0 | 77 | 2910 | 121.66 |  | 2910 |  | 250476.25 | 30000 | 26968.34 | 89.89%
01/18/23 |  | 04/14/23 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Beau C. Devillier, Brian Willery, Cristino Vega, Jacob Sennett, James Elmore, James Elmore, Lauren J Kennewell, Sophia Quinter |  |  | Brian Willery, Cristino Vega, Prince Owusu, Ron Loge, Sophia Quinter |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00014561 | Remote ISE Nodes Installation and Config | Closed | 100% | 127.6% | 138.94 | -38.36 | 20455 | 24312.5 | -27.61% | 20455 | 0 | 177.3 | 23862.5 | 0 |  | 24312.5 |  | 28911.2 | 33750.4 | 9437.9 | 27.96%
10/24/22 |  | 04/21/23 | Open | Joanna Herrera | Edward Padron, Rogelio Dominguez |  | Joanna Herrera, Ruben Cantu, Steve J Rodriguez, Xavier A Trevino |  |  | Felix Martinez, Francisco Medrano, Joanna Herrera, Jose Salazar, Marisela Contreras, Ruben Cantu |  |  | Xavier A Trevino | TX-SOUT | City of Brownsville | J00012772 | Work Order – IDF Closet @ IS Bldg B | Closed | 100% | 89.9% | 52 | 12.75 | 4908.5 | 4945 | 24.52% | 4908.5 | 7.5 | 46.75 | 4375 | 35.83 |  | 4945 |  | 25065.12 | 21160.32 | 16179.49 | 76.46%
04/18/22 |  | 04/28/23 | Open | Brian Willery | Charles Brown, David Escamilla |  | Osazee Eweka |  |  | Brian Willery, Charles Brown, Osazee Eweka |  |  | N/A | N/A | Amazon Web Services | J00012911 | AWS Migration Evaluator - Work Order | Closed | 100% | 0% | 24.75 | 24.75 | 2895.75 | 0 | 100% | 2895.75 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 3958.8 | 3958.8 | 100%
04/18/22 |  | 04/28/23 | Open | Brian Willery | Charles Brown, David Escamilla |  | Osazee Eweka |  |  | Brian Willery, Charles Brown, Osazee Eweka |  |  | Susan Richardson | TX-HOU | Amazon Web Services | J00012911 | AWS Migration Evaluator - Work Order | Closed | 0% | 0% | 0 | -43 | 0 | 5475 | 0% | 0 | 0 | 43 | 5475 | 0 |  | 5475 |  | 0 | 3958.8 | -1516.2 | -38.3%
10/14/22 |  | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014148 | 23111694 | Closed | 100% | 12.5% | 8 | 7 | 314.2 | 125 | 87.5% | 314.2 | 0 | 1 | 125 | 0 |  | 125 |  | 0 | 607.48 | 482.48 | 79.42%
10/14/22 |  | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014163 | 23111721 | Closed | 100% | 69.44% | 1.44 | 0.44 | 64.8 | 125 | 30.56% | 64.8 | 0 | 1 | 125 | 0 |  | 125 |  | 0 | 104.4 | -20.6 | -19.73%
11/14/22 |  | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014379 | 23111961 | Closed | 100% | 208.3% | 0.48 | -0.52 | 18.6 | 125 | -108.3% | 18.6 | 0 | 1 | 125 | 0 |  | 125 |  | 0 | 29.92 | -95.08 | -317.8%
11/04/22 |  | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Dedric Bowens, Jesus Guadian, Samsoni Jean Claude, Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - Katy | J00014184 | 23080892 | Closed | 100% | 134.2% | 8.94 | -3.06 | 351.6 | 455 | -34.23% | 351.6 | 0 | 12 | 455 | 0 |  | 455 |  | 0 | 871.92 | 416.92 | 47.82%
11/04/22 |  | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Austin | J00014189 | 23130698 | Closed | 100% | 7.44% | 13.44 | 12.44 | 528 | 125 | 92.56% | 528 | 0 | 1 | 125 | 0 |  | 125 |  | 0 | 790 | 665 | 84.18%
12/19/22 |  | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Tray Giddens |  |  | Monica Johnson | TX-HOU | Harmony Public Schools El Paso | J00014387 | 23041098 | Closed | 100% | 15.87% | 6.3 | 5.3 | 247.5 | 125 | 84.13% | 247.5 | 0 | 1 | 125 | 0 |  | 125 |  | 0 | 544.28 | 419.28 | 77.03%
02/25/22 |  | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Tray Giddens |  |  | Ana Morales, Antonio Acosta, Dedric Bowens, Delilah Davis, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Mauricio Gomez, Hussein Majeed, Ishmeal Vaughn, Jesus Guadian, Kai Rose , Lorenzo Hernandez, Maria Rivera, Monica Cavazos, Oscar Nunez, Safa Abdallah, Samsoni Jean Claude, William Van der Voort |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Sugarland | J00012155 | 22081022 houston west | Closed | 100% | 49.55% | 646.85 | 326.35 | 22639.75 | 9705 | 50.45% | 22639.75 | 0 | 320.5 | 9705 | 231.32 |  | 9705 |  | 4843.68 | 37500 | 27563.68 | 73.5%
06/20/22 |  | 05/19/23 | Open | Brian Willery | Bryan Geoghan |  | Anthony Towsley, Brian Willery, Bryan Mullen, Lauren J Kennewell, Shiraz Humayun |  |  | Abdulrahman Farhan, Brian Willery, Bryan Mullen, Mohaymen Sodi |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00013293 | Library - Network Infrastructure Install | Closed | 100% | 59.42% | 369.39 | 149.89 | 40794.75 | 27637.5 | 40.58% | 40794.75 | 0 | 219.5 | 27637.5 | 219.72 |  | 27637.5 |  | 1053772.05 | 61491.68 | 33634.46 | 54.7%
05/22/23 |  | 05/22/23 | Open | Jim Blackwell | Firas Abood |  | Firas Abood, Jim Blackwell, Khalid Abunaja, Meredith A Richardson |  |  | Andy Pham, Jaime Flores, Jim Blackwell, Joshua Hubbard, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio |  |  | N/A | N/A | Houston ISD | J00015369 | Synology Video Storage | Closed | 100% | 40% | 43.75 | 29 | 5781.25 | 1505 | 66.29% | 5781.25 | 2.75 | 17.5 | 1340 | 10.4 |  | 1505 |  | 48323.52 | 4950 | 3434.6 | 69.39%
08/15/22 |  | 05/26/23 | Open | Brian Willery | Matthew Duncan |  | Brian Willery, Charles Brown, Matthew Duncan, Steve J Rodriguez, Xavier A Trevino |  |  | Brian Willery, Charles Brown, Juan Saenz, Osazee Eweka |  |  | N/A | N/A | Amazon Web Services | J00013506 | AWS Cybersecurity Migration | Closed | 100% | 0% | 114.4 | 114.4 | 13156 | 0 | 100% | 13156 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 21218 | 21218 | 100%
08/15/22 |  | 05/26/23 | Open | Brian Willery | Matthew Duncan |  | Brian Willery, Charles Brown, Matthew Duncan, Steve J Rodriguez, Xavier A Trevino |  |  | Brian Willery, Charles Brown, Juan Saenz, Osazee Eweka |  |  | Xavier A Trevino | TX-SOUT | Amazon Web Services | J00013506 | AWS Cybersecurity Migration | Closed | 0% | 0% | 0 | -181 | 0 | 24155 | 0% | 0 | 0 | 181 | 24155 | 0 |  | 24155 |  | 0 | 21218 | -2937 | -13.84%
11/14/22 |  | 05/29/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | N/A |  |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014380 | 23111847-001 | Closed | 100% | 0% | 2.1 | 2.1 | 82.5 | 0 | 100% | 82.5 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 110.24 | 110.24 | 100%
12/08/21 |  | 05/31/23 | Open | Jim Blackwell | Albert H Nguyen |  | Albert H Nguyen, Aleksei Lavrushenkov, Jim Blackwell, Mustafa Al-Tamimi, Truong Nguyen |  |  | Aaron Johns, Ahmed Jameel, Andy Alvarenga, Andy Pham, Craig St. Rose, David Dobbs, Hector Rivera, Jeff Ogbor, Jim Blackwell, Justin Higgins, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mustafa Al-Tamimi, Nathan Dao, Syed Zaidi, Victor Estrada |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00011620 | Fine Arts x8 Site Network & Wireless Upgrades | Closed | 0% | 0% | 0 | -530.25 | 0 | 31895 | 0% | 0 | 28 | 558.25 | 30495 | 1710.2628 |  | 31895 |  | 462660.4 | 41683.1 | 8077.8372 | 19.38%
03/07/22 |  | 06/01/23 | Open | Tray Giddens | Mark J Chambliss |  | Mark J Chambliss, Tray Giddens |  |  | Isaac Brown, Alexander Sanchez, Ana Morales, Andrew Comeaux, Anthony Balogun, Antonio Acosta, Axel Zavala, Brendacia Morgan, Brianna Mosqueda, Darrick Bonner, David Gonzalez, David Lenihan, Dedric Bowens, Devante Humphrey, Devin Bradford, Diana Cabrera, Eleazar Guzman, Eliana Guzman, Elliot Henriquez, Enrique Valdes, Felipe Ajche, Gregory Posey, Harold Gomez, Harold Mauricio Gomez, Ishmeal Vaughn, Jarshawn Newsome, Jaylen Morgan, Jesus Guadian, John Silva, Josias Ajche , Justin Jefferson, |  |  | N/A | N/A | Houston ISD | J00012230 | Esser Computer Lab 6690 | Closed | 100% | 86.06% | 6690 | 932.47 | 234150 | 201735.9 | 13.94% | 234150 | 0 | 5757.53 | 201735.9 | 7322.76 |  | 201735.9 |  | 6201880 | 0 | -209058.66 | 0%
04/24/23 |  | 06/02/23 | Open | Jim Blackwell | Albert H Nguyen |  | Ashley F Freeman, Jim Blackwell, Larry Noble |  |  | Ben Crouch, Moises Rodriguez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00015332 | T&E - Wireless Controller Debug | Closed | 0% | 0% | 0 | -22 | 0 | 3017.5 | 0% | 0 | 0 | 22 | 3017.5 | 0 |  | 3017.5 |  | 0 | 2700 | -317.5 | -11.76%
03/03/23 |  | 06/22/23 | Open | Brian Willery | N/A |  | Brian Willery, Felipe D. Waterwall, Felipe Waterwall, Larry Noble, Susan Richardson |  |  | Aaron Johns, Andy Alvarenga, Felipe Waterwall |  |  | Susan Richardson | TX-HOU | Klein ISD | J00013316 | WebEx Room Kit | Closed | 100% | 101.6% | 11.81 | -0.19 | 1003.75 | 750 | -1.609% | 1003.75 | 0 | 12 | 750 | 38.22 |  | 750 |  | 4739.4 | 1219.96 | 431.74 | 35.39%
07/05/23 |  | 07/05/23 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Adiel Alvarez, Felipe Ajche, Gregory Posey, Harold Gomez, Jarshawn Newsome, Jesus Guadian, Josias Ajche, Josue Iglesias, Nathanael Morales, Samsoni Jean Claude |  |  | Joshua Parker | TX-DAL | Universal Service Administrative Company | J00015697 | ECF2290007795-SLD | Closed | 0% | 0% | 0 | -349.5 | 0 | 10485 | 0% | 0 | 0 | 349.5 | 10485 | 373.84 |  | 10485 |  | 1200000 | 0 | -10858.84 | 0%
07/05/23 |  | 07/05/23 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Adiel Alvarez, Felipe Ajche, Gregory Posey, Harold Gomez, Jarshawn Newsome, Jesus Guadian, Josias Ajche, Josue Iglesias, Nathanael Morales, Samsoni Jean Claude |  |  | N/A | N/A | Universal Service Administrative Company | J00015697 | ECF2290007795-SLD | Closed | 100% | 0% | 3000 | 3000 | 105000 | 0 | 100% | 105000 | 0 | 0 | 0 | 373.84 |  | 0 |  | 1200000 | 0 | -373.84 | 0%
06/16/23 |  | 07/14/23 | Open | Tray Giddens | Robert Berken |  | Camille Elizabeth Taber, Jeff Barker, Tray Giddens |  |  | James Adams, Tray Giddens |  |  | Camille Taber | FL | Mainline | J00015193 | NSK Santa Fe AP\Switch Install | Closed | 100% | 117.4% | 34.5 | 9 | 2362.5 | 2852.5 | 26.09% | 2362.5 | 15 | 40.5 | 1952.5 | 1359.03 |  | 2852.5 |  | 0 | 3723.32 | -488.21 | -13.11%
07/22/23 |  | 07/22/23 | Open | Michelle Duenes | N/A |  | N/A |  |  | David Gonzalez, Harold Gomez, Oscar Nunez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00015863 | 0000457944 | N/A | 0% | 85% | 15 | 2.25 | 525 | 382.5 | 15% | 525 | 0 | 12.75 | 382.5 | 0 |  | 382.5 |  | 9810 | 450 | 67.5 | 15%
07/18/23 |  | 07/25/23 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Larry Noble, Tray Giddens |  |  | Jaime Flores, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00016071 | Deploy 90 Phones at ES 58 | Closed | 100% | 98.46% | 16.25 | 1.25 | 1506.25 | 1090 | 7.692% | 1506.25 | 1 | 16 | 1030 | 0 |  | 1090 |  | 0 | 2428.8 | 1338.8 | 55.12%
09/24/21 |  | 07/28/23 | Open | Jim Blackwell | Christine A Hupe |  | Ahmed Jameel, Aleksei Lavrushenkov, Christine A Hupe, Craig St. Rose, Craig St. Rose, Jim Blackwell, Mustafa Al-Tamimi |  |  | Ahmed Jameel, Aleksei Lavrushenkov, Andy Alvarenga, Andy Pham, Bobby Fontenot, Craig St. Rose, Daniel Hernandez, David Dobbs, Hector Rivera, Jaime Flores, Jim Blackwell, Justin Higgins, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mustafa Al-Tamimi, Paul Serres, Victor Estrada |  |  | N/A | N/A | Dickinson ISD | J00011303 | PO 21003551 - ERATE21 - Meraki | Closed | 100% | 0% | 537.71 | 537.71 | 31832.8 | 0 | 100% | 31832.8 | 0 | 0 | 0 | 2831.258 |  | 0 |  | 979744.4 | 59016.2 | 56184.942 | 95.2%
09/24/21 |  | 07/28/23 | Open | Jim Blackwell | Christine A Hupe |  | Ahmed Jameel, Aleksei Lavrushenkov, Christine A Hupe, Craig St. Rose, Craig St. Rose, Jim Blackwell, Mustafa Al-Tamimi |  |  | Ahmed Jameel, Aleksei Lavrushenkov, Andy Alvarenga, Andy Pham, Bobby Fontenot, Craig St. Rose, Daniel Hernandez, David Dobbs, Hector Rivera, Jaime Flores, Jim Blackwell, Justin Higgins, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mustafa Al-Tamimi, Paul Serres, Victor Estrada |  |  | Neel Shah | TX-HOU | Dickinson ISD | J00011303 | PO 21003551 - ERATE21 - Meraki | Closed | 0% | 0% | 0 | -769.75 | 0 | 62397.5 | 0% | 0 | 175.5 | 945.25 | 53762.5 | 2831.258 |  | 62397.5 |  | 979744.4 | 59016.2 | -6212.558 | -10.53%
04/25/22 |  | 07/31/23 | Open | Karyn Hubbard | Joshua Adam Engle |  | Alexander Gutman, Beau C. Devillier, Chase Davis, Chase Davis, Juan Pomares, Kairo Sauceda, Karyn Hubbard, Magdalena Rodriguez, Moises Rodriguez, Nazario Armenta Barraza, Prince Owusu, Shawn Sutton, Taylor Poole, Thai Truong |  |  | Chase Davis, Kairo Sauceda, Karyn Hubbard, Lauren Lanzini Coffey, Moises Rodriguez, Nazario Armenta Barraza, Prince Owusu, Taylor Poole, Thai Truong, Timothy Mitchell, Zachary Newman |  |  | N/A | N/A | Dallas ISD | J00012901 | Unified Network Access - Surveys only | Closed | 100% | 0% | 594.14 | 594.14 | 43142.5 | 0 | 100% | 43142.5 | 0 | 0 | 0 | 949.042 |  | 0 |  | 0 | 100724.2 | 99775.158 | 99.06%
04/25/22 |  | 07/31/23 | Open | Karyn Hubbard | Joshua Adam Engle |  | Alexander Gutman, Beau C. Devillier, Chase Davis, Chase Davis, Juan Pomares, Kairo Sauceda, Karyn Hubbard, Magdalena Rodriguez, Moises Rodriguez, Nazario Armenta Barraza, Prince Owusu, Shawn Sutton, Taylor Poole, Thai Truong |  |  | Chase Davis, Kairo Sauceda, Karyn Hubbard, Lauren Lanzini Coffey, Moises Rodriguez, Nazario Armenta Barraza, Prince Owusu, Taylor Poole, Thai Truong, Timothy Mitchell, Zachary Newman |  |  | Shawn Sutton | TX-DAL | Dallas ISD | J00012901 | Unified Network Access - Surveys only | Closed | 0% | 0% | 0 | -691.9 | 0 | 80027.5 | 0% | 0 | 0 | 691.9 | 80027.5 | 949.042 |  | 80027.5 |  | 0 | 100724.2 | 19747.658 | 19.61%
02/09/23 |  | 08/08/23 | Open | Summer Abunaja | N/A |  | Aaron Christopher Pfeifer, Jamie Lewis, Jeff Barker, Summer Abunaja |  |  | Aaron Christopher Pfeifer, Media Alsewaili, Rafael Rodriguez-Vargas, Ron Loge |  |  | Jamie Lewis | US-SP | NineStar Connect | J00014942 | T&E PrePost Sales Network Consultation | Not started | 0% | 0% | 0 | -124.95 | 0 | 16801.25 | 0% | 0 | 0 | 124.95 | 15006.25 | 0 |  | 16801.25 |  | 0 | 0 | -16801.25 | 0%
12/19/22 |  | 08/10/23 | Open | Jason Esry | Emilio Carrillo |  | David D Tijerina, Jason Esry, Larry Noble |  |  | Jason Esry |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00014559 | x1 UPS for Central Office | Closed | 100% | 10.78% | 9.28 | 8.28 | 623.75 | 125 | 89.22% | 623.75 | 0 | 1 | 125 | 0 |  | 125 |  | 3500.39 | 818.8 | 693.8 | 84.73%
08/07/23 |  | 08/11/23 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Larry Noble, Tray Giddens |  |  | David Dobbs, Jaime Flores, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00016270 | MS 20 phone deployment 140 phones | Closed | 100% | 68.42% | 28.5 | 11 | 2080.5 | 1430 | 38.6% | 2080.5 | 2 | 19.5 | 1310 | 45.5 |  | 1430 |  | 0 | 4488.8 | 3013.3 | 67.13%
11/04/22 |  | 08/11/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Dedric Bowens, Eleazar Guzman, Lorenzo Hernandez |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Beaumont | J00014185 | 23080921 | Closed | 100% | 146.7% | 6 | -2.8 | 236.1 | 264 | -46.67% | 236.1 | 0 | 8.8 | 264 | 0 |  | 264 |  | 0 | 417.4 | 153.4 | 36.75%
08/29/22 |  | 08/14/23 | Open | LaQisha Marshall | Christopher Puyear, Timothy Ramsey |  | Hannah Paul, LaQisha Marshall, Larry Noble |  |  | Christopher Brown, Christopher Puyear, LaQisha Marshall |  |  | Hannah Edmunds | TX-CEN | Workforce Solutions Capital Area | J00013728 | PEN Test Remediation Support - Services | Closed | 100% | 130.6% | 81.16 | -24.84 | 10897.1 | 13932.5 | -30.61% | 10897.1 | 0 | 106 | 13932.5 | 0 |  | 13932.5 |  | 0 | 15361.2 | 1428.7 | 9.301%
07/28/23 |  | 08/18/23 | Open | Tray Giddens | David Escamilla |  | Dustin Huffman, Kathleen Brown, Kurt Sell, Luis Ovalles, Tray Giddens |  |  | Brian Willery, Carlo Enriquez, Dionisio Oscar Medina-Marcelino, Luis Ovalles, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Chevron Phillips Chemical | J00014755 | Nutanix cluster for Bartlesville | Closed | 100% | 188.5% | 71.1 | -47.9 | 9950.5 | 17297.5 | -67.37% | 9950.5 | 15 | 134 | 15272.5 | 929.93 |  | 17297.5 |  | 187618.05 | 14050.8 | -4176.63 | -29.73%
05/08/23 |  | 08/25/23 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Bryan Mullen, Joshua Adam Engle, Lauren J Kennewell, Shiraz Humayun |  |  | Bryan Mullen |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014251 | DC Site - Networking 2023 | Closed | 100% | 31.05% | 93.41 | 64.41 | 9789.3 | 3625 | 68.95% | 9789.3 | 0 | 29 | 3625 | 0 |  | 3625 |  | 34993.35 | 15417.6 | 11792.6 | 76.49%
05/12/23 |  | 08/25/23 | Open | Karyn Hubbard | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Dhulfiqar Al Hashimi, Karyn Hubbard, Kurt Sell, Lindie Lorraine Lamar |  |  | Dhulfiqar Al Hashimi, Karyn Hubbard, Timothy Sean Marcyes |  |  | Lindie Lamar | TX-HOU | Cloud Nine | J00015609 | Firewall Upgrade | Closed | 100% | 72.21% | 72.29 | 20.09 | 10642.5 | 7900 | 27.79% | 10642.5 | 0 | 52.2 | 7900 | 69.25 |  | 7900 |  | 1034.85 | 14331.72 | 6362.47 | 44.39%
03/15/21 |  | 08/25/23 | Open | Tray Giddens | Ahmed Al-Zubaidi, Billy Pearson, Wyley Johnson |  | Ahmed Al-Zubaidi, Billy Pearson, Jacob Sennett, Shannon Rico, Tray Giddens |  |  | Jacob Sennett, Tray Giddens |  |  | Susan Richardson | TX-HOU | Aldine ISD | J00010029 | Cisco Umbrella - Infloblox | Closed | 100% | 191.6% | 119.25 | -109.25 | 14932.75 | 25872.5 | -91.61% | 14932.75 | 0 | 228.5 | 25872.5 | 0 |  | 25872.5 |  | 6151.6 | 20483.2 | -5389.3 | -26.31%
07/03/23 |  | 08/28/23 | Open | Tray Giddens | Warren Wilson |  | Larry Noble, Lindie Lorraine Lamar, Tray Giddens |  |  | Garrett Hart, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Houston Housing Authority | J00015701 | Genetec Access Control | Closed | 100% | 120% | 30 | -6 | 3630 | 6000 | -20% | 3630 | 0 | 36 | 6000 | 0 |  | 6000 |  | 0 | 5082 | -918 | -18.06%
05/25/23 |  | 08/30/23 | Open | Jim Blackwell | Bryan Brown |  | Ashley F Freeman, Christopher Garcia, Felipe D. Waterwall, Felipe Waterwall, Jim Blackwell, Larry Noble |  |  | Felipe Waterwall, Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00015390 | WORK ORDER - Extron Services | Closed | 100% | 221.9% | 9.69 | -11.81 | 1327.5 | 2637.5 | -121.9% | 1327.5 | 0 | 21.5 | 2637.5 | 0 |  | 2637.5 |  | 0 | 2183.28 | -454.22 | -20.8%
12/14/22 |  | 08/31/23 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Bryan Mullen, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Bryan Mullen |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014341 | AFIS Router Setup | Closed | 100% | 101.5% | 41.64 | -0.61 | 4489.35 | 5281.25 | -1.465% | 4489.35 | 0 | 42.25 | 5281.25 | 0 |  | 5281.25 |  | 7821.65 | 7069.6 | 1788.35 | 25.3%
06/12/23 |  | 09/01/23 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Bryan Mullen |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014250 | Router for CH Site | Closed | 100% | 18.74% | 36.01 | 29.26 | 4110.6 | 843.75 | 81.26% | 4110.6 | 0 | 6.75 | 843.75 | 0 |  | 843.75 |  | 7046.55 | 6042.8 | 5199.05 | 86.04%
10/18/22 |  | 09/08/23 | Open | LaQisha Marshall | Timothy Ramsey |  | David D Tijerina, Eric Firestone, Kurt Sell, LaQisha Marshall, Timothy Ramsey |  |  | Eric Firestone, LaQisha Marshall |  |  | David D Tijerina | TX-CEN | Travis County | J00014116 | ISE Fixes - Labor Only | Closed | 100% | 42.13% | 54 | 31.25 | 7950 | 3043.75 | 57.87% | 7950 | 0 | 22.75 | 3043.75 | 0 |  | 3043.75 |  | 0 | 0 | -3043.75 | 0%
02/08/22 |  | 09/15/23 | Open | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Jim Blackwell, Larry Noble |  |  | Cory Bradfield, Craig St. Rose, Jeff Ogbor, Jim Blackwell, Jose R. Duarte, Justin Higgins, Kord Mullins, Luis Alvarez, Victor Estrada |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00011958 | DELL EMC Implementation | Closed | 100% | 257.6% | 53.76 | -68.24 | 5480.45 | 12360.5 | -126.9% | 5480.45 | 16.5 | 138.5 | 10543.5 | 45.84 |  | 12360.5 |  | 1022368.6 | 26001.2 | 13594.86 | 52.29%
01/11/23 |  | 09/15/23 | Open | LaQisha Marshall | Emilio Carrillo |  | Christi D Hubbard, Emilio Carrillo, Ernesto Gonzalez, James Danner, LaQisha Marshall, Larry Noble |  |  | Aldo Cortes, An Le, Angel Alicea-Torres, Ben Crouch, Delton Childs, Devon LeMoine, Ernesto Gonzalez, James Danner, Jeffrey Charles Primeaux, John Senkulics, Juan Carlos Flores, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kristopher Dwight, Kyle Linder, LaQisha Marshall, Matthew D'Ambrosio, Michael Torres, Mohammed Almoola, Stephen Camacho, Trevor Youngman, Vernon McAfee |  |  | Christi D Hubbard | TX-CEN | Schertz-Cibolo-Universal City ISD | J00013468 | ERATE 2020 - Network & Wireless | Closed | 100% | 131.5% | 1292.13 | -283.47 | 71386.5 | 122482.4 | -21.94% | 71386.5 | 123.94 | 1699.54 | 114866 | 5818.69 |  | 122482.4 |  | 1528155.36 | 135197.5 | 6896.41 | 5.101%
06/23/23 |  | 09/22/23 | Open | Brian Willery | Mark J Chambliss |  | Ming Chiu |  |  | Brian Willery, Ming Chiu |  |  | Susan Richardson | TX-HOU | Klein ISD | J00015542 | RedSky | Closed | 0% | 0% | 0 | -44.75 | 0 | 5713.75 | 0% | 0 | 0 | 44.75 | 5713.75 | 0 |  | 5713.75 |  | 87002.95 | 13204.8 | 7491.05 | 56.73%
09/01/23 |  | 09/29/23 | Open | Ali Al-Haddad | N/A |  | Ali Al-Haddad, Khalid Abunaja, Meredith A Richardson |  |  | Ali Al-Haddad, James Adams, Sajjad Abo Dbs |  |  | N/A | N/A | Houston ISD | J00016573 | FMOT - SFP | Closed | 0% | 0% | 0 | -12.5 | 0 | 1280 | 0% | 0 | 4.5 | 17 | 1010 | 0 |  | 1280 |  | 2162 | 0 | -1280 | 0%
07/10/23 |  | 09/29/23 | Open | Jim Blackwell | Albert H Nguyen |  | Albert H Nguyen, Ashley F Freeman, Jim Blackwell, Larry Noble |  |  | Andy Pham, Baq Alsaedi, Craig St. Rose, Devon LeMoine, Jaime Flores, Jesus Gonzalez, Jim Blackwell, Joanna Herrera, Justin Cornish, Justin Smallwood, Kord Mullins, Mustafa Al-Tamimi |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00015833 | Briargate ES Equipment decommission | Closed | 100% | 74.11% | 135.61 | 49.57 | 9450.25 | 6972.5 | 36.55% | 9450.25 | 14.46 | 100.5 | 6104.9 | 209.04 |  | 6972.5 |  | 0 | 19916 | 12734.46 | 63.94%
09/02/21 |  | 09/29/23 | Open | LaQisha Marshall | Emilio Carrillo |  | LaQisha Marshall |  |  | Aldo Cortes, Angel Alicea, Angel Alicea-Torres, Chase Delhaye, Delton Childs, Isaiah Covington, Jacobo Padilla, James Danner, Jeffrey Charles Primeaux, John Senkulics, Juan Carlos Flores, Kristopher Dwight, Kyle Linder, LaQisha Marshall, Micah Rendon, Michael Torres, Sarah Beatrice Williamson, Stephen Camacho, Trevor Youngman, Victor Estrada |  |  | Hannah Edmunds | TX-CEN | Judson ISD | J00011165 | 30010019 - District UPS Upgrade | Closed | 100% | 385.1% | 422.74 | -1028.26 | 24354.05 | 88463.75 | -243.2% | 24354.05 | 177 | 1628 | 79508.75 | 5610.318 |  | 88463.75 |  | 399267.5 | 38132.38 | -55941.688 | -146.7%
09/29/23 |  | 09/29/23 | Open | Media Alsewaili | Christopher Puyear |  | Henry Pugsley |  |  | Henry Pugsley, Media Alsewaili |  |  | Christi D Hubbard | TX-CEN | EANES ISD | J00011030 | NO PO AAAQ333694 - Informacast | Closed | 100% | 248.2% | 38.25 | -56.7 | 4551.75 | 13731.25 | -148.2% | 4551.75 | 0 | 94.95 | 13731.25 | 0 |  | 13731.25 |  | 52567.6 | 6872 | -6859.25 | -99.81%
05/12/23 |  | 10/13/23 | Open | LaQisha Marshall | Christopher Puyear, Emilio Carrillo |  | Christi D Hubbard, George McGann, LaQisha Marshall, Larry Noble, Raul Velazquez |  |  | Andy Pham, Charles Knox, Daniel Hernandez, David Dobbs, George McGann, James Adams, Jeffrey Charles Primeaux, Jose R. Duarte, Kevin Curtis, Kolawole Ayeni, Kyle Linder, LaQisha Marshall, Matthew D'Ambrosio, Miguel Reed, Paul Serres, Raul Velazquez, Richard Shea, Robert Jones, Sajjad Abo Dbs, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Del Valle ISD | J00014593 | Summer 2023 - Del Valle Middle School Install | Closed | 100% | 120.8% | 271.46 | 17.46 | 25106.75 | 24760 | 6.432% | 25106.75 | 74 | 328 | 19622.5 | 3340.46 |  | 24760 |  | 427062.8 | 27834 | -266.46 | -0.9573%
10/11/21 |  | 10/20/23 | Open | Media Alsewaili | N/A |  | Henry Pugsley, Kyle Linder, Media Alsewaili |  |  | Chase Delhaye, Henry Pugsley, Isaiah Covington, Jeffrey Charles Primeaux, Kyle Linder, Media Alsewaili, Micah Rendon, Robert Lavender |  |  | Christi D Hubbard | TX-CEN | EANES ISD | J00011467 | 6192200112 - A\V LCD Installs - AppSpace | Closed | 100% | 117.4% | 224.44 | -20.16 | 14720.3 | 15599 | -8.982% | 14720.3 | 19 | 263.6 | 14749 | 585.32 |  | 15599 |  | 0 | 0 | -16184.32 | 0%
08/25/21 |  | 10/26/23 | Open | Karyn Hubbard | David Watkins |  | David Watkins, Karyn Hubbard, Kirk O'Guinn, Matthew Veach, Patrick Shea Thompson, Patrick Thompson, Saravanan Lakshmanan, Shawn Sutton, Vitalii Stepanchenko |  |  | Adam Ko, Carlo Enriquez, Chase Davis, Conner MacDonnell, Daniel Crawford, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelin, Dionisio Oscar Medina-Marcelino, Dylan Pittsinger, Jean Pierre Obenda, Joel Fleming, Joel Hubbard, Joshua Hubbard, Juan Pomares, Kairo Sauceda, Kanoa Parman, Karyn Hubbard, Kirk O'Guinn, Matthew Veach, Moises Rodriguez, Noah Trump, Pablo Bernal, Patrick Shea Thompson, Phillip Thornton, Robert Kelly, Roberto Bernal, Saravanan Lakshmanan, Thai Truong, Timothy Mitch |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00011108 | ERATE - Partial Cat2 HW\Services for Wireless RFP | Closed | 100% | 77.52% | 2475.33 | 616.98 | 157073.7 | 148949.25 | 24.93% | 157073.7 | 60.5 | 1918.85 | 144544.25 | 5263.23 |  | 148949.25 |  | 231076.13 | 353445.58 | 199233.1 | 56.37%
02/20/23 |  | 10/26/23 | Open | LaQisha Marshall | Emilio Carrillo |  | Christi D Hubbard, Ernesto Gonzalez, LaQisha Marshall, Larry Noble, Raul Velazquez |  |  | Charles Knox, Chase Delhaye, Ernesto Gonzalez, Ethan Thomas George, Jeffrey Charles Primeaux, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kyle Linder, LaQisha Marshall, Matthew D'Ambrosio, Paul Serres, Raul Velazquez, Richard Shea, Robert Jones, Stephen Michael Murillo, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00013596 | Last x18 Sites - Servers_APs_UPs | Closed | 100% | 52.31% | 1445.18 | 717.73 | 102883.75 | 57648.25 | 49.66% | 102883.75 | 28.5 | 755.95 | 56208.25 | 2477.48 |  | 57648.25 |  | 1813387.63 | 86735.83 | 26610.1 | 30.68%
06/14/21 |  | 10/27/23 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Freddie Scott, James Elmore, James Elmore, Lauren J Kennewell, Shiraz Humayun |  |  | Andrew Comeaux, Brian Willery, Conner MacDonnell, Dionisio Oscar Medina-Marcelin, Freddie Scott, Gena Robbins, Jason Espino, Juan Pomares, Justin Thompson, Kimberly DeVos, Orlando Francis, Phillip Thornton, Tevin Beanum, William Chris Roome |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00010152 | PO 02102463 - Court Bldg. Network & Wireless | Closed | 100% | 236.4% | 58.91 | -71.84 | 4350.4 | 10145.75 | -121.9% | 4350.4 | 8.5 | 139.25 | 9653.25 | 135.15 |  | 10145.75 |  | 84505.4 | 9804.4 | -476.5 | -4.86%
10/17/22 |  | 10/27/23 | Open | Jim Blackwell | Albert H Nguyen, Mark J Chambliss |  | Albert H Nguyen, Aleksei Lavrushenkov, Jim Blackwell, Mark J Chambliss, Mustafa Al-Tamimi, Robert Brim |  |  | Aaron Johns, Ahmed Jameel, Andy Alvarenga, Andy Pham, Craig St. Rose, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jeff Ogbor, Jim Blackwell, Jose R. Duarte, Julio C Montoya, Justin Higgins, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mustafa Al-Tamimi, Nathan Dao, Sajjad Abo Dbs, Syed Zaidi |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00012883 | Bhuchar ES#53 Network - ERATE | Closed | 100% | 303.5% | 181.11 | -331.64 | 12452.25 | 38672.5 | -183.1% | 12452.25 | 37 | 549.75 | 36452.5 | 1684.684 |  | 38672.5 |  | 650692.36 | 28294.96 | -12062.224 | -42.63%
09/29/23 |  | 10/27/23 | Open | Jim Blackwell | Firas Abood, Jeremy R Freeman |  | Firas Abood, Jeremy R Freeman, Jim Blackwell |  |  | Ali Al-Haddad, Cory Bradfield, Devon LeMoine, James Adams, Jim Blackwell, Jose R. Duarte, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Truong Nguyen |  |  | N/A | N/A | Houston ISD | J00013099 | UCSX MDS Refresh - Option1 | Closed | 100% | 149.4% | 167.63 | -42.67 | 20144.5 | 29796.25 | -25.45% | 20144.5 | 40.2 | 250.5 | 24526.75 | 20.15 |  | 29796.25 |  | 2139728.68 | 32152 | 2335.6 | 7.264%
11/28/22 |  | 10/27/23 | Open | Richard Keith Arnst | N/A |  | Ashley F Freeman, John W. Geddie, Juan Saenz, Lee McChesney, Richard Keith Arnst, Ron Loge |  |  | Juan Saenz, Richard Keith Arnst |  |  | Ashley F Freeman | TX-HOU | Harris County Clerks Office | J00014401 | AWS Control Tower Setup - AWS FUNDED | Closed | 100% | 86.84% | 36.56 | 4.81 | 4212.5 | 4163.75 | 13.16% | 4212.5 | 0 | 31.75 | 4163.75 | 0 |  | 4163.75 |  | 0 | 0 | -4163.75 | 0%
02/06/23 |  | 10/27/23 | Open | Tray Giddens | Chad Hart |  | Dustin Huffman, Kurt Sell, Robert Brim, Tray Giddens |  |  | Andy Pham, Cory Bradfield, David Dobbs, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mustafa Al-Tamimi, Paul Serres, Robert Brim, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Central Bank | J00014583 | Main Site + Colo Switch Refresh | Closed | 0% | 0% | 0 | -65 | 0 | 7172.5 | 0% | 0 | 8 | 73 | 6352.5 | 120.37 |  | 7172.5 |  | 78813.01 | 7752.4 | 459.53 | 5.928%
02/06/23 |  | 10/27/23 | Open | Tray Giddens | Chad Hart |  | Dustin Huffman, Kurt Sell, Robert Brim, Tray Giddens |  |  | Andy Pham, Cory Bradfield, David Dobbs, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mustafa Al-Tamimi, Paul Serres, Robert Brim, Tray Giddens |  |  | N/A | N/A | Central Bank | J00014583 | Main Site + Colo Switch Refresh | Closed | 100% | 0% | 52.76 | 52.76 | 4912.8 | 0 | 100% | 4912.8 | 0 | 0 | 0 | 120.37 |  | 0 |  | 78813.01 | 7752.4 | 7632.03 | 98.45%
08/01/23 |  | 10/27/23 | Open | Tray Giddens | Warren Wilson |  | Garrett Hart, Larry Noble, Lindie Lorraine Lamar, Tray Giddens |  |  | Garrett Hart, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Houston Housing Authority | J00015960 | Genetec Cameras | Closed | 100% | 124.3% | 18.5 | -4.5 | 2118.5 | 3725 | -24.32% | 2118.5 | 0 | 23 | 3725 | 0 |  | 3725 |  | 3230.7 | 6456.7 | 2731.7 | 42.31%
07/04/22 |  | 11/08/23 | Open | Jason Esry | Emilio Carrillo |  | David D Tijerina, Jason Esry, Larry Noble |  |  | Aldo Cortes, Ernesto Gonzalez, James Danner, Jason Esry, Juan Carlos Flores, Kristopher Dwight, Michael Torres, Mohammed Almoola, Robert Kelly, Trevor Youngman |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00013221 | Cisco DNA Center Upgrade | Closed | 100% | 773% | 48.38 | -322.62 | 4847.5 | 46115 | -666.8% | 4847.5 | 3 | 374 | 45735 | 275.93 |  | 46115 |  | 209723.78 | 17532.8 | -28858.13 | -164.6%
11/28/22 |  | 11/10/23 | Open | Jim Blackwell | Ahmed Al-Zubaidi, Wyley Johnson |  | Abdulrahman Farhan, Ashley F Freeman, Jim Blackwell, Larry Noble |  |  | Abdulrahman Farhan, Jim Blackwell, Saif Qaissi |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00013692 | Qty2 - Cisco Secure Firewall 3130s Install | Closed | 100% | 108.4% | 202.5 | -17 | 29812.5 | 31825 | -8.395% | 29812.5 | 0 | 219.5 | 31825 | 0 |  | 31825 |  | 278449.6 | 50321.24 | 18496.24 | 36.76%
10/17/22 |  | 11/14/23 | Open | Jason Esry | Aman Khan |  | David D Tijerina, Ernesto Gonzalez, Jason Esry, Kristan Crawford, Kristan Kimberly Crawford, Kurt Sell |  |  | Ernesto Gonzalez, James Adams, Jason Esry, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Almoola, Nick Varga, Paul Serres |  |  | David D Tijerina | TX-CEN | Travis County Central Health DBA: Central Health | J00013956 | Large Switch Refresh | Closed | 100% | 64.35% | 237.78 | 105.03 | 19822.25 | 15907.5 | 44.17% | 19822.25 | 20.25 | 153 | 13782.5 | 205.4 |  | 15907.5 |  | 1905869.96 | 22614.88 | 6501.98 | 28.75%
02/06/23 |  | 11/15/23 | Open | Abiodun David Babasola | William Birdsong |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Abiodun David Babasola, Adam Ko, Austen Howard, Carlo Enriquez, Chase Davis, Conner MacDonnell, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelino, Dylan Pittsinger, Eleazar Guzman, Joel Fleming, Joel Hubbard, Joshua Hubbard, Kairo Sauceda, Kanoa Parman, Kirk O'Guinn, Luis Hernandez, Moises Rodriguez, Pablo Bernal, Patrick Thompson, Roberto Bernal, Tavis Jackson, Timothy Mitchell, William Chris Roome, Zachary Newman |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00013794 | ERATE - Summer 2023 District AP Refresh | Closed | 100% | 100.8% | 898.83 | 23.68 | 52748.25 | 66019 | 2.635% | 52748.25 | 31.25 | 906.4 | 63949 | 1392.504 |  | 66019 |  | 7338133.88 | 73490 | 6078.496 | 8.271%
04/21/23 |  | 11/15/23 | Open | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Julio C Montoya, Justin Smallwood, Khalid Abunaja, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Justin Smallwood, Karrar Al-Azzawi, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | J00015168 | Benavidez ES - CCTV | Closed | 0% | 0% | 0 | -28 | 0 | 1970 | 0% | 0 | 0.5 | 28.5 | 1940 | 0 |  | 1970 |  | 68927.7 | 900 | -1070 | -118.9%
06/30/23 |  | 11/17/23 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00015681 | 02321337 | Closed | 100% | 0% | 3000 | 3000 | 105000 | 0 | 100% | 105000 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 666000 | 666000 | 100%
07/11/22 |  | 11/17/23 | Open | Brian Willery | Mark J Chambliss |  | Brian Willery, Larry Noble, Ming Chiu, Susan Richardson |  |  | Aaron Johns, Aleksei Lavrushenkov, Andy Alvarenga, Andy Pham, Brian Willery, Bryant Bush, Craig St. Rose, Dana Rieger, Daniel Hernandez, David Dobbs, Devon LeMoine, Felipe Waterwall, Hector Rivera, Jaime Flores, James Adams, Jeff Ogbor, Jerald Garner, Jose R. Duarte, Justin Higgins, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Ming Chiu, Mohammed Al-Shaikhli, Nathan Dao, Syed Zaidi, Truong Nguyen |  |  | Susan Richardson | TX-HOU | Klein ISD | J00012392 | UC -Refresh | Closed | 100% | 180.4% | 3798.55 | -2411.15 | 458213.6 | 638425.7 | -63.48% | 458213.6 | 644.57 | 6854.27 | 599214 | 15062.2106 |  | 638425.7 |  | 4872674.22 | 156677.02 | -496810.8906 | -317.1%
09/08/23 |  | 11/17/23 | Open | Joaquin Marroquin | Edward Padron |  | Christopher Prado, Edward Padron, Joaquin Marroquin, Xavier A Trevino |  |  | Antonio Rivera, Carlos Carrillo, Christopher Prado, Francisco Hernandez, Jesus Cantu, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Security First Credit Union | J00014877 | Qty 16 Meraki APs for Branch Locations (RGV) | Closed | 100% | 153.4% | 43.47 | -17.56 | 4166.75 | 5394.55 | -40.4% | 4166.75 | 5.65 | 66.68 | 5055.55 | 116.26 |  | 5394.55 |  | 14205.92 | 5792.2 | 281.39 | 4.858%
10/18/22 |  | 11/30/23 | Open | Jason Esry | Robert Berken |  | David D Tijerina, Ernesto Gonzalez, Jason Esry, Kurt Sell |  |  | Charles Knox, Ernesto Gonzalez, Isaiah Covington, Jason Esry, Jeffrey Charles Primeaux, Kyle Linder, LaQisha Marshall, Micah Rendon, Robert Jones, Steven Shipmon, Truong Nguyen |  |  | David D Tijerina | TX-CEN | Travis County Central Health DBA: Central Health | J00014096 | Cisco DNAC Appliance Setup | Closed | 100% | 393.7% | 47.62 | -125.88 | 5400 | 16570 | -264.3% | 5400 | 14 | 187.5 | 15500 | 577.11 |  | 16570 |  | 0 | 45500 | 28352.89 | 62.31%
10/14/22 |  | 11/30/23 | Open | Media Alsewaili | William Birdsong, Wyley Johnson |  | Jeff Barker, Kreshnik Memaj, Media Alsewaili, Randy Schamberger, Romar Roca |  |  | Kreshnik Memaj, Media Alsewaili, Romar Roca |  |  | Randy Schamberger | FL | Sarasota Manatee Airport Auth. | J00013889 | Phase II Network Upgrade | Closed | 80% | 22.44% | 192.05 | 150.95 | 25156.25 | 5987.5 | 78.6% | 25156.25 | 2 | 43.1 | 5737.5 | 0 |  | 5987.5 |  | 0 | 34097.2 | 28109.7 | 82.44%
07/14/23 |  | 11/30/23 | Open | Tray Giddens | N/A |  | Ashley F Freeman, Larry Noble, Tray Giddens |  |  | Isaac Brown, Andrew Comeaux, David Gonzalez, David Lenihan, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Gomez, Jarshawn Newsome, Jesus Guadian, Josias Ajche, Josue Iglesias, Lorenzo Hernandez, Miguel Reed, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Shannan Thomas, Tray Giddens, Valentin Vasquez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016036 | FBISD Crawford HS pc | Closed | 100% | 59.44% | 1465.51 | 594.46 | 54509.45 | 30526.5 | 40.56% | 54509.45 | 0 | 871.05 | 30526.5 | 1158.88 |  | 30526.5 |  | 241086 | 44430 | 12744.62 | 28.68%
07/14/23 |  | 11/30/23 | Open | Tray Giddens | N/A |  | Ashley F Freeman, Larry Noble, Tray Giddens |  |  | Adiel Alvarez, Andrew Comeaux, Camila Guzman, David Gonzalez, David Lenihan, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Gomez, Jarshawn Newsome, Jesus Guadian, Josias Ajche, Josue Iglesias, Julienne Atangana, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Tray Giddens, Valentin Vasquez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016037 | FBISD Buchar ES | Closed | 100% | 49.47% | 797.46 | 402.96 | 34436.1 | 17392.5 | 50.53% | 34436.1 | 0 | 394.5 | 17392.5 | 360.4 |  | 17392.5 |  | 335296.9 | 18720 | 967.1 | 5.166%
07/14/23 |  | 11/30/23 | Open | Tray Giddens | N/A |  | Ashley F Freeman, Larry Noble, Tray Giddens |  |  | Adiel Alvarez, Andrew Comeaux, Camila Guzman, David Gonzalez, David Lenihan, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Gomez, Jarshawn Newsome, Jesus Guadian, Josias Ajche, Nathanael Morales, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez, Tray Giddens, Valentin Vasquez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016038 | FBISD Ferguson ES PC | Closed | 100% | 39.97% | 766.92 | 460.42 | 33117 | 14562.5 | 60.03% | 33117 | 0 | 306.5 | 14562.5 | 213.52 |  | 14562.5 |  | 782460.4 | 40321.28 | 25545.26 | 63.35%
06/01/23 |  | 12/01/23 | Open | Richard Keith Arnst | Albert H Nguyen, Bryan Brown, Mark J Chambliss |  | Felipe D. Waterwall, Felipe Waterwall, Larry Noble, Lindie Lorraine Lamar, Richard Keith Arnst |  |  | Aaron Johns, Andy Alvarenga, Daniel Hernandez, David Dobbs, Hector Rivera, Jose R. Duarte, Justin Higgins, Luis Alvarez, Miguel Reed, Nathan Dao, Richard Keith Arnst, Sajjad Abo Dbs |  |  | Lindie Lamar | TX-HOU | Prime Contractors | J00015431 | Meraki & AV Hardware Installs | Closed | 100% | 197.8% | 241.54 | -166.21 | 23267.75 | 35018.75 | -68.81% | 23267.75 | 70 | 477.75 | 30818.75 | 5897.085 |  | 35018.75 |  | 152360.41 | 51011.88 | 10096.045 | 19.79%
10/20/23 |  | 12/05/23 | Open | Karyn Hubbard | David Pena, Joshua Adam Engle, Timothy Rosser |  | Alexander Gutman, Arcangelo Fanelli, Beau C. Devillier, Darrell Walton, Darrell Walton, David Pena, Jonathan Weir, Jonathan Weir, Jose Gutierrez, Kairo Sauceda, Karyn Hubbard, Tavis Jackson, Timothy Rosser |  |  | Angelo Gallegos, Austen Howard, Bryan Mullen, Chase Davis, Conner MacDonnell, Darrell Walton, Dylan Pittsinger, Joel Hubbard, Jonathan Weir, Jose Gutierrez, Karyn Hubbard, Patrick Thompson, Tavis Jackson, Timothy Mitchell |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | J00013573 | 2023 - ERATE - Optical WAN | Closed | 100% | 80.7% | 827.72 | 167.77 | 91277.5 | 80013.75 | 20.27% | 91277.5 | 8 | 667.95 | 79623.75 | 2878.54 |  | 80013.75 |  | 1846998.52 | 93619.2 | 10726.91 | 11.46%
03/27/23 |  | 12/08/23 | Open | Media Alsewaili | N/A |  | Diana Berger, Mariana Pacheco, Media Alsewaili |  |  | Media Alsewaili |  |  | Mariana Pacheco | TX-SOUT | City of Socorro | J00015088 | Cancel- orders shipped direct to customer | Cancelled | 0% | 0% | 0 | -6.4 | 0 | 800 | 0% | 0 | 0 | 6.4 | 800 | 0 |  | 800 |  | 0 | 0 | -800 | 0%
03/27/23 |  | 12/08/23 | Open | Media Alsewaili | N/A |  | Diana Berger, Mariana Pacheco, Media Alsewaili |  |  | Media Alsewaili |  |  | N/A | N/A | City of Socorro | J00015088 | Cancel- orders shipped direct to customer | Cancelled | 0% | 0% | 525.5 | 525.5 | 64876.5 | 0 | 100% | 64876.5 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
11/13/23 |  | 12/11/23 | Open | Summer Abunaja | Saif Qaissi |  | Kord Mullins, Larry Noble, Mohammed Al-Shaikhli, Neel Shah, Saif Qaissi, Summer Abunaja |  |  | Kord Mullins, Lauren Lanzini Coffey, Mohammed Al-Shaikhli, Summer Abunaja |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00016849 | Kronos | Closed | 100% | 51.22% | 180.6 | 88.1 | 12445 | 5727.5 | 48.78% | 12445 | 0 | 92.5 | 5727.5 | 367.9 |  | 5727.5 |  | 0 | 19384 | 13288.6 | 68.55%
03/04/22 |  | 12/13/23 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Brian Newman, Brian Newman, Christopher Kutalek, Lauren Lanzini Coffey, Nelson Alonso, Shiraz Humayun |  |  | Brian Newman, Media Alsewaili, Nelson Alonso |  |  | Christopher Kutalek | TX-HOU | Fugro USA, Inc. | J00012365 | (CUCM) Upgrade and Migration to New Servers | Closed | 100% | 140.2% | 175.95 | -70.7 | 23799.75 | 33685 | -40.18% | 23799.75 | 0 | 246.65 | 33685 | 0 |  | 33685 |  | 52977.1 | 33947.6 | 262.6 | 0.7735%
03/23/23 |  | 12/14/23 | Open | Jason Esry | Jacob Parks, Jeffrey Holman, William Birdsong |  | Fadi Ashour, Jason Esry, Jeff Barker |  |  | Jason Esry, William Chris Roome |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00015199 | ISE and TACACS | Closed | 100% | 0% | 28 | 28 | 3500 | 0 | 100% | 3500 | 0 | 0 | 0 | 0 |  | 0 |  | 302464.72 | 47300 | 47300 | 100%
03/23/23 |  | 12/14/23 | Open | Jason Esry | Jacob Parks, Jeffrey Holman, William Birdsong |  | Fadi Ashour, Jason Esry, Jeff Barker |  |  | Jason Esry, William Chris Roome |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00015199 | ISE and TACACS | Closed | 0% | 0% | 0 | -32 | 0 | 3987.5 | 0% | 0 | 0 | 32 | 3987.5 | 0 |  | 3987.5 |  | 302464.72 | 47300 | 43312.5 | 91.57%
10/24/22 |  | 12/15/23 | Open | Jim Blackwell | Albert H Nguyen, Mark J Chambliss |  | Albert H Nguyen, Aleksei Lavrushenkov, Ashley F Freeman, Jim Blackwell, Larry Noble, Mark J Chambliss, Mustafa Al-Tamimi, Nathan Dao, Robert Brim |  |  | Aaron Johns, Aleksei Lavrushenkov, Andy Alvarenga, Andy Pham, Bryant Bush, Craig St. Rose, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, James Adams, Jeff Ogbor, Jesus Gonzalez, Jim Blackwell, Jose R. Duarte, Justin Higgins, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Mustafa Al-Tamimi, Nathan Dao, Syed Zaidi |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00012886 | Ferguson #54 Network ERATE | Closed | 100% | 207.3% | 181.11 | -148.89 | 12452.25 | 26682.5 | -82.21% | 12452.25 | 45.5 | 375.5 | 23952.5 | 888.621 |  | 26682.5 |  | 630283.16 | 26385.48 | -1185.641 | -4.494%
09/01/23 |  | 12/15/23 | Open | Jim Blackwell | Firas Abood |  | Cory Bradfield, Cory Bradfield, Jim Blackwell, Kurt Sell, Monica Johnson |  |  | Cory Bradfield, Jaime Flores, Jim Blackwell, Julio C Montoya, Justin Smallwood, Mohammed Al-Shaikhli |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00015034 | Compute Refresh | Closed | 100% | 0% | 89.39 | 89.39 | 11366.85 | 0 | 100% | 11366.85 | 0 | 0 | 0 | 135.41 |  | 0 |  | 162945.49 | 14930.8 | 14795.39 | 99.09%
09/01/23 |  | 12/15/23 | Open | Jim Blackwell | Firas Abood |  | Cory Bradfield, Cory Bradfield, Jim Blackwell, Kurt Sell, Monica Johnson |  |  | Cory Bradfield, Jaime Flores, Jim Blackwell, Julio C Montoya, Justin Smallwood, Mohammed Al-Shaikhli |  |  | Monica Johnson | TX-HOU | Harris County Auditor | J00015034 | Compute Refresh | Closed | 0% | 0% | 0 | -103 | 0 | 14471.25 | 0% | 0 | 14.75 | 117.75 | 12630 | 135.41 |  | 14471.25 |  | 162945.49 | 14930.8 | 324.14 | 2.171%
07/24/23 |  | 12/15/23 | Open | Richard Keith Arnst | N/A |  | Christopher Butler, Randy Schamberger, Richard Keith Arnst |  |  | Anthony Towsley, Richard Keith Arnst |  |  | Randy Schamberger | FL | Collier County Board of County Commissioners | J00015945 | 311 Call Center Project | Closed | 100% | 65.39% | 71.88 | 24.88 | 9847.5 | 6422.5 | 34.61% | 9847.5 | 0 | 47 | 6422.5 | 0 |  | 6422.5 |  | 0 | 0 | -6422.5 | 0%
06/05/23 |  | 12/15/23 | Open | Richard Keith Arnst | Ahmed Al-Zubaidi, David Watkins, Wyley Johnson |  | Abdulrahman Farhan, Ashutosh Patel, Camille Elizabeth Taber, Raymond Michael Imbrigiotta, Richard Keith Arnst |  |  | Abdulrahman Farhan, Ashutosh Patel, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres, Richard Keith Arnst, Timothy Sean Marcyes |  |  | N/A | N/A | David Posnack Jewish Day School | J00015541 | Fortinet Install | Closed | 100% | 0% | 225.11 | 225.11 | 31014.25 | 0 | 100% | 31014.25 | 0 | 0 | 0 | 2927.65 |  | 0 |  | 85333.72 | 37042.32 | 34114.67 | 92.1%
06/05/23 |  | 12/15/23 | Open | Richard Keith Arnst | Ahmed Al-Zubaidi, David Watkins, Wyley Johnson |  | Abdulrahman Farhan, Ashutosh Patel, Camille Elizabeth Taber, Raymond Michael Imbrigiotta, Richard Keith Arnst |  |  | Abdulrahman Farhan, Ashutosh Patel, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres, Richard Keith Arnst, Timothy Sean Marcyes |  |  | Raymond Imbrigiotta | FL | David Posnack Jewish Day School | J00015541 | Fortinet Install | Closed | 0% | 0% | 0 | -155 | 0 | 23067.5 | 0% | 0 | 10 | 165 | 21567.5 | 2927.65 |  | 23067.5 |  | 85333.72 | 37042.32 | 11047.17 | 29.82%
08/07/23 |  | 12/22/23 | Open | Jason Esry | Albert H Nguyen |  | Jason Esry, Kurt Sell, Mustafa Al-Tamimi, Susan Richardson |  |  | Devon LeMoine, Jason Esry, Jesus Gonzalez, Jose R. Duarte, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mustafa Al-Tamimi, Paul Serres |  |  | Susan Richardson | TX-HOU | PetroChina International (America), Inc. | J00016142 | Network Refresh - Wireless Only | Closed | 100% | 127.2% | 55.11 | -13.84 | 6083.95 | 7293.5 | -25.11% | 6083.95 | 1.15 | 70.1 | 7224.5 | 0 |  | 7293.5 |  | 13057.2 | 7762.8 | 469.3 | 6.045%
12/26/23 |  | 12/26/23 | Open | Christopher Ngang | David Pena, Jeremy Hoffpauir |  | N/A |  |  | Darrell Walton |  |  | Zachary Short | US-SP | Securus Technologies, Inc. | J00017171 | Merged with J00017170 | Cancelled | 0% | 0% | 0 | -12 | 0 | 1620 | 0% | 0 | 0 | 12 | 1620 | 0 |  | 1620 |  | 19753.2 | 5004 | 3384 | 67.63%
06/22/22 |  | 12/29/23 | Open | Media Alsewaili | N/A |  | Kurt Sell, Media Alsewaili, Monica Johnson, Nelson Garcia, Susan Richardson |  |  | Abdulrahman Farhan, David Dobbs, Jaime Flores, Justin Cornish, Media Alsewaili, Vitalii Stepanchenko |  |  | Monica Johnson | TX-HOU | YES Prep Public Schools | J00012350 | Multi-Campus Network Upgrades ERATE | Cancelled | 0% | 15.37% | 214.75 | 185.5 | 15327.95 | 4323.75 | 86.38% | 15327.95 | 3.75 | 33 | 3918.75 | 64.18 |  | 4323.75 |  | 0 | 0 | -4387.93 | 0%
10/02/23 |  | 12/29/23 | Open | Shannon Marie Alvarado | Albert H Nguyen |  | Jason Osuna, Larry Noble, Mustafa Al-Tamimi, Shannon Marie Alvarado |  |  | LaQisha Marshall, Mustafa Al-Tamimi, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00016572 | Wireless Survey | Closed | 100% | 100% | 17.5 | 3 | 2400.5 | 1992.5 | 17.14% | 2400.5 | 3 | 17.5 | 1812.5 | 897.41 |  | 1992.5 |  | 0 | 3033.8 | 143.89 | 4.743%
06/01/23 |  | 01/05/24 | Open | Marco Lish | Vernon Jackson |  | N/A |  |  | Henry Pugsley, Marco Lish |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00015721 | SSO Configuration for Cisco Webex | Closed | 100% | 35.86% | 72.5 | 46.5 | 9932.5 | 4037.5 | 64.14% | 9932.5 | 0 | 26 | 4037.5 | 0 |  | 4037.5 |  | 0 | 14001.6 | 9964.1 | 71.16%
05/01/23 |  | 01/05/24 | Open | Richard Keith Arnst | Albert H Nguyen, Bryan Brown, Mark J Chambliss |  | Felipe D. Waterwall, Felipe Waterwall, Larry Noble, Lindie Lorraine Lamar, Mustafa Al-Tamimi, Richard Keith Arnst |  |  | Andy Pham, David Dobbs, Hector Rivera, Jaime Flores, Justin Cornish, Richard Keith Arnst |  |  | Lindie Lamar | TX-HOU | Prime Contractors | J00015454 | Mance Park MS (Huntsville ISD) Cafeteria | Closed | 0% | 0% | 0 | -54.5 | 0 | 6082.5 | 0% | 0 | 16 | 70.5 | 5122.5 | 422.79 |  | 6082.5 |  | 35919.9 | 12770.68 | 6265.39 | 49.06%
05/01/23 |  | 01/05/24 | Open | Richard Keith Arnst | Albert H Nguyen, Bryan Brown, Mark J Chambliss |  | Felipe D. Waterwall, Felipe Waterwall, Larry Noble, Lindie Lorraine Lamar, Mustafa Al-Tamimi, Richard Keith Arnst |  |  | Andy Pham, David Dobbs, Hector Rivera, Jaime Flores, Justin Cornish, Richard Keith Arnst |  |  | N/A | N/A | Prime Contractors | J00015454 | Mance Park MS (Huntsville ISD) Cafeteria | Closed | 100% | 0% | 97.07 | 97.07 | 9917.85 | 0 | 100% | 9917.85 | 0 | 0 | 0 | 422.79 |  | 0 |  | 35919.9 | 12770.68 | 12347.89 | 96.69%
10/11/23 |  | 01/05/24 | Open | Richard Keith Arnst | Aman Khan, David Watkins, Joseph Hayes |  | Aman Khan, David Watkins, Joseph Hayes, Monica Johnson, Richard Keith Arnst |  |  | Justin Cornish, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio |  |  | Monica Johnson | TX-HOU | Sarvicus | J00016485 | 5012169 | Implementation/Deployment | 0% | 0% | 0 | -25.5 | 0 | 2400 | 0% | 0 | 14.5 | 40 | 1530 | 0 |  | 2400 |  | 721924.68 | 0 | -2400 | 0%
10/11/23 |  | 01/05/24 | Open | Richard Keith Arnst | Aman Khan, David Watkins, Joseph Hayes |  | Aman Khan, David Watkins, Joseph Hayes, Monica Johnson, Richard Keith Arnst |  |  | Justin Cornish, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio |  |  | Susan Richardson | TX-HOU | Sarvicus | J00016485 | 5012169 | Implementation/Deployment | 30% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 721924.68 | 0 | 0 | 0%
08/01/23 |  | 01/05/24 | Open | Richard Keith Arnst | Aman Khan |  | Garrett Curran, Magdalena Rodriguez, Moises Rodriguez, Nick Varga, Richard Keith Arnst, Yong Kim |  |  | Baq Alsaedi, Carlo Enriquez, Craig Collinsworth, James Adams, Jesus Gonzalez, Kanoa Parman, Mohammed Al-Shaikhli, Moises Rodriguez, Nick Varga, Prince Owusu, Richard Keith Arnst, Sajjad Abo Dbs |  |  | Garrett Curran | CA-LAX | Westside Union School District | J00015361 | Juniper Access Point Replacement Implementation | Closed | 100% | 127.9% | 777.35 | -60.5 | 79955.15 | 83790 | -7.783% | 79955.15 | 156.25 | 994.1 | 74155 | 13418.66 |  | 83790 |  | 534864.16 | 149626.84 | 52418.18 | 35.03%
11/10/22 |  | 01/05/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Baq Alsaedi, Cory Bradfield, Jose R. Duarte, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Central Bank | J00014299 | Cohesity Deployment | Closed | 0% | 0% | 0 | -83.75 | 0 | 11501.25 | 0% | 0 | 8 | 91.75 | 10421.25 | 88.73 |  | 11501.25 |  | 179107.62 | 19417.6 | 7827.62 | 40.31%
11/10/22 |  | 01/05/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Baq Alsaedi, Cory Bradfield, Jose R. Duarte, Tray Giddens |  |  | N/A | N/A | Central Bank | J00014299 | Cohesity Deployment | Closed | 100% | 0% | 93.94 | 93.94 | 12427.5 | 0 | 100% | 12427.5 | 0 | 0 | 0 | 88.73 |  | 0 |  | 179107.62 | 19417.6 | 19328.87 | 99.54%
05/18/23 |  | 01/08/24 | Open | Karyn Hubbard | George Edwin Jacob |  | Alexander Gutman, Arcangelo Fanelli, Beau C. Devillier, Bryan Mullen, Eric Rodriguez, George Edwin Jacob, Juan Pomares, Karyn Hubbard, Tony Dean Skipworth |  |  | Bryan Mullen, Karyn Hubbard, Lauren Lanzini Coffey, Tabais Prater, Tony Dean Skipworth |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | J00015128 | Data Center Core Refresh | Closed | 100% | 276.2% | 80.8 | -134.4 | 9705 | 29342.5 | -166.3% | 9705 | 8 | 223.2 | 28262.5 | 416.54 |  | 29342.5 |  | 208001.68 | 12302.4 | -17456.64 | -141.9%
10/10/22 |  | 01/10/24 | Open | LaQisha Marshall | Albert H Nguyen |  | Andy Alvarenga, Andy Pham, Jennifer Huie, Justin Cornish, Kurt Sell, LaQisha Marshall, Mario Sanchez, Miguel Reed, Monica Johnson |  |  | Andy Alvarenga, Baq Alsaedi, Craig St. Rose, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jesus Gonzalez, Julio C Montoya, Justin Higgins, Justin Cornish, LaQisha Marshall, Luis Alvarez, Mario Sanchez |  |  | Monica Johnson | TX-HOU | Port Neches-Groves ISD | J00014008 | Port-Neches Primary - Meraki & Aruba | Closed | 100% | 131% | 131.34 | 10.34 | 7905 | 13500 | 7.873% | 7905 | 51 | 172 | 10440 | 760.48 |  | 13500 |  | 210843.81 | 12798 | -1462.48 | -11.43%
10/10/22 |  | 01/10/24 | Open | LaQisha Marshall | Albert H Nguyen |  | Andy Alvarenga, Andy Pham, Jennifer Huie, Justin Cornish, Kurt Sell, LaQisha Marshall, Mario Sanchez, Miguel Reed, Monica Johnson |  |  | Aaron Johns, Baq Alsaedi, Bryant Bush, Craig St. Rose, David Dobbs, Jaime Flores, Julio C Montoya, Justin Higgins, Justin Cornish, Kevin Curtis, Kolawole Ayeni, LaQisha Marshall, Luis Alvarez, Mario Sanchez, Matthew D'Ambrosio, Nathan Dao, Paul Serres |  |  | Monica Johnson | TX-HOU | Port Neches-Groves ISD | J00014009 | Groves Primary School - Meraki & Aruba | Closed | 100% | 95.65% | 133.04 | 30.79 | 8015.5 | 10246.25 | 23.14% | 8015.5 | 25 | 127.25 | 8746.25 | 305.52 |  | 10246.25 |  | 210843.81 | 12966 | 2414.23 | 18.62%
07/24/23 |  | 01/11/24 | Open | LaQisha Marshall | N/A |  | Hannah Paul, LaQisha Marshall, Larry Noble |  |  | Aleksei Lavrushenkov, James Danner, Kord Mullins, Kyle Linder, LaQisha Marshall, Raul Velazquez, Ruben Cantu, Taylor Poole |  |  | Hannah Edmunds | TX-CEN | Texas Facilities Commission | J00015958 | Managed T&E Network Survey | Closed | 0% | 0% | 0 | -343 | 0 | 36442.5 | 0% | 0 | 56 | 399 | 33082.5 | 3212.19 |  | 36442.5 |  | 0 | 0 | -39654.69 | 0%
09/01/23 |  | 01/15/24 | Open | LaQisha Marshall | Aman Khan |  | Aman Khan, David D Tijerina, Kurt Sell, LaQisha Marshall |  |  | LaQisha Marshall, Mohammed Almoola |  |  | David D Tijerina | TX-CEN | Travis County | J00015950 | Tactical Network Implementation | Closed | 100% | 67.63% | 21.07 | 6.82 | 2132.95 | 1781.25 | 32.37% | 2132.95 | 0 | 14.25 | 1781.25 | 0 |  | 1781.25 |  | 172700.34 | 0 | -1781.25 | 0%
08/28/23 |  | 01/17/24 | Open | LaQisha Marshall | Emilio Carrillo |  | Kurt Sell, LaQisha Marshall, Raul Velazquez, Thomas McClanahan |  |  | Kevin Curtis, Kolawole Ayeni, Kyle Linder, LaQisha Marshall, Matthew D'Ambrosio, Nelson Garcia, Raul Velazquez, Robert Jones, Steven Shipmon |  |  | Thomas McClanahan | TX-CEN | Temple ISD | J00015986 | WAN - Erate - TX 2023-C1 WAN | Closed | 100% | 63.27% | 335.48 | 135.73 | 30222 | 21440 | 40.46% | 30222 | 12.5 | 212.25 | 20500 | 555.67 |  | 21440 |  | 698030.22 | 64867.84 | 42872.17 | 66.09%
04/03/23 |  | 01/18/24 | Open | Tray Giddens | David Escamilla |  | David Escamilla, Dustin Huffman, Kathleen Brown, Kurt Sell, Luis Ovalles, Tray Giddens |  |  | Carlo Enriquez, Luis Ovalles, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Chevron Phillips Chemical | J00015266 | Sweeny Nutanix Cluster | Closed | 100% | 50.09% | 121.79 | 72.79 | 14077.75 | 7835 | 59.77% | 14077.75 | 12 | 61 | 6215 | 704.05 |  | 7835 |  | 374682.47 | 21000 | 12460.95 | 59.34%
11/10/22 |  | 01/19/24 | Open | Marco Lish | David Escamilla |  | Cory Bradfield, Cory Bradfield, Larry Noble, Marco Lish, Neel Shah |  |  | Jorge Ortiz Cardozo, Lauren Lanzini Coffey, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Airport System | J00014307 | AWS- Control Tower, Dir Connect & Veem | Closed | 100% | 48.21% | 29.25 | 15.15 | 3836.25 | 1762.5 | 51.79% | 3836.25 | 0 | 14.1 | 1762.5 | 0 |  | 1762.5 |  | 0 | 55542 | 53779.5 | 96.83%
09/05/23 |  | 01/26/24 | Open | Jennifer Soliz | Timothy Ramsey |  | Ibrahim Altaweel, Jennifer Soliz, Larry Noble, Lonnie Owens, Mohammad Solomon, Rogelio Morgado-Perez, Tom Magboo |  |  | Ibrahim Altaweel, Jennifer Soliz, Jerome Tanyag Mara, Mohammad Solomon, Rogelio Morgado-Perez, Tom Magboo |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00016373 | No SOW - IT Pen Testing | Closed | 100% | 110.4% | 695 | -72.25 | 104150 | 114981.25 | -10.4% | 104150 | 0 | 767.25 | 114981.25 | 820.91 |  | 114981.25 |  | 0 | 76832.8 | -38969.36 | -50.72%
11/13/20 |  | 01/26/24 | Open | Marco Lish | Christopher Garcia |  | Jeff Barker, Jonathan Pendrich, Kevin Jones, Kevin Jones, Marco Lish |  |  | Aaron Abshire, Benjamin Brooks, Conner MacDonnell, Darrell Walton, Devin Moreno, Dionisio Oscar Medina-Marcelin, Jason Duggan, Joel Fleming, Joel Hubbard, Jordan Newman, Joshua Hubbard, Kevin Jones, Marco Lish, Matthew Kennewell, Orlando Francis, Phillip Thornton, Robert Lavender, Sean Cowhey, William Chris Roome |  |  | Jonathan Pendrich | TX-DAL | Oncor Electric Delivery Company LLC | J00008935 | Digital Signage Bid & Cabling (Able Electrical) | Closed | 100% | 42.17% | 2025.89 | 1313.14 | 166295.35 | 81004.5 | 64.82% | 166295.35 | 141.5 | 854.25 | 68313.5 | 2061.502 |  | 81004.5 |  | 163457.55 | 112850.96 | 29784.958 | 26.39%
06/01/23 |  | 01/26/24 | Open | Richard Keith Arnst | Bryan Geoghan |  | Christopher Butler, Randy Schamberger, Richard Keith Arnst |  |  | Henry Pugsley, James Adams, Richard Keith Arnst, Romar Roca, Samuel Newland |  |  | Randy Schamberger | FL | Collier County Board of County Commissioners | J00015723 | Expressway MRA | Closed | 100% | 51.53% | 138.75 | 67.25 | 19008.75 | 9862.5 | 48.47% | 19008.75 | 0 | 71.5 | 9862.5 | 0 |  | 9862.5 |  | 0 | 41279.84 | 31417.34 | 76.11%
06/01/23 |  | 01/26/24 | Open | Richard Keith Arnst | Bryan Brown |  | Beau C. Devillier, Lauren J Kennewell, Richard Keith Arnst |  |  | Dante Torres, Dylan Pittsinger, Joel Hubbard, Joshua Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | Las Colinas Medical Center | J00015639 | Classroom AV - 2 Sides | Closed | 100% | 169.6% | 186.25 | -124.55 | 16556.25 | 27546.5 | -66.87% | 16556.25 | 5.1 | 315.9 | 27225.5 | 1502.5 |  | 27546.5 |  | 51385.28 | 27530.8 | -1518.2 | -5.515%
01/31/22 |  | 01/26/24 | Open | Tray Giddens | Andrew Wells |  | Tray Giddens |  |  | Aboobiada Aliabdalla, Adeline Tidjon, Adiel Alvarez, Akuchii Iwunze, Anatalia Solis, Axel Zavala, Cameron Farris, Darrick Bonner, David Lenihan, Dedric Bowens, Delilah Davis, Eleazar Guzman, Eliana Guzman, Enrique Valdes, Felipe Ajche, Gerardo Guzman, Geremy Howard, Gregory Posey, Harold Gomez, Hussein Majeed, James Charvis, Jarshawn Newsome, Jaylen Morgan, Jesus Guadian, Jose Silva, Josias Ajche, Juan Mendoza, Kai Rose , Kimberly Santillan, Lorenzo Hernandez, Luis Hernandez, Monica Cavazo |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00012229 | 4500 ipads | Closed | 100% | 91.5% | 2176.88 | 184.98 | 90703.6 | 72817 | 8.497% | 90703.6 | 0 | 1991.9 | 72817 | 565.23 |  | 72817 |  | 0 | 104490 | 31107.77 | 29.77%
08/31/23 |  | 01/26/24 | Open | Tray Giddens | N/A |  | Ashley F Freeman, Larry Noble, Tray Giddens |  |  | Andrew Comeaux, Anthony Balogun, David Lenihan, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Gomez, Jarshawn Newsome, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez, Tray Giddens, Valentin Vasquez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016391 | 1500 x360 | Closed | 100% | 61.09% | 1138.5 | 443 | 49162.5 | 27325 | 38.91% | 49162.5 | 0 | 695.5 | 27325 | 235.81 |  | 27325 |  | 981000 | 45000 | 17439.19 | 38.75%
12/08/23 |  | 01/31/24 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, Alexander Gutman, Beau C. Devillier, David Babasola, Joshua Hubbard |  |  | Abiodun David Babasola, Joel Hubbard, Robert Lavender |  |  | Alex Gutman | TX-DAL | Nucor Business Technology Inc. | J00016971 | SX80 Replacement for Iverson Room | Closed | 100% | 73.83% | 24.38 | 6.38 | 2380 | 2270 | 26.17% | 2380 | 0 | 18 | 2270 | 0 |  | 2270 |  | 13379.62 | 5316.8 | 3046.8 | 57.31%
07/10/23 |  | 01/31/24 | Open | Jim Blackwell | Graylon Hampton, William Birdsong |  | Camille Elizabeth Taber, Graylon Hampton, Jeff Barker, Jim Blackwell, Kreshnik Memaj, Magdalena Rodriguez, Moises Rodriguez |  |  | Andy Alvarenga, Conner MacDonnell, Jaime Flores, Jim Blackwell, Jose R. Duarte, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kreshnik Memaj, Matthew D'Ambrosio, Moises Rodriguez, Taylor Poole |  |  | Camille Taber | FL | Bradford County School District | J00015744 | Juniper MIST WI-FI | Closed | 0% | 0% | 0 | -512.75 | 0 | 45487.5 | 0% | 0 | 37.5 | 550.25 | 43237.5 | 10629.33 |  | 45487.5 |  | 266954.5 | 30977.72 | -25139.11 | -81.15%
07/10/23 |  | 01/31/24 | Open | Jim Blackwell | Graylon Hampton, William Birdsong |  | Camille Elizabeth Taber, Graylon Hampton, Jeff Barker, Jim Blackwell, Kreshnik Memaj, Magdalena Rodriguez, Moises Rodriguez |  |  | Andy Alvarenga, Conner MacDonnell, Jaime Flores, Jim Blackwell, Jose R. Duarte, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kreshnik Memaj, Matthew D'Ambrosio, Moises Rodriguez, Taylor Poole |  |  | N/A | N/A | Bradford County School District | J00015744 | Juniper MIST WI-FI | Closed | 100% | 0% | 296.13 | 296.13 | 24018.75 | 0 | 100% | 24018.75 | 0 | 0 | 0 | 10629.33 |  | 0 |  | 266954.5 | 30977.72 | 20348.39 | 65.69%
01/10/22 |  | 02/02/24 | Open | Jason Esry | Aman Khan, Chad Hart |  | Aman Khan, David Neal Gravatt, Dustin Huffman, Jason Esry, Larry Noble |  |  | Aaron Abshire, Andy Alvarenga, David Neal Gravatt, Devon LeMoine, James Adams, Jason Esry, Jorge Ortiz Cardozo, Jose R. Duarte, Julio C Montoya, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Mustafa Al-Tamimi |  |  | Dustin Huffman | TX-HOU | Clutch City Sports & Entertainment | J00011488 | Switch Upgrade for Houston Rockets | Closed | 100% | 380.9% | 69.63 | -184.32 | 5821.5 | 21775 | -264.7% | 5821.5 | 11.3 | 265.25 | 20850 | 324 |  | 21775 |  | 96489.26 | 9613.6 | -12485.4 | -129.9%
06/05/23 |  | 02/02/24 | Open | Jim Blackwell | Mark J Chambliss |  | Ashley F Freeman, Jim Blackwell, Larry Noble, Ming Chiu |  |  | Jim Blackwell, Julio C Montoya, Justin Smallwood, Ming Chiu, Sajjad Abo Dbs |  |  | Ashley F Freeman | TX-HOU | Greater Harris County 911 Emergency Network | J00015046 | WORK ORDER - CUBE Configurations | Closed | 100% | 156% | 37.5 | -19 | 5137.5 | 7317.5 | -50.67% | 5137.5 | 2 | 58.5 | 7197.5 | 27.3 |  | 7317.5 |  | 17135.22 | 8253 | 908.2 | 11%
10/16/23 |  | 02/02/24 | Open | Summer Abunaja | Michael Brett Beggs |  | Garrett Curran, Summer Abunaja, Yong Kim |  |  | N/A |  |  | N/A | N/A | Amazon Web Services | J00016683 | AWS Control Tower | Closed | 100% | 0% | 13.5 | 13.5 | 1728 | 0 | 100% | 1728 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 6032.49 | 6032.49 | 100%
07/28/23 |  | 02/02/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, James Adams, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Central Bank | J00015894 | HPE DL380 Gen11 | Closed | 0% | 0% | 0 | -57.25 | 0 | 9361.25 | 0% | 0 | 21.25 | 78.5 | 6605 | 15.68 |  | 9361.25 |  | 62113.32 | 13699.6 | 4322.67 | 31.55%
07/28/23 |  | 02/02/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, James Adams, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Paul Serres, Tray Giddens |  |  | N/A | N/A | Central Bank | J00015894 | HPE DL380 Gen11 | Closed | 100% | 0% | 70 | 70 | 8710 | 0 | 100% | 8710 | 0 | 0 | 0 | 15.68 |  | 0 |  | 62113.32 | 13699.6 | 13683.92 | 99.89%
06/05/23 |  | 02/02/24 | Open | Tray Giddens | Ahmed Al-Zubaidi, Aman Khan, Wyley Johnson |  | Abdulrahman Farhan, Dustin Huffman, Kurt Sell, Nelson Garcia, Tray Giddens |  |  | Abdulrahman Farhan, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nelson Garcia, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Susman Godfrey LLP | J00015755 | Network and Security Refresh - NY LA Lifecycle | Closed | 100% | 64.47% | 139.59 | 49.59 | 18014.4 | 12420 | 35.53% | 18014.4 | 0 | 90 | 12420 | 0 |  | 12420 |  | 100016.07 | 22859.4 | 10439.4 | 45.67%
10/09/23 |  | 02/02/24 | Open | Tray Giddens | Aman Khan |  | Dustin Huffman, Kurt Sell, Nelson Garcia, Tray Giddens |  |  | Nelson Garcia |  |  | Dustin Huffman | TX-HOU | Susman Godfrey LLP | J00016601 | 49th Floor Single Switch Install | Closed | 100% | 74.07% | 5.4 | 1.4 | 675 | 500 | 25.93% | 675 | 0 | 4 | 500 | 0 |  | 500 |  | 0 | 884.4 | 384.4 | 43.46%
01/08/24 |  | 02/05/24 | Open | Summer Abunaja | David Watkins |  | David Watkins, Nathan Dao, Neel Shah, Robert Kelly, Robert Kelly, Shiraz Humayun, Summer Abunaja |  |  | Nathan Dao, Robert Kelly |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00017215 | Post-Inst Survey–Pavi II Fl 12 OB GYN Clinic | Closed | 100% | 58.18% | 27.5 | 11.5 | 2780 | 1800 | 41.82% | 2780 | 0 | 16 | 1800 | 0 |  | 1800 |  | 0 | 4813.6 | 3013.6 | 62.61%
04/03/23 |  | 02/06/24 | Open | Richard Keith Arnst | Vernon Jackson |  | Beau C. Devillier, Mark Forehand, Richard Keith Arnst |  |  | Andrew Comeaux, Christopher Ceykovsky, Richard Keith Arnst |  |  | Mark Forehand | TX-DAL | Justin Brands | J00015120 | WORK ORDER - SIP Migration | Closed | 100% | 164.1% | 29.25 | -18.75 | 4046.25 | 6250 | -64.1% | 4046.25 | 0 | 48 | 6250 | 0 |  | 6250 |  | 0 | 5934.48 | -315.52 | -5.317%
08/30/22 |  | 02/08/24 | Open | Abiodun David Babasola | Jacob Parks, Jeffrey Holman |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Kristy L Dice, Romar Roca, Sophia Quinter |  |  | Abiodun David Babasola, Sophia Quinter |  |  | Kristy L Dice | TX-DAL | Irving ISD | J00013181 | Cisco ISE Implementation | Closed | 100% | 43.89% | 239.23 | 134.23 | 34920 | 15100 | 56.11% | 34920 | 0 | 105 | 15100 | 0 |  | 15100 |  | 446529.2 | 57667.6 | 42567.6 | 73.82%
09/28/23 |  | 02/09/24 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, David Babasola, Garrett Curran, Robert Lavender, Yong Kim |  |  | Abiodun David Babasola, Robert Lavender |  |  | Garrett Curran | CA-LAX | Etiwanda School District | J00016508 | Boardroom Microphone Upgrade | Closed | 100% | 149.7% | 22.55 | -2.7 | 4109.55 | 4516.25 | -11.97% | 4109.55 | 8.5 | 33.75 | 3368.75 | 1877.28 |  | 4516.25 |  | 14042.74 | 6792.12 | 398.59 | 5.868%
04/22/21 |  | 02/16/24 | Open | Jason Esry | Emilio Carrillo |  | Brandon McMillan, Jason Esry |  |  | Aldo Cortes, Andy Alvarenga, Angel Alicea, Angel Alicea-Torres, Chase Delhaye, David Dobbs, Delton Childs, Devon LeMoine, Ernesto Gonzalez, Hector Rivera, Isaiah Covington, Jacob Lee, Jacobo Padilla, James Danner, Jason Esry, Jeffrey Charles Primeaux, Jeffrey Primeaux, John Senkulics, Jose R. Duarte, Joshua Baumgartner, Juan Carlos Flores, Julio Cerrato, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kristopher Dwight, Kyle Linder, Luis Alvarez, Matthew D'Ambrosio, Matthew Vannoy, Micah Rendon |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00010252 | ERATE 2020 Wireless Refresh | Closed | 100% | 101.5% | 4065.94 | 222.54 | 231101.6 | 278300 | 5.473% | 231101.6 | 281.9 | 4125.3 | 263347.5 | 6337.2502 |  | 278300 |  | 1186894.8 | 126300.12 | -158337.1302 | -125.4%
02/22/22 |  | 02/21/24 | Open | Jennifer Soliz | Joshua Adam Engle |  | Jennifer Soliz, Mohammad Jilani |  |  | Eric Firestone, Henry Pugsley, Jason Espino, Jennifer Soliz, Julian M Rodriguez-Yunes, Ming Chiu, Mohammad Jilani, Moises Rodriguez, Raul Velazquez, Robert Kelly, Ron Loge |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00012442 | Monthly T&E (Original - Not To Exceed x160 HRs) | Not started | 60% | 741.8% | 98.11 | -604.14 | 10326.25 | 106440.25 | -615.8% | 10326.25 | 25.5 | 727.75 | 98667.5 | 201.23 |  | 106440.25 |  | 0 | 33340 | -73301.48 | -219.9%
04/10/23 |  | 02/21/24 | Open | Joaquin Marroquin | Edward Padron, Timothy Ramsey |  | Felix Martinez, Joaquin Marroquin, Ruben Cantu, Xavier A Trevino |  |  | David Rodriguez, Joaquin Marroquin, Jose Salazar, Ruben Cantu, William Brown |  |  | Xavier A Trevino | TX-SOUT | City of Port Isabel | J00015228 | Meraki Network Upgrades | Closed | 100% | 175.7% | 33.86 | -19.14 | 3245.15 | 6885 | -56.53% | 3245.15 | 6.5 | 59.5 | 6072.5 | 150 |  | 6885 |  | 20302.06 | 4253.6 | -2781.4 | -65.39%
10/05/23 |  | 02/27/24 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, David Babasola, Jeff Barker |  |  | Abiodun David Babasola, George McGann |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00016407 | Expressway Deployment | Closed | 100% | 0% | 87.63 | 87.63 | 12005.25 | 0 | 100% | 12005.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 18162 | 18162 | 100%
10/05/23 |  | 02/27/24 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, David Babasola, Jeff Barker |  |  | Abiodun David Babasola, George McGann |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00016407 | Expressway Deployment | Closed | 0% | 0% | 0 | -85.1 | 0 | 11659 | 0% | 0 | 0 | 85.1 | 11659 | 0 |  | 11659 |  | 0 | 18162 | 6503 | 35.81%
11/13/23 |  | 02/29/24 | Open | Christopher Ngang | N/A |  | N/A |  |  | N/A |  |  | Jessica Anderson | US-SP | Fiberlight | J00016864 | Cancel- no service needed | Cancelled | 0% | 0% | 157.2 | 157.2 | 20960 | 0 | 100% | 20960 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
10/30/23 |  | 02/29/24 | Open | Jason Esry | Albert H Nguyen |  | Daniel Hernandez, Daniel R Hernandez, Jason Esry, Larry Noble, Lindie Lorraine Lamar, Nelson Garcia |  |  | Craig St. Rose, Jason Esry, Jerald Garner, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Nelson Garcia, Nicolas Garakani |  |  | Lindie Lamar | TX-HOU | Jasper ISD | J00016550 | Switching and Wireless Equipment Installation | Closed | 100% | 86.15% | 86.77 | 27.02 | 8030.4 | 5135 | 31.14% | 8030.4 | 15 | 74.75 | 4235 | 266.1 |  | 5135 |  | 78218.7 | 10523.52 | 5122.42 | 48.68%
08/28/23 |  | 02/29/24 | Open | Jason Esry | Christopher Puyear |  | David D Tijerina, Jason Esry, John Stephen Kurkjian, Kurt Sell |  |  | Jason Esry, John Stephen Kurkjian, LaQisha Marshall |  |  | David D Tijerina | TX-CEN | Travis County | J00015484 | PSTN Gateway Replacement | Closed | 100% | 103.1% | 40 | -1.25 | 5480 | 5583.75 | -3.125% | 5480 | 0 | 41.25 | 5583.75 | 0 |  | 5583.75 |  | 45184.08 | 8803.6 | 3219.85 | 36.57%
11/07/22 |  | 02/29/24 | Open | Marco Lish | Ahmed Al-Zubaidi, Hugh Miller, Pradeep Tyagi , Wyley Johnson |  | Abdulrahman Farhan, Dhulfiqar Al Hashimi, Jorge Ortiz Cardozo, Larry Noble, Marco Lish, Neel Shah |  |  | Abdulrahman Farhan, Dhulfiqar Al Hashimi, Jorge Ortiz Cardozo, Lauren Lanzini Coffey, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00014237 | HEC FW install | Closed | 100% | 78.22% | 148.93 | 34.43 | 20753.75 | 16437.5 | 23.12% | 20753.75 | 2 | 116.5 | 16137.5 | 48.59 |  | 16437.5 |  | 0 | 28863.2 | 12377.11 | 42.88%
12/04/23 |  | 02/29/24 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Beau C. Devillier, Shannon Marie Alvarado, Taylor Leger |  |  | John Stephen Kurkjian, Shannon Marie Alvarado |  |  | Taylor Leger | TX-DAL | Cleburne ISD | J00016870 | Cisco Emergency Responder (CER) Setup | Closed | 100% | 104.4% | 31.13 | -1.37 | 4264.75 | 4452.5 | -4.401% | 4264.75 | 0 | 32.5 | 4452.5 | 0 |  | 4452.5 |  | 0 | 5529.6 | 1077.1 | 19.48%
08/09/23 |  | 03/05/24 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Jeffrey Charles Primeaux, Jeffrey Primeaux, LaQisha Marshall, Larry Noble |  |  | Adam Felix, An Le, Angel Alicea, Angel Alicea-Torres, Arius Deautrè Yarborough, Billy Lumbaya, Daniel Quade, George McGann, Jaime Flores, James Danner, Jason Andrews, Jeffrey Charles Primeaux, John Senkulics, Justin Cornish, Kyle Linder, LaQisha Marshall, Michael Torres, Oscar Gonzalez, Richard Shea, Robert Jones, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Pflugerville ISD | J00016065 | Handset replacement and migration | Closed | 100% | 178.7% | 725.2 | -393.87 | 68895.3 | 108630.55 | -54.31% | 68895.3 | 177 | 1296.07 | 98160.55 | 7801.74 |  | 108630.55 |  | 741852.1 | 87315.2 | -29117.09 | -33.35%
01/17/24 |  | 03/05/24 | Open | LaQisha Marshall | Christopher Puyear |  | Hannah Paul, James O Sykes, LaQisha Marshall |  |  | LaQisha Marshall, Ming Chiu |  |  | Hannah Edmunds | TX-CEN | Texas Parks and Wildlife | J00017086 | UCCX Priority Queue Scripting | Closed | 100% | 77.5% | 20 | 4.5 | 2740 | 2147.5 | 22.5% | 2740 | 0 | 15.5 | 2147.5 | 0 |  | 2147.5 |  | 0 | 4145.2 | 1997.7 | 48.19%
08/21/23 |  | 03/08/24 | Open | Jason Esry | Bryan Brown |  | Clinton Bennett Deason, Jackory Nash, Jason Esry, Jose E. Duarte Jr, Jose R Duarte, Jose R. Duarte, Kendric Mamou, Kurt Sell, Robert Lavender, Susan Richardson |  |  | Aaron Johns, Clinton Bennett Deason, Jason Esry, Jesus Gonzalez, Joel Hubbard, Kord Mullins, Remi Martinez-Montenegro, Robert Lavender |  |  | Susan Richardson | TX-HOU | PetroChina International (America), Inc. | J00016301 | Codec and config & install | Closed | 100% | 177.3% | 56.25 | -24.5 | 4906.25 | 9696.25 | -43.56% | 4906.25 | 19 | 99.75 | 7791.25 | 1832.61 |  | 9696.25 |  | 31362.93 | 8138.68 | -3390.18 | -41.66%
01/29/24 |  | 03/15/24 | Open | Shannon Marie Alvarado | Albert H Nguyen |  | Albert H Nguyen, Christopher Prado, Jason Osuna, Larry Noble, Mario Sanchez, Shannon Marie Alvarado |  |  | Christopher Prado, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00017363 | Wireless Survey – Birmingham, AL | Closed | 100% | 130.3% | 16.88 | -1.12 | 2544.79 | 2072.5 | -6.635% | 2544.79 | 4 | 22 | 1832.5 | 0 |  | 2072.5 |  | 0 | 4795.96 | 2723.46 | 56.79%
12/13/23 |  | 03/18/24 | Open | Summer Abunaja | George Delp |  | Aaron Christopher Pfeifer, George Delp, Jeff Barker, Kristi Hart, Summer Abunaja |  |  | Rafael Rodriguez-Vargas, Summer Abunaja |  |  | Kristi Hart | US-SP | Ben Lomand Connect | J00017055 | NO PM SCOPED? - IPv6/BGP Project | Closed | 100% | 137.5% | 24 | 1 | 4176 | 4420 | 4.167% | 4176 | 10 | 33 | 3070 | 0 |  | 4420 |  | 0 | 5313.2 | 893.2 | 16.81%
02/12/24 |  | 03/20/24 | Open | Jason Esry | Emilio Carrillo |  | David D Tijerina, James Danner, Jason Esry, Larry Noble |  |  | Daniel Quade, James Danner, Jason Esry, John Senkulics, Michael Torres |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00017511 | TrippLite Battery Replacement | Closed | 100% | 190% | 5 | -4.5 | 365 | 667.5 | -90% | 365 | 0 | 9.5 | 667.5 | 0 |  | 667.5 |  | 1411.27 | 525 | -142.5 | -27.14%
03/04/24 |  | 03/21/24 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Hamzeh Tahat, Taylor Leger |  |  | Abiodun David Babasola, Hamzeh Tahat |  |  | Taylor Leger | TX-DAL | BBB Serving North Central Texas | J00017499 | Unity Connection SU Patch for OAuth Support | Closed | 100% | 111.1% | 9 | -1 | 1245 | 1025 | -11.11% | 1245 | 0 | 10 | 1025 | 1035 |  | 1025 |  | 0 | 1600.8 | -459.2 | -28.69%
06/27/22 |  | 03/21/24 | Open | Brian Willery | Jacob Parks, Jeffrey Holman, Kenneth Dieter |  | Beau C. Devillier, Brian Willery, Lauren J Kennewell |  |  | Brian Willery, James Elmore, Juan Saenz, Mohaymen Sodi, Ron Loge, Tony Dean Skipworth |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00013362 | Net-Pro-Srvc - ACI Configurations | Closed | 100% | 56.6% | 1133.13 | 516.79 | 151009.25 | 85975 | 45.61% | 151009.25 | 25 | 641.34 | 72023.75 | 258.81 |  | 85975 |  | 0 | 49989 | -36244.81 | -72.51%
03/13/23 |  | 03/26/24 | Open | LaQisha Marshall | Warren Wilson |  | Christi D Hubbard, Garrett Hart, LaQisha Marshall, Larry Noble |  |  | Garrett Hart, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Lee Lewis Construction, Inc. | J00015021 | Verkada Implementation K-8 Campus | Closed | 100% | 54.73% | 195.06 | 101.31 | 22625.15 | 15618.75 | 51.94% | 22625.15 | 13 | 106.75 | 13343.75 | 1098.9 |  | 15618.75 |  | 526812.42 | 198460.6 | 181742.95 | 91.58%
03/28/24 |  | 03/28/24 | Open | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Julio C Montoya, Khalid Abunaja, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Devon LeMoine, Garrett Hart, Justin Smallwood, Miguel Reed, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | J00017631 | Northside HS SB1398 | Training/Knowledge Transfer/Documentation | 90% | 4430% | 1 | -41.5 | 92.83 | 3918 | -4150% | 92.83 | 1.8 | 44.3 | 3810 | 0 |  | 3918 |  | 24413.3 | 1800 | -2118 | -117.7%
12/01/23 |  | 03/28/24 | Open | Joaquin Marroquin | Vernon Jackson |  | Diana Berger, Eric Rodriguez, Joaquin Marroquin, Robert Lavender |  |  | Brian Willery, Joaquin Marroquin, Robert Lavender |  |  | Eric Rodriguez | TX-SOUT | United ISD | J00016556 | Vbrick Virtualization | Closed | 0% | 0% | 0 | -48.25 | 0 | 6108.75 | 0% | 0 | 0 | 48.25 | 6108.75 | 0 |  | 6108.75 |  | 28886.4 | 7613.6 | 1504.85 | 19.77%
12/01/23 |  | 03/28/24 | Open | Joaquin Marroquin | Vernon Jackson |  | Diana Berger, Eric Rodriguez, Joaquin Marroquin, Robert Lavender |  |  | Brian Willery, Joaquin Marroquin, Robert Lavender |  |  | N/A | N/A | United ISD | J00016556 | Vbrick Virtualization | Closed | 100% | 0% | 45 | 45 | 6225 | 0 | 100% | 6225 | 0 | 0 | 0 | 0 |  | 0 |  | 28886.4 | 7613.6 | 7613.6 | 100%
10/02/23 |  | 03/29/24 | Open | Gena Robbins | Michael Brett Beggs |  | Beau C. Devillier, Gena Robbins, Jeffery Giles, Joshua Osgood, Kristy L Dice, Luis Ovalles, Michael Brett Beggs |  |  | Austen Howard, Cory Bradfield, Gena Robbins, Jeffery Giles, Joshua Osgood, Luis Ovalles, Raymond Phan, Saravanan Lakshmanan |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00016505 | ISE - HX Compute Nodes | Closed | 100% | 242.4% | 41.25 | -54.25 | 4998.75 | 11087.5 | -131.5% | 4998.75 | 4.5 | 100 | 10817.5 | 501.08 |  | 11087.5 |  | 159523.88 | 11419.8 | -168.78 | -1.478%
01/29/24 |  | 03/29/24 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Christopher Prado, Jason Osuna, Larry Noble, Mario Sanchez, Shannon Marie Alvarado |  |  | Christopher Prado, Jhon Genao, Juan Pomares, Mario Sanchez, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00017361 | Chicago Office Wireless Survey | Closed | 100% | 372.2% | 28.75 | -24.25 | 3928.75 | 7737.5 | -84.35% | 3928.75 | 54 | 107 | 4497.5 | 0 |  | 7737.5 |  | 0 | 5900.56 | -1836.94 | -31.13%
02/06/24 |  | 04/01/24 | Open | Summer Abunaja | Steven Walker |  | David Monasmith, David Monasmith, Larry Noble, Luis Ovalles, Steven Walker, Summer Abunaja |  |  | Luis Ovalles |  |  | David Monasmith | TX-HOU | Texas A&M Health Science Center | J00017459 | SQL Support Work Order | Closed | 100% | 44.44% | 9 | 5 | 1180 | 540 | 55.56% | 1180 | 0 | 4 | 540 | 0 |  | 540 |  | 0 | 1795 | 1255 | 69.92%
02/20/24 |  | 04/01/24 | Open | Summer Abunaja | N/A |  | Beau C. Devillier, Cory Bradfield, Cory Bradfield, Katharine McCarley, Katherine McCarley, Michael Brett Beggs, Summer Abunaja |  |  | Cory Bradfield |  |  | Katie McCarley | TX-DAL | Winstead PC | J00017627 | T&E - Data Center Software Upgrades | Closed | 0% | 0% | 0 | -7.5 | 0 | 1012.5 | 0% | 0 | 0 | 7.5 | 1012.5 | 0 |  | 1012.5 |  | 0 | 0 | -1012.5 | 0%
11/21/22 |  | 04/01/24 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Larry Noble, Tray Giddens |  |  | Brian Newman, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00014372 | Collab PS per Mohammad - Migration to New Cluster | Closed | 100% | 110.5% | 66.04 | -6.96 | 9135.5 | 10032.5 | -10.54% | 9135.5 | 0 | 73 | 10032.5 | 0 |  | 10032.5 |  | 0 | 12558.8 | 2526.3 | 20.12%
09/25/23 |  | 04/02/24 | Open | Karyn Hubbard | Jacob Parks, Jeffrey Holman |  | Garrett Curran, Jacob Sennett, Karyn Hubbard, Yong Kim |  |  | Jacob Sennett |  |  | Garrett Curran | CA-LAX | San Bernardino County Sheriff’s Department | J00016525 | FTD UPGRADE (Fireworks Program) | Closed | 100% | 21.05% | 19 | 15 | 2850 | 600 | 78.95% | 2850 | 0 | 4 | 600 | 364 |  | 600 |  | 0 | 2992.48 | 2028.48 | 67.79%
03/05/24 |  | 04/02/24 | Open | LaQisha Marshall | Firas Abood, Michael Brett Beggs |  | Firas Abood, Kurt Sell, LaQisha Marshall, Michael Brett Beggs, Thomas McClanahan |  |  | Adam Felix, Grayson Rigsby, LaQisha Marshall, Michael Steven Foster, Oscar Gonzalez, Richard Shea, Robert Jones, Steven Shipmon, Tabais Prater, Taylor Poole |  |  | Thomas McClanahan | TX-CEN | Samsung Austin Semiconductor, LLC (SAS) | J00017764 | Uninstall Project | Closed | 100% | 64.75% | 239.4 | 96.4 | 15105 | 8575 | 40.27% | 15105 | 12 | 155 | 7855 | 752.5 |  | 8575 |  | 0 | 19822 | 10494.5 | 52.94%
08/07/23 |  | 04/02/24 | Open | LaQisha Marshall | Ahmed Al-Zubaidi, Wyley Johnson |  | David D Tijerina, Fadi Ashour, Kurt Sell, LaQisha Marshall, Sophia Quinter |  |  | LaQisha Marshall |  |  | David D Tijerina | TX-CEN | Travis County | J00016224 | ISE Upgrade and Azure AD | Closed | 100% | 64.42% | 52 | 18.5 | 6519.15 | 4187.5 | 35.58% | 6519.15 | 0 | 33.5 | 4187.5 | 0 |  | 4187.5 |  | 0 | 47555.2 | 43367.7 | 91.19%
05/24/22 |  | 04/05/24 | Open | Abiodun David Babasola | Warren Wilson |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Garrett Hart, Taylor Leger |  |  | Abiodun David Babasola, Adam Ko, Conner MacDonnell, Daniel Crawford, Dante Torres, Dylan Pittsinger, Garrett Hart, Joel Fleming, Joel Hubbard, Jordan Newman, Joshua Hubbard, Kairo Sauceda, Kirk O'Guinn, Pablo Bernal, Phillip Thornton, Taylor Poole, Thai Truong, Zachary Newman |  |  | Taylor Leger | TX-DAL | Cleburne ISD | J00013201 | Video Management System (VMS) Appliance Refresh | Closed | 100% | 2547% | 52.09 | -1020.16 | 5789.75 | 84550 | -1958% | 5789.75 | 254.5 | 1326.75 | 69280 | 5549.5 |  | 84550 |  | 122409.3 | 9228.4 | -80871.1 | -876.3%
06/26/23 |  | 04/10/24 | Open | Tray Giddens | Warren Wilson |  | Larry Noble, Lindie Lorraine Lamar, Tray Giddens |  |  | Garrett Hart, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Houston Housing Authority | J00015800 | Paging, Access Control work | Closed | 100% | 353.3% | 7.5 | -19 | 937.5 | 4062.5 | -253.3% | 937.5 | 0 | 26.5 | 4062.5 | 0 |  | 4062.5 |  | 0 | 12643.52 | 8581.02 | 67.87%
05/15/23 |  | 04/12/24 | Open | Marco Lish | Ahmed Al-Zubaidi, Mark J Chambliss, Pradeep Tyagi , Wyley Johnson |  | Larry Noble, Marco Lish, Neel Shah |  |  | Lauren Lanzini Coffey, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00015439 | COH HITS Webex UCCE- PM oversight | Closed | 100% | 43.62% | 600 | 338.25 | 75000 | 32718.75 | 56.38% | 75000 | 0 | 261.75 | 32718.75 | 0 |  | 32718.75 |  | 0 | 59850 | 27131.25 | 45.33%
04/03/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla, Kenneth Dieter, Kinton Connelly |  | Camille Elizabeth Taber, Jeff Barker, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | Aaron Abshire, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | Camille Taber | FL | St. Johns River Water Management District | J00011917 | DC Network Redesign | Closed | 0% | 0% | 0 | -68.25 | 0 | 9056.25 | 0% | 0 | 0 | 68.25 | 9056.25 | 0 |  | 9056.25 |  | 56504.8 | 2781.2 | -6275.05 | -225.6%
05/23/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla |  | Camille Elizabeth Taber, David Escamilla, Jeff Barker, LaQisha Marshall, Tony Dean Skipworth |  |  | LaQisha Marshall |  |  | Camille Taber | FL | St. Johns River Water Management District | J00015630 | Phase 2 | Closed | 0% | 0% | 0 | -18 | 0 | 2250 | 0% | 0 | 0 | 18 | 2250 | 0 |  | 2250 |  | 58048.57 | 0 | -2250 | 0%
04/03/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla, Kenneth Dieter, Kinton Connelly |  | Camille Elizabeth Taber, Jeff Barker, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | Aaron Abshire, LaQisha Marshall, Luis Ovalles, Tony Dean Skipworth |  |  | N/A | N/A | St. Johns River Water Management District | J00011917 | DC Network Redesign | Closed | 100% | 0% | 16.26 | 16.26 | 1840.6 | 0 | 100% | 1840.6 | 0 | 0 | 0 | 0 |  | 0 |  | 56504.8 | 2781.2 | 2781.2 | 100%
05/23/23 |  | 04/15/24 | Open | LaQisha Marshall | David Escamilla |  | Camille Elizabeth Taber, David Escamilla, Jeff Barker, LaQisha Marshall, Tony Dean Skipworth |  |  | LaQisha Marshall |  |  | N/A | N/A | St. Johns River Water Management District | J00015630 | Phase 2 | Closed | 100% | 0% | 30.85 | 30.85 | 5771.25 | 0 | 100% | 5771.25 | 0 | 0 | 0 | 0 |  | 0 |  | 58048.57 | 0 | 0 | 0%
12/11/23 |  | 04/17/24 | Open | Richard Keith Arnst | Bryan Brown |  | Beau C. Devillier, Kristy L Dice, Richard Keith Arnst |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00016970 | ALC TRAINING ROOM AV | Closed | 100% | 95.15% | 41.25 | 11.25 | 5651.25 | 4703.75 | 27.27% | 5651.25 | 9.25 | 39.25 | 3605 | 0 |  | 4703.75 |  | 14452.58 | 9510.8 | 4807.05 | 50.54%
05/01/23 |  | 04/22/24 | Open | Brian Willery | Joshua Adam Engle |  | Beau C. Devillier, Brian Willery, Dante Torres, Devin Moreno, Dylan Pittsinger, Jhon Genao, Joel Hubbard, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Lauren J Kennewell, Majid Shirzadeh, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Sean Cowhey, Tabais Prater, Tavis Jackson, Timothy Fain, Vitalii Stepanchenko |  |  | Albert Bernal, Angelo Gallegos, Austen Howard, Blake Garibaldi, Brian Willery, Carlo Enriquez, Conner MacDonnell, Craig Collinsworth, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelino, Dylan Pittsinger, Eric Firestone, Eric Rodriguez, Ethan Thomas George, Jean Pierre Obenda, Jeffery Giles, Jeremy Frank Jackson, Jhon Genao, Joel Fleming, Joel Hubbard, Jonquil Hines, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Thompson, Kanoa Parman, Kebret Eshetu, Kirk O'Guinn, Mario Sanchez, Ma |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00014976 | 2023 Switch & AP Refresh | Closed | 100% | 130.4% | 3220.22 | -894.78 | 276266.45 | 380287.75 | -27.79% | 276266.45 | 84.15 | 4199.15 | 372362.5 | 36717.34 |  | 380287.75 |  | 3374316 | 353446.32 | -63558.77 | -17.98%
10/08/21 |  | 04/30/24 | Open | Brian Willery | Jacob Parks |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Conner MacDonnell, Gena Robbins, James Elmore, Kimberly DeVos, Orlando Francis |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00010998 | 02103485 - CCECC Firepower 2110 Threat Defense | Closed | 100% | 47.19% | 80 | 42.25 | 9618 | 3041.25 | 52.81% | 9618 | 0 | 37.75 | 3041.25 | 22.4 |  | 3041.25 |  | 10818 | 14112 | 11048.35 | 78.29%
08/09/21 |  | 04/30/24 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Bryan Mullen, Gena Robbins, Kimberly DeVos, Ron Loge |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00011044 | 02103926 - ATT FirstNet - ISR 4351s | Closed | 100% | 369.3% | 71.29 | -191.96 | 5983.7 | 25088.75 | -269.3% | 5983.7 | 0 | 263.25 | 25088.75 | 0 |  | 25088.75 |  | 22770.77 | 10028.76 | -15059.99 | -150.2%
02/28/24 |  | 04/30/24 | Open | LaQisha Marshall | Warren Wilson |  | Christi D Hubbard, LaQisha Marshall, Larry Noble |  |  | Garrett Hart, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00017674 | Verkada DMS | Closed | 100% | 54.87% | 55.59 | 25.09 | 6012 | 4262.5 | 45.13% | 6012 | 0 | 30.5 | 4262.5 | 0 |  | 4262.5 |  | 186291 | 22435.8 | 18173.3 | 81%
02/12/24 |  | 04/30/24 | Open | Shannon Marie Alvarado | N/A |  | Kurt Sell, Lindie Lorraine Lamar, Mark J Chambliss, Shannon Marie Alvarado |  |  | N/A |  |  | Lindie Lamar | TX-HOU | Texas First Bank | J00017466 | Local Gateway for Webex Calling Deployment | Cancelled | 0% | 0% | 22.5 | 22.5 | 3082.5 | 0 | 100% | 3082.5 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
03/01/24 |  | 04/30/24 | Open | Tray Giddens | Warren Wilson |  | Garrett Hart, Jeff Barker, Joseph Boglino, Tray Giddens |  |  | Garrett Hart, Tray Giddens |  |  | Joseph Boglino | US-FED | Infinavate Consultancy Services, LLC | J00017723 | OpenPath Maintenance | Closed | 100% | 76.92% | 16.9 | 3.9 | 2047.5 | 2225 | 23.08% | 2047.5 | 0 | 13 | 2225 | 0 |  | 2225 |  | 0 | 3380.8 | 1155.8 | 34.19%
04/18/22 |  | 05/01/24 | Open | Brian Willery | N/A |  | Brian Willery, Larry Noble, Osazee Eweka, Susan Richardson |  |  | Brian Willery, Osazee Eweka |  |  | N/A | N/A | Amazon Web Services | J00012912 | AWS Migration - AppStream - Work Order | Closed | 100% | 0% | 35.16 | 35.16 | 4051.25 | 0 | 100% | 4051.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
04/18/22 |  | 05/01/24 | Open | Brian Willery | N/A |  | Brian Willery, Larry Noble, Osazee Eweka, Susan Richardson |  |  | Brian Willery, Osazee Eweka |  |  | Susan Richardson | TX-HOU | Amazon Web Services | J00012912 | AWS Migration - AppStream - Work Order | Closed | 0% | 0% | 0 | -6.25 | 0 | 806.25 | 0% | 0 | 0 | 6.25 | 806.25 | 0 |  | 806.25 |  | 0 | 0 | -806.25 | 0%
03/06/23 |  | 05/01/24 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Bryan Mullen, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Bryan Mullen, Robert Kelly |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00013749 | Internet Routers | Closed | 100% | 37.85% | 60.77 | 37.77 | 6244.75 | 2880 | 62.15% | 6244.75 | 0 | 23 | 2880 | 0 |  | 2880 |  | 23328.9 | 10119.6 | 7239.6 | 71.54%
03/06/23 |  | 05/01/24 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00013755 | DC Site - Access & Mgmt Switches | Closed | 100% | 0% | 43.25 | 43.25 | 4323.25 | 0 | 100% | 4323.25 | 0 | 0 | 0 | 0 |  | 0 |  | 28898.4 | 6814 | 6814 | 100%
10/16/23 |  | 05/01/24 | Open | Brian Willery | Bryan Geoghan |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Anthony Towsley, Brian Willery |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00016418 | UCCX Advanced Supervisor Capabilities | Closed | 100% | 477.8% | 15.75 | -59.5 | 2043.75 | 9743.75 | -377.8% | 2043.75 | 0 | 75.25 | 9743.75 | 0 |  | 9743.75 |  | 0 | 3250.8 | -6492.95 | -199.7%
10/16/23 |  | 05/01/24 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Bryan Mullen, Sean Cowhey, Tabais Prater |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00016702 | Athletic Center APs | Closed | 100% | 86.32% | 15.06 | 2.06 | 1229.9 | 1040 | 13.68% | 1229.9 | 0 | 13 | 1040 | 28.1 |  | 1040 |  | 7170.76 | 2029.2 | 961.1 | 47.36%
11/01/23 |  | 05/01/24 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh, Shiraz Humayun |  |  | Patrick Shea Thompson |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00016825 | AP Refresh - Work Order – 220054578 | Closed | 100% | 6.998% | 14.29 | 13.29 | 1166.8 | 60 | 93% | 1166.8 | 0 | 1 | 60 | 0 |  | 60 |  | 9043.68 | 3852 | 3792 | 98.44%
04/21/23 |  | 05/03/24 | Open | Jason Esry | William Birdsong |  | Blake Garibaldi, Bradley Buchanan, Dylan Pittsinger, Erick Sanchez, Jason Esry, Jean Pierre Obenda, Jeff Barker, Jeffery Giles, Joshua Osgood, Sean Cowhey, Tabais Prater, Taylor Poole, Vitalii Stepanchenko, William Birdsong |  |  | Austen Howard, Blake Garibaldi, Bradley Buchanan, Carlo Enriquez, Dante Torres, Devin Moreno, Dylan Pittsinger, Erick Sanchez, Jason Esry, Jean Pierre Obenda, Jeffery Giles, Jhon Genao, Joshua Hubbard, Joshua Osgood, Kanoa Parman, Kebret Eshetu, Kenia Dimas, Kirk O'Guinn, Moises Rodriguez, Noah Trump, Phillip Luvane Coleman, Sean Cowhey, Tabais Prater, Tavis Jackson, Taylor Poole, Vitalii Stepanchenko, William Chris Roome |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00014134 | Wireless ERATE 2022 | Closed | 100% | 0% | 2533.82 | 2533.82 | 211939.3 | 0 | 100% | 211939.3 | 0 | 0 | 0 | 5520.49 |  | 0 |  | 2391549.2 | 173796.66 | 168276.17 | 96.82%
04/21/23 |  | 05/03/24 | Open | Jason Esry | William Birdsong |  | Blake Garibaldi, Bradley Buchanan, Dylan Pittsinger, Erick Sanchez, Jason Esry, Jean Pierre Obenda, Jeff Barker, Jeffery Giles, Joshua Osgood, Sean Cowhey, Tabais Prater, Taylor Poole, Vitalii Stepanchenko, William Birdsong |  |  | Austen Howard, Blake Garibaldi, Bradley Buchanan, Carlo Enriquez, Dante Torres, Devin Moreno, Dylan Pittsinger, Erick Sanchez, Jason Esry, Jean Pierre Obenda, Jeffery Giles, Jhon Genao, Joshua Hubbard, Joshua Osgood, Kanoa Parman, Kebret Eshetu, Kenia Dimas, Kirk O'Guinn, Moises Rodriguez, Noah Trump, Phillip Luvane Coleman, Sean Cowhey, Tabais Prater, Tavis Jackson, Taylor Poole, Vitalii Stepanchenko, William Chris Roome |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00014134 | Wireless ERATE 2022 | Closed | 0% | 0% | 0 | -2134.5 | 0 | 194990.5 | 0% | 0 | 118.3 | 2252.8 | 187307.5 | 5520.49 |  | 194990.5 |  | 2391549.2 | 173796.66 | -26714.33 | -15.37%
05/10/23 |  | 05/09/24 | Open | Summer Abunaja | Jeremy Hoffpauir |  | Andrew G Wagenhofer, Jeff Barker, Jessica Anderson, Summer Abunaja |  |  | Aaron Christopher Pfeifer |  |  | Jessica Anderson | US-SP | Allens Cable TV Internet (ATVCI) | J00015578 | T&E | Not started | 0% | 0% | 0 | -18.5 | 0 | 2497.5 | 0% | 0 | 0 | 18.5 | 2497.5 | 0 |  | 2497.5 |  | 0 | 3515 | 1017.5 | 28.95%
05/13/24 |  | 05/13/24 | Open | David Babasola | Bryan Brown |  | N/A |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00018025 | 02417796 | N/A | 0% | 0% | 4 | 4 | 140 | 0 | 100% | 140 | 0 | 0 | 0 | 0 |  | 0 |  | 2272.25 | 52.36 | 52.36 | 100%
07/24/23 |  | 05/15/24 | Open | LaQisha Marshall | Timothy Ramsey |  | Christi D Hubbard, Jacob Sennett, LaQisha Marshall, Larry Noble |  |  | Jacob Sennett, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | J00015915 | Security EA | Closed | 100% | 33.06% | 122.5 | 82 | 17762.5 | 5450 | 66.94% | 17762.5 | 0 | 40.5 | 5450 | 0 |  | 5450 |  | 0 | 27975.6 | 22525.6 | 80.52%
08/14/23 |  | 05/15/24 | Open | LaQisha Marshall | David Watkins, Firas Abood, Michael Brett Beggs |  | David Watkins, Firas Abood, Kurt Sell, LaQisha Marshall, Lori Endsley, Michael Brett Beggs, Romar Roca, Ron Loge, Thomas McClanahan, Tony Dean Skipworth |  |  | LaQisha Marshall, Ron Loge, Tony Dean Skipworth |  |  | Thomas McClanahan | TX-CEN | Samsung Austin Semiconductor, LLC (SAS) | J00016213 | ACI Network refresh | Closed | 100% | 73.72% | 648.74 | 188.49 | 84856.2 | 74426.25 | 29.05% | 84856.2 | 18 | 478.25 | 71676.25 | 310.41 |  | 74426.25 |  | 0 | 127285 | 52548.34 | 41.28%
04/08/24 |  | 05/15/24 | Open | Richard Keith Arnst | Bryan Brown |  | Beau C. Devillier, Lauren J Kennewell, Richard Keith Arnst |  |  | Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | Medical City Healthcare | J00017976 | Med City Lewisville - Amplifier Replacement | Closed | 100% | 55.42% | 4.06 | 1.81 | 572.5 | 296.25 | 44.58% | 572.5 | 0 | 2.25 | 296.25 | 0 |  | 296.25 |  | 566.66 | 783.6 | 487.35 | 62.19%
06/05/23 |  | 05/17/24 | Open | Jason Esry | Emilio Carrillo |  | David D Tijerina, James Danner, Jason Esry, Larry Noble, Mohammed Almoola |  |  | An Le, Daniel Quade, Ernesto Gonzalez, James Danner, Jason Esry, John Senkulics, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Almoola |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00014649 | Access Switch Install - Convocation Campus | Closed | 100% | 293.2% | 42.37 | -81.88 | 4260.97 | 9600 | -193.2% | 4260.97 | 0 | 124.25 | 9600 | 0 |  | 9600 |  | 45004.46 | 6966.8 | -2633.2 | -37.8%
04/15/24 |  | 05/23/24 | Open | Jim Blackwell | Mark J Chambliss |  | Ashley F Freeman, Hamzeh Tahat, Jim Blackwell, Larry Noble, Mark J Chambliss |  |  | Jim Blackwell, Ming Chiu |  |  | Ashley F Freeman | TX-HOU | Fort Bend County | J00018071 | Editing UCCX Script Work Order | Closed | 100% | 93.33% | 7.5 | 0.5 | 1057.5 | 935 | 6.667% | 1057.5 | 0 | 7 | 935 | 0 |  | 935 |  | 0 | 1650.6 | 715.6 | 43.35%
01/30/24 |  | 05/24/24 | Open | LaQisha Marshall | Amanda Barney, Jacob Parks, Jeffrey Holman |  | Alexander Gutman, Amanda Barney, Ashutosh Patel, Beau C. Devillier, Ibrahim Altaweel, Jacob Sennett, Joshua Osgood, LaQisha Marshall, Rogelio Morgado-Perez, Sean Cowhey, Tavis Jackson |  |  | Ashutosh Patel, Conner MacDonnell, Jacob Sennett, Joshua Osgood, LaQisha Marshall |  |  | Alex Gutman | TX-DAL | Vantage Financial, LLC Division of Peoples Bank | J00017392 | 2023 Palo Alto Renewal | Closed | 100% | 110.3% | 128.75 | -13.25 | 17858.75 | 19820 | -10.29% | 17858.75 | 0 | 142 | 19820 | 0 |  | 19820 |  | 656872.6 | 35360.8 | 15540.8 | 43.95%
04/15/24 |  | 05/30/24 | Open | Tray Giddens | Aman Khan |  | Ahmed Jameel, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Ahmed Jameel, Tray Giddens |  |  | Dustin Huffman | TX-HOU | City of League City | J00018033 | Core Replacement | Closed | 100% | 71.9% | 61.2 | 19.2 | 6935 | 5500 | 31.37% | 6935 | 2 | 44 | 5250 | 0 |  | 5500 |  | 0 | 9860 | 4360 | 44.22%
01/23/24 |  | 05/31/24 | Open | Jason Esry | Christopher Puyear |  | Christopher Puyear, David D Tijerina, Jason Esry, Kurt Sell, Samuel Newland |  |  | George McGann, Jason Esry, Ryan Scott, Samuel Newland |  |  | David D Tijerina | TX-CEN | Travis County | J00017335 | Webex Calling and Webex Contact Center Trial | Closed | 100% | 62.54% | 71.95 | 26.95 | 9857.15 | 6045 | 37.46% | 9857.15 | 0 | 45 | 6045 | 0 |  | 6045 |  | 0 | 14500 | 8455 | 58.31%
12/31/20 |  | 05/31/24 | Open | Karyn Hubbard | Alan Dumdei, Joseph Hayes, Timothy Rosser |  | Beau C. Devillier, Joseph Hayes, Karyn Hubbard, Shawn Sutton, Timothy Rosser |  |  | Daniel Crawford, Darrell Walton, Dionisio Oscar Medina-Marcelin, Jonathan Plante, Karyn Hubbard, Rafael Rodriguez-Vargas, Timothy Sean Marcyes, Vitalii Stepanchenko |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00009292 | ASR Internet Upgrade | Cancelled | 50% | 161.1% | 26.44 | -14.16 | 2459.3 | 3941 | -53.56% | 2459.3 | 2 | 42.6 | 3841 | 40.6 |  | 3941 |  | 6680.6 | 4002 | 20.4 | 0.5097%
06/19/23 |  | 05/31/24 | Open | Marco Lish | Ahmed Al-Zubaidi, Wyley Johnson |  | Abdulrahman Farhan, Christine A Hupe, Dhulfiqar Al Hashimi, Larry Noble, Marco Lish, Neel Shah |  |  | Dhulfiqar Al Hashimi, Jeffery Giles, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00015795 | HITS VPN Deployment | Closed | 100% | 100.9% | 293.75 | -2.75 | 42593.75 | 42952.5 | -0.9362% | 42593.75 | 0 | 296.5 | 40852.5 | 77.57 |  | 42952.5 |  | 0 | 57544 | 14513.93 | 25.22%
01/02/24 |  | 05/31/24 | Open | Richard Keith Arnst | Bryan Brown, Christopher Garcia |  | Beau C. Devillier, Lauren J Kennewell, Richard Keith Arnst |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | Medical City Healthcare | J00017213 | Auditorium AV - Medical City Plano | Closed | 100% | 162.7% | 37.5 | -22.5 | 4977.5 | 6707.5 | -60% | 4977.5 | 1 | 61 | 6632.5 | 0 |  | 6707.5 |  | 36353.07 | 8364.4 | 1656.9 | 19.81%
05/31/24 |  | 05/31/24 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Christopher Prado, Daniel Snyder, Jason Osuna, Larry Noble, Mario Sanchez, Shannon Marie Alvarado |  |  | Christopher Prado, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00017362 | Wireless Validation Survey at Houston Corp Office | Closed | 100% | 89.03% | 38.75 | 4.25 | 4018.75 | 3397.5 | 10.97% | 4018.75 | 0 | 34.5 | 3397.5 | 0 |  | 3397.5 |  | 0 | 6333.6 | 2936.1 | 46.36%
02/12/24 |  | 06/04/24 | Open | LaQisha Marshall | Timothy Ramsey |  | Christi D Hubbard, Ibrahim Altaweel, LaQisha Marshall, Larry Noble, Rogelio Morgado-Perez, Timothy Ramsey, Tom Magboo |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, LaQisha Marshall, Mohammad Solomon, Rogelio Morgado-Perez, Tom Magboo |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | J00017497 | Offensive Security Assessment | Closed | 100% | 103.7% | 180.4 | -6.6 | 26950 | 27900 | -3.659% | 26950 | 0 | 187 | 27900 | 0 |  | 27900 |  | 0 | 17623.2 | -10276.8 | -58.31%
05/30/24 |  | 06/06/24 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, Christopher Garcia, David Babasola, Joel Hubbard, Lauren J Kennewell, Robert Lavender |  |  | Abiodun David Babasola, Joel Hubbard |  |  | Lauren J Kennewell | TX-DAL | Methodist Health System | J00018408 | Barco Clickshare CX-30 Installation | Closed | 100% | 80% | 2.5 | 0.5 | 352.5 | 175 | 20% | 352.5 | 0 | 2 | 175 | 0 |  | 175 |  | 2531.27 | 481.8 | 306.8 | 63.68%
06/13/23 |  | 06/06/24 | Open | Abiodun David Babasola | David Watkins |  | Abiodun David Babasola, David Babasola, Kristy L Dice, Nazario Armenta Barraza |  |  | Abiodun David Babasola, Austen Howard, Jeffery Giles, Kebret Eshetu, Moises Rodriguez, Nazario Armenta Barraza, William Chris Roome, Zachary Newman |  |  | Kristy L Dice | TX-DAL | Prestonwood Baptist Church | J00015084 | Virtual to Physical Wireless Infrastructure | Closed | 100% | 250.5% | 80.63 | -119.37 | 9456.25 | 25477.5 | -148% | 9456.25 | 2 | 202 | 25287.5 | 28.6 |  | 25477.5 |  | 79863.7 | 15610.64 | -9895.46 | -63.39%
09/20/21 |  | 06/06/24 | Open | Jennifer Soliz | Emilio Carrillo, Mark J Chambliss |  | David D Tijerina, George McGann, Jennifer Soliz, Larry Noble, Lonnie Owens, Michael Torres, Robert Kelly, Robert Kelly |  |  | Aldo Cortes, An Le, Angel Alicea, Angel Alicea-Torres, Daniel Quade, George McGann, James Danner, Jennifer Soliz, John Senkulics, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Almoola, Robert Kelly |  |  | Lonnie Owens | TX-CEN | City of San Antonio | J00011273 | AVFM MDF (mirroring) | Closed | 0% | 0% | 0 | -181.5 | 0 | 13994.5 | 0% | 0 | 3 | 184.5 | 13709.5 | 1101.22 |  | 13994.5 |  | 86790.6 | 14018.4 | -1077.32 | -7.685%
09/20/21 |  | 06/06/24 | Open | Jennifer Soliz | Emilio Carrillo, Mark J Chambliss |  | David D Tijerina, George McGann, Jennifer Soliz, Larry Noble, Lonnie Owens, Michael Torres, Robert Kelly, Robert Kelly |  |  | Aldo Cortes, An Le, Angel Alicea, Angel Alicea-Torres, Daniel Quade, George McGann, James Danner, Jennifer Soliz, John Senkulics, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Almoola, Robert Kelly |  |  | N/A | N/A | City of San Antonio | J00011273 | AVFM MDF (mirroring) | Closed | 100% | 0% | 80.3 | 80.3 | 6373 | 0 | 100% | 6373 | 0 | 0 | 0 | 1101.22 |  | 0 |  | 86790.6 | 14018.4 | 12917.18 | 92.14%
07/24/23 |  | 06/07/24 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Diana Berger, Edward Padron, Ivan Uribe, Jason Osuna, Karen Grant-Dennison, Mariana Pacheco, Mario Sanchez, Robert McIver |  |  | Carlo Enriquez, Conner MacDonnell, Ivan Uribe, Kanoa Parman, Kebret Eshetu, Mario Sanchez, Robert McIver, William Chris Roome |  |  | Mariana Pacheco | TX-SOUT | Las Cruces Public Schools | J00015891 | Erate 2021 Cat 2 Broadband Equipment Upgrade II | Closed | 0% | 0% | 0 | -395.75 | 0 | 43807.5 | 0% | 0 | 0 | 395.75 | 43807.5 | 0 |  | 43807.5 |  | 1814340.98 | 159769.07 | 115961.57 | 72.58%
07/24/23 |  | 06/07/24 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Diana Berger, Edward Padron, Ivan Uribe, Jason Osuna, Karen Grant-Dennison, Mariana Pacheco, Mario Sanchez, Robert McIver |  |  | Carlo Enriquez, Conner MacDonnell, Ivan Uribe, Kanoa Parman, Kebret Eshetu, Mario Sanchez, Robert McIver, William Chris Roome |  |  | N/A | N/A | Las Cruces Public Schools | J00015891 | Erate 2021 Cat 2 Broadband Equipment Upgrade II | Closed | 100% | 0% | 342.51 | 342.51 | 38873.25 | 0 | 100% | 38873.25 | 0 | 0 | 0 | 0 |  | 0 |  | 1814340.98 | 159769.07 | 159769.07 | 100%
07/14/21 |  | 06/10/24 | Open | Robert McIver | David Pena, Edward Padron, Firas Abood, Jose Padilla Jr., Wyley Johnson |  | Christopher Prado, Cory Bradfield, Cory Bradfield, Eric Rodriguez, Felix Martinez, Francisco Medrano, Ivan Uribe, Mario Sanchez, Michael Hilton, Robert McIver |  |  | Alexander Reyes, Carlos Carrillo, Christopher Prado, Cory Bradfield, Erasmo Ramos, Eric Firestone, Felix Martinez, Francisco Medrano, Ivan Uribe, Juan Saenz, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Matthew D'Ambrosio, Michael Hilton, Robert McIver, Sophia Quinter |  |  | Eric Rodriguez | TX-SOUT | McAllen ISD | J00011019 | Multiple PIRs - Multiple PSEs | Closed | 0% | 0% | 0 | -735.52 | 0 | 78832.25 | 0% | 0 | 68.07 | 803.59 | 71528.75 | 2450 |  | 78832.25 |  | 796612.16 | 126433.6 | 45151.35 | 35.71%
07/14/21 |  | 06/10/24 | Open | Robert McIver | David Pena, Edward Padron, Firas Abood, Jose Padilla Jr., Wyley Johnson |  | Christopher Prado, Cory Bradfield, Cory Bradfield, Eric Rodriguez, Felix Martinez, Francisco Medrano, Ivan Uribe, Mario Sanchez, Michael Hilton, Robert McIver |  |  | Alexander Reyes, Carlos Carrillo, Christopher Prado, Cory Bradfield, Erasmo Ramos, Eric Firestone, Felix Martinez, Francisco Medrano, Ivan Uribe, Juan Saenz, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Matthew D'Ambrosio, Michael Hilton, Robert McIver, Sophia Quinter |  |  | N/A | N/A | McAllen ISD | J00011019 | Multiple PIRs - Multiple PSEs | Closed | 100% | 0% | 1120.2 | 1120.2 | 100578.14 | 0 | 100% | 100578.14 | 0 | 0 | 0 | 2450 |  | 0 |  | 796612.16 | 126433.6 | 123983.6 | 98.06%
02/05/24 |  | 06/12/24 | Open | Jason Esry | Timothy Ramsey |  | David D Tijerina, Jason Esry, Larry Noble, Marcos Jabian, Sophia Quinter, Timothy Ramsey |  |  | Jason Esry, Sophia Quinter |  |  | David D Tijerina | TX-CEN | Leander ISD | J00017341 | ISE Health Check | Closed | 100% | 48.61% | 57.6 | 29.6 | 8400 | 3887.5 | 51.39% | 8400 | 0 | 28 | 3887.5 | 0 |  | 3887.5 |  | 57372.8 | 13230 | 9342.5 | 70.62%
03/01/23 |  | 06/17/24 | Open | Robert McIver | Steven Walker, Timothy Ramsey |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Ibrahim Altaweel, Robert McIver, Rogelio Morgado-Perez, Ronan Empig, Tom Magboo |  |  | Christopher Brown, Patrick Shea Thompson, Robert McIver |  |  | Eric Rodriguez | TX-SOUT | Edinburg CISD | J00014974 | Active Directory and Azure Audit | Closed | 0% | 0% | 0 | -85 | 0 | 10675 | 0% | 0 | 0 | 85 | 10675 | 229.55 |  | 10675 |  | 0 | 6926.8 | -3977.75 | -57.43%
03/01/23 |  | 06/17/24 | Open | Robert McIver | Steven Walker, Timothy Ramsey |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Ibrahim Altaweel, Robert McIver, Rogelio Morgado-Perez, Ronan Empig, Tom Magboo |  |  | Christopher Brown, Patrick Shea Thompson, Robert McIver |  |  | N/A | N/A | Edinburg CISD | J00014974 | Active Directory and Azure Audit | Closed | 100% | 0% | 40.25 | 40.25 | 5381.25 | 0 | 100% | 5381.25 | 0 | 0 | 0 | 229.55 |  | 0 |  | 0 | 6926.8 | 6697.25 | 96.69%
06/03/24 |  | 06/19/24 | Open | Tray Giddens | Chad Hart |  | Ahmed Jameel, Dustin Huffman, Larry Noble, Tray Giddens |  |  | Ahmed Jameel, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018363 | Police Department Network Refresh | Closed | 100% | 45% | 20 | 11 | 2435 | 1125 | 55% | 2435 | 0 | 9 | 1125 | 0 |  | 1125 |  | 105334.52 | 0 | -1125 | 0%
03/28/24 |  | 06/20/24 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Osgood, Joshua Parker, Tavis Jackson |  |  | Isaac Brown, Andrew Comeaux, Anthony Balogun, David Gonzalez, David Lenihan, Eliana Guzman, Gregory Posey, Harold Gomez, Jacob Hill, Jarshawn Newsome, Jaylen Morgan, Jennifer Mares, Joshua Osgood, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Mia Rose, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez, Steven Thomas, Valentin Vasquez, Walter Hanchett |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00017834 | Chromebooks Imaging and Distribution | Closed | 100% | 16.19% | 7600 | 6372.5 | 266062.64 | 38040 | 83.85% | 266062.64 | 3 | 1230.5 | 37860 | 0 |  | 38040 |  | 2965000 | 1785000 | 1746960 | 97.87%
02/15/24 |  | 06/21/24 | Open | Jennifer Soliz | Warren Wilson |  | Garrett Hart, Jennifer Soliz, Steve J Rodriguez, Xavier A Trevino |  |  | Alexis Cantu, Carlos Carrillo, Felix Martinez, Garrett Hart, Jennifer Soliz |  |  | Xavier A Trevino | TX-SOUT | University of Texas Rio Grande Valley | J00017566 | EENGR Railway Safety Video Surveillance | Closed | 100% | 227.6% | 21.53 | -24.72 | 2134.15 | 5395 | -114.8% | 2134.15 | 2.75 | 49 | 5230 | 0 |  | 5395 |  | 5264.25 | 3600 | -1795 | -49.86%
05/17/24 |  | 06/21/24 | Open | Jennifer Soliz | David Escamilla |  | Cory Bradfield, Cory Bradfield, Diana Berger, Jennifer Soliz, Juan Saenz, Xavier A Trevino |  |  | Cory Bradfield, Jennifer Soliz, Juan Saenz |  |  | Xavier A Trevino | TX-SOUT | Xcell Orthopaedics Physical Therapy | J00018336 | Small Backup Solution | Closed | 100% | 96.99% | 29.9 | 0.9 | 4141.49 | 3845 | 3.01% | 4141.49 | 0 | 29 | 3845 | 0 |  | 3845 |  | 3415.55 | 6296 | 2451 | 38.93%
12/12/22 |  | 06/25/24 | Open | Robert McIver | N/A |  | Amy Martinez-Nagy, Andrew G Wagenhofer, David Avila, Diana Berger, Remi Martinez-Montenegro, Robert McIver, Robert Mulholland |  |  | Remi Martinez-Montenegro, Robert McIver |  |  | David Avila | TX-SOUT | LAREDO ISD | J00014466 | Kawas Installation - Digital Signage | Closed | 0% | 0% | 0 | -9.5 | 0 | 837.5 | 0% | 0 | 0 | 9.5 | 837.5 | 0 |  | 837.5 |  | 40219.43 | 9016.8 | 8179.3 | 90.71%
12/12/22 |  | 06/25/24 | Open | Robert McIver | N/A |  | Amy Martinez-Nagy, Andrew G Wagenhofer, David Avila, Diana Berger, Remi Martinez-Montenegro, Robert McIver, Robert Mulholland |  |  | Remi Martinez-Montenegro, Robert McIver |  |  | N/A | N/A | LAREDO ISD | J00014466 | Kawas Installation - Digital Signage | Closed | 100% | 0% | 25.31 | 25.31 | 3755.25 | 0 | 100% | 3755.25 | 0 | 0 | 0 | 0 |  | 0 |  | 40219.43 | 9016.8 | 9016.8 | 100%
05/27/24 |  | 06/26/24 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Beau C. Devillier, John Stephen Kurkjian, Shannon Marie Alvarado, Taylor Leger |  |  | John Stephen Kurkjian, Shannon Marie Alvarado |  |  | Taylor Leger | TX-DAL | Cleburne ISD | J00018392 | Cisco Unity Connection (CUC) Service Update | Closed | 100% | 103.6% | 14 | -0.5 | 1950 | 1985 | -3.571% | 1950 | 0 | 14.5 | 1985 | 0 |  | 1985 |  | 0 | 2866.4 | 881.4 | 30.75%
02/05/24 |  | 06/28/24 | Open | Brian Willery | Robert V Eubanks |  | Beau C. Devillier, Brian Willery, Lauren J Kennewell, Robert V Eubanks |  |  | Brian Willery |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00017296 | APC for Additional EOL Campuses | Closed | 100% | 15.97% | 186.25 | 156.5 | 13596.25 | 3718.75 | 84.03% | 13596.25 | 0 | 29.75 | 3718.75 | 0 |  | 3718.75 |  | 144250.5 | 22433.8 | 18715.05 | 83.42%
01/15/24 |  | 06/28/24 | Open | LaQisha Marshall | Warren Wilson |  | Christi D Hubbard, Garrett Hart, LaQisha Marshall, Larry Noble |  |  | Grayson Rigsby, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Braun and Butler Construction Inc. | J00017282 | Video Surveillance and Access Control | Closed | 100% | 52.03% | 73.52 | 36.27 | 8478.35 | 4456.25 | 49.33% | 8478.35 | 1 | 38.25 | 4216.25 | 0 |  | 4456.25 |  | 15813.06 | 44700.49 | 40244.24 | 90.03%
04/02/24 |  | 06/28/24 | Open | Lauren Lanzini Coffey | N/A |  | Amanda Barney, Lauren Lanzini Coffey, Neel Shah, Shiraz Humayun |  |  | Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00016940 | Azure Governance | Cancelled | 5% | 5.952% | 21 | 19.75 | 2685 | 156.25 | 94.05% | 2685 | 0 | 1.25 | 156.25 | 0 |  | 156.25 |  | 0 | 0 | -156.25 | 0%
04/29/24 |  | 06/28/24 | Open | Shannon Marie Alvarado | Albert H Nguyen |  | Conner MacDonnell, Ernesto Gonzalez, Jason Osuna, Juan Pomares, Larry Noble, Shannon Marie Alvarado |  |  | Ernesto Gonzalez, Joshua Osgood, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00018252 | Kennesaw Georgia Office Wireless Survey | Closed | 100% | 142.6% | 28.75 | -0.25 | 7558.71 | 3597.5 | -0.8696% | 7558.71 | 12 | 41 | 2877.5 | 0 |  | 3597.5 |  | 0 | 6304.4 | 2706.9 | 42.94%
04/08/24 |  | 06/28/24 | Open | Tray Giddens | David Escamilla |  | Ashley F Freeman, Juan Saenz, Larry Noble, Tray Giddens |  |  | Juan Saenz, Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Amazon Web Services | J00018008 | VMC on AWS POC | Closed | 0% | 0% | 0 | -8.5 | 0 | 1107.5 | 0% | 0 | 0 | 8.5 | 1107.5 | 0 |  | 1107.5 |  | 0 | 10000 | 8892.5 | 88.92%
04/08/24 |  | 06/28/24 | Open | Tray Giddens | David Escamilla |  | Ashley F Freeman, Juan Saenz, Larry Noble, Tray Giddens |  |  | Juan Saenz, Tray Giddens |  |  | N/A | N/A | Amazon Web Services | J00018008 | VMC on AWS POC | Closed | 100% | 0% | 36 | 36 | 4788 | 0 | 100% | 4788 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 10000 | 10000 | 100%
02/26/24 |  | 06/28/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Galveston County | J00017664 | Data Center (DC) Expansion | Closed | 100% | 88.21% | 109.11 | 21.61 | 14112.45 | 12883.75 | 19.81% | 14112.45 | 8.75 | 96.25 | 11702.5 | 0 |  | 12883.75 |  | 302015.22 | 20437.6 | 7553.85 | 36.96%
04/11/24 |  | 07/01/24 | Open | Brian Willery | Ahmed Al-Zubaidi, Wyley Johnson |  | Brian Willery, Jason Osuna, Larry Noble, Romar Roca |  |  | Brian Willery, Romar Roca |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00016797 | cdFMC Migration Svcs - Cisco Fireworks | Closed | 100% | 21.45% | 313.5 | 246.25 | 45737.5 | 9631.25 | 78.55% | 45737.5 | 0 | 67.25 | 9631.25 | 0 |  | 9631.25 |  | 0 | 63036 | 53404.75 | 84.72%
02/01/24 |  | 07/01/24 | Open | Jennifer Soliz | Emilio Carrillo |  | Hannah Paul, James Danner, Jennifer Soliz, Larry Noble, Michael Torres |  |  | An Le, Angel Alicea, Angel Alicea-Torres, Daniel Quade, James Danner, Jennifer Soliz, John Senkulics, Michael Torres |  |  | Hannah Edmunds | TX-CEN | Edgewood ISD | J00017066 | Eaton UPS Refresh | Closed | 100% | 64.52% | 756 | 268.25 | 55464.75 | 30776.25 | 35.48% | 55464.75 | 0 | 487.75 | 30776.25 | 189.637 |  | 30776.25 |  | 380151.8 | 85189.2 | 54223.313 | 63.65%
07/03/23 |  | 07/02/24 | Open | Abiodun David Babasola | Jacob Parks, Jeffrey Holman, William Birdsong |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Mark Forehand, Sophia Quinter |  |  | Abiodun David Babasola, Sophia Quinter, Todd Melby |  |  | Mark Forehand | TX-DAL | City of Richardson | J00015836 | Wireless Authentication WO 220051356 | Closed | 100% | 71.1% | 39.38 | 11.38 | 4225 | 3855 | 28.9% | 4225 | 0 | 28 | 3705 | 0 |  | 3855 |  | 0 | 3705 | -150 | -4.049%
07/02/24 |  | 07/02/24 | Open | LaQisha Marshall | Timothy Ramsey |  | Eric Firestone, Kurt Sell, LaQisha Marshall, Thomas McClanahan |  |  | Eric Firestone, Haris Rashid, LaQisha Marshall |  |  | Lonnie Owens | TX-CEN | Key Government Finance | M00015559 | 2003290182-01-BOH | Closed | 0% | 0% | 0 | -0.25 | 0 | 12.5 | 0% | 0 | 0 | 0.25 | 0 | 0 |  | 12.5 |  | 0 | 54000 | 53987.5 | 99.98%
07/02/24 |  | 07/02/24 | Open | LaQisha Marshall | Timothy Ramsey |  | Eric Firestone, Kurt Sell, LaQisha Marshall, Thomas McClanahan |  |  | Eric Firestone, Haris Rashid, LaQisha Marshall |  |  | Thomas McClanahan | TX-CEN | Temple ISD | M00015559 | 2003290182-01-BOH | Closed | 0% | 0% | 0 | -56 | 0 | 8137.5 | 0% | 0 | 0 | 56 | 8137.5 | 0 |  | 8137.5 |  | 0 | 54000 | 45862.5 | 84.93%
10/07/22 |  | 07/03/24 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson |  | Larry Noble, Monica Johnson, Tray Giddens |  |  | Oscar Nunez |  |  | Monica Johnson | TX-HOU | Harmony Public Schools | J00013842 | NTE$5K / BPO 23160299 | Cancelled | 80% | 222.2% | 1.35 | -1.65 | 52.65 | 90 | -122.2% | 52.65 | 0 | 3 | 90 | 0 |  | 90 |  | 0 | 0 | -90 | 0%
04/29/24 |  | 07/05/24 | Open | Marco Lish | Michael Brett Beggs |  | Beau C. Devillier, Kirk O'Guinn, Kristy L Dice, Luis Ovalles, Marco Lish, Michael Brett Beggs, Tavis Jackson |  |  | Conner MacDonnell, Dante Torres, Eric Mitchell Frisby, Luis Ovalles, Marco Lish, Sebastian Stanislaw Salata |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00018263 | Additional Video Surveillance Server Install | Closed | 100% | 363.1% | 32.5 | -82.5 | 3347.5 | 9310 | -253.8% | 3347.5 | 3 | 118 | 6970 | 0 |  | 9310 |  | 81293.01 | 5272.32 | -4037.68 | -76.58%
07/03/23 |  | 07/08/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs |  | Amy Martinez-Nagy, Daniel Saenz, David Avila, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Ivan Uribe, Mario Sanchez, Michael Brett Beggs, Robert McIver, Ruben Cantu, Steve J Rodriguez |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Edgar Gonzalez, Felix Martinez, Francisco Hernandez, Francisco Rosa, Jorge Robert Rangel, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Mark Rosa, Matthew D'Ambrosio, Moises Rodriguez, Robert McIver, Roger Guerra, Ruben Cantu, William Brown |  |  | Eric Rodriguez | TX-SOUT | La Joya ISD | J00014847 | E-Rate 25 (2022-2023) Category 2 | Closed | 0% | 0% | 0 | -872.75 | 0 | 81999 | 0% | 0 | 73.4 | 946.15 | 77010 | 8895.92 |  | 81999 |  | 2083295.29 | 299827.53 | 208932.61 | 69.68%
07/03/23 |  | 07/08/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs |  | Amy Martinez-Nagy, Daniel Saenz, David Avila, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Ivan Uribe, Mario Sanchez, Michael Brett Beggs, Robert McIver, Ruben Cantu, Steve J Rodriguez |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Edgar Gonzalez, Felix Martinez, Francisco Hernandez, Francisco Rosa, Jorge Robert Rangel, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Mark Rosa, Matthew D'Ambrosio, Moises Rodriguez, Robert McIver, Roger Guerra, Ruben Cantu, William Brown |  |  | N/A | N/A | La Joya ISD | J00014847 | E-Rate 25 (2022-2023) Category 2 | Closed | 100% | 0% | 1176.06 | 1176.06 | 93868.09 | 0 | 100% | 93868.09 | 0 | 0 | 0 | 8895.92 |  | 0 |  | 2083295.29 | 299827.53 | 290931.61 | 97.03%
04/26/22 |  | 07/12/24 | Open | Jennifer Soliz | Emilio Carrillo |  | Christi D Hubbard, James Danner, Jennifer Soliz, Larry Noble, Lori Endsley |  |  | Aldo Cortes, An Le, Angel Alicea, Angel Alicea-Torres, James Danner, Jennifer Soliz, John Senkulics, Kristopher Dwight, Michael Torres, Trevor Youngman |  |  | Christi D Hubbard | TX-CEN | Schertz-Cibolo-Universal City ISD | J00012856 | ERATE 2020 - UPS Refresh | Closed | 100% | 135.5% | 311.41 | -74.09 | 18540.5 | 26652.5 | -23.79% | 18540.5 | 36.5 | 422 | 24462.5 | 843.378 |  | 26652.5 |  | 320814.1 | 27601.75 | 105.872 | 0.3836%
03/25/24 |  | 07/12/24 | Open | Joaquin Marroquin | Michael Brett Beggs |  | Cory Bradfield, Cory Bradfield, Joaquin Marroquin, Larry Noble, Lonnie Owens |  |  | An Le, Cory Bradfield, Daniel Quade, Joaquin Marroquin, Luis Ovalles, Michael Torres |  |  | Lonnie Owens | TX-CEN | Boerne ISD | J00017856 | Pure Storage FlashArray Installation | Closed | 100% | 50.68% | 166.25 | 93 | 21612.75 | 10216.25 | 55.94% | 21612.75 | 11 | 84.25 | 8881.25 | 0 |  | 10216.25 |  | 238441.2 | 33326.4 | 23110.15 | 69.34%
01/18/24 |  | 07/12/24 | Open | Marco Lish | George Edwin Jacob |  | George Edwin Jacob, Jeff Barker, Jonathan Pendrich, Luis Ovalles, Marco Lish |  |  | Luis Ovalles, Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Oncor Electric Delivery Company LLC | J00017315 | Nutanix Upgrade | Closed | 100% | 48.38% | 146.25 | 85.5 | 19411.25 | 9363.75 | 58.46% | 19411.25 | 10 | 70.75 | 8013.75 | 0 |  | 9363.75 |  | 0 | 28346.8 | 18983.05 | 66.97%
08/25/23 |  | 07/17/24 | Open | Abiodun David Babasola | Aman Khan, Jacob Parks, Jeffrey Holman |  | Abiodun David Babasola, Aman Khan, Carmen Isela Brandt, David Babasola, Romar Roca, Yong Kim |  |  | Abiodun David Babasola, Conner MacDonnell, Romar Roca |  |  | Carmen Brandt | CA-LAX | Lowell Joint School District | J00016238 | Palo Alto Implementation | Closed | 100% | 62.69% | 83.75 | 31.25 | 11873.75 | 7372.5 | 37.31% | 11873.75 | 0 | 52.5 | 7372.5 | 0 |  | 7372.5 |  | 238761.3 | 19556.76 | 12184.26 | 62.3%
06/05/23 |  | 07/19/24 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Bryan Mullen |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014223 | CAD Switch Replacement | Closed | 100% | 20.3% | 41.87 | 33.37 | 4439.45 | 1062.5 | 79.7% | 4439.45 | 0 | 8.5 | 1062.5 | 0 |  | 1062.5 |  | 33165.4 | 6992.4 | 5929.9 | 84.8%
12/13/23 |  | 07/19/24 | Open | Marco Lish | Jacob Parks, Jeffrey Holman |  | Jeff Barker, Marco Lish, Mark Forehand, Sophia Quinter |  |  | Marco Lish, Sophia Quinter |  |  | Mark Forehand | TX-DAL | Prosper ISD | J00016995 | ISE Upgrade | Closed | 0% | 0% | 0 | -57.5 | 0 | 8425 | 0% | 0 | 0 | 57.5 | 8425 | 0 |  | 8425 |  | 0 | 16721.2 | 8296.2 | 49.61%
12/13/23 |  | 07/19/24 | Open | Marco Lish | Jacob Parks, Jeffrey Holman |  | Jeff Barker, Marco Lish, Mark Forehand, Sophia Quinter |  |  | Marco Lish, Sophia Quinter |  |  | N/A | N/A | Prosper ISD | J00016995 | ISE Upgrade | Closed | 100% | 0% | 78 | 78 | 11375 | 0 | 100% | 11375 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 16721.2 | 16721.2 | 100%
04/15/24 |  | 07/24/24 | Open | LaQisha Marshall | Daniel Snyder |  | Daniel Snyder, Kurt Sell, LaQisha Marshall, Thomas McClanahan |  |  | Grayson McClanahan, Grayson Rigsby, LaQisha Marshall, Robert Jones |  |  | Thomas McClanahan | TX-CEN | Capital Factory | J00017997 | UPS refresh APC | Closed | 100% | 108% | 21.06 | -0.69 | 1537.25 | 1706.25 | -3.276% | 1537.25 | 1 | 22.75 | 1646.25 | 0 |  | 1706.25 |  | 12228.34 | 2400 | 693.75 | 28.91%
07/24/23 |  | 07/25/24 | Open | Jason Esry | Emilio Carrillo |  | David D Tijerina, Jason Esry, Larry Noble |  |  | Abdulrahman Farhan, James Danner, Jason Esry, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Almoola |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00015884 | SAISD Convo and Alamo Stadium Ap replacement | Closed | 100% | 89.57% | 56.1 | 5.85 | 5793.75 | 5152.5 | 10.43% | 5793.75 | 0 | 50.25 | 5002.5 | 0 |  | 5152.5 |  | 19585.05 | 7999 | 2846.5 | 35.59%
01/10/24 |  | 07/26/24 | Open | Christina Rice | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Christina Rice, Christina Rice, Mark Forehand, Michael Brett Beggs, Ron Loge, William Davenport |  |  | Christina Rice, Jarshawn Newsome, Ron Loge |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | J00016982 | UTSW: ARDC DMZ to ACI | Closed | 100% | 40.58% | 128.75 | 77.5 | 17123.75 | 8086.25 | 60.19% | 17123.75 | 1 | 52.25 | 7911.25 | 0 |  | 8086.25 |  | 0 | 25171.6 | 17085.35 | 67.88%
03/08/24 |  | 07/26/24 | Open | Richard Keith Arnst | Warren Wilson |  | Larry Noble, Monica Johnson, Richard Keith Arnst |  |  | Garrett Hart |  |  | Monica Johnson | TX-HOU | Harmony Public Schools | J00017797 | Verkada Vaping Security Solution - Houston North | Closed | 0% | 0% | 0 | -2 | 0 | 350 | 0% | 0 | 0 | 2 | 350 | 0 |  | 350 |  | 55194.4 | 0 | -350 | 0%
03/08/24 |  | 07/26/24 | Open | Richard Keith Arnst | Warren Wilson |  | Larry Noble, Monica Johnson, Richard Keith Arnst |  |  | Richard Keith Arnst |  |  | Monica Johnson | TX-HOU | Harmony Public Schools | J00017798 | Verkada Vaping Security Solution - Central TX | Closed | 0% | 0% | 0 | -19 | 0 | 2375 | 0% | 0 | 0 | 19 | 2375 | 0 |  | 2375 |  | 25324.65 | 25138.23 | 22763.23 | 90.55%
03/11/24 |  | 07/26/24 | Open | Richard Keith Arnst | Warren Wilson |  | Larry Noble, Monica Johnson, Richard Keith Arnst |  |  | Garrett Hart |  |  | Monica Johnson | TX-HOU | Harmony Public Schools | J00017801 | Verkada Vaping Security Solution - West Texas | Closed | 0% | 0% | 0 | -2 | 0 | 350 | 0% | 0 | 0 | 2 | 350 | 0 |  | 350 |  | 38961 | 38674.2 | 38324.2 | 99.1%
08/29/22 |  | 07/26/24 | Open | Tray Giddens | N/A |  | Dustin Huffman, Larry Noble, Tray Giddens |  |  | Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00013762 | Install Staff Directory App | Closed | 50% | 10.61% | 113.06 | 101.06 | 15137.5 | 1500 | 89.39% | 15137.5 | 0 | 12 | 1500 | 0 |  | 1500 |  | 0 | 10476.6 | 8976.6 | 85.68%
04/08/24 |  | 07/26/24 | Open | Tray Giddens | Warren Wilson |  | Garrett Hart, Haley Glasscock, Lindie Lorraine Lamar, Tray Giddens |  |  | Garrett Hart, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Houston Housing Authority | J00018014 | Card Readers for Fountain View | Closed | 100% | 136.5% | 35.89 | -13.11 | 4084.5 | 7750 | -36.53% | 4084.5 | 0 | 49 | 7750 | 0 |  | 7750 |  | 13853.72 | 10784.02 | 3034.02 | 28.13%
08/08/23 |  | 07/30/24 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Lauren J Kennewell, Samuel Newland |  |  | Abiodun David Babasola, Samuel Newland |  |  | Lauren J Kennewell | TX-DAL | North Texas Municipal Water District (NTMWD) | J00016015 | Singlewire Deployment for Paging | Closed | 100% | 82.05% | 48.75 | 8.75 | 6518.75 | 5450 | 17.95% | 6518.75 | 0 | 40 | 5450 | 0 |  | 5450 |  | 15300 | 10965.2 | 5515.2 | 50.3%
07/18/24 |  | 07/30/24 | Open | Tray Giddens | Chad Hart |  | Dustin Huffman, Larry Noble, Tray Giddens |  |  | David Dobbs, Justin Cornish |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018681 | NetStage Only - Qty 10 C9200CX-12P-2X2G-E | Closed | 100% | 0% | 0 | -2.5 | 29.02 | 300 | 0% | 29.02 | 2.5 | 5 | 150 | 0 |  | 300 |  | 7240 | 0 | -300 | 0%
04/22/24 |  | 07/31/24 | Open | Abiodun David Babasola | William Birdsong |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Hubbard, Joshua Parker, Michael McGee, Sean Cowhey |  |  | Abiodun David Babasola, Jacob Hill, Jhon Genao, Joshua Hubbard, Michael McGee |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00018091 | UPS Installation - JJ Pearce HS | Closed | 100% | 88.48% | 41.25 | 8.5 | 3051.26 | 2710 | 20.61% | 3051.26 | 3.75 | 36.5 | 2485 | 0 |  | 2710 |  | 40338.88 | 4140.4 | 1430.4 | 34.55%
07/05/23 |  | 08/02/24 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Lauren J Kennewell, Magdalena Rodriguez, Moises Rodriguez, Nazario Armenta Barraza, Shiraz Humayun |  |  | Bryan Mullen, Joel Fleming, Moises Rodriguez, Nazario Armenta Barraza, Timothy Mitchell |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014113 | Wireless Refresh - Anchor Controllers | Closed | 100% | 158.9% | 82.13 | -48.37 | 9371.25 | 17657.5 | -58.89% | 9371.25 | 0 | 130.5 | 17657.5 | 0 |  | 17657.5 |  | 87712.2 | 14300 | -3357.5 | -23.48%
09/11/23 |  | 08/02/24 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Abdulrahman Farhan, Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Bryan Mullen, Dhulfiqar Al Hashimi, Eric Firestone |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00016419 | FTD Upgrades with Azure Tunnels | Closed | 100% | 169.3% | 67.5 | -46.75 | 9787.5 | 16718.75 | -69.26% | 9787.5 | 0 | 114.25 | 16718.75 | 0 |  | 16718.75 |  | 0 | 15415.2 | -1303.55 | -8.456%
08/17/22 |  | 08/02/24 | Open | Brian Willery | Warren Wilson |  | Brian Willery, Garrett Hart, Larry Noble, Monica Johnson |  |  | Andy Pham, Brian Willery, Garrett Hart, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Matthew D'Ambrosio, Media Alsewaili |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Houston | J00013213 | Camera Install - Science Academy Northwest | Closed | 100% | 123.5% | 95.58 | -22.42 | 10621.5 | 15372.5 | -23.46% | 10621.5 | 0 | 118 | 15372.5 | 193.77 |  | 15372.5 |  | 45841.42 | 44928.44 | 29362.17 | 65.35%
03/01/21 |  | 08/02/24 | Open | Lauren Lanzini Coffey | Alan Dumdei, Mark J Chambliss |  | Donald Muskaj, Lauren Lanzini Coffey, Nazario Armenta Barraza, Neel Shah |  |  | Aaron Johns, Ahmed Jameel, Aleksei Lavrushenkov, Andy Pham, Craig St. Rose, David Dobbs, Donald Muskaj, Jaime Flores, Jason Espino, Jeffrey Charles Primeaux, Jose E. Duarte Jr, Justin Cornish, Justin Smallwood, Kevin Jones, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Lauren Lanzini Coffey, Luis Alvarez, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Moises Rodriguez, Nazario Armenta Barraza, Paul Serres, Remi Martinez-Montenegro, Rogelio Morgado-Perez, Sarah Beatrice Williamson, Victor Estrada |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00009747 | Wireless and Network Staging Services | Implementation/Deployment | 80% | 49.63% | 751.5 | 389.55 | 42367.5 | 35314.25 | 51.84% | 42367.5 | 11 | 372.95 | 34764.25 | 1435.52 |  | 35314.25 |  | 1966321.22 | 108228.6 | 71478.83 | 66.04%
05/27/24 |  | 08/02/24 | Open | Lauren Lanzini Coffey | David Watkins |  | David Watkins, Lauren Lanzini Coffey, Neel Shah |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00018424 | Woodlands Core Equipment | Not started | 0% | 0% | 143.75 | 143.75 | 12378.75 | 0 | 100% | 12378.75 | 0 | 0 | 0 | 0 |  | 0 |  | 1101626.4 | 22096 | 22096 | 100%
10/31/22 |  | 08/02/24 | Open | Richard Keith Arnst | N/A |  | Felipe D. Waterwall, Felipe Waterwall, Kevin Jones, Kevin Jones, Larry Noble, Remi Martinez-Montenegro, Richard Keith Arnst, Susan Richardson |  |  | Felipe Waterwall, James Adams, Jeff Ogbor, Justin Higgins, Kevin Jones, LaQisha Marshall, Luis Alvarez, Remi Martinez-Montenegro, Richard Keith Arnst, Robert Lavender |  |  | Susan Richardson | TX-HOU | Humble ISD | J00013955 | Innovation | Closed | 100% | 233.6% | 176.34 | -221.66 | 15089.76 | 39352.5 | -125.7% | 15089.76 | 14 | 412 | 38272.5 | 3332.75 |  | 39352.5 |  | 3121.47 | 11153.2 | -31532.05 | -282.7%
11/28/22 |  | 08/02/24 | Open | Richard Keith Arnst | N/A |  | Larry Noble, Richard Keith Arnst, Susan Richardson |  |  | Jeremiah Solomon, LaQisha Marshall, Remi Martinez-Montenegro, Richard Keith Arnst, Robert Lavender |  |  | Susan Richardson | TX-HOU | Humble ISD | J00014367 | A/V Idea Room | Closed | 100% | 82.94% | 176.34 | 43.34 | 16093.75 | 18678.75 | 24.58% | 16093.75 | 13.25 | 146.25 | 16477.5 | 248.08 |  | 18678.75 |  | 0 | 11153.2 | -7773.63 | -69.7%
03/27/23 |  | 08/02/24 | Open | Richard Keith Arnst | N/A |  | Larry Noble, Richard Keith Arnst, Susan Richardson |  |  | Aaron Johns, Andy Alvarenga, Andy Pham, Carson Broussard, Clinton Bennett Deason, Devon LeMoine, Felipe Waterwall, Jesus Gonzalez, Joel Hubbard, Jose R. Duarte, Justin Higgins, Justin Cornish, Justin Smallwood, Kevin Jones, Kord Mullins, LaQisha Marshall, Nathan Dao, Richard Keith Arnst, Robert Lavender, Sajjad Abo Dbs |  |  | Susan Richardson | TX-HOU | Humble ISD | J00014719 | Video Conferencing - Rooms 1005 & 1007 | Closed | 100% | 438.1% | 325.31 | -991.94 | 33341.07 | 119599.25 | -304.9% | 33341.07 | 108.05 | 1425.3 | 109666.25 | 6676.428 |  | 119599.25 |  | 250029.74 | 38906.78 | -87368.898 | -224.6%
03/20/23 |  | 08/02/24 | Open | Richard Keith Arnst | Bryan Brown |  | Felipe D. Waterwall, Felipe Waterwall, Monica Johnson, Richard Keith Arnst, Susan Richardson |  |  | Aaron Johns, Andy Alvarenga, Clinton Bennett Deason, David Dobbs, Felipe Waterwall, James Adams, Jeremiah Solomon, Jesus Gonzalez, Jose R. Duarte, Justin Higgins, Kendric Mamou, Kord Mullins, Luis Alvarez, Nathan Dao, Richard Keith Arnst |  |  | Monica Johnson | TX-HOU | Waller ISD | J00015033 | Promethean Boards – x110 Units Waller JHS | Closed | 100% | 68.41% | 903.75 | 337.75 | 71395.66 | 43587.5 | 37.37% | 71395.66 | 52.25 | 618.25 | 40662.5 | 3160.245 |  | 43587.5 |  | 450594.1 | 99411.05 | 52663.305 | 52.98%
08/25/23 |  | 08/05/24 | Open | Joaquin Marroquin | Steven Walker |  | Christopher Brown, Christopher Brown, Joaquin Marroquin, Xavier A Trevino |  |  | Christopher Brown, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Del Mar College | J00014476 | Work Order - Microsoft Endpoint Manager | Closed | 100% | 127.8% | 45 | -12.5 | 6025 | 7702.5 | -27.78% | 6025 | 0 | 57.5 | 7702.5 | 0 |  | 7702.5 |  | 0 | 7534.8 | -167.7 | -2.226%
03/07/24 |  | 08/05/24 | Open | LaQisha Marshall | Timothy Ramsey |  | Christi D Hubbard, LaQisha Marshall, Larry Noble, Romar Roca, Timothy Ramsey |  |  | LaQisha Marshall, Romar Roca |  |  | Christi D Hubbard | TX-CEN | Del Valle ISD | J00017561 | CES Pro-Services | Closed | 100% | 35.96% | 136.25 | 87.25 | 19756.25 | 6775 | 64.04% | 19756.25 | 0 | 49 | 6775 | 0 |  | 6775 |  | 142995.94 | 28626.8 | 21851.8 | 76.33%
05/12/23 |  | 08/09/24 | Open | Christina Rice | George Edwin Jacob |  | Beau C. Devillier, Christina Rice, Christina Rice, George Edwin Jacob, Kristy L Dice, Ron Loge |  |  | Christina Rice, Ron Loge |  |  | Kristy L Dice | TX-DAL | UT Southwestern Medical Center | J00015440 | UTSW: Integration of VMWare to ACI | Closed | 0% | 0% | 0 | -88.75 | 0 | 13418.75 | 0% | 0 | 0 | 88.75 | 13418.75 | 0 |  | 13418.75 |  | 0 | 33480.8 | 20062.05 | 59.92%
05/12/23 |  | 08/09/24 | Open | Christina Rice | George Edwin Jacob |  | Beau C. Devillier, Christina Rice, Christina Rice, George Edwin Jacob, Kristy L Dice, Ron Loge |  |  | Christina Rice, Ron Loge |  |  | N/A | N/A | UT Southwestern Medical Center | J00015440 | UTSW: Integration of VMWare to ACI | Closed | 100% | 0% | 181.25 | 181.25 | 24106.25 | 0 | 100% | 24106.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 33480.8 | 33480.8 | 100%
04/10/24 |  | 08/09/24 | Open | Jennifer Soliz | David Escamilla |  | Jennifer Soliz, Joseph Redford Scowden, Larry Noble, Luis Ovalles |  |  | Jennifer Soliz, Luis Ovalles |  |  | Joseph Scowden | TX-HOU | DDI Leasing Inc dba DDI Capital | J00017661 | Revision One - UCS | Closed | 0% | 0% | 0 | -141.5 | 0 | 18927.5 | 0% | 0 | 0 | 141.5 | 18927.5 | 0 |  | 18927.5 |  | 517363.31 | 37229.84 | 18302.34 | 49.16%
04/10/24 |  | 08/09/24 | Open | Jennifer Soliz | David Escamilla |  | Jennifer Soliz, Joseph Redford Scowden, Larry Noble, Luis Ovalles |  |  | Jennifer Soliz, Luis Ovalles |  |  | N/A | N/A | DDI Leasing Inc dba DDI Capital | J00017661 | Revision One - UCS | Closed | 100% | 0% | 206.25 | 206.25 | 27693.5 | 0 | 100% | 27693.5 | 0 | 0 | 0 | 0 |  | 0 |  | 517363.31 | 37229.84 | 37229.84 | 100%
11/27/23 |  | 08/09/24 | Open | Tray Giddens | Chad Hart |  | Ahmed Jameel, Andy Pham, Craig St. Rose, Craig St. Rose, Dustin Huffman, Jaime B Flores, Jaime Flores, James Adams, Justin Cornish , Larry Noble, Nelson Garcia, Sajjad Abo Dbs, Tray Giddens |  |  | Abdalsattar Albaghdadi, Ahmed Jameel, Andy Pham, Bryant Bush, Craig St. Rose, David Dobbs, Devinn Anthony Campbell, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Justin Cornish, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nelson Garcia, Nicolas Garakani, Sajjad Abo Dbs, Shannan Thomas, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00016927 | Elementary Network Refresh Green Consolidated | Closed | 100% | 96.28% | 934.9 | 107.15 | 77796.2 | 74935.3 | 11.46% | 77796.2 | 72.38 | 900.13 | 70300 | 1100.75 |  | 74935.3 |  | 1950763.16 | 164953.6 | 88917.55 | 53.9%
11/27/23 |  | 08/09/24 | Open | Tray Giddens | Chad Hart |  | Ahmed Jameel, Craig St. Rose, Craig St. Rose, Devon LeMoine, Dustin Huffman, Jaime B Flores, Jaime Flores, Justin Cornish, Larry Noble, Nelson Garcia, Tray Giddens |  |  | Abdalsattar Albaghdadi, Ahmed Jameel, Andy Pham, Baq Alsaedi, Bryant Bush, Craig St. Rose, David Dobbs, Devinn Anthony Campbell, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Justin Cornish, Justin Smallwood, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Nelson Garcia, Nicolas Garakani, Shannan Thomas, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00016928 | Elementary Network Refresh Gold Quadrant | Closed | 100% | 126.5% | 827.6 | -93 | 69807.28 | 80025 | -11.24% | 69807.28 | 126.4 | 1047 | 71726 | 2107.85 |  | 80025 |  | 1606996.74 | 154644 | 72511.15 | 46.89%
04/29/24 |  | 08/09/24 | Open | Tray Giddens | Chad Hart |  | Ahmed Jameel, Craig St. Rose, Craig St. Rose, Dustin Huffman, Kevin Curtis, Kevin L Curtis, Kolawole Ayeni, Kord Mullins, Larry Noble, Matthew D'Ambrosio, Nelson Garcia, Savitha Ramakrishnan, Shannan Thomas, Tray Giddens |  |  | Ahmed Jameel, Anthony Lange, Craig St. Rose, Daniel Hernandez, Devon LeMoine, Jose R. Duarte, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Nelson Garcia, Nicolas Garakani, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018246 | Switches in Pink Quadrant | Closed | 100% | 74.42% | 746.61 | 233.26 | 63462.39 | 48872.2 | 31.24% | 63462.39 | 42.27 | 555.62 | 45686 | 0 |  | 48872.2 |  | 1421030.9 | 134024.8 | 85152.6 | 63.53%
04/29/24 |  | 08/09/24 | Open | Tray Giddens | Chad Hart |  | Ahmed Jameel, Craig St. Rose, Craig St. Rose, Dustin Huffman, Jaime B Flores, Jaime Flores, Larry Noble, Nelson Garcia, Tray Giddens |  |  | Ahmed Jameel, Anthony Lange, Craig St. Rose, David Dobbs, Devon LeMoine, Hector Rivera, Jerald Garner, Jesus Gonzalez, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Nelson Garcia, Nicolas Garakani, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018247 | 11 Campuses in Blue Quadrant | Closed | 100% | 95.66% | 629.4 | 86.45 | 53425.01 | 49124.2 | 13.74% | 53425.01 | 59.12 | 602.07 | 44862 | 0 |  | 49124.2 |  | 1166156.9 | 113405.6 | 64281.4 | 56.68%
11/08/23 |  | 08/13/24 | Open | LaQisha Marshall | Mark J Chambliss |  | David Monasmith, David Monasmith, George McGann, LaQisha Marshall, Larry Noble |  |  | George McGann, LaQisha Marshall |  |  | David Monasmith | TX-HOU | Texas A&M University | J00016580 | Contact Center | Closed | 100% | 92.61% | 115 | 8.5 | 16005 | 14572.5 | 7.391% | 16005 | 0 | 106.5 | 14572.5 | 0 |  | 14572.5 |  | 8114.4 | 24995 | 10422.5 | 41.7%
10/09/23 |  | 08/14/24 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Graylon Hampton, Steven Walker, Timothy Rosser, William Birdsong, Wyley Johnson |  | Camille Elizabeth Taber, Christopher Butler, Graylon Hampton, Kreshnik Memaj, Shannon Marie Alvarado, Steven Walker |  |  | Hamzeh Tahat, Kevin Curtis, Kolawole Ayeni, Kreshnik Memaj, Matthew D'Ambrosio, Ryan Scott, Shannon Marie Alvarado |  |  | Camille Taber | FL | Polk County Sheriffs Office | J00016072 | Backend Network for VVS | Closed | 100% | 105.1% | 304.51 | -11.49 | 39026.55 | 35732.5 | -3.773% | 39026.55 | 4 | 320 | 35232.5 | 13627.5 |  | 35732.5 |  | 333965.89 | 0 | -49360 | 0%
05/27/24 |  | 08/15/24 | Open | Joaquin Marroquin | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, Joaquin Marroquin, Larry Noble |  |  | Adam Felix, Grayson Rigsby, Joaquin Marroquin, Julio Perez |  |  | Christi D Hubbard | TX-CEN | Dripping Springs ISD | J00018437 | Equipment Removal and Reinstallation | Closed | 100% | 30.19% | 96.05 | 69.05 | 7046.67 | 2390 | 71.89% | 7046.67 | 2 | 29 | 2270 | 0 |  | 2390 |  | 0 | 8489.6 | 6099.6 | 71.85%
06/21/24 |  | 08/15/24 | Open | Joaquin Marroquin | Edward Padron |  | David Avila, Joaquin Marroquin, Magdalena Rodriguez, Moises Rodriguez, Ruben Cantu, Steve J Rodriguez |  |  | Joaquin Marroquin, Moises Rodriguez, Ruben Cantu |  |  | Daniel Saenz | TX-SOUT | Lyford CISD | J00016795 | CRADLEPOINT REFRESH | Closed | 100% | 112.9% | 27.02 | 0.52 | 2921.2 | 3887.5 | 1.925% | 2921.2 | 4 | 30.5 | 3387.5 | 0 |  | 3887.5 |  | 2090.7 | 5691.81 | 1804.31 | 31.7%
07/10/23 |  | 08/16/24 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Dylan Pittsinger |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00015181 | Cisco Switch Refresh qty 11 Sites | Closed | 100% | 18.55% | 271.49 | 222.94 | 25546.05 | 5962.25 | 82.12% | 25546.05 | 1.8 | 50.35 | 5854.25 | 73.83 |  | 5962.25 |  | 354871.2 | 42151 | 36114.92 | 85.68%
05/27/24 |  | 08/16/24 | Open | Tray Giddens | Mark J Chambliss |  | Daniel Hernandez, Daniel R Hernandez, Dustin Huffman, Larry Noble, Tray Giddens |  |  | Hector Rivera, Justin Cornish, Justin Smallwood, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018333 | ES #59 Phone Deployment | Closed | 100% | 109.5% | 23.75 | 3.75 | 1803.49 | 1885 | 15.79% | 1803.49 | 6 | 26 | 1525 | 0 |  | 1885 |  | 17209.4 | 2860.4 | 975.4 | 34.1%
06/26/23 |  | 08/19/24 | Open | LaQisha Marshall | Christopher Puyear, Emilio Carrillo |  | Christi D Hubbard, Daniel Snyder, David Gonzalez, George McGann, LaQisha Marshall, Larry Noble, Lori Endsley, Michael Torres, Robert Kelly, Robert Kelly |  |  | Abdalsattar Albaghdadi, Adam Felix, An Le, Andy Alvarenga, Andy Pham, Charles Knox, Daniel Quade, David Dobbs, Devon LeMoine, George McGann, Grayson Rigsby, Jeffrey Charles Primeaux, John Senkulics, Julio Perez, Kevin Curtis, Kolawole Ayeni, Kyle Linder, LaQisha Marshall, Matthew D'Ambrosio, Michael Torres, Miguel Reed, Mohammed Al-Shaikhli, Oscar Gonzalez, Paul Serres, Richard Shea, Robert Kelly, Robert Brim, Robert Jones, Steven Shipmon, Wilangel Francis |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00014605 | x4 Site CAT2 Hardware Installations | Closed | 100% | 108% | 968.73 | 30.19 | 96609.65 | 94518.1 | 3.116% | 96609.65 | 108 | 1046.54 | 87598.1 | 2199.53 |  | 94518.1 |  | 1148068.17 | 142013.2 | 45295.57 | 31.9%
06/24/24 |  | 08/19/24 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, George McGann, LaQisha Marshall, Larry Noble |  |  | George McGann, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Pflugerville ISD | J00018580 | UC Upgrade | Closed | 100% | 84.55% | 110 | 17 | 15510 | 12915 | 15.45% | 15510 | 0 | 93 | 12915 | 0 |  | 12915 |  | 0 | 23342.4 | 10427.4 | 44.67%
07/17/23 |  | 08/19/24 | Open | Richard Keith Arnst | N/A |  | Garrett Curran, Richard Keith Arnst, Vernon Jackson, Yong Kim |  |  | Henry Pugsley, Richard Keith Arnst |  |  | Garrett Curran | CA-LAX | Westside Union School District | J00015770 | MPLS/SIP migration | Cancelled | 10% | 2.526% | 47.5 | 46.3 | 6507.5 | 160 | 97.47% | 6507.5 | 0 | 1.2 | 160 | 1277.7 |  | 160 |  | 0 | 0 | -1437.7 | 0%
03/29/24 |  | 08/20/24 | Open | Tray Giddens | Bryan Brown, Chad Hart, Mark J Chambliss |  | Christopher Kutalek, Jennifer Huie, Robert Lavender, Shiraz Humayun, Tray Giddens |  |  | Clinton Bennett Deason, Devon LeMoine, Joel Hubbard, Rene Trejo, Robert Lavender, Tray Giddens |  |  | Christopher Kutalek | TX-HOU | University of Texas - UTMB Galveston Medical Bran | J00015305 | WORK ORDER - ROOM KIT PLUS POC | Closed | 100% | 305.9% | 47.81 | -54.33 | 7522.79 | 15693.75 | -113.6% | 7522.79 | 44.11 | 146.25 | 11115.9 | 1079.526 |  | 15693.75 |  | 1165574.9 | 3980.4 | -12792.876 | -321.4%
06/10/24 |  | 08/21/24 | Open | LaQisha Marshall | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, Ernesto Gonzalez, Kurt Sell, LaQisha Marshall |  |  | Ernesto Gonzalez, Kevin Curtis, LaQisha Marshall, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Robert Jones, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018348 | Davis Elementary AP refresh | Closed | 100% | 78.95% | 79.48 | 16.73 | 7485.92 | 6495 | 21.05% | 7485.92 | 0 | 62.75 | 6495 | 0 |  | 6495 |  | 79601.8 | 0 | -6495 | 0%
07/26/24 |  | 08/21/24 | Open | Robert McIver | Emilio Carrillo |  | Larry Noble, Lonnie Owens, Robert McIver, Ruben Cantu |  |  | An Le, Angel Alicea, Angel Alicea-Torres, John Senkulics, Michael Torres, Mohammed Almoola, Robert McIver, Ruben Cantu |  |  | Lonnie Owens | TX-CEN | John Hagee Ministries | J00018588 | JHM - IDF Buildout Project | Closed | 100% | 108.3% | 111.26 | -9.24 | 10986.85 | 10740 | -8.305% | 10986.85 | 0 | 120.5 | 10740 | 0 |  | 10740 |  | 146647.19 | 17304.4 | 6564.4 | 37.93%
05/06/24 |  | 08/22/24 | Open | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Garrett Hart, Julio C Montoya, Khalid Abunaja, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, David Dobbs, Garrett Hart, Jose R. Duarte, Julio C Montoya, Luis Alvarez, Mohammed Al-Shaikhli, Nathan Dao |  |  | N/A | N/A | Houston ISD | J00018296 | CCTV-BT Washington Camera for Plaza | Implementation/Deployment | 95% | 1410% | 5 | -62 | 273.34 | 6670 | -1240% | 273.34 | 3.5 | 70.5 | 4865 | 0 |  | 6670 |  | 8290 | 1000 | -5670 | -567%
10/15/21 |  | 08/22/24 | Open | Robert McIver | David Pena, Edward Padron |  | Amy Martinez-Nagy, Christopher Prado, Eric Rodriguez, Erick Nunez , Felix Martinez, Francisco Medrano, Ivan Uribe, Mario Sanchez, Robert McIver, Ruben Cantu |  |  | Alexander Reyes, Andy Alvarenga, Antonio Rivera, Carlos Carrillo, Christopher Prado, Daniel Dominguez, Erick Nunez , Felix Martinez, Francisco Hernandez, Francisco Medrano, Francisco Rosa, Ivan Uribe, Jesus Angel Cantu, Jesus Cantu, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Juan Rodriguez, Juan Saenz, Kevin Curtis, Kevin Hi, Kolawole Ayeni, Manuel Rodriguez Guerra, Mario Alberto Aguilar, Mario Sanchez, Marisela Contreras, Mark Rosa, Matthew D'Ambrosio, Oscar Garcia, Robert McIver, Rog |  |  | Eric Rodriguez | TX-SOUT | McAllen ISD | J00011404 | 8072200052 - ERATE 24 CAT2 | Closed | 0% | 0% | 0 | -3758.64 | 0 | 252221.35 | 0% | 0 | 130.27 | 3888.91 | 245600.45 | 6662.01 |  | 252221.35 |  | 3744251.74 | 0 | -258883.36 | 0%
10/15/21 |  | 08/22/24 | Open | Robert McIver | David Pena, Edward Padron |  | Amy Martinez-Nagy, Christopher Prado, Eric Rodriguez, Erick Nunez , Felix Martinez, Francisco Medrano, Ivan Uribe, Mario Sanchez, Robert McIver, Ruben Cantu |  |  | Alexander Reyes, Andy Alvarenga, Antonio Rivera, Carlos Carrillo, Christopher Prado, Daniel Dominguez, Erick Nunez , Felix Martinez, Francisco Hernandez, Francisco Medrano, Francisco Rosa, Ivan Uribe, Jesus Angel Cantu, Jesus Cantu, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Juan Rodriguez, Juan Saenz, Kevin Curtis, Kevin Hi, Kolawole Ayeni, Manuel Rodriguez Guerra, Mario Alberto Aguilar, Mario Sanchez, Marisela Contreras, Mark Rosa, Matthew D'Ambrosio, Oscar Garcia, Robert McIver, Rog |  |  | N/A | N/A | McAllen ISD | J00011404 | 8072200052 - ERATE 24 CAT2 | Closed | 100% | 0% | 2442.52 | 2442.52 | 143726.9 | 0 | 100% | 143726.9 | 0 | 0 | 0 | 6662.01 |  | 0 |  | 3744251.74 | 0 | -6662.01 | 0%
05/20/24 |  | 08/26/24 | Open | Joaquin Marroquin | Timothy Ramsey |  | Daniel Saenz, Diana Berger, Ibrahim Altaweel, Jerome Tanyag Mara, Joaquin Marroquin, Rogelio Morgado-Perez, Timothy Ramsey, Tom Magboo |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, Joaquin Marroquin, Rogelio Morgado-Perez, Tom Magboo |  |  | Daniel Saenz | TX-SOUT | United ISD | J00018328 | OffSec Assessment | Closed | 100% | 100% | 266 | 0 | 39825 | 39825 | 0% | 39825 | 0 | 266 | 39825 | 0 |  | 39825 |  | 0 | 28204.8 | -11620.2 | -41.2%
02/20/23 |  | 08/28/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs, Timothy Ramsey, Wyley Johnson |  | David Avila, Diana Berger, Eric Rodriguez, Ivan Uribe, Robert McIver, Romar Roca, Ruben Cantu |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Conner MacDonnell, Felix Martinez, Francisco Hernandez, Francisco Rosa, Ivan Uribe, Jesus Angel Cantu, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Mark Rosa, Oscar Garcia, Robert McIver, Roger Guerra, Romar Roca, Ruben Cantu, William Brown |  |  | David Avila | TX-SOUT | Rio Grande City Grulla ISD | J00013577 | x15 Campus - Network Upgrades | Closed | 0% | 0% | 0 | -680.04 | 0 | 68816.3 | 0% | 0 | 161.87 | 841.91 | 57679.8 | 1430.08 |  | 68816.3 |  | 885850.85 | 28782.6 | -41463.78 | -144.1%
02/20/23 |  | 08/28/24 | Open | Robert McIver | Edward Padron, Michael Brett Beggs, Timothy Ramsey, Wyley Johnson |  | David Avila, Diana Berger, Eric Rodriguez, Ivan Uribe, Robert McIver, Romar Roca, Ruben Cantu |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Conner MacDonnell, Felix Martinez, Francisco Hernandez, Francisco Rosa, Ivan Uribe, Jesus Angel Cantu, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Mark Rosa, Oscar Garcia, Robert McIver, Roger Guerra, Romar Roca, Ruben Cantu, William Brown |  |  | N/A | N/A | Rio Grande City Grulla ISD | J00013577 | x15 Campus - Network Upgrades | Closed | 100% | 0% | 470.88 | 470.88 | 40630.5 | 0 | 100% | 40630.5 | 0 | 0 | 0 | 1430.08 |  | 0 |  | 885850.85 | 28782.6 | 27352.52 | 95.03%
06/26/24 |  | 08/29/24 | Open | Robert McIver | Edward Padron |  | Erick Nunez , Robert McIver, Steve J Rodriguez, Xavier A Trevino |  |  | Erick Nunez |  |  | Xavier A Trevino | TX-SOUT | South Texas College | J00018281 | Edge Network Upgrade (ASR) - Pecan Campus | Closed | 100% | 62.6% | 43.13 | 16.13 | 4708.75 | 3375 | 37.4% | 4708.75 | 0 | 27 | 3375 | 0 |  | 3375 |  | 87542.74 | 7768.4 | 4393.4 | 56.55%
07/26/24 |  | 08/30/24 | Open | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Khalid Abunaja, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Devon LeMoine, Garrett Hart, Hector Rivera, Jesus Gonzalez, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kord Mullins, Mohammed Al-Shaikhli, Robert Brim |  |  | N/A | N/A | Houston ISD | J00018710 | HISD SPED 1398 -Shadydale ES | Training/Knowledge Transfer/Documentation | 50% | 7500% | 1 | -67 | 130 | 6610 | -6700% | 130 | 7 | 75 | 5710 | 0 |  | 6610 |  | 35740.2 | 3400 | -3210 | -94.41%
01/17/24 |  | 08/30/24 | Open | Christina Rice | Joshua Adam Engle |  | Austen New LN: Howard Cockerham, Beau C. Devillier, Blake Garibaldi, Bradley Buchanan, Christina Rice, Christina Rice, Conner MacDonnell, Dante Torres, Devin Moreno, Dylan Pittsinger, Frank Jaimes, Jhon Genao, Joshua Hubbard, Joshua Osgood, Kirk O'Guinn, Kristy L Dice, Mohaymen Sodi, Noah Trump, Phillip Ma Lim, Sattar Mohseni, Sean Cowhey, Tabais Prater, Tavis Jackson |  |  | Austen Howard, Blake Garibaldi, Bradley Buchanan, Cason Spencer, Christina Rice, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jean Pierre Obenda, Jeffery Giles, Jhon Genao, Joan Brito, Joshua Hubbard, Joshua Osgood, Kirk O'Guinn, Michael McGee, Mohaymen Sodi, Noah Castleberry, Noah Trump, Phillip Ma Lim, Remijio Hernandez, Sean Cowhey, Tavis Jackson |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | J00015167 | UTSW: 2023 Refresh - C9300's | Closed | 100% | 90.65% | 634.05 | 103.8 | 54258.25 | 40530 | 16.37% | 54258.25 | 44.5 | 574.75 | 37610 | 165.292 |  | 40530 |  | 1892283.2 | 77600 | 36904.708 | 47.56%
05/01/24 |  | 08/30/24 | Open | Robert McIver | Edward Padron |  | Diana Berger, Jason Osuna, Mario Sanchez, Robert McIver, William Barrett Chancellor |  |  | Mario Sanchez, Robert McIver |  |  | Jason Osuna | TX-CEN | Cobre Consolidated School District | J00018101 | E-Rate FY24 Cat2 Meraki Wireless APs | Closed | 100% | 85.94% | 32 | 4.5 | 4520 | 3537.5 | 14.06% | 4520 | 0 | 27.5 | 3537.5 | 0 |  | 3537.5 |  | 20139.2 | 17717.25 | 14179.75 | 80.03%
03/29/24 |  | 09/02/24 | Open | Tray Giddens | Mark J Chambliss |  | Ashley F Freeman, Larry Noble, Ming Chiu, Tray Giddens |  |  | Henry Pugsley, Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00015606 | uccx scripting help | Closed | 100% | 27.67% | 30 | 21.7 | 4110 | 1227.5 | 72.33% | 4110 | 0 | 8.3 | 1227.5 | 0 |  | 1227.5 |  | 0 | 6602.4 | 5374.9 | 81.41%
03/25/24 |  | 09/06/24 | Open | Jason Esry | Emilio Carrillo |  | David D Tijerina, Ernesto Gonzalez, Jason Esry, Larry Noble |  |  | Ernesto Gonzalez, James Danner, Jason Esry, John Senkulics, Michael Torres |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00017836 | Cisco Ruggedized Switches | Closed | 100% | 123% | 44.3 | -9.2 | 4871.37 | 5220 | -20.77% | 4871.37 | 1 | 54.5 | 5095 | 0 |  | 5220 |  | 68719.56 | 6343.2 | 1123.2 | 17.71%
07/26/24 |  | 09/06/24 | Open | Richard Keith Arnst | Chad Hart |  | Christopher Kutalek, Kurt Sell, Richard Keith Arnst |  |  | Ben Crouch, Jerald Garner, Richard Keith Arnst |  |  | Christopher Kutalek | TX-HOU | Electra Link | J00018571 | Wireless Survey - 5th Floor at 5995 Rogerdale | Closed | 0% | 0% | 0 | -15.25 | 0 | 1398.75 | 0% | 0 | 0 | 15.25 | 1398.75 | 0 |  | 1398.75 |  | 0 | 4420.8 | 3022.05 | 68.36%
07/26/24 |  | 09/06/24 | Open | Richard Keith Arnst | Chad Hart |  | Christopher Kutalek, Kurt Sell, Richard Keith Arnst |  |  | Ben Crouch, Jerald Garner, Richard Keith Arnst |  |  | Susan Richardson | TX-HOU | Electra Link | J00018571 | Wireless Survey - 5th Floor at 5995 Rogerdale | Closed | 100% | 0% | 25 | 25 | 2805 | 0 | 100% | 2805 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 4420.8 | 4420.8 | 100%
09/06/24 |  | 09/06/24 | Open | Richard Keith Arnst | Steven Walker |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Richard Keith Arnst |  |  | Christopher Brown, Richard Keith Arnst, Ron Loge |  |  | Eric Rodriguez | TX-SOUT | Great Hearts Texas | J00015293 | MS O365 & AD Migration | Closed | 0% | 0% | 0 | -472 | 0 | 63455 | 0% | 0 | 0 | 472 | 63455 | 99.74 |  | 63455 |  | 14700 | 55249.2 | -8305.54 | -15.03%
09/06/24 |  | 09/06/24 | Open | Richard Keith Arnst | Steven Walker |  | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Richard Keith Arnst |  |  | Christopher Brown, Richard Keith Arnst, Ron Loge |  |  | N/A | N/A | Great Hearts Texas | J00015293 | MS O365 & AD Migration | Closed | 100% | 0% | 316.25 | 316.25 | 42061.25 | 0 | 100% | 42061.25 | 0 | 0 | 0 | 99.74 |  | 0 |  | 14700 | 55249.2 | 55149.46 | 99.82%
06/10/24 |  | 09/06/24 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Larry Noble, Patrick Joseph Palermo, Tray Giddens |  |  | Patrick Joseph Palermo, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018462 | Migrate CCX Scripts to new CCX Server | Closed | 100% | 117.4% | 53.25 | -9.25 | 7508.25 | 11290 | -17.37% | 7508.25 | 0 | 62.5 | 11290 | 0 |  | 11290 |  | 0 | 12388.4 | 1098.4 | 8.866%
09/10/24 |  | 09/10/24 | Open | Tray Giddens | David Escamilla, Mark J Chambliss |  | Christopher Ceykovsky, Jaime B Flores, Jaime Flores, John Stephen Kurkjian, Justin Cornish , Larry Noble, Susan Richardson, Tray Giddens |  |  | Bryant Bush, Hector Rivera, Jaime Flores, John Stephen Kurkjian, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Tray Giddens |  |  | Susan Richardson | TX-HOU | University of Houston Clear Lake | J00016300 | VMware and VoIP upgrades | Closed | 100% | 122.9% | 156.25 | -24.25 | 21246.25 | 24800 | -15.52% | 21246.25 | 11.5 | 192 | 24110 | 0 |  | 24800 |  | 67677.74 | 29881.52 | 5081.52 | 17.01%
02/05/24 |  | 09/11/24 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker |  |  | Abiodun David Babasola |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00017435 | UPS Install - Forest Meadow Junior High | Closed | 100% | 11% | 27.28 | 24.28 | 1868.2 | 375 | 89% | 1868.2 | 0 | 3 | 375 | 0 |  | 375 |  | 0 | 0 | -375 | 0%
07/29/24 |  | 09/13/24 | Open | Tray Giddens | Albert H Nguyen |  | Kurt Sell, Susan Richardson, Tray Giddens |  |  | Matthew Veach, Nathan Dao, Tray Giddens |  |  | Susan Richardson | TX-HOU | Electra Link | J00018760 | Post-Installation Validation Survey for 19th Floor | Closed | 100% | 79.98% | 20.63 | 4.13 | 2320.25 | 1965 | 20.02% | 2320.25 | 0 | 16.5 | 1965 | 0 |  | 1965 |  | 0 | 3200 | 1235 | 38.59%
07/29/24 |  | 09/13/24 | Open | Tray Giddens | N/A |  | Kurt Sell, Susan Richardson, Tray Giddens |  |  | Matthew Veach, Nathan Dao, Tray Giddens |  |  | Susan Richardson | TX-HOU | Electra Link | J00018761 | 1400 Post Oak - Wireless Survey & Predictive | Closed | 100% | 72.65% | 23.4 | 6.4 | 2602.5 | 2060 | 27.35% | 2602.5 | 0 | 17 | 2060 | 0 |  | 2060 |  | 0 | 0 | -2060 | 0%
04/03/24 |  | 09/23/24 | Open | Shannon Marie Alvarado | David Watkins |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Mullen, David Watkins, Jeffery Alan Jorzig, Jeffery Jorzig, Nathan Dao, Quan Tran, Shannon Marie Alvarado |  |  | Austen Howard, Bryan Mullen, Jay Daniel De Leon, Jeffery Alan Jorzig, Jerald Garner, Nathan Dao, Nazario Armenta Barraza, Shannon Marie Alvarado, Taylor Poole |  |  | Arcangelo Fanelli | TX-DAL | Baptist Hospitals of Southeast Texas | J00017964 | Pre-Installation Walkthrough & Network Discovery | Closed | 100% | 48.48% | 521.88 | 288.88 | 52641.38 | 24077.5 | 55.35% | 52641.38 | 20 | 253 | 22877.5 | 0 |  | 24077.5 |  | 0 | 63197.6 | 39120.1 | 61.9%
05/21/24 |  | 09/24/24 | Open | LaQisha Marshall | Christopher Puyear, Daniel Snyder |  | Christi D Hubbard, Christopher Puyear, Daniel Snyder, Ernesto Gonzalez, James Danner, John Stephen Kurkjian, Kurt Sell, LaQisha Marshall, Lori Endsley, Michael Torres |  |  | Adam Felix, Alexander Chambless, Angel Alicea, Ernesto Gonzalez, Grayson Rigsby, James Danner, John Senkulics, John Stephen Kurkjian, Julio Perez, LaQisha Marshall, Michael Torres, Mohammed Almoola, Oscar Gonzalez, Robert Jones |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018374 | Installation - 7 sites | Closed | 100% | 54.44% | 863.78 | 473.53 | 75526.62 | 41136.25 | 54.82% | 75526.62 | 80 | 470.25 | 35036.25 | 0 |  | 41136.25 |  | 0 | 102290.4 | 61154.15 | 59.78%
07/01/24 |  | 09/25/24 | Open | Karyn Hubbard | David Watkins |  | Alexander Gutman, Beau C. Devillier, Karyn Hubbard |  |  | Justin Thompson, Patrick Shea Thompson, Thai Truong |  |  | Alex Gutman | TX-DAL | Dallas College | J00018624 | Brookhaven Campus – W 2nd Floor | Closed | 100% | 220% | 2.5 | -3 | 377.08 | 477.5 | -120% | 377.08 | 0 | 5.5 | 477.5 | 0 |  | 477.5 |  | 52803.33 | 625 | 147.5 | 23.6%
06/13/22 |  | 09/26/24 | Open | Robert McIver | Edward Padron |  | Antonio Rivera, Christopher Prado, Diana Berger, Edward Padron, Felix Martinez, Ivan Uribe, Mario Sanchez, Michelle Bailey, Robert McIver, Ruben Cantu, Steve J Rodriguez, Xavier A Trevino |  |  | Alexis Cantu, Antonio Rivera, Carlos Carrillo, Christopher Prado, Conner MacDonnell, David Rodriguez, Felix Martinez, Francisco Hernandez, Francisco Medrano, Francisco Rosa, Ivan Uribe, Jesus Angel Cantu, Jesus Cantu, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Juan Rodriguez, Manuel Rodriguez Guerra, Mario Alberto Aguilar, Mario Sanchez, Mark Rosa, Rene Trejo, Richard Colby, Robert McIver, Roger Guerra, Ruben Cantu, William Brown |  |  | Xavier A Trevino | TX-SOUT | Pharr-San Juan-Alamo ISD | J00012242 | ERATE24 - District Wireless Refresh | Closed | 100% | 322.2% | 1870.83 | -3693.72 | 121940.25 | 429425.6 | -197.4% | 121940.25 | 462.54 | 6027.09 | 401184.3 | 18834.04 |  | 429425.6 |  | 4580664.9 | 511762.53 | 63502.89 | 12.41%
06/26/23 |  | 09/27/24 | Open | Jennifer Soliz | David Pena, Joshua Adam Engle |  | Jennifer Soliz, Larry Noble, Lonnie Owens, Raul Velazquez |  |  | Carlo Enriquez, Dionisio Oscar Medina-Marcelino, Eric Firestone, Jennifer Soliz, Mohammad Jilani, Raul Velazquez, Ron Loge, William Chris Roome |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00014718 | Nexus 9336 switches for OT | Closed | 100% | 124.9% | 195.8 | -39.7 | 25863.4 | 34088.75 | -20.28% | 25863.4 | 9 | 244.5 | 32663.75 | 435.96 |  | 34088.75 |  | 448675.16 | 44161.6 | 9636.89 | 21.82%
06/24/24 |  | 09/27/24 | Open | Marco Lish | Christopher Puyear |  | Beau C. Devillier, Kristy L Dice, Marco Lish |  |  | Hamzeh Tahat, Marco Lish |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00018533 | CUCM Prefix Change | Closed | 100% | 122.7% | 22 | -5 | 3110 | 2725 | -22.73% | 3110 | 0 | 27 | 2725 | 1035 |  | 2725 |  | 0 | 4145.2 | 385.2 | 9.293%
09/27/24 |  | 09/27/24 | Open | Michelle Duenes | N/A |  | N/A |  |  | Dedric Bowens |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018873 | 0000484530 | N/A | 0% | 25% | 6 | 4.5 | 255.62 | 45 | 75% | 255.62 | 0 | 1.5 | 45 | 0 |  | 45 |  | 0 | 0 | -45 | 0%
02/19/24 |  | 09/27/24 | Open | Richard Keith Arnst | Warren Wilson |  | Garrett Hart, Larry Noble, Monica Johnson, Richard Keith Arnst |  |  | Garrett Hart, Richard Keith Arnst |  |  | Monica Johnson | TX-HOU | Harmony Public Schools Sugarland | J00017581 | Vape Detector Installation for MS & HS | Closed | 100% | 104.3% | 265.5 | -11.5 | 27437.5 | 35075 | -4.331% | 27437.5 | 0 | 277 | 35075 | 0 |  | 35075 |  | 70129.38 | 69613.56 | 34538.56 | 49.61%
07/25/24 |  | 09/27/24 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Beau C. Devillier, Shannon Marie Alvarado, Taylor Leger |  |  | John Stephen Kurkjian, Shannon Marie Alvarado |  |  | Taylor Leger | TX-DAL | Cleburne ISD | J00018715 | Unity Connection Upgrade | Closed | 100% | 100% | 27.5 | 0 | 3877.5 | 3767.5 | 0% | 3877.5 | 0 | 27.5 | 3767.5 | 0 |  | 3767.5 |  | 0 | 5292.4 | 1524.9 | 28.81%
06/28/24 |  | 09/27/24 | Open | Shannon Marie Alvarado | Jacob Parks, Jeffrey Holman |  | Beau C. Devillier, Jacob Parks, Jeffrey Holman, Mark Forehand, Shannon Marie Alvarado |  |  | Shannon Marie Alvarado |  |  | Mark Forehand | TX-DAL | Grapevine-Colleyville ISD | J00018625 | F5 Physical to Virtual Migration | Closed | 100% | 15.99% | 159.48 | 133.98 | 23257.5 | 3187.5 | 84.01% | 23257.5 | 0 | 25.5 | 3187.5 | 0 |  | 3187.5 |  | 133144.04 | 38390 | 35202.5 | 91.7%
06/10/24 |  | 09/27/24 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Larry Noble, Patrick Joseph Palermo, Tray Giddens |  |  | Patrick Joseph Palermo, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018481 | UC Upgrade to 15 | Closed | 100% | 103.2% | 101.25 | -3.25 | 14456.25 | 19140 | -3.21% | 14456.25 | 0 | 104.5 | 19140 | 0 |  | 19140 |  | 0 | 16169.2 | -2970.8 | -18.37%
06/26/24 |  | 09/30/24 | Open | Marco Lish | Mark J Chambliss |  | Kristian Martell, Larry Noble, Marco Lish, Mark J Chambliss, Neel Shah, Taylar Hansen, Thomas Francis LoMonaco |  |  | Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | City of Houston Public Works | J00018604 | Customer Account Services IVR Options Update | Not started | 0% | 10% | 85 | 76.5 | 15045 | 1615 | 90% | 15045 | 0 | 8.5 | 1615 | 0 |  | 1615 |  | 0 | 30229.88 | 28614.88 | 94.66%
10/20/23 |  | 09/30/24 | Open | Robert McIver | Amanda Barney, Emilio Carrillo, Paul Garza, Wyley Johnson |  | Larry Noble, Lonnie Owens, Robert McIver, Taylor Leger |  |  | Aldo Cortes, An Le, Angel Alicea, Angel Alicea-Torres, Daniel Quade, Delton Childs, Donald Muskaj, Ernesto Gonzalez, Isaiah Rosales, James Danner, John Senkulics, Juan Carlos Flores, Kevin Curtis, Kolawole Ayeni, Kristopher Dwight, Matthew D'Ambrosio, Michael Torres, Mohammed Almoola, Robert Kelly, Robert McIver, Sarah Beatrice Williamson, Trevor Youngman |  |  | Lonnie Owens | TX-CEN | John Hagee Ministries | J00011274 | 21-ER-8284-EA - Route Switch & Wireless | Closed | 100% | 115.8% | 834.69 | -99.56 | 74050.7 | 96496.25 | -11.93% | 74050.7 | 32 | 966.25 | 92561.25 | 667.49 |  | 96496.25 |  | 1312028.4 | 73312 | -23851.74 | -32.53%
07/17/24 |  | 10/01/24 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, Jaclyn Pias, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, Tray Giddens |  |  | Jaclyn Pias | TX-HOU | Houston Federal Credit Union | J00018673 | 2024 VDI Project Extension SSO Adjustment | Closed | 100% | 109.6% | 33.75 | 13.75 | 4688.75 | 4935 | 40.74% | 4688.75 | 17 | 37 | 2640 | 0 |  | 4935 |  | 0 | 6288.96 | 1353.96 | 21.53%
08/25/23 |  | 10/04/24 | Open | Brian Willery | Jacob Parks, Jeffrey Holman, William Birdsong |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Bryan Mullen |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014221 | 3rd Internet Connection for FirstNet Solution | Closed | 100% | 35.4% | 110.87 | 71.62 | 13853.8 | 4906.25 | 64.6% | 13853.8 | 0 | 39.25 | 4906.25 | 0 |  | 4906.25 |  | 29771.35 | 19951.2 | 15044.95 | 75.41%
03/11/24 |  | 10/04/24 | Open | Marco Lish | Bryan Geoghan |  | Austen New LN: Howard Cockerham, Bryan Geoghan, Gearld Stanley McNiel, Jeff Barker, Jonathan Pendrich, Marco Lish, Samuel Newland, Stan McNiel |  |  | Austen Howard, Marco Lish, Samuel Newland |  |  | Jonathan Pendrich | TX-DAL | Oncor Electric Delivery Company LLC | J00017763 | UCS Hardware Upgrade | Closed | 100% | 82.18% | 43.5 | 12.75 | 5392.5 | 4228.75 | 29.31% | 5392.5 | 5 | 35.75 | 3928.75 | 0 |  | 4228.75 |  | 0 | 8811.4 | 4582.65 | 52.01%
07/01/24 |  | 10/04/24 | Open | Robert McIver | Khalid Abunaja |  | Daniel Saenz, Diana Berger, Khalid Abunaja, Mario Sanchez, Robert McIver |  |  | Carlos Carrillo, Daniel Dominguez, Felix Martinez, Francisco Hernandez, Joaquin Marroquin, Jorge Robert Rangel, Mario Sanchez, Robert McIver, Roger Guerra, Trevor Galloso |  |  | Daniel Saenz | TX-SOUT | City of Edinburg | J00018629 | New Construction Network Hardware ACE Building | Closed | 100% | 86.44% | 129.28 | 23.53 | 12565.49 | 10307.5 | 18.2% | 12565.49 | 6 | 111.75 | 9947.5 | 0 |  | 10307.5 |  | 74018.71 | 18080.27 | 7772.77 | 42.99%
08/28/23 |  | 10/07/24 | Open | Robert McIver | Edward Padron |  | Edward Padron, Eric Rodriguez, Robert McIver, Steve J Rodriguez |  |  | Robert McIver |  |  | Eric Rodriguez | TX-SOUT | City Of Rio Grande | J00016340 | Network Cabling Copper and Fiber for Building | Closed | 0% | 0% | 0 | -14 | 0 | 1750 | 0% | 0 | 0 | 14 | 1750 | 0 |  | 1750 |  | 0 | 37478.56 | 35728.56 | 95.33%
08/28/23 |  | 10/07/24 | Open | Robert McIver | Edward Padron |  | Edward Padron, Eric Rodriguez, Robert McIver, Steve J Rodriguez |  |  | Robert McIver |  |  | N/A | N/A | City Of Rio Grande | J00016340 | Network Cabling Copper and Fiber for Building | Closed | 100% | 0% | 11.5 | 11.5 | 1525.18 | 0 | 100% | 1525.18 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 37478.56 | 37478.56 | 100%
05/13/24 |  | 10/07/24 | Open | Robert McIver | Edward Padron, Rogelio Dominguez |  | Christopher Prado, Erick Nunez , Robert McIver, Rogelio Dominguez, Xavier A Trevino |  |  | An Le, Erick Nunez , James Danner, John Senkulics, Kebret Eshetu, Quentin Sowels, Robert McIver, William Chris Roome |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018231 | New Construction Mesquite Hills – El Paso | Closed | 100% | 171.3% | 56.34 | -28.16 | 8927.01 | 7630 | -49.98% | 8927.01 | 12 | 96.5 | 6910 | 0 |  | 7630 |  | 62473.93 | 7186.4 | -443.6 | -6.173%
08/14/24 |  | 10/09/24 | Open | Robert McIver | Edward Padron |  | Daniel Saenz, Diana Berger, Robert McIver |  |  | Mario Sanchez |  |  | Daniel Saenz | TX-SOUT | Webb CISD | J00018833 | 2024 Additional Cisco Switches and APs | Closed | 100% | 27.92% | 35.82 | 25.82 | 3735.25 | 1300 | 72.08% | 3735.25 | 0 | 10 | 520 | 0 |  | 1300 |  | 23056.44 | 5979.2 | 4679.2 | 78.26%
01/08/24 |  | 10/11/24 | Open | Jennifer Soliz | Emilio Carrillo, George Edwin Jacob, Timothy Ramsey, Wyley Johnson |  | Emilio Carrillo, George Edwin Jacob, Hannah Paul, Jennifer Soliz, Larry Noble, Mohammed Almoola, Raul Velazquez, Timothy Ramsey, Tony Dean Skipworth, Wyley Johnson |  |  | An Le, Angel Alicea, Angel Alicea-Torres, Anthony Lange, Daniel Quade, Hector Rivera, James Danner, Jennifer Soliz, John Senkulics, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Michael Torres, Mohammed Almoola, Paul Serres, Raul Velazquez, Ron Loge, Tony Dean Skipworth |  |  | Hannah Edmunds | TX-CEN | Comal ISD | J00016474 | DC Nexus Equipment | Closed | 100% | 178.1% | 347.78 | -208.47 | 40978.53 | 71836.25 | -59.94% | 40978.53 | 63 | 619.25 | 67081.25 | 0 |  | 71836.25 |  | 469327.71 | 56983.6 | -14852.65 | -26.06%
09/03/24 |  | 10/11/24 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Larry Noble, Patrick Joseph Palermo, Tray Giddens |  |  | Patrick Joseph Palermo |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018906 | Speed Dial Configuration for Emergency Services | Closed | 100% | 100% | 10 | 0 | 1410 | 1900 | 0% | 1410 | 0 | 10 | 1900 | 0 |  | 1900 |  | 0 | 1839.6 | -60.4 | -3.283%
08/28/23 |  | 10/17/24 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Daniel Saenz, Edgardo Lopez, Edward Padron, Eric Rodriguez, Robert McIver, Ruben Cantu, Steve J Rodriguez |  |  | Carlos Carrillo, Francisco Hernandez, Oscar Garcia, Robert McIver, Ruben Cantu |  |  | Eric Rodriguez | TX-SOUT | City Of Rio Grande | J00016309 | Wireless and Switch Implementation | Closed | 0% | 0% | 0 | -54 | 0 | 6690 | 0% | 0 | 5.5 | 59.5 | 6262.5 | 68.45 |  | 6690 |  | 45295.72 | 6694.8 | -63.65 | -0.9507%
09/11/23 |  | 10/17/24 | Open | Robert McIver | Edward Padron |  | Edward Padron, Eric Rodriguez, Robert McIver, Romar Roca, Timothy Ramsey |  |  | Robert McIver, Romar Roca |  |  | Eric Rodriguez | TX-SOUT | City Of Rio Grande | J00016351 | Fortinet Firewall | Closed | 0% | 0% | 0 | -36 | 0 | 5125 | 0% | 0 | 0 | 36 | 5125 | 63.68 |  | 5125 |  | 3270.43 | 6747.6 | 1558.92 | 23.1%
08/28/23 |  | 10/17/24 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Daniel Saenz, Edgardo Lopez, Edward Padron, Eric Rodriguez, Robert McIver, Ruben Cantu, Steve J Rodriguez |  |  | Carlos Carrillo, Francisco Hernandez, Oscar Garcia, Robert McIver, Ruben Cantu |  |  | N/A | N/A | City Of Rio Grande | J00016309 | Wireless and Switch Implementation | Closed | 100% | 0% | 47.06 | 47.06 | 5357.9 | 0 | 100% | 5357.9 | 0 | 0 | 0 | 68.45 |  | 0 |  | 45295.72 | 6694.8 | 6626.35 | 98.98%
09/11/23 |  | 10/17/24 | Open | Robert McIver | Edward Padron |  | Edward Padron, Eric Rodriguez, Robert McIver, Romar Roca, Timothy Ramsey |  |  | Robert McIver, Romar Roca |  |  | N/A | N/A | City Of Rio Grande | J00016351 | Fortinet Firewall | Closed | 100% | 0% | 35.65 | 35.65 | 5141.25 | 0 | 100% | 5141.25 | 0 | 0 | 0 | 63.68 |  | 0 |  | 3270.43 | 6747.6 | 6683.92 | 99.06%
11/10/22 |  | 10/18/24 | Open | Brian Willery | Jacob Parks |  | Brian Willery, Jacob Sennett, James Elmore, James Elmore, Lauren J Kennewell, Shiraz Humayun |  |  | Abdulrahman Farhan, Brian Willery, Jacob Sennett |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00011434 | 02104820 - FTD for SCADA | Closed | 100% | 98.98% | 61.88 | 0.63 | 7748.6 | 8593.75 | 1.018% | 7748.6 | 0 | 61.25 | 8593.75 | 0 |  | 8593.75 |  | 17791.8 | 8559.44 | -34.31 | -0.4008%
12/02/22 |  | 10/18/24 | Open | Brian Willery | Christopher Puyear, Joshua Adam Engle |  | Brian Willery, Jeffery Giles, Justin Thompson, Kirk O'Guinn, Lauren J Kennewell, Phillip Ma Lim, Shiraz Humayun |  |  | Adam Ko, Brian Willery, Dylan Pittsinger, Jeffery Giles, Justin Thompson, Kirk O'Guinn, Kord Mullins, Phillip Ma Lim, Tavis Jackson |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00012382 | Distribution Switches - Public Works | Closed | 100% | 89.64% | 109.32 | 16.82 | 8635.5 | 9520 | 15.39% | 8635.5 | 5.5 | 98 | 8962.5 | 21.44 |  | 9520 |  | 422957.2 | 64177.4 | 54635.96 | 85.13%
07/25/23 |  | 10/18/24 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Abdulrahman Farhan, Beau C. Devillier, Brian Willery, Jeffrey Holman, Lauren J Kennewell, Romar Roca |  |  | Brian Willery, Romar Roca, Ron Loge, Sophia Quinter |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00015961 | Cisco Security EA, Edge Firewall Updates | Closed | 100% | 97.12% | 130 | 3.75 | 18850 | 17931.25 | 2.885% | 18850 | 0 | 126.25 | 17931.25 | 0 |  | 17931.25 |  | 0 | 29688.4 | 11757.15 | 39.6%
05/06/24 |  | 10/18/24 | Open | Jason Esry | Jacob Parks, Jeffrey Holman |  | Jacob Parks, Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Giles, Jeffery Jorzig, Jeffrey Holman, Jhon Genao, Joshua Hubbard, William Davenport |  |  | Jason Esry, Jeffery Alan Jorzig, Jeffery Giles, Kebret Eshetu, Quentin Sowels |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00018272 | Data Center Upgrade Palo Alto Firewalls | Closed | 100% | 0% | 137.5 | 137.5 | 19127.5 | 0 | 100% | 19127.5 | 0 | 0 | 0 | 0 |  | 0 |  | 590791.9 | 30140.24 | 30140.24 | 100%
05/06/24 |  | 10/18/24 | Open | Jason Esry | Jacob Parks, Jeffrey Holman |  | Jacob Parks, Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Giles, Jeffery Jorzig, Jeffrey Holman, Jhon Genao, Joshua Hubbard, William Davenport |  |  | Jason Esry, Jeffery Alan Jorzig, Jeffery Giles, Kebret Eshetu, Quentin Sowels |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00018272 | Data Center Upgrade Palo Alto Firewalls | Closed | 0% | 0% | 0 | -68.5 | 0 | 8225 | 0% | 0 | 2.5 | 71 | 8075 | 0 |  | 8225 |  | 590791.9 | 30140.24 | 21915.24 | 72.71%
07/15/24 |  | 10/18/24 | Open | Joaquin Marroquin | N/A |  | David D Tijerina, David Escamilla, Joaquin Marroquin, Larry Noble |  |  | N/A |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00018665 | CANCELLED | Cancelled | 0% | 0% | 77.63 | 77.63 | 10393.75 | 0 | 100% | 10393.75 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
10/18/24 |  | 10/18/24 | Open | Michelle Duenes | N/A |  | Mark J Chambliss |  |  | N/A |  |  | Neel Shah | TX-HOU | Lone Star College System | J00018985 | LSC01-0000068360 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
02/14/24 |  | 10/18/24 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Anthony Towsley, Christopher Butler, Ismael Velazquez, Shannon Marie Alvarado |  |  | Anthony Towsley, Shannon Marie Alvarado |  |  | Ismael Velazquez | FL | City of Weston | J00017538 | Singlewire InformaCast Deployment | Closed | 100% | 116% | 37.5 | -6 | 5137.5 | 5902.5 | -16% | 5137.5 | 0 | 43.5 | 5902.5 | 0 |  | 5902.5 |  | 11332.28 | 6107.04 | 204.54 | 3.349%
08/13/24 |  | 10/18/24 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Jason Osuna, Jesus Escobedo, Larry Noble, Shannon Marie Alvarado |  |  | Jesus Escobedo, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00018826 | Wireless Survey Minnetonka Office | Closed | 100% | 94.4% | 31.25 | 5.75 | 5465.06 | 3210 | 18.4% | 5465.06 | 4 | 29.5 | 2970 | 0 |  | 3210 |  | 0 | 6353.6 | 3143.6 | 49.48%
08/13/24 |  | 10/18/24 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Jason Osuna, Jesus Escobedo, Larry Noble, Shannon Marie Alvarado |  |  | Jesus Escobedo, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00018827 | Wireless Survey Kennesaw 2nd and 3rd Floor | Closed | 100% | 89.57% | 57.5 | 15 | 8917.12 | 5135 | 26.09% | 8917.12 | 9 | 51.5 | 4595 | 0 |  | 5135 |  | 0 | 10772.8 | 5637.8 | 52.33%
02/22/24 |  | 10/21/24 | Open | Abiodun David Babasola | Edward Padron, Timothy Ramsey |  | Abiodun David Babasola, Daniel Saenz, David Babasola, Diana Berger, Edward Padron, Eric Firestone, Eric Rodriguez, Jacob Sennett, Ruben Cantu, Timothy Ramsey |  |  | Abiodun David Babasola, Carlos Carrillo, Daniel Dominguez, Eric Firestone, Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Oscar Garcia, Roger Guerra, Ruben Cantu, Trevor Galloso |  |  | Eric Rodriguez | TX-SOUT | Harlingen CISD | J00017312 | Category 2 E-Rate Funding Year 2023 | Closed | 0% | 0% | 0 | -548.08 | 0 | 53444.8 | 0% | 0 | 99.5 | 647.58 | 47279.8 | 0 |  | 53444.8 |  | 639041.65 | 87986.67 | 34541.87 | 39.26%
02/22/24 |  | 10/21/24 | Open | Abiodun David Babasola | Edward Padron, Timothy Ramsey |  | Abiodun David Babasola, Daniel Saenz, David Babasola, Diana Berger, Edward Padron, Eric Firestone, Eric Rodriguez, Jacob Sennett, Ruben Cantu, Timothy Ramsey |  |  | Abiodun David Babasola, Carlos Carrillo, Daniel Dominguez, Eric Firestone, Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Oscar Garcia, Roger Guerra, Ruben Cantu, Trevor Galloso |  |  | N/A | N/A | Harlingen CISD | J00017312 | Category 2 E-Rate Funding Year 2023 | Closed | 100% | 0% | 564.65 | 564.65 | 53377.31 | 0 | 100% | 53377.31 | 0 | 0 | 0 | 0 |  | 0 |  | 639041.65 | 87986.67 | 87986.67 | 100%
08/02/24 |  | 10/24/24 | Open | Ryan Scott | William Birdsong |  | Beau C. Devillier, Jesus Escobedo, Jonathan Weir, Jonathan Weir, Rusty Bryan, Ryan Scott |  |  | Jesus Escobedo, Jonathan Weir, Ryan Scott |  |  | Rusty Bryan | TX-DAL | Shallowater ISD | J00018722 | APs & Switches E-Rate 2024-2025 Cat 2 | Closed | 100% | 85.39% | 120.91 | 17.66 | 14806.3 | 13166.25 | 14.61% | 14806.3 | 0 | 103.25 | 13166.25 | 0 |  | 13166.25 |  | 120098.4 | 19544 | 6377.75 | 32.63%
06/10/24 |  | 10/25/24 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | Jacob Hill, Phillip Ma Lim, Tavis Jackson |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00018484 | Wireless APs Installation PD Building | Closed | 100% | 40.67% | 35.65 | 22.65 | 2602.45 | 870 | 63.53% | 2602.45 | 1.5 | 14.5 | 780 | 0 |  | 870 |  | 14068.4 | 4294 | 3424 | 79.74%
05/07/24 |  | 10/25/24 | Open | Jennifer Soliz | Mark J Chambliss |  | Anthony Towsley, Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Anthony Towsley, Cory Bradfield, Henry Pugsley, Jennifer Soliz |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00018237 | UC SU Upgrades | Closed | 100% | 108.8% | 91.25 | -8 | 12866.25 | 13906.25 | -8.767% | 12866.25 | 0 | 99.25 | 13906.25 | 0 |  | 13906.25 |  | 0 | 20264 | 6357.75 | 31.37%
06/25/24 |  | 10/29/24 | Open | Ryan Scott | David Watkins, William Birdsong |  | Beau C. Devillier, Brandon McMillan, David Watkins, Matthew Veach, Ryan Scott, Saravanan Lakshmanan, Taylor Leger, William Birdsong |  |  | Calvin Darby, Jacob Hill, Jhon Genao, Matthew Veach, Noah Trump, Quy Le, Ryan Scott |  |  | Taylor Leger | TX-DAL | Forney ISD | J00018417 | NFHS Stadium Addition (Opt. 1) | Closed | 100% | 98.9% | 180.23 | 4.48 | 19133.03 | 15781.25 | 2.486% | 19133.03 | 2.5 | 178.25 | 15631.25 | 0 |  | 15781.25 |  | 83421.14 | 29913.2 | 14131.95 | 47.24%
08/26/24 |  | 10/31/24 | Open | Jim Blackwell | Aman Khan |  | Ashley F Freeman, Jim Blackwell, Larry Noble |  |  | Craig St. Rose, Jerald Garner, Jim Blackwell, Luis Alvarez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018881 | FBISD Admin Building: Water-Damaged Replacement | Closed | 100% | 90.67% | 18.75 | 2.75 | 1390.48 | 1215 | 14.67% | 1390.48 | 1 | 17 | 1155 | 0 |  | 1215 |  | 0 | 2260.52 | 1045.52 | 46.25%
08/28/24 |  | 10/31/24 | Open | Walter Clay Knight | George Edwin Jacob |  | Jeff Barker, Joseph Boglino |  |  | Juan Saenz, Osazee Eweka, Walter Clay Knight |  |  | Joseph Boglino | US-FED | Amazon Web Services | J00018897 | AWS POC | Cancelled | 0% | 0% | 0 | -12.25 | 0 | 1591.25 | 0% | 0 | 0 | 12.25 | 1591.25 | 0 |  | 1591.25 |  | 0 | 23584.9 | 21993.65 | 93.25%
08/28/24 |  | 10/31/24 | Open | Walter Clay Knight | George Edwin Jacob |  | Jeff Barker, Joseph Boglino |  |  | Juan Saenz, Osazee Eweka, Walter Clay Knight |  |  | N/A | N/A | Amazon Web Services | J00018897 | AWS POC | Cancelled | 5% | 0% | 109.25 | 109.25 | 14606.25 | 0 | 100% | 14606.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 23584.9 | 23584.9 | 100%
10/15/24 |  | 11/01/24 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Lauren J Kennewell, Patrick Joseph Palermo |  |  | Abiodun David Babasola, Patrick Joseph Palermo |  |  | Lauren J Kennewell | TX-DAL | Duncanville ISD | J00019156 | Auto Attendant Services | Closed | 100% | 95% | 10 | 0.5 | 1410 | 1675 | 5% | 1410 | 0 | 9.5 | 1675 | 0 |  | 1675 |  | 0 | 2200.88 | 525.88 | 23.89%
07/10/23 |  | 11/01/24 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Bradley Buchanan, Brian Willery, Bryan Mullen |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014222 | PD(DR site) Networking Hardware Install | Closed | 100% | 30.47% | 151.29 | 106.19 | 16540.05 | 5177.5 | 70.19% | 16540.05 | 1 | 46.1 | 5117.5 | 0 |  | 5177.5 |  | 49622.2 | 6992.4 | 1814.9 | 25.96%
07/31/23 |  | 11/01/24 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Ashutosh Patel, Brian Willery, Jeffrey Holman, Lauren J Kennewell, Shiraz Humayun, Yasser Sartawi |  |  | Ashutosh Patel, Brian Willery, Jason Espino, Joshua Hubbard, Thai Truong, Yasser Sartawi |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00015875 | F5 - 4x46xx BT (1YR) with Install | Closed | 100% | 90.18% | 224 | 24.5 | 32390 | 27603.75 | 10.94% | 32390 | 2.5 | 202 | 27378.75 | 0 |  | 27603.75 |  | 425350.8 | 52228.8 | 24625.05 | 47.15%
12/06/23 |  | 11/01/24 | Open | Brian Willery | David Watkins |  | Brian Willery, David Watkins, Ismael Velazquez, Jeff Barker, Saravanan Lakshmanan |  |  | Brian Willery, Saravanan Lakshmanan, Sophia Quinter |  |  | Ismael Velazquez | FL | City of Pembroke Pines | J00016978 | WLC Assessment and Refresh | Closed | 100% | 123.4% | 123.13 | -28.87 | 15883.75 | 19630 | -23.45% | 15883.75 | 0 | 152 | 19630 | 696.81 |  | 19630 |  | 0 | 24989 | 4662.19 | 18.66%
05/13/24 |  | 11/01/24 | Open | Brian Willery | Majid Shirzadeh |  | Beau C. Devillier, Brian Willery, Dante Torres, Frank Jaimes, Joshua Hubbard, Kirk O'Guinn, Lauren J Kennewell, Patrick Shea Thompson, Patrick Thompson, Vitalii Stepanchenko |  |  | Bradley Buchanan, Brian Willery, Carlo Enriquez, Cason Spencer, Frank Jaimes, Jacob Hill, Jhon Genao, Joshua Hubbard, Joshua Osgood, Juan Pomares, Kebret Eshetu, Kirk O'Guinn, Noah Trump, Patrick Shea Thompson, Quentin Sowels, Quy Le, Vitalii Stepanchenko, William Chris Roome |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00018300 | Cisco Switch Installation - 4 Locations | Closed | 100% | 213.7% | 173.14 | -188.36 | 16798.88 | 29321.25 | -108.8% | 16798.88 | 8.5 | 370 | 28713.75 | 0 |  | 29321.25 |  | 0 | 27183 | -2138.25 | -7.866%
09/27/24 |  | 11/01/24 | Open | Jennifer Soliz | Timothy Ramsey |  | Eric Firestone, Hannah Paul, Jennifer Soliz, John Randall Bailey, Jr. |  |  | Eric Firestone, Jennifer Soliz |  |  | Hannah Edmunds | TX-CEN | Health and Human Services Commission | J00018418 | SNS 3595's Replacements with Virtual Servers | Closed | 100% | 57.9% | 41.88 | 17.63 | 6072.5 | 3512.5 | 42.1% | 6072.5 | 0 | 24.25 | 3512.5 | 0 |  | 3512.5 |  | 10830 | 8288 | 4775.5 | 57.62%
06/20/24 |  | 11/01/24 | Open | Jim Blackwell | Albert H Nguyen, Aman Khan |  | Abdalsattar Albaghdadi, Albert H Nguyen, Aleksei Lavrushenkov, Aman Khan, Brandon McMillan, Daniel Hernandez, Daniel R Hernandez, Jim Blackwell, Julio C Montoya, Kolawole Ayeni, Mustafa Al-Tamimi |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Andy Pham, Anthony Lange, Baq Alsaedi, Bryant Bush, Craig St. Rose, David Dobbs, Devon LeMoine, Hector Rivera, James Adams, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Jose R. Duarte, Julio C Montoya, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Nicolas Garakani, Paul Serres |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018349 | LAN Phase 3 Switch Deployments | Closed | 100% | 136.4% | 1310.34 | -269.27 | 130874.49 | 138475.85 | -20.55% | 130874.49 | 208.3 | 1787.91 | 124082.85 | 0 |  | 138475.85 |  | 6537342.5 | 227374.9 | 88899.05 | 39.1%
02/07/24 |  | 11/01/24 | Open | Shannon Marie Alvarado | Matthew Duncan |  | Jamie Lewis, Juan Saenz, Kathryn Santoni Menza, Matthew Duncan, Osazee Eweka, Shannon Marie Alvarado, William Isaac Sears |  |  | Juan Saenz, Osazee Eweka, Shannon Marie Alvarado |  |  | Jamie Lewis | US-SP | Amazon Web Services | J00017464 | Amazon Web Services (AWS) | Closed | 0% | 0% | 0 | -120.5 | 0 | 15997.5 | 0% | 0 | 0 | 120.5 | 15997.5 | 0 |  | 15997.5 |  | 0 | 123456.79 | 107459.29 | 87.04%
02/07/24 |  | 11/01/24 | Open | Shannon Marie Alvarado | Matthew Duncan |  | Jamie Lewis, Juan Saenz, Kathryn Santoni Menza, Matthew Duncan, Osazee Eweka, Shannon Marie Alvarado, William Isaac Sears |  |  | Juan Saenz, Osazee Eweka, Shannon Marie Alvarado |  |  | N/A | N/A | Amazon Web Services | J00017464 | Amazon Web Services (AWS) | Closed | 100% | 0% | 382.91 | 382.91 | 50911.75 | 0 | 100% | 50911.75 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 123456.79 | 123456.79 | 100%
04/08/24 |  | 11/04/24 | Open | Richard Keith Arnst | Aman Khan, Eduardo Chavez |  | Aman Khan, Austen New LN: Howard Cockerham, Eduardo Chavez, Garrett Curran, Karyn Hubbard, Meray Doughly, Mohammad Jilani, Nick Varga, Richard Keith Arnst, Yong Kim |  |  | Austen Howard, Caleb Baik, Carlo Enriquez, Conner MacDonnell, Henry Pugsley, Kebret Eshetu, Nick Varga, Quentin Sowels, Quy Le, Richard Keith Arnst, William Chris Roome |  |  | Garrett Curran | CA-LAX | Westside Union School District | J00018007 | Juniper Switch Refresh Project | Closed | 100% | 63.53% | 867.03 | 345.18 | 89975.91 | 58706.25 | 39.81% | 89975.91 | 29 | 550.85 | 56071.25 | 0 |  | 58706.25 |  | 1202012.68 | 159408.1 | 100701.85 | 63.17%
10/29/24 |  | 11/04/24 | Open | Ryan Scott | Bryan Geoghan |  | Alexander Gutman, Anthony Towsley, Beau C. Devillier, Bryan Geoghan, Ryan Scott |  |  | Anthony Towsley, Ryan Scott |  |  | Alex Gutman | TX-DAL | Dallas College | J00017163 | Singlewire InformaCast Upgrade | Closed | 100% | 88.51% | 58.75 | 6.75 | 8048.75 | 7088.75 | 11.49% | 8048.75 | 0 | 52 | 7026.25 | 0 |  | 7088.75 |  | 36223.25 | 17395.6 | 10306.85 | 59.25%
09/30/24 |  | 11/05/24 | Open | Robert McIver | Edward Padron |  | Daniel Saenz, Edward Padron, Mario Sanchez, Robert McIver, Ruben Cantu |  |  | Robert McIver, Ruben Cantu |  |  | Daniel Saenz | TX-SOUT | South Texas ISD | J00019031 | Network Assessment Discovery Phase 1 | Closed | 100% | 118.1% | 21.6 | -1.9 | 2700 | 3187.5 | -8.796% | 2700 | 2 | 25.5 | 2937.5 | 0 |  | 3187.5 |  | 0 | 3537.2 | 349.7 | 9.886%
09/05/24 |  | 11/05/24 | Open | Robert McIver | Bryan Brown |  | Diana Berger, Jason Osuna, Robert McIver |  |  | N/A |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | J00018932 | President's Conf Rm - USB Mode / HDMI Mode | Closed | 100% | 0% | 7 | 7 | 945 | 0 | 100% | 945 | 0 | 0 | 0 | 0 |  | 0 |  | 1885.21 | 1920 | 1920 | 100%
04/28/23 |  | 11/06/24 | Open | Richard Keith Arnst | Albert H Nguyen, Bryan Brown, Mark J Chambliss |  | Larry Noble, Lindie Lorraine Lamar, Richard Keith Arnst, Susan Richardson |  |  | Devon LeMoine, Jesus Gonzalez, Mohammed Al-Shaikhli, Nathan Dao, Richard Keith Arnst |  |  | Lindie Lamar | TX-HOU | Prime Contractors | J00015399 | Huntsville ISD HS Network and AV Auditorium | Closed | 0% | 0% | 0 | -65.01 | 0 | 6564.75 | 0% | 0 | 11.09 | 76.1 | 5899.35 | 0 |  | 6564.75 |  | 44102.5 | 10511.12 | 3946.37 | 37.54%
04/28/23 |  | 11/06/24 | Open | Richard Keith Arnst | Albert H Nguyen, Bryan Brown, Mark J Chambliss |  | Larry Noble, Lindie Lorraine Lamar, Richard Keith Arnst, Susan Richardson |  |  | Devon LeMoine, Jesus Gonzalez, Mohammed Al-Shaikhli, Nathan Dao, Richard Keith Arnst |  |  | N/A | N/A | Prime Contractors | J00015399 | Huntsville ISD HS Network and AV Auditorium | Closed | 100% | 4.273% | 70.21 | 67.21 | 7952.13 | 375 | 95.73% | 7952.13 | 0 | 3 | 0 | 0 |  | 375 |  | 44102.5 | 10511.12 | 10136.12 | 96.43%
12/04/23 |  | 11/07/24 | Open | Joaquin Marroquin | Bryan Brown |  | Diana Berger, Joaquin Marroquin, Mariana Pacheco, Robert Lavender, William Barrett Chancellor |  |  | Joaquin Marroquin |  |  | Mariana Pacheco | TX-SOUT | University of Texas - El Paso | J00016850 | Samsung video wall -Huntsville, AL | Closed | 0% | 0% | 0 | -5.5 | 0 | 687.5 | 0% | 0 | 0 | 5.5 | 687.5 | 0 |  | 687.5 |  | 17325.34 | 8456.22 | 7768.72 | 91.87%
12/04/23 |  | 11/07/24 | Open | Joaquin Marroquin | Bryan Brown |  | Diana Berger, Joaquin Marroquin, Mariana Pacheco, Robert Lavender, William Barrett Chancellor |  |  | Joaquin Marroquin |  |  | N/A | N/A | University of Texas - El Paso | J00016850 | Samsung video wall -Huntsville, AL | Closed | 100% | 0% | 10 | 10 | 1302.5 | 0 | 100% | 1302.5 | 0 | 0 | 0 | 0 |  | 0 |  | 17325.34 | 8456.22 | 8456.22 | 100%
10/18/23 |  | 11/08/24 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Lauren J Kennewell |  |  | Abiodun David Babasola, Hamzeh Tahat |  |  | Lauren J Kennewell | TX-DAL | City of Midlothian | J00016497 | PSTN Migration | Closed | 100% | 61.44% | 38.25 | 14.75 | 5291.25 | 2450 | 38.56% | 5291.25 | 0 | 23.5 | 2200 | 2242.5 |  | 2450 |  | 0 | 6558.8 | 1866.3 | 28.45%
02/06/23 |  | 11/08/24 | Open | Robert McIver | Rogelio Dominguez, Warren Wilson |  | Amy Martinez-Nagy, Garrett Hart, Michelle Bailey, Remi Martinez-Montenegro, Robert McIver, Rogelio Dominguez, Warren Wilson, Xavier A Trevino |  |  | Carlos Carrillo, Francisco Hernandez, Garrett Hart, Jaime Galvan, Jesus Cantu, Jorge Robert Rangel, Jose Salazar, Juan Rodriguez, Mario Alberto Aguilar, Oscar Garcia, Richard Colby, Robert McIver, William Brown |  |  | Xavier A Trevino | TX-SOUT | Pharr-San Juan-Alamo ISD | J00014678 | District Security Camera Installations | Closed | 100% | 59.29% | 556.2 | 227.7 | 57225 | 26657.5 | 40.94% | 57225 | 1.25 | 329.75 | 26320 | 487.5 |  | 26657.5 |  | 269953.68 | 113937.71 | 86792.71 | 76.18%
05/15/23 |  | 11/08/24 | Open | Robert McIver | Rogelio Dominguez, Warren Wilson |  | Amy Martinez-Nagy, Garrett Hart, Michelle Bailey, Remi Martinez-Montenegro, Robert McIver, Rogelio Dominguez, Warren Wilson, Xavier A Trevino |  |  | Francisco Hernandez, Garrett Hart, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Pharr-San Juan-Alamo ISD | J00015016 | Access Control Project - Equipment District-Wide | Closed | 100% | 197.1% | 70 | -68 | 8750 | 16857.5 | -97.14% | 8750 | 0 | 138 | 15595 | 0 |  | 16857.5 |  | 62519.04 | 71742.89 | 54885.39 | 76.5%
06/19/24 |  | 11/12/24 | Open | Marshall Chuck Pugh | Jacob Parks, Jeffrey Holman, William Birdsong |  | Beau C. Devillier, Marshall Chuck Pugh , Patrick Joseph Palermo, Taylor Leger |  |  | Austen Howard, Devin Moreno, Jacob Hill, Joan Brito, Marshall Chuck Pugh, Noah Trump, Phillip Ma Lim, Remijio Hernandez, Ryan Frankeberger, Tavis Jackson |  |  | Taylor Leger | TX-DAL | Corsicana ISD | J00018548 | UPS Implementation | Closed | 100% | 76.5% | 185.62 | 68.62 | 12712.1 | 10470 | 36.97% | 12712.1 | 25 | 142 | 8970 | 0 |  | 10470 |  | 86217 | 16441.41 | 5971.41 | 36.32%
03/25/24 |  | 11/15/24 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Alexander Gutman, Arcangelo Fanelli, John Stephen Kurkjian, Shannon Marie Alvarado |  |  | John Stephen Kurkjian, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | J00017865 | Collaboration Upgrade | Closed | 100% | 99.92% | 160.63 | 0.13 | 22648.75 | 21990 | 0.08093% | 22648.75 | 0 | 160.5 | 21515 | 0 |  | 21990 |  | 577.82 | 44918 | 22928 | 51.04%
09/06/24 |  | 11/15/24 | Open | Shannon Marie Alvarado | Mark J Chambliss |  | Kurt Sell, Lindie Lorraine Lamar, Shannon Marie Alvarado |  |  | Anthony Towsley, David Dobbs, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Texas First Bank | J00018920 | Algo 8301 Installation | Closed | 100% | 126.7% | 7.5 | 0.5 | 1136.41 | 1027.5 | 6.667% | 1136.41 | 2.5 | 9.5 | 877.5 | 0 |  | 1027.5 |  | 365.64 | 1379.68 | 352.18 | 25.53%
08/23/24 |  | 11/18/24 | Open | Tray Giddens | Albert H Nguyen |  | Albert H Nguyen, Brittney Antoinette Hickman, Larry Noble, Lindie Lorraine Lamar, Nelson Garcia, Tray Giddens |  |  | Andy Pham, Brittney Antoinette Hickman, James Adams, Kevin Curtis, Matthew D'Ambrosio, Nelson Garcia, Paul Serres, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Jasper ISD | J00018875 | Switching and UPS Implementation | Closed | 100% | 68.06% | 155.02 | 67.52 | 13694.51 | 9027.5 | 43.56% | 13694.51 | 18 | 105.5 | 7312.5 | 0 |  | 9027.5 |  | 83011.69 | 16697.5 | 7670 | 45.94%
12/21/20 |  | 11/21/24 | Open | Karyn Hubbard | Joshua Adam Engle |  | Arcangelo Fanelli, Beau C. Devillier, Karyn Hubbard |  |  | Bryan Mullen, Gena Robbins, Jonathan Weir, Jonathan Weir, Kairo Sauceda, Karyn Hubbard, Luis Ovalles, Mohaymen Sodi, Phillip Thornton, Ron Loge, Ryan Scott, Walton Osiemo, Zachary Newman |  |  | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00008548 | ACI & SDA for CCTV - Network Refresh Phase 1 | Closed | 100% | 903.6% | 1158.24 | -9263.96 | 110032.8 | 1002951.5 | -799.8% | 110032.8 | 44 | 10466.2 | 997526.5 | 8474.93 |  | 1002951.5 |  | 7073959.56 | 524296 | -487130.43 | -92.91%
12/18/23 |  | 11/22/24 | Open | Jim Blackwell | Albert H Nguyen, Mark J Chambliss |  | Albert H Nguyen, Aleksei Lavrushenkov, Ashley F Freeman, Craig St. Rose, Craig St. Rose, Jaime B Flores, Jaime Flores, Jim Blackwell, Julio C Montoya, Kord Mullins, Larry Noble, Mark J Chambliss, Mustafa Al-Tamimi |  |  | Aleksei Lavrushenkov, Bryant Bush, Craig St. Rose, David Dobbs, Devon LeMoine, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Jose R. Duarte, Julio C Montoya, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mustafa Al-Tamimi, Nicolas Garakani, Paul Serres |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00017122 | Clements HS FH | Closed | 100% | 114.6% | 236.74 | 5.47 | 22011.49 | 20234.7 | 2.311% | 22011.49 | 40.1 | 271.37 | 17493.7 | 0 |  | 20234.7 |  | 232882.4 | 14761.16 | -5473.54 | -37.08%
09/19/24 |  | 11/25/24 | Open | Robert McIver | Mark J Chambliss |  | Diana Berger, Jason Osuna, Robert McIver, Thomas Francis LoMonaco, William Barrett Chancellor |  |  | Robert McIver, Thomas Francis LoMonaco |  |  | Jason Osuna | TX-CEN | University Medical Center of El Paso | J00018995 | CCX Callback Scripting | Closed | 100% | 114.3% | 35 | -5 | 4935 | 7112.5 | -14.29% | 4935 | 0 | 40 | 4647.5 | 0 |  | 7112.5 |  | 0 | 5838.4 | -1274.1 | -21.82%
08/14/24 |  | 11/25/24 | Open | Ryan Scott | Ahmed Al-Zubaidi, Aman Khan |  | Ahmed Jameel, Aman Khan, Dustin Huffman, Larry Noble, Ryan Scott |  |  | Ahmed Jameel, Jose R. Duarte, Julio C Montoya, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Nathan Dao, Paul Serres, Ryan Scott |  |  | Dustin Huffman | TX-HOU | Landry's Restaurants | J00018758 | Hilton Network Refresh | Closed | 100% | 93.84% | 133.21 | 17.71 | 13163.62 | 12147.5 | 13.29% | 13163.62 | 9.5 | 125 | 9515 | 0 |  | 12147.5 |  | 75550.12 | 21230.4 | 9082.9 | 42.78%
12/13/21 |  | 11/29/24 | Open | Brian Willery | Michael Brett Beggs |  | Brian Willery, Jason Osuna, Larry Noble |  |  | Brian Willery |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00011889 | New Shelf - ESeries 12x12 TB Drives | Closed | 100% | 1.736% | 14.4 | 14.15 | 1596 | 23.75 | 98.26% | 1596 | 0 | 0.25 | 23.75 | 0 |  | 23.75 |  | 25127.9 | 2709 | 2685.25 | 99.12%
12/13/21 |  | 11/29/24 | Open | Brian Willery | Michael Brett Beggs |  | N/A |  |  | Brian Willery |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00011890 | New Shelf - ESeries 12x12 TB Drives | Closed | 100% | 5.208% | 14.4 | 13.65 | 1596 | 71.25 | 94.79% | 1596 | 0 | 0.75 | 0 | 0 |  | 71.25 |  | 59785.1 | 2709 | 2637.75 | 97.37%
06/03/24 |  | 11/29/24 | Open | Marco Lish | Firas Abood |  | Cory Bradfield, Cory Bradfield, Larry Noble, Marco Lish, Neel Shah |  |  | Cory Bradfield, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00018457 | Moving GIS Cluster | Closed | 100% | 39.73% | 98.15 | 64.65 | 13090.75 | 5215 | 65.87% | 13090.75 | 5.5 | 39 | 4472.5 | 0 |  | 5215 |  | 0 | 20617.2 | 15402.2 | 74.71%
07/28/23 |  | 12/02/24 | Open | LaQisha Marshall | Kenneth Dieter, Naveed Hussain |  | Cory Bradfield, Cory Bradfield, Hannah Paul, LaQisha Marshall, Naveed Hussain, Steve J Rodriguez |  |  | Cory Bradfield, Hector Rivera, Jaime Flores, Justin Cornish, LaQisha Marshall, Sarah Beatrice Williamson |  |  | Hannah Edmunds | TX-CEN | Texas Department of Transportation | J00010567 | PO 601330000075694 - Houston Transtar VDI | Closed | 100% | 136% | 352.29 | -51.71 | 38676.45 | 61727.5 | -14.68% | 38676.45 | 75 | 479 | 51665 | 42.09 |  | 61727.5 |  | 464234.12 | 54362.4 | -7407.19 | -13.63%
06/01/23 |  | 12/02/24 | Open | Marco Lish | N/A |  | Arcangelo Fanelli, Beau C. Devillier, Dante Torres, Joshua Hubbard, Marco Lish, Noah Trump |  |  | Dante Torres, Henry Pugsley, Joshua Hubbard, Kebret Eshetu, Kirk O'Guinn, Marco Lish |  |  | Arcangelo Fanelli | TX-DAL | Fort Worth ISD | J00015617 | Olympus with Digital Signage | Closed | 100% | 105.3% | 67.31 | 0.46 | 8631.1 | 9685 | 0.6834% | 8631.1 | 4 | 70.85 | 9445 | 39.05 |  | 9685 |  | 10588.5 | 13809.6 | 4085.55 | 29.58%
06/24/24 |  | 12/02/24 | Open | Tray Giddens | Chad Hart |  | Ahmed Jameel, Chad Hart, Dustin Huffman, Larry Noble, Michelle Bailey, Nelson Garcia, Tray Giddens |  |  | Ahmed Jameel, Craig St. Rose, Devon LeMoine, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Nelson Garcia, Nicolas Garakani, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018591 | Middle School Network Refresh | Closed | 100% | 93.56% | 1613.26 | 246.01 | 140128.87 | 129269.7 | 15.25% | 140128.87 | 142.12 | 1509.37 | 111180 | 0 |  | 129269.7 |  | 0 | 10309.6 | -118960.1 | -1154%
03/31/23 |  | 12/03/24 | Open | Ryan Scott | Mark J Chambliss |  | Dustin Huffman, Larry Noble, Mark J Chambliss, Ryan Scott, Samuel Newland |  |  | Henry Pugsley, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nathan Dao, Ryan Scott, Samuel Newland |  |  | Dustin Huffman | TX-HOU | Landry's Restaurants | J00014545 | x1 Voice Router Configuration | Closed | 100% | 108.9% | 33.75 | -3 | 4668.75 | 4907.5 | -8.889% | 4668.75 | 0 | 36.75 | 3912.5 | 0 |  | 4907.5 |  | 18562.08 | 7705.2 | 2797.7 | 36.31%
10/28/24 |  | 12/04/24 | Open | Jennifer Soliz | Saif Qaissi |  | Ashley F Freeman, Jennifer Soliz, Larry Noble, Saif Qaissi |  |  | Ben Crouch, Jennifer Soliz |  |  | Ashley F Freeman | TX-HOU | Fort Bend County | J00019323 | RF Predictive Design - Richmond, Fulshear & Sienna | Closed | 100% | 30.1% | 14.95 | 10.45 | 1653.75 | 577.5 | 69.9% | 1653.75 | 0 | 4.5 | 130 | 0 |  | 577.5 |  | 0 | 1791.24 | 1213.74 | 67.76%
08/01/23 |  | 12/04/24 | Open | Joaquin Marroquin | Bryan Brown |  | Bryan Brown, Joaquin Marroquin, Michelle Bailey, Remi Martinez-Montenegro, Rene Trejo, Steve J Rodriguez, Xavier A Trevino |  |  | Clinton Bennett Deason, David Michael Castillo, Edgardo Lopez, Joaquin Marroquin, Remi Martinez-Montenegro, Rene Trejo |  |  | Xavier A Trevino | TX-SOUT | Del Mar College | J00015998 | Oso Creek - Main Building AV | Closed | 100% | 111.7% | 1360 | -95.25 | 143787.92 | 140231.25 | -7.004% | 143787.92 | 64.5 | 1519.75 | 132168.75 | 36166.91 |  | 140231.25 |  | 412901.98 | 250408.8 | 74010.64 | 29.56%
11/14/22 |  | 12/04/24 | Open | Tray Giddens | Ahmed Al-Zubaidi, Chad Hart, Wyley Johnson |  | Dustin Huffman, Jason Esry, Kurt Sell, Tray Giddens |  |  | Bryan Mullen, Eric Firestone, Mohaymen Sodi, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Clear Creek ISD | J00014360 | BOH - SD-Access Troubleshooting | Closed | 0% | 0% | 0 | -97.25 | 0 | 12743.75 | 0% | 0 | 0 | 97.25 | 12743.75 | 0 |  | 12743.75 |  | 0 | 25600 | 12856.25 | 50.22%
08/01/24 |  | 12/05/24 | Open | Richard Keith Arnst | Bryan Brown |  | Beau C. Devillier, Lauren J Kennewell, Richard Keith Arnst |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | HCA Healthcare, Inc. | J00018788 | AV Installation - Medical City Sachse | Closed | 100% | 112.1% | 89.69 | -10.81 | 10502.66 | 10927.5 | -12.05% | 10502.66 | 0 | 100.5 | 10177.5 | 0 |  | 10927.5 |  | 18059.97 | 15325.6 | 4398.1 | 28.7%
01/03/24 |  | 12/06/24 | Open | Brian Willery | David Watkins |  | Beau C. Devillier, Brian Willery, Ismael Velazquez, Jesus Escobedo, Magdalena Rodriguez, Moises Rodriguez |  |  | Brian Willery, Jesus Escobedo, Kolawole Ayeni, Moises Rodriguez |  |  | Ismael Velazquez | FL | City of Coral Springs | J00017051 | WAP/WLC Upgrade | Closed | 100% | 79.55% | 110 | 22.5 | 13161 | 11410 | 20.45% | 13161 | 0 | 87.5 | 10806.25 | 0 |  | 11410 |  | 190008.84 | 17701.64 | 6291.64 | 35.54%
02/12/20 |  | 12/06/24 | Open | Jason Esry | Chad Hart, Wyley Johnson |  | Jason Esry, Nelson Garcia |  |  | Abdulrahman Farhan, Adrian Barboza, Ahmed Al-Zubaidi, Ahmed Jameel, Aleksei Lavrushenkov, Andy Pham, Eiffel Garcia Alvarez, Hector Rivera, Jason Esry, Julio C Montoya, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Layth Abbood, Mohammad Jilani, Muthanna Alameri, Nelson Garcia, Rogelio Morgado-Perez, Saif Qaissi, Syed Zaidi, Yasser Sartawi |  |  | Susan Richardson | TX-HOU | Daikin Comfort Technologies Manufacturing, L.P. | J00006774 | Fannin DC Network HW Replace | Implementation/Deployment | 85% | 263.6% | 520.8109 | -798.1891 | 58428.65 | 154676.5 | -153.3% | 58428.65 | 53.75 | 1372.75 | 144353.25 | 794.4 |  | 154676.5 |  | 90928.36 | 65771.56 | -89699.34 | -136.4%
08/07/24 |  | 12/06/24 | Open | Jennifer Soliz | N/A |  | Hannah Paul, Jennifer Soliz, John Randall Bailey, Jr., Tony Dean Skipworth |  |  | Jennifer Soliz, Tony Dean Skipworth |  |  | Hannah Edmunds | TX-CEN | Health and Human Services Commission | J00018538 | APIC Cluster Replacement | Closed | 100% | 96.39% | 99.6 | 3.6 | 12978.5 | 12805 | 3.614% | 12978.5 | 0 | 96 | 10171.25 | 0 |  | 12805 |  | 0 | 0 | -12805 | 0%
01/30/24 |  | 12/06/24 | Open | Marco Lish | Firas Abood |  | Cory Bradfield, Cory Bradfield, Jaime B Flores, Jaime Flores, Larry Noble, Marco Lish, Neel Shah |  |  | Cory Bradfield, Hector Rivera, Jaime Flores, Kenneth Stevenson, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00017295 | HITS Enterprise HX Expansion | Closed | 100% | 70.45% | 87.3 | 36.55 | 10430.4 | 7570 | 41.87% | 10430.4 | 10.75 | 61.5 | 6156.25 | 35.1 |  | 7570 |  | 19182.2 | 16427.6 | 8822.5 | 53.71%
11/21/23 |  | 12/06/24 | Open | Ryan Scott | Bryan Geoghan |  | Beau C. Devillier, Lauren J Kennewell, Ryan Scott |  |  | Ryan Scott, Samuel Newland |  |  | Lauren J Kennewell | TX-DAL | North Texas Municipal Water District (NTMWD) | J00016934 | Collaboration Environment Rebuild | Closed | 100% | 76.71% | 145.68 | 33.93 | 19958.1 | 15341.25 | 23.29% | 19958.1 | 0 | 111.75 | 15247.5 | 0 |  | 15341.25 |  | 0 | 32048.8 | 16707.55 | 52.13%
09/23/24 |  | 12/06/24 | Open | Shannon Marie Alvarado | David Watkins |  | Arcangelo Fanelli, Beau C. Devillier, David Watkins, Ernesto Gonzalez, Mohammed Almoola, Shannon Marie Alvarado |  |  | Ernesto Gonzalez, Jeffery Alan Jorzig, Mohammed Almoola, Moises Rodriguez, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Baptist Hospitals of Southeast Texas | J00019004 | Network Deployment- New Admin office | Closed | 100% | 33.42% | 179.54 | 119.54 | 22821.6 | 7600 | 66.58% | 22821.6 | 0 | 60 | 4350 | 0 |  | 7600 |  | 0 | 35145.6 | 27545.6 | 78.38%
07/05/23 |  | 12/06/24 | Open | Tray Giddens | Mark J Chambliss |  | Andy Pham, Dustin Huffman, John Stephen Kurkjian, Justin Cornish , Kord Mullins, Kurt Sell, Mark J Chambliss, Tray Giddens |  |  | Aleksei Lavrushenkov, Andy Alvarenga, Andy Pham, Devon LeMoine, John Stephen Kurkjian, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Matthew D'Ambrosio, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Clear Creek ISD | J00015714 | UC Refresh | Closed | 100% | 110.5% | 316.25 | -25.25 | 41566.25 | 44700 | -7.984% | 41566.25 | 8 | 349.5 | 42210 | 204.77 |  | 44700 |  | 387628.03 | 51703.2 | 6798.43 | 13.15%
06/25/24 |  | 12/06/24 | Open | Tray Giddens | Chad Hart |  | Ahmed Jameel, Chad Hart, Dustin Huffman, Larry Noble, Nelson Garcia, Tray Giddens |  |  | Ahmed Jameel, Jerald Garner, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Nelson Garcia, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018597 | Facilities Network Refresh | Closed | 100% | 57.4% | 693.34 | 311.84 | 64957.62 | 40455 | 44.98% | 64957.62 | 16.5 | 398 | 28965 | 0 |  | 40455 |  | 717458.17 | 119492.4 | 79037.4 | 66.14%
06/17/24 |  | 12/06/24 | Open | Tray Giddens | Ahmed Al-Zubaidi, Wyley Johnson |  | Dustin Huffman, Jacob Sennett, Kurt Sell, Tray Giddens |  |  | Jacob Sennett, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Susman Godfrey LLP | J00018536 | Okta MFA – Network Devices Admin Access Opt2 | Closed | 100% | 51.55% | 88.75 | 43 | 12868.75 | 6462.5 | 48.45% | 12868.75 | 0 | 45.75 | 4525 | 0 |  | 6462.5 |  | 0 | 20268 | 13805.5 | 68.11%
07/22/24 |  | 12/10/24 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, John Stephen Kurkjian, Kurt Sell, LaQisha Marshall |  |  | John Stephen Kurkjian, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018683 | Cisco Unified Communications (UC) Upgrade | Closed | 100% | 80.29% | 324.75 | 64 | 45789.75 | 35743.75 | 19.71% | 45789.75 | 0 | 260.75 | 29861.25 | 0 |  | 35743.75 |  | 0 | 59706.4 | 23962.65 | 40.13%
05/20/24 |  | 12/12/24 | Open | Joaquin Marroquin | Edward Padron |  | Christopher Prado, Erick Nunez , Joaquin Marroquin, Steve J Rodriguez, Xavier A Trevino |  |  | Carlos Carrillo, Christopher Prado, Francisco Hernandez, Joaquin Garcia, Joaquin Marroquin, Jorge Robert Rangel, Juan Arturo Gonzalez Jr, Kolawole Ayeni, Lance Daniel Waitschies, Oscar Garcia, Roger Guerra |  |  | Xavier A Trevino | TX-SOUT | Robstown ISD | J00018081 | Erate Wireless Infrastructure HS and JHS | Closed | 100% | 178.7% | 201.83 | -104.92 | 19774.35 | 28055 | -51.98% | 19774.35 | 54 | 360.75 | 24440 | 2220 |  | 28055 |  | 208153.42 | 27726.69 | -2548.31 | -9.191%
12/12/24 |  | 12/12/24 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | Neel Shah | TX-HOU | Lone Star College System | J00019384 | LSC01-0000069554 | N/A | 0% | 12.5% | 8 | 7 | 280 | 30 | 87.5% | 280 | 0 | 1 | 0 | 0 |  | 30 |  | 11332.94 | 0 | -30 | 0%
05/01/24 |  | 12/13/24 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Karen Grant-Dennison, Michael Brett Beggs, William Davenport |  |  | Austen Howard, Carlo Enriquez, Cason Spencer, Jason Esry, Joan Brito, Joshua Osgood, Kebret Eshetu, Luis Ovalles, Patrick Shea Thompson, Quy Le, Remijio Hernandez, William Chris Roome |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00018256 | Data Centers Modernization Project | Closed | 100% | 0% | 418.38 | 418.38 | 47059.1 | 0 | 100% | 47059.1 | 0 | 0 | 0 | 0 |  | 0 |  | 1538061.88 | 72866 | 72866 | 100%
05/01/24 |  | 12/13/24 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Karen Grant-Dennison, Michael Brett Beggs, William Davenport |  |  | Austen Howard, Carlo Enriquez, Cason Spencer, Jason Esry, Joan Brito, Joshua Osgood, Kebret Eshetu, Luis Ovalles, Patrick Shea Thompson, Quy Le, Remijio Hernandez, William Chris Roome |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00018256 | Data Centers Modernization Project | Closed | 0% | 0% | 0 | -307.5 | 0 | 37342.5 | 0% | 0 | 3 | 310.5 | 37162.5 | 0 |  | 37342.5 |  | 1538061.88 | 72866 | 35523.5 | 48.75%
07/03/23 |  | 12/13/24 | Open | Jason Esry | Ahmed Al-Zubaidi, Albert H Nguyen, Wyley Johnson |  | Ahmed Al-Zubaidi, Albert H Nguyen, Brandon McMillan, Chad Stewart, Craig St. Rose, Craig St. Rose, David Neal Gravatt, Eric Firestone, Jason Esry, Jose E. Duarte Jr, Jose R Duarte, Jose R. Duarte, Kolawole Ayeni, Kord Mullins, Larry Noble, Luis A Alvarez, Luis Alvarez, Mohammed Almoola, Romar Roca, Susan Richardson, Wyley Johnson |  |  | Abdalsattar Albaghdadi, Andy Pham, Anthony Lange, Bryant Bush, Craig St. Rose, David Neal Gravatt, Devon LeMoine, Eric Firestone, Hector Rivera, James Adams, Jason Esry, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenia Dimas, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Mohammed Almoola, Mustafa Al-Tamimi, Nicolas Garakani, Paul Serres, Romar Roca, Sajja |  |  | Susan Richardson | TX-HOU | Pasadena ISD | J00015713 | Wireless Refresh / ISE Implementation | Closed | 100% | 67.62% | 4320.88 | 1535.71 | 391600.89 | 246971.7 | 35.54% | 391600.89 | 136.65 | 2921.82 | 237297.7 | 171.39 |  | 246971.7 |  | 3790719.61 | 1388606.9 | 1141463.81 | 82.2%
07/10/23 |  | 12/13/24 | Open | Jason Esry | Mark J Chambliss |  | Brian Newman, Brian Newman, Chad Stewart, Herman Cardell Wade, Jason Esry, John Stephen Kurkjian, Larry Noble, Susan Richardson |  |  | Jason Esry, John Stephen Kurkjian |  |  | Susan Richardson | TX-HOU | Pasadena ISD | J00015880 | UC Upgrade | Closed | 100% | 100.6% | 135.25 | -0.75 | 18529.25 | 18620 | -0.5545% | 18529.25 | 0 | 136 | 18620 | 119.87 |  | 18620 |  | 0 | 26065.4 | 7325.53 | 28.1%
09/18/23 |  | 12/13/24 | Open | Marco Lish | Christopher Puyear, William Birdsong |  | Beau C. Devillier, Bradley Buchanan, Cason Spencer, Hamzeh Tahat, Joshua Hubbard, Justin Thompson, Kirk O'Guinn, Kristy L Dice, Marco Lish, Saravanan Lakshmanan, Tavis Jackson |  |  | Angelo Gallegos, Cason Spencer, Dylan Pittsinger, Frank Jaimes, Hamzeh Tahat, Jacob Hill, Jhon Genao, Joan Brito, Justin Thompson, Kebret Eshetu, Kirk O'Guinn, Marco Lish, Matthew Veach, Michael McGee, Noah Trump, Phillip Ma Lim, Quentin Sowels, Quy Le, Saravanan Lakshmanan, Tavis Jackson, William Chris Roome |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00015946 | Network & Wireless for New Elem #7 | Closed | 100% | 184% | 219.12 | -167.63 | 20777.82 | 36775 | -76.5% | 20777.82 | 16.5 | 403.25 | 32992.5 | 7807 |  | 36775 |  | 404054.37 | 32954.8 | -11627.2 | -35.28%
01/29/24 |  | 12/13/24 | Open | Marco Lish | Ahmed Al-Zubaidi, Albert H Nguyen, Wyley Johnson |  | Abdalsattar Albaghdadi, Abdulrahman Farhan, Jorge Ortiz Cardozo, Larry Noble, Marco Lish, Neel Shah |  |  | Abdalsattar Albaghdadi, Abdulrahman Farhan, Dhulfiqar Al Hashimi, Jorge Ortiz Cardozo, Marco Lish, Saif Qaissi |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00017367 | Libraries (HPL) System Equipment E-Rate FY2023 | Closed | 100% | 84.99% | 449.44 | 67.44 | 61019.06 | 53237.5 | 15.01% | 61019.06 | 0 | 382 | 52506.25 | 0 |  | 53237.5 |  | 1346796.8 | 105146.4 | 51908.9 | 49.37%
02/01/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Jeff Barker, Justin Thompson, Marco Lish, Mark Forehand, Mohammad Jilani, Vitalii Stepanchenko |  |  | Carlo Enriquez, Conner MacDonnell, Marco Lish, Vitalii Stepanchenko |  |  | Mark Forehand | TX-DAL | Prosper ISD | J00015671 | New ES #5 & ES New MS #18 CAT1 | Closed | 0% | 0% | 0 | -27.25 | 0 | 3227.5 | 0% | 0 | 0 | 27.25 | 3227.5 | 0 |  | 3227.5 |  | 57477 | 6922 | 3694.5 | 53.37%
02/01/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Dante Torres, Devin Moreno, Dylan Pittsinger, Frank Jaimes, Jeff Barker, Jhon Genao, Juan Pomares, Justin Thompson, Marco Lish, Mark Forehand, Mohammad Jilani, Phillip Ma Lim, Sean Cowhey, Thai Truong, Vitalii Stepanchenko, William Birdsong, William Davenport |  |  | Carlo Enriquez, Cason Spencer, Dante Torres, Devin Moreno, Dylan Pittsinger, Frank Jaimes, Jacob Hill, Jhon Genao, Juan Pomares, Justin Thompson, Kebret Eshetu, Kirk O'Guinn, Marco Lish, Michael McGee, Noah Castleberry, Noah Trump, Phillip Ma Lim, Sean Cowhey, Vitalii Stepanchenko, William Chris Roome |  |  | Mark Forehand | TX-DAL | Prosper ISD | J00015688 | New ES #5 & New MS #18 ¦ EDU-K12 CAT2 2024 | Closed | 0% | 0% | 0 | -521.25 | 0 | 39491.75 | 0% | 0 | 31.8 | 553.05 | 37583.75 | 0 |  | 39491.75 |  | 571658.9 | 18135.9 | -21355.85 | -117.8%
05/06/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Marco Lish, Mark Forehand, Saravanan Lakshmanan, Vitalii Stepanchenko |  |  | Carlo Enriquez, Marco Lish, Vitalii Stepanchenko, William Chris Roome |  |  | Mark Forehand | TX-DAL | Prosper ISD | J00018286 | UPS Replacement C1 2024 | Closed | 0% | 0% | 0 | -111.5 | 0 | 13285 | 0% | 0 | 2 | 113.5 | 13035 | 0 |  | 13285 |  | 233017.8 | 39773.7 | 26488.7 | 66.6%
05/27/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Marco Lish, Mark Forehand, Saravanan Lakshmanan, Vitalii Stepanchenko |  |  | Angelo Gallegos, Austen Howard, Carlo Enriquez, Cason Spencer, Conner MacDonnell, Danny Laird, Dante Torres, Frank Jaimes, Hector Rivera, Jacob Hill, Jacqueline Barnes, Jayden Colon, Jhon Genao, Joan Brito, Joshua Hubbard, Juan Pomares, Kebret Eshetu, Kenia Dimas, Kirk O'Guinn, Marco Lish, Michael McGee, Nicolas Garakani, Phillip Ma Lim, Quentin Sowels, Quy Le, Raymond Phan, Remijio Hernandez, Saravanan Lakshmanan, Tavis Jackson, Vitalii Stepanchenko, William Chris Roome |  |  | Mark Forehand | TX-DAL | Prosper ISD | J00018396 | Distribution Switch & UPS Replacement | Closed | 0% | 0% | 0 | -1624 | 0 | 124280 | 0% | 0 | 116 | 1740 | 117320 | 12363 |  | 124280 |  | 2110417.7 | 85147 | -51496 | -60.48%
02/01/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Jeff Barker, Justin Thompson, Marco Lish, Mark Forehand, Mohammad Jilani, Vitalii Stepanchenko |  |  | Carlo Enriquez, Conner MacDonnell, Marco Lish, Vitalii Stepanchenko |  |  | N/A | N/A | Prosper ISD | J00015671 | New ES #5 & ES New MS #18 CAT1 | Closed | 100% | 0% | 47.81 | 47.81 | 4708.75 | 0 | 100% | 4708.75 | 0 | 0 | 0 | 0 |  | 0 |  | 57477 | 6922 | 6922 | 100%
02/01/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Dante Torres, Devin Moreno, Dylan Pittsinger, Frank Jaimes, Jeff Barker, Jhon Genao, Juan Pomares, Justin Thompson, Marco Lish, Mark Forehand, Mohammad Jilani, Phillip Ma Lim, Sean Cowhey, Thai Truong, Vitalii Stepanchenko, William Birdsong, William Davenport |  |  | Carlo Enriquez, Cason Spencer, Dante Torres, Devin Moreno, Dylan Pittsinger, Frank Jaimes, Jacob Hill, Jhon Genao, Juan Pomares, Justin Thompson, Kebret Eshetu, Kirk O'Guinn, Marco Lish, Michael McGee, Noah Castleberry, Noah Trump, Phillip Ma Lim, Sean Cowhey, Vitalii Stepanchenko, William Chris Roome |  |  | N/A | N/A | Prosper ISD | J00015688 | New ES #5 & New MS #18 ¦ EDU-K12 CAT2 2024 | Closed | 100% | 0% | 384.71 | 384.71 | 31439.65 | 0 | 100% | 31439.65 | 0 | 0 | 0 | 0 |  | 0 |  | 571658.9 | 18135.9 | 18135.9 | 100%
05/06/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Marco Lish, Mark Forehand, Saravanan Lakshmanan, Vitalii Stepanchenko |  |  | Carlo Enriquez, Marco Lish, Vitalii Stepanchenko, William Chris Roome |  |  | N/A | N/A | Prosper ISD | J00018286 | UPS Replacement C1 2024 | Closed | 100% | 2.439% | 286.95 | 279.95 | 27057.35 | 875 | 97.56% | 27057.35 | 0 | 7 | 0 | 0 |  | 875 |  | 233017.8 | 39773.7 | 38898.7 | 97.8%
05/27/24 |  | 12/13/24 | Open | Marco Lish | William Birdsong |  | Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Marco Lish, Mark Forehand, Saravanan Lakshmanan, Vitalii Stepanchenko |  |  | Angelo Gallegos, Austen Howard, Carlo Enriquez, Cason Spencer, Conner MacDonnell, Danny Laird, Dante Torres, Frank Jaimes, Hector Rivera, Jacob Hill, Jacqueline Barnes, Jayden Colon, Jhon Genao, Joan Brito, Joshua Hubbard, Juan Pomares, Kebret Eshetu, Kenia Dimas, Kirk O'Guinn, Marco Lish, Michael McGee, Nicolas Garakani, Phillip Ma Lim, Quentin Sowels, Quy Le, Raymond Phan, Remijio Hernandez, Saravanan Lakshmanan, Tavis Jackson, Vitalii Stepanchenko, William Chris Roome |  |  | N/A | N/A | Prosper ISD | J00018396 | Distribution Switch & UPS Replacement | Closed | 100% | 2.826% | 1495.1 | 1458.85 | 126673.98 | 4598.75 | 97.58% | 126673.98 | 6 | 42.25 | 360 | 12363 |  | 4598.75 |  | 2110417.7 | 85147 | 68185.25 | 80.08%
12/13/24 |  | 12/13/24 | Open | Michelle Duenes | N/A |  | Mark J Chambliss |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00019389 | 8000495446 | N/A | 0% | 0% | 3 | 3 | 105 | 0 | 100% | 105 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
12/13/24 |  | 12/13/24 | Open | Michelle Duenes | N/A |  | Mark J Chambliss |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00019390 | 8000495479 | N/A | 0% | 0% | 10 | 10 | 350 | 0 | 100% | 350 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
12/13/24 |  | 12/13/24 | Open | Michelle Duenes | N/A |  | Mark J Chambliss |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00019391 | 8000495438 | N/A | 0% | 0% | 12 | 12 | 420 | 0 | 100% | 420 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
02/26/24 |  | 12/13/24 | Open | Richard Keith Arnst | Albert H Nguyen, Bryan Brown, Mark J Chambliss |  | Albert H Nguyen, Haley Glasscock, Kord Mullins, Larry Noble, Lindie Lorraine Lamar, Richard Keith Arnst |  |  | Clinton Bennett Deason, Devon LeMoine, Jerald Garner, Jeremiah Solomon, Jesus Gonzalez, Kord Mullins, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Nicolas Garakani, Richard Keith Arnst |  |  | Lindie Lamar | TX-HOU | Prime Contractors | J00017653 | Mance Park Middle School – Phase 3 | Closed | 100% | 100.2% | 220.64 | 29.58 | 26861.22 | 17062.5 | 13.41% | 26861.22 | 29.94 | 221 | 14113.6 | 0 |  | 17062.5 |  | 255256.95 | 34517.76 | 17455.26 | 50.57%
12/16/24 |  | 12/16/24 | Open | Michelle Duenes | N/A |  | Mark J Chambliss |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00019402 | 8000495586 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
12/16/24 |  | 12/16/24 | Open | Michelle Duenes | N/A |  | Mark J Chambliss |  |  | N/A |  |  | N/A | N/A | Houston ISD | J00019409 | 8000495651 | N/A | 0% | 0% | 1 | 1 | 35 | 0 | 100% | 35 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
12/16/24 |  | 12/16/24 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | Neel Shah | TX-HOU | Lone Star College System | J00019399 | LSC01-0000069586 | Not started | 0% | 100% | 1 | 0 | 35 | 30 | 0% | 35 | 0 | 1 | 0 | 0 |  | 30 |  | 2023.46 | 0 | -30 | 0%
10/09/24 |  | 12/17/24 | Open | LaQisha Marshall | David Goss |  | Christi D Hubbard, David Goss, LaQisha Marshall, Larry Noble |  |  | Cory Bradfield, David Goss, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Pflugerville ISD | J00019162 | ESXi Hosts Upgrade | Closed | 100% | 62.22% | 22.5 | 8.5 | 2992.5 | 1825 | 37.78% | 2992.5 | 0 | 14 | 885 | 0 |  | 1825 |  | 0 | 4398.8 | 2573.8 | 58.51%
10/24/24 |  | 12/17/24 | Open | Marshall Chuck Pugh | Vernon Jackson, William Birdsong |  | Beau C. Devillier, Joshua Parker, Marshall Chuck Pugh , Vernon Jackson, William Birdsong |  |  | Austen Howard, Dante Torres, Devin Moreno, Marshall Chuck Pugh |  |  | Joshua Parker | TX-DAL | Collin County - Texas | J00019309 | Change order ID 1004999 for J00017337 | Closed | 100% | 140% | 7.5 | -2 | 502.5 | 695 | -26.67% | 502.5 | 1 | 10.5 | 60 | 0 |  | 695 |  | 7764.83 | 1557.12 | 862.12 | 55.37%
12/04/24 |  | 12/17/24 | Open | Robert McIver | Bryan Brown |  | Jason Osuna, Robert McIver |  |  | N/A |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200000203 | N/A | Closed | 100% | 0% | 6.88 | 6.88 | 915 | 0 | 100% | 915 | 0 | 0 | 0 | 0 |  | 0 |  | 871.91 | 1690.85 | 1690.85 | 100%
09/30/24 |  | 12/17/24 | Open | Robert McIver | Bryan Brown |  | Diana Berger, Jason Osuna, Robert McIver |  |  | Clinton Bennett Deason, Remi Martinez-Montenegro, Robert McIver |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | J00019096 | AV Upgrade MOB 403 | Closed | 100% | 152.2% | 15.44 | -8.06 | 6380.63 | 2087.5 | -52.2% | 6380.63 | 0 | 23.5 | 312.5 | 0 |  | 2087.5 |  | 16888.71 | 6057.8 | 3970.3 | 65.54%
09/05/23 |  | 12/18/24 | Open | Tray Giddens | Mark J Chambliss |  | Ashley F Freeman, Larry Noble, Ming Chiu, Tray Giddens |  |  | Ming Chiu, Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Harris County - Texas | J00016316 | CMS Upgrade | Closed | 100% | 213.8% | 81.6 | -92.9 | 11220 | 24227.5 | -113.8% | 11220 | 0 | 174.5 | 22142.5 | 0 |  | 24227.5 |  | 0 | 18894.48 | -5333.02 | -28.23%
12/29/23 |  | 12/20/24 | Open | Jennifer Soliz | Kenneth Dieter |  | Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Andrew G Wagenhofer, Christopher Knipe, Jennifer Soliz, Michael Hilton, Ron Loge, Sarah Beatrice Williamson |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00009890 | 2194850 - ACI NERC | Cancelled | 95% | 48.44% | 398.42 | 215.42 | 45052.12 | 32855 | 54.07% | 45052.12 | 10 | 193 | 31105 | 279.63 |  | 32855 |  | 860337.8 | 74726 | 41591.37 | 55.66%
11/15/21 |  | 12/20/24 | Open | Jennifer Soliz | N/A |  | Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Jennifer Soliz, Ron Loge |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00011601 | ACI Leafs + Optics ¦ VBlock Replacement | Training/Knowledge Transfer/Documentation | 95% | 534.1% | 27.9 | -121.1 | 2477.5 | 19195 | -434.1% | 2477.5 | 0 | 149 | 19195 | 0 |  | 19195 |  | 407259.6 | 3596.8 | -15598.2 | -433.7%
06/04/19 |  | 12/20/24 | Open | Marshall Chuck Pugh | Joshua Adam Engle |  | Marshall Chuck Pugh |  |  | Abiodun David Babasola, Andrew Adikwu, Charles Phillips, Conner MacDonnell, Darrell Walton, Deon Branish , Edward Quinonez, Henry Pugsley, Juan Pomares, Julio Cerrato, Justin Thompson, Keiaudra Parker, Korede Oluwatobiloba Adeola, Marshall Chuck Pugh , Matthew Kennewell, Matthew Veach, Moises Rodriguez, Orlando Francis, Robert Reid, Roland Hernandez, Sean Cowhey, Tabais Prater, Tavis Jackson, Thai Truong, William Chris Roome, Zachary Newman |  |  | Kristy L Dice | TX-DAL | Highland Park ISD | J00004602 | PO 9181900076 - Combined 2019 Projects | On HOLD | 80% | 156.1% | 1021.45 | -491.05 | 68030.3 | 106395 | -48.07% | 68030.3 | 81.75 | 1594.25 | 100683.75 | 2885.5 |  | 106395 |  | 2658729.52 | 90592.62 | -18687.88 | -20.63%
11/01/23 |  | 12/20/24 | Open | Robert McIver | Rogelio Dominguez, Warren Wilson |  | Garrett Hart, Michelle Bailey, Robert McIver, Rogelio Dominguez, Warren Wilson, Xavier A Trevino |  |  | Francisco Hernandez, Garrett Hart, Joaquin Garcia, Jonathan Pina, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Pharr-San Juan-Alamo ISD | J00016788 | Cameras and Door Strikes for Transport | Closed | 100% | 52.87% | 13.24 | 7.74 | 1576.65 | 747.5 | 58.46% | 1576.65 | 1.5 | 7 | 470 | 0 |  | 747.5 |  | 4435.23 | 5127.67 | 4380.17 | 85.42%
05/27/24 |  | 12/23/24 | Open | Joaquin Marroquin | Mark J Chambliss |  | Joaquin Marroquin, Larry Noble, Lonnie Owens, Samuel Newland |  |  | George McGann, Joaquin Marroquin, Samuel Newland |  |  | Lonnie Owens | TX-CEN | Boerne ISD | J00018406 | BISD Phones Viola Wilson ES | Closed | 100% | 86% | 25 | 3.5 | 3525 | 2957.5 | 14% | 3525 | 0 | 21.5 | 2957.5 | 0 |  | 2957.5 |  | 0 | 5551.6 | 2594.1 | 46.73%
06/22/23 |  | 12/26/24 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Anthony Towsley, Beau C. Devillier, David Babasola, Taylor Leger |  |  | Abiodun David Babasola, Anthony Towsley, Carlo Enriquez, Henry Pugsley |  |  | Taylor Leger | TX-DAL | BBB Serving North Central Texas | J00014450 | Voice Gateway work Order | Closed | 100% | 177.7% | 16.88 | -10.62 | 2175 | 4087.5 | -62.91% | 2175 | 2.5 | 30 | 2267.5 | 76.91 |  | 4087.5 |  | 17233.29 | 3196 | -968.41 | -30.3%
03/18/24 |  | 12/27/24 | Open | Shannon Marie Alvarado | Amanda Barney, David Watkins |  | Beau C. Devillier, Bryan Mullen, David Watkins, Jeffery Alan Jorzig, Jeffery Jorzig, Katharine McCarley, Katherine McCarley, Shannon Marie Alvarado |  |  | Bradley Buchanan, Bryan Mullen, Carlo Enriquez, Jeffery Alan Jorzig, Kebret Eshetu, Quentin Sowels, Quy Le, Shannon Marie Alvarado, William Chris Roome |  |  | Katie McCarley | TX-DAL | Winstead PC | J00017832 | SD-WAN Advice, Implementation & Migration MT&E | Closed | 0% | 0% | 0 | -519.25 | 0 | 64021.25 | 0% | 0 | 1 | 520.25 | 63961.25 | 0 |  | 64021.25 |  | 53701.2 | 0 | -64021.25 | 0%
03/18/24 |  | 12/27/24 | Open | Shannon Marie Alvarado | Amanda Barney, David Watkins |  | Beau C. Devillier, Bryan Mullen, David Watkins, Jeffery Alan Jorzig, Jeffery Jorzig, Katharine McCarley, Katherine McCarley, Shannon Marie Alvarado |  |  | Bradley Buchanan, Bryan Mullen, Carlo Enriquez, Jeffery Alan Jorzig, Kebret Eshetu, Quentin Sowels, Quy Le, Shannon Marie Alvarado, William Chris Roome |  |  | N/A | N/A | Winstead PC | J00017832 | SD-WAN Advice, Implementation & Migration MT&E | Closed | 100% | 0% | 0 | -4.5 | 244.27 | 562.5 | 0% | 244.27 | 0 | 4.5 | 0 | 0 |  | 562.5 |  | 53701.2 | 0 | -562.5 | 0%
01/01/24 |  | 12/31/24 | Open | Karyn Hubbard | N/A |  | N/A |  |  | Abiodun David Babasola, Aladdin Ghaibah, Ali Al-Haddad, Brian Willery, Brittney Antoinette Hickman, Christina Rice, Jason Esry, Jason Matthew Davis, Jennifer Soliz, Jim Blackwell, Joanna Herrera, Joaquin Marroquin, Karyn Hubbard, LaQisha Marshall, Lauren Lanzini Coffey, Marco Lish, Marshall Chuck Pugh, Richard Keith Arnst, Robert McIver, Ryan Scott, Shannon Marie Alvarado, Summer Abunaja, Tray Giddens, Walter Clay Knight, Warren Llewellyn Flynn, William Chris Roome |  |  | N/A | N/A | Netsync Network Solutions | PS-PMO-2025 | PS-PMO-2024 Netsync | N/A | 0% | 0% | 0 | -11150.75 | 5646.2 | 1361668.75 | 0% | 5646.2 | 0 | 11150.75 | 0 | 0 |  | 1361668.75 |  | 0 | 0 | -1361668.75 | 0%
01/01/24 |  | 12/31/24 | Open | Michelle Duenes | N/A |  | N/A |  |  | Aboobiada Ali Abdalla, Ana Morales, Andrew Comeaux, Anthony Balogun, Brenda Dimas, Collin Mazzeno, Cristian Housenick, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Harold Gomez, Jaren Smallwood, Jarshawn Newsome, Jeffery Howard, Jesus Guadian, Jonathan McCoy, Josue Iglesias, Kai Rose , Kenia Dimas, Lorenzo Hernandez, Luis Mendoza, Michael Resendez, Michelle Duenes, Michelle Rose, Monica Cavazos, Nathanael Morales, Oscar Nunez, Osman Abdalla, Pedro Cavazos, Rashaud Compton, Sam |  |  | N/A | N/A | Netsync Network Solutions | PS-EU-2025 | PS-EU-2024 PC Deployment Netsync | N/A | 0% | 0% | 0 | -20032 | 2022.68 | 596070 | 0% | 2022.68 | 0 | 20032 | 0 | 0 |  | 596070 |  | 0 | 0 | -596070 | 0%
07/22/24 |  | 01/02/25 | Open | Christina Rice | Joshua Adam Engle |  | Beau C. Devillier, Christina Rice, Christina Rice, Joshua Adam Engle, Mark Forehand |  |  | Christina Rice, Jeffery Alan Jorzig |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | J00018672 | UTSW: WAN Link Installation Services [JJ/VS] | Closed | 100% | 41.05% | 166.25 | 98 | 18896.25 | 8531.25 | 58.95% | 18896.25 | 0 | 68.25 | 4125 | 0 |  | 8531.25 |  | 0 | 33171.6 | 24640.35 | 74.28%
12/03/24 |  | 01/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000186 | N/A | Closed | 100% | 0% | 0 | -2 | 19.63 | 60 | 0% | 19.63 | 0 | 2 | 0 | 0 |  | 60 |  | 1647 | 0 | -60 | 0%
12/03/24 |  | 01/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000187 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4315 | 0 | -30 | 0%
12/03/24 |  | 01/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Jesus Guadian, Josue Iglesias, Kai Rose , Nathanael Morales, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200000188 | N/A | Closed | 0% | 0% | 0 | -91.5 | 0 | 2745 | 0% | 0 | 0 | 91.5 | 0 | 0 |  | 2745 |  | 159300 | 0 | -2745 | 0%
12/03/24 |  | 01/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000190 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 755 | 0 | -30 | 0%
12/03/24 |  | 01/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000191 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4460 | 0 | -30 | 0%
07/15/24 |  | 01/03/25 | Closed | Brittney Antoinette Hickman | George Edwin Jacob |  | Arcangelo Fanelli, Brittney Antoinette Hickman, Bryan Mullen, George Edwin Jacob, Tony Dean Skipworth |  |  | Brittney Antoinette Hickman, Bryan Mullen, Jay Daniel De Leon, Tony Dean Skipworth |  |  | Arcangelo Fanelli | TX-DAL | Atmos Energy | J00018666 | ACI / APIC Controllers Upgrade | Closed | 100% | 146.9% | 78.6 | -36.9 | 8945.5 | 15347.5 | -46.95% | 8945.5 | 0 | 115.5 | 10413.75 | 0 |  | 15347.5 |  | 80837.4 | 15404.4 | 56.9 | 0.3694%
12/04/24 |  | 01/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000195 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 6312 | 0 | -30 | 0%
12/04/24 |  | 01/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000198 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 3568 | 0 | -60 | 0%
12/04/24 |  | 01/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Dedric Bowens, Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200000200 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 10704 | 0 | -60 | 0%
12/04/24 |  | 01/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, David Lenihan, Dedric Bowens, Jarshawn Newsome, Kai Rose |  |  | N/A | N/A | Houston ISD | 200000201 | N/A | Closed | 0% | 0% | 0 | -11 | 0 | 330 | 0% | 0 | 0 | 11 | 0 | 0 |  | 330 |  | 51990 | 0 | -330 | 0%
10/07/24 |  | 01/03/25 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Ibrahim Altaweel, Jacob Sennett, Jerome Tanyag Mara, Kurt Sell, Lindie Lorraine Lamar, Rogelio Morgado-Perez, Shannon Marie Alvarado, Tom Magboo, Wyley Johnson |  |  | Ibrahim Altaweel, Rogelio Morgado-Perez, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Raul Yzaguirre Schools for Success | J00019144 | Security Assessment | Closed | 100% | 88.89% | 99 | 11 | 14912.75 | 13125 | 11.11% | 14912.75 | 0 | 88 | 250 | 0 |  | 13125 |  | 0 | 15697.48 | 2572.48 | 16.39%
05/13/24 |  | 01/06/25 | Open | Abiodun David Babasola | Christopher Puyear |  | Abiodun David Babasola, Anthony Towsley, David Babasola, Kristy L Dice, Patrick Shea Thompson, Patrick Thompson |  |  | Abiodun David Babasola, Anthony Towsley, Jeffery Giles, Joshua Osgood, Ron Loge, Sean Cowhey |  |  | Kristy L Dice | TX-DAL | Prestonwood Baptist Church | J00018067 | Cisco Unified Communications (UC) Upgrade | Closed | 100% | 99.26% | 135 | 2 | 18865 | 18150 | 1.481% | 18865 | 1 | 134 | 14430 | 0 |  | 18150 |  | 53197.46 | 36450 | 18300 | 50.21%
03/21/24 |  | 01/07/25 | Closed | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, John Stephen Kurkjian, Joshua Osgood, Sean Cowhey, Taylor Leger |  |  | Abiodun David Babasola, Hamzeh Tahat, Henry Pugsley, Kirk O'Guinn, Phillip Ma Lim |  |  | Taylor Leger | TX-DAL | BBB Serving North Central Texas | J00017771 | Collaboration Upgrade & Server Refresh | Closed | 100% | 122.2% | 80.63 | -15.37 | 10726.25 | 10225 | -19.06% | 10726.25 | 2.5 | 98.5 | 8125 | 8222.5 |  | 10225 |  | 7738.5 | 15053.2 | -3394.3 | -22.55%
10/01/24 |  | 01/07/25 | Closed | Joanna Herrera | Bryan Brown |  | Joanna Herrera, Steve J Rodriguez, Xavier A Trevino |  |  | Blake Nadler, James Danner, Joanna Herrera, John Senkulics |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00019111 | Ewing Halsell - Ceiling Projector Extron | Closed | 0% | 0% | 0 | -13.75 | 0 | 938.75 | 0% | 0 | 0 | 13.75 | 0 | 0 |  | 938.75 |  | 1321.6 | 2196.97 | 1258.22 | 57.27%
11/01/24 |  | 01/07/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Steve J Rodriguez, Xavier A Trevino |  |  | Garrett Hart, Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00019347 | SB507 FY24-25 - Hidden Meadows | Closed | 100% | 59.76% | 7.53 | 3.03 | 902.35 | 662.5 | 40.24% | 902.35 | 0 | 4.5 | 350 | 0 |  | 662.5 |  | 1742.26 | 2330.89 | 1668.39 | 71.58%
10/31/24 |  | 01/08/25 | Closed | Jason Matthew Davis | N/A |  | Dennis Odneal, Jason Matthew Davis, Larry Noble, Mark J Chambliss |  |  | Jason Matthew Davis |  |  | Dennis Odneal | TX-HOU | Sam Houston State University | J00019196 | Webex Calling Design & Small Deployment | Cancelled | 0% | 0.9696% | 103.13 | 102.13 | 14541.25 | 125 | 99.03% | 14541.25 | 0 | 1 | 125 | 0 |  | 125 |  | 0 | 0 | -125 | 0%
11/13/23 |  | 01/08/25 | Closed | Joaquin Marroquin | Edward Padron |  | Christopher Prado, Joaquin Marroquin, Xavier A Trevino |  |  | Christopher Prado, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | J00016861 | Flex Connect Migration | Closed | 100% | 90.9% | 101.49 | 9.24 | 12686.25 | 10305 | 9.104% | 12686.25 | 0 | 92.25 | 10305 | 0 |  | 10305 |  | 0 | 15497.6 | 5192.6 | 33.51%
04/22/24 |  | 01/08/25 | Closed | Lauren Lanzini Coffey | George Edwin Jacob |  | Gearld Stanley McNiel, George Edwin Jacob, Jeff Barker, Jonathan Pendrich, Karyn Hubbard, Katharine McCarley, Katherine McCarley, Lauren Lanzini Coffey, Schfronda Ford, Stan McNiel, William Chris Roome |  |  | Carlo Enriquez, Conner MacDonnell, Jay Daniel De Leon, Joan Brito, Juan Pomares, Kebret Eshetu, Lauren Lanzini Coffey, Noah Castleberry, Phillip Ma Lim, Quentin Sowels, Quy Le, Ron Loge, William Chris Roome |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | J00018080 | Exadata X10M & ZS9-2 Re-Rack/Install & Config | Closed | 100% | 36.2% | 1080 | 689 | 109807.54 | 42865 | 63.8% | 109807.54 | 0 | 391 | 41421.25 | 48015.02 |  | 42865 |  | 554068.9 | 1054350 | 963469.98 | 91.38%
10/30/24 |  | 01/09/25 | Closed | Joaquin Marroquin | Warren Wilson |  | Christi D Hubbard, Garrett Hart, Joaquin Marroquin, Larry Noble |  |  | Garrett Hart, Joaquin Marroquin |  |  | Christi D Hubbard | TX-CEN | Dripping Springs ISD | J00019339 | Cameras and Microphones Installation | Closed | 100% | 70.71% | 14.85 | 4.35 | 1731.25 | 1812.5 | 29.29% | 1731.25 | 0 | 10.5 | 0 | 0 |  | 1812.5 |  | 4747 | 4430.8 | 2618.3 | 59.09%
12/10/24 |  | 01/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | N/A |  |  | N/A | N/A | Houston ISD | 200000224 | N/A | Closed | 100% | 0% | 0 | 0 | 25.18 | 0 | 0% | 25.18 | 0 | 0 | 0 | 0 |  | 0 |  | 1005 | 0 | 0 | 0%
12/04/23 |  | 01/09/25 | Open | Richard Keith Arnst | Bryan Brown |  | Jesus Gonzalez, Kurt Sell, Mark Forehand, Monica Johnson, Richard Keith Arnst |  |  | Clinton Bennett Deason, Jackory Nash, Jeremiah Solomon, Jesus Gonzalez, Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Mark Forehand | TX-DAL | Stewart Title | J00016824 | Video Conference Solution | Closed | 100% | 229% | 83.75 | -95 | 9620.18 | 19371.25 | -113.4% | 9620.18 | 13 | 191.75 | 15591.25 | 395.33 |  | 19371.25 |  | 36998.72 | 16209.6 | -3556.98 | -21.94%
06/20/24 |  | 01/10/25 | Closed | Christina Rice | Bryan Geoghan |  | Anthony Towsley, Beau C. Devillier, Christina Rice, Christina Rice, Joel Hubbard, Joshua Hubbard, Karyn Hubbard, Lauren J Kennewell, Timothy Fain |  |  | Anthony Towsley, Christina Rice, Henry Pugsley, Joel Hubbard, Joshua Hubbard, Lauren Lanzini Coffey, Sebastian Stanislaw Salata, William Chris Roome |  |  | Lauren J Kennewell | TX-DAL | Allen ISD | J00018503 | Allen ISD: Speakers Refresh & Singlewire [Norton] | Closed | 100% | 85.52% | 235.43 | 41.83 | 23102.51 | 17623.75 | 17.77% | 23102.51 | 7.75 | 201.35 | 17065 | 860 |  | 17623.75 |  | 112710.23 | 33512.8 | 15029.05 | 44.85%
08/26/24 |  | 01/10/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Steve J Rodriguez, Warren Wilson, Xavier A Trevino |  |  | Garrett Hart, Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00019049 | SB507 FY24-25 - Request II Verkada Camera | Closed | 100% | 48.87% | 112.55 | 57.55 | 13354.25 | 7725 | 51.13% | 13354.25 | 0 | 55 | 5475 | 0 |  | 7725 |  | 14608.16 | 23332.61 | 15607.61 | 66.89%
12/12/24 |  | 01/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Dedric Bowens, Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200000244 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 3186 | 0 | -60 | 0%
12/12/24 |  | 01/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200000245 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 11554 | 0 | -60 | 0%
12/12/24 |  | 01/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Aboobiada Ali Abdalla, Dedric Bowens, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200000246 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 26550 | 0 | -150 | 0%
12/12/24 |  | 01/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Gregory Posey, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000256 | N/A | Closed | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 14581 | 0 | -105 | 0%
12/12/24 |  | 01/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Kai Rose |  |  | N/A | N/A | Houston ISD | 200000257 | N/A | Closed | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 14094 | 0 | -195 | 0%
12/12/24 |  | 01/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Dedric Bowens, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200000258 | N/A | Closed | 0% | 0% | 0 | -16.5 | 0 | 495 | 0% | 0 | 0 | 16.5 | 0 | 0 |  | 495 |  | 53595 | 0 | -495 | 0%
05/28/24 |  | 01/10/25 | Closed | Ryan Scott | David Watkins |  | Beau C. Devillier, David Watkins, Karen Grant-Dennison, Mario Sanchez, Matthew Veach, Rusty Bryan, Ryan Scott |  |  | Carlo Enriquez, Conner MacDonnell, Frank Jaimes, Joshua Osgood, Kebret Eshetu, Mario Sanchez, Matthew Veach, Moises Rodriguez, Quentin Sowels, Quy Le, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | J00018370 | THOP – Sierra Campus | Closed | 100% | 75.86% | 770.21 | 237.96 | 95578.69 | 65686.25 | 30.9% | 95578.69 | 52 | 584.25 | 56926.25 | 0 |  | 65686.25 |  | 0 | 399936.1 | 334249.85 | 83.58%
12/17/24 |  | 01/13/25 | Closed | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Ali Al-Haddad, Jose R. Duarte, Kevin Curtis, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Paul Serres |  |  | N/A | N/A | Houston ISD | 200000310 | N/A | Closed | 0% | 0% | 0 | -16.75 | 0 | 1265 | 0% | 0 | 0 | 16.75 | 0 | 0 |  | 1265 |  | 5981.6 | 800 | -465 | -58.13%
07/29/24 |  | 01/13/25 | Closed | Walter Clay Knight | Eduardo Chavez |  | Garrett Curran, Meray Doughly, Yong Kim |  |  | James Adams, Nick Varga, Walter Clay Knight |  |  | Garrett Curran | CA-LAX | Alvord USD | J00018748 | Switch Gear E-Rate | Closed | 100% | 71.84% | 707.78 | 289.78 | 83640.56 | 56152.5 | 40.94% | 83640.56 | 90.5 | 508.5 | 33062.5 | 73.69 |  | 56152.5 |  | 489445.87 | 110073.1 | 53846.91 | 48.92%
08/30/24 |  | 01/14/25 | Closed | Joaquin Marroquin | Edward Padron, Vernon Jackson |  | Christopher Prado, Felix Martinez, Joaquin Marroquin, Ming Chiu, Xavier A Trevino |  |  | Adam Morataya, Antonio Rivera, Carlo Enriquez, Carlos Carrillo, Christopher Prado, David Michael Castillo, Dionisio Oscar Medina-Marcelino, Edgardo Lopez, Felix Martinez, Francisco Hernandez, Jesus Angel Cantu, Joaquin Marroquin, Jorge Robert Rangel, Jose Salazar, Juan Arturo Gonzalez Jr, Kanoa Parman, Lance Daniel Waitschies, Ming Chiu, Rene Trejo, Richard Colby, Rodney Sincere Robinson, Roger Guerra, Sammie Simon Valero, Trevor Galloso, William Brown, William Chris Roome |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | J00014674 | Network HW - Creekside_Cullen Place_Gibson ES | Closed | 100% | 138.9% | 895.23 | -218.6 | 98065.44 | 103222.55 | -24.42% | 98065.44 | 129.65 | 1243.48 | 96088.55 | 22583.59 |  | 103222.55 |  | 882848.01 | 118065.8 | -7740.34 | -6.556%
12/17/24 |  | 01/16/25 | Closed | Michelle Duenes | N/A |  | Ashley F Freeman, Michelle Duenes, Michelle Moncayo |  |  | Gerardo Ramirez, Gregory Posey, Harold Gomez, Kai Rose , Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200000283 | N/A | Closed | 100% | 0% | 0 | -268 | 147.22 | 8040 | 0% | 147.22 | 0 | 268 | 0 | 0 |  | 8040 |  | 0 | 27616.32 | 19576.32 | 70.89%
12/17/24 |  | 01/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200000281 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 4720 | 0 | -60 | 0%
06/17/24 |  | 01/17/25 | Open | Jason Esry | Aman Khan |  | David D Tijerina, Jason Esry, Larry Noble |  |  | Jason Esry, Oscar Gonzalez, Robert Kelly, Steven Shipmon |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018519 | Switches Refresh - Rutledge ES | Closed | 100% | 84.93% | 61.23 | 10.73 | 5380.05 | 4812.5 | 17.52% | 5380.05 | 1.5 | 52 | 4722.5 | 0 |  | 4812.5 |  | 130949.59 | 7800 | 2987.5 | 38.3%
02/05/24 |  | 01/17/25 | Open | Marshall Chuck Pugh | Vernon Jackson, William Birdsong |  | Anthony Towsley, Beau C. Devillier, Conner MacDonnell, Dante Torres, Dylan Pittsinger, Jhon Genao, Joshua Hubbard, Joshua Parker, Juan Pomares, Marshall Chuck Pugh , Noah Castleberry, Noah Trump, Phillip Ma Lim, Taylor Poole, Timothy Fain, Vernon Jackson, William Birdsong |  |  | Anthony Towsley, Austen Howard, Cason Spencer, Conner MacDonnell, Dante Torres, Devin Moreno, Dylan Pittsinger, Jacob Hill, Jhon Genao, Juan Pomares, Kirk O'Guinn, Marshall Chuck Pugh, Michael McGee, Noah Castleberry, Noah Trump |  |  | Joshua Parker | TX-DAL | Ratcliff Constructors, L.P. | J00017337 | Equipment Installation | Closed | 100% | 150.1% | 69.81 | -23.94 | 5845.89 | 7258.75 | -34.29% | 5845.89 | 11 | 104.75 | 6388.75 | 0 |  | 7258.75 |  | 113640.95 | 8744.4 | 1485.65 | 16.99%
12/19/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Dedric Bowens, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200000302 | N/A | Closed | 100% | 0% | 0 | -23 | 54.92 | 690 | 0% | 54.92 | 0 | 23 | 0 | 0 |  | 690 |  | 79650 | 0 | -690 | 0%
12/19/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000303 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1510 | 0 | -30 | 0%
12/20/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200000309 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 11596 | 0 | -30 | 0%
12/20/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales, Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200000311 | N/A | Closed | 0% | 0% | 0 | -16 | 0 | 480 | 0% | 0 | 0 | 16 | 0 | 0 |  | 480 |  | 66555 | 0 | -480 | 0%
12/20/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200000313 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 15345 | 0 | -30 | 0%
12/20/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200000319 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2500 | 0 | -30 | 0%
12/18/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200000288 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1806.9 | 0 | -30 | 0%
12/18/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200000297 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2892.77 | 0 | -30 | 0%
12/20/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200000306 | N/A | Closed | 100% | 0% | 0 | -0.5 | 23.57 | 15 | 0% | 23.57 | 0 | 0.5 | 0 | 0 |  | 15 |  | 1170 | 0 | -15 | 0%
12/20/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200000321 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 500 | 0 | -30 | 0%
12/20/24 |  | 01/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | N/A |  |  | Neel Shah | TX-HOU | Lone Star College System | 200000322 | N/A | Closed | 100% | 0% | 0 | 0 | 51.35 | 0 | 0% | 51.35 | 0 | 0 | 0 | 0 |  | 0 |  | 6210 | 0 | 0 | 0%
07/10/24 |  | 01/17/25 | Open | Walter Clay Knight | N/A |  | Aaron Christopher Pfeifer, George Delp, Jessica Anderson |  |  | Aaron Christopher Pfeifer, Walter Clay Knight |  |  | Jessica Anderson | US-SP | LTC Connect | J00018661 | Lawful Intercept Services T&E | Closed | 0% | 0% | 0 | -23 | 0 | 3075 | 0% | 0 | 0 | 23 | 2568.75 | 0 |  | 3075 |  | 0 | 0 | -3075 | 0%
11/05/24 |  | 01/22/25 | Closed | Brittney Antoinette Hickman | Daniel Snyder |  | Brittney Antoinette Hickman, David D Tijerina, Larry Noble, Saravanan Lakshmanan |  |  | Brittney Antoinette Hickman, Phillip Ma Lim, Tavis Jackson |  |  | David D Tijerina | TX-CEN | University of Texas - Austin | J00019373 | Access Points (APs) Installation Dallas Campus | Closed | 100% | 29.87% | 35.15 | 25.65 | 3335.95 | 1085 | 72.97% | 3335.95 | 1 | 10.5 | 60 | 0 |  | 1085 |  | 0 | 5043.56 | 3958.56 | 78.49%
12/23/24 |  | 01/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200000337 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 22300 | 0 | -150 | 0%
12/23/24 |  | 01/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales, Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200000340 | N/A | Closed | 0% | 0% | 0 | -13.5 | 0 | 405 | 0% | 0 | 0 | 13.5 | 0 | 0 |  | 405 |  | 47072 | 0 | -405 | 0%
12/23/24 |  | 01/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200000341 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8920 | 0 | -30 | 0%
12/23/24 |  | 01/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Andrew Comeaux, Dedric Bowens, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200000342 | N/A | Closed | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 15930 | 0 | -195 | 0%
12/23/24 |  | 01/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200000343 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1835.46 | 0 | -30 | 0%
01/13/25 |  | 01/22/25 | Open | Ryan Scott | N/A |  | George Delp, Jessica Anderson, Ryan Scott |  |  | Ryan Scott |  |  | Jessica Anderson | US-SP | Bluegrass Network | 200000278 | N/A | Cancelled | 0% | 3.75% | 20 | 19.25 | 2660 | 93.75 | 96.25% | 2660 | 0 | 0.75 | 0 | 0 |  | 93.75 |  | 0 | 0 | -93.75 | 0%
12/24/24 |  | 01/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Dedric Bowens, Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200000354 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 1400 | 0 | -60 | 0%
09/11/23 |  | 01/23/25 | Open | Robert McIver | Rogelio Dominguez |  | Amy Martinez-Nagy, Daniel Saenz, Eric Rodriguez, Garrett Hart, Robert McIver, Warren Wilson |  |  | Francisco Hernandez, Garrett Hart, Joaquin Garcia, Oscar Garcia, Robert McIver, Romar Roca, Trevor Galloso |  |  | Eric Rodriguez | TX-SOUT | City Of Rio Grande | J00016339 | Public Safety Physical Security | Closed | 0% | 0% | 0 | -159 | 0 | 19150 | 0% | 0 | 17 | 176 | 17415 | 0 |  | 19150 |  | 67798.43 | 107155.36 | 88005.36 | 82.13%
09/11/23 |  | 01/23/25 | Open | Robert McIver | Rogelio Dominguez |  | Amy Martinez-Nagy, Daniel Saenz, Eric Rodriguez, Garrett Hart, Robert McIver, Warren Wilson |  |  | Francisco Hernandez, Garrett Hart, Joaquin Garcia, Oscar Garcia, Robert McIver, Romar Roca, Trevor Galloso |  |  | N/A | N/A | City Of Rio Grande | J00016339 | Public Safety Physical Security | Closed | 100% | 14.65% | 232.09 | 198.09 | 25345.93 | 5650 | 85.35% | 25345.93 | 0 | 34 | 0 | 0 |  | 5650 |  | 67798.43 | 107155.36 | 101505.36 | 94.73%
09/29/23 |  | 01/24/25 | Open | Jennifer Soliz | Timothy Ramsey |  | Jason Espino, Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Jason Espino, Jennifer Soliz |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00016067 | JMUX Firepower Deployment | Closed | 100% | 147.7% | 207.5 | -96.5 | 30087.5 | 45250 | -46.51% | 30087.5 | 2.5 | 306.5 | 44750 | 15 |  | 45250 |  | 416678.09 | 54186 | 8921 | 16.46%
08/23/24 |  | 01/24/25 | Open | Jennifer Soliz | Timothy Ramsey |  | Jason Espino, Jennifer Soliz, Larry Noble, Lonnie Owens, Timothy Ramsey |  |  | Jason Espino, Jennifer Soliz |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00018874 | SSN to OT Migration | Closed | 100% | 71.48% | 296.25 | 84.5 | 42956.25 | 30543.75 | 28.52% | 42956.25 | 0 | 211.75 | 17000 | 0 |  | 30543.75 |  | 0 | 67656 | 37112.25 | 54.85%
03/05/24 |  | 01/24/25 | Closed | Joanna Herrera | David Escamilla |  | David D Tijerina, Joanna Herrera, Kurt Sell |  |  | Joanna Herrera, Juan Saenz |  |  | David D Tijerina | TX-CEN | Bexar County | J00018478 | AWS Professional Services | Closed | 100% | 104.2% | 26.4 | -1.1 | 3540 | 3687.5 | -4.167% | 3540 | 0 | 27.5 | 3687.5 | 0 |  | 3687.5 |  | 0 | 4850 | 1162.5 | 23.97%
12/27/24 |  | 01/24/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Harold Gomez, Jarshawn Newsome, Josue Iglesias, Lorenzo Hernandez, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200001497 | N/A | Closed | 0% | 0% | 0 | -153.5 | 0 | 4605 | 0% | 0 | 0 | 153.5 | 0 | 0 |  | 4605 |  | 414185 | 15000 | 10395 | 69.3%
12/25/24 |  | 01/24/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales, Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200000550 | N/A | Closed | 0% | 0% | 0 | -8 | 0 | 240 | 0% | 0 | 0 | 8 | 0 | 0 |  | 240 |  | 45867 | 0 | -240 | 0%
12/25/24 |  | 01/24/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200000551 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 2685 | 0 | -60 | 0%
12/25/24 |  | 01/24/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Dedric Bowens, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200000559 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 900 | 0 | -60 | 0%
12/26/24 |  | 01/24/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss, Meredith A Richardson, Michelle Duenes, Michelle Moncayo |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200000878 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1726 | 0 | -30 | 0%
12/27/24 |  | 01/24/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gerardo Ramirez, Gregory Posey, Harold Gomez, Oscar Nunez, Samsoni Jean Claude, Valentin Vasquez |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001496 | N/A | Closed | 0% | 0% | 0 | -68 | 0 | 2040 | 0% | 0 | 0 | 68 | 0 | 0 |  | 2040 |  | 220280 | 0 | -2040 | 0%
07/01/24 |  | 01/27/25 | Closed | Abiodun David Babasola | William Birdsong |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Jesus Escobedo, Joshua Parker, Nazario Armenta Barraza, Timothy Fain |  |  | Abiodun David Babasola, Moises Rodriguez |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00018492 | Richardson ISD - Wireless Bridges | Closed | 100% | 33.33% | 45 | 30 | 5805 | 2125 | 66.67% | 5805 | 0 | 15 | 250 | 0 |  | 2125 |  | 30640.88 | 8776.8 | 6651.8 | 75.79%
12/05/24 |  | 01/27/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Justin Smallwood, Kord Mullins, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao |  |  | N/A | N/A | Houston ISD | 200000227 | N/A | Closed | 0% | 0% | 0 | -30 | 0 | 3440 | 0% | 0 | 2.5 | 32.5 | 150 | 0 |  | 3440 |  | 24140.9 | 1600 | -1840 | -115%
06/17/24 |  | 01/27/25 | Closed | Joaquin Marroquin | Aman Khan, Christopher Puyear |  | Aman Khan, Amy Martinez-Nagy, Christopher Puyear, David D Tijerina, Ernesto Gonzalez, Hamzeh Tahat, Joaquin Marroquin, Larry Noble |  |  | Adam Felix, Alexander Chambless, Ernesto Gonzalez, Hamzeh Tahat, Joaquin Marroquin, Julio Perez, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Robert Jones |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018444 | Portables - Austin Community College | Closed | 100% | 121.9% | 149.08 | -28.67 | 13780.19 | 16438.75 | -19.23% | 13780.19 | 4 | 181.75 | 16198.75 | 3565 |  | 16438.75 |  | 314142.09 | 16500 | -3503.75 | -21.23%
09/05/24 |  | 01/27/25 | Closed | Joaquin Marroquin | Bryan Brown |  | Amy Martinez-Nagy, Brian Newman, Brian Newman, David D Tijerina, Joaquin Marroquin, Larry Noble |  |  | Brian Newman, Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018818 | Portables Atlas Speakers - RBMS Campus | Closed | 100% | 76.18% | 34.13 | 8.13 | 4632.25 | 3445 | 23.82% | 4632.25 | 0 | 26 | 2260 | 0 |  | 3445 |  | 20556.59 | 13199.02 | 9754.02 | 73.9%
09/05/24 |  | 01/27/25 | Closed | Joaquin Marroquin | Bryan Brown |  | Brian Newman, Brian Newman, David D Tijerina, Joaquin Marroquin, Larry Noble |  |  | Brian Newman, Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018820 | Portables Atlas Speakers - VRHS Campus | Closed | 100% | 72.4% | 48 | 13.25 | 6470.85 | 4553.75 | 27.6% | 6470.85 | 0 | 34.75 | 3118.75 | 0 |  | 4553.75 |  | 36401.27 | 20757.11 | 16203.36 | 78.06%
09/09/24 |  | 01/27/25 | Closed | Joaquin Marroquin | Bryan Brown |  | Brian Newman, Brian Newman, David D Tijerina, Joaquin Marroquin, Larry Noble |  |  | Brian Newman, Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018821 | Portable Atlas Speakers - CPHS Campus | Closed | 100% | 146% | 38.88 | -17.87 | 5328.66 | 7693.75 | -45.96% | 5328.66 | 0 | 56.75 | 2353.75 | 0 |  | 7693.75 |  | 26632.45 | 15700.29 | 8006.54 | 51%
12/04/24 |  | 01/27/25 | Open | Richard Keith Arnst | Bryan Brown |  | Christopher Garcia, Lauren J Kennewell, Richard Keith Arnst, Robert Lavender |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | Medical City Healthcare | 200000178 | N/A | Closed | 100% | 87.39% | 37.19 | 10.69 | 4070.36 | 3807.5 | 28.74% | 4070.36 | 6 | 32.5 | 690 | 0 |  | 3807.5 |  | 8773.45 | 6638.4 | 2830.9 | 42.64%
08/19/24 |  | 01/27/25 | Open | Ryan Scott | George Delp |  | Jeff Barker, Jessica Anderson, Ryan Scott |  |  | Carlo Enriquez, Rafael Rodriguez-Vargas, Ryan Scott |  |  | Jessica Anderson | US-SP | Duo County Telephone Coop | J00017979 | NCS 55A2 Series Router-Liberty Location | Closed | 100% | 57.58% | 15.63 | 6.63 | 1741.25 | 1070 | 42.42% | 1741.25 | 0 | 9 | 507.5 | 0 |  | 1070 |  | 60512 | 2741.2 | 1671.2 | 60.97%
05/31/24 |  | 01/28/25 | Open | Jennifer Soliz | Christopher Puyear, Daniel Snyder |  | George McGann, Hannah Paul, Jennifer Soliz, Larry Noble |  |  | George McGann, Jennifer Soliz |  |  | Hannah Edmunds | TX-CEN | Workforce Solutions Capital Area | J00018372 | Unified Communications - South Office Relocation | Closed | 100% | 45.43% | 75.94 | 41.44 | 8895 | 4642.5 | 54.57% | 8895 | 0 | 34.5 | 3552.5 | 0 |  | 4642.5 |  | 0 | 11954.4 | 7311.9 | 61.16%
10/04/24 |  | 01/28/25 | Open | Richard Keith Arnst | N/A |  | Christopher Butler, Jorge Ortiz Cardozo, Randy Schamberger, Richard Keith Arnst |  |  | Jorge Ortiz Cardozo, Ming Chiu, Richard Keith Arnst |  |  | Randy Schamberger | FL | Collier County Board of County Commissioners | J00019154 | Multicast Professional Services T&E | Closed | 0% | 0% | 0 | -17.75 | 0 | 2233.75 | 0% | 0 | 0 | 17.75 | 375 | 0 |  | 2233.75 |  | 0 | 0 | -2233.75 | 0%
04/22/24 |  | 01/28/25 | Open | Richard Keith Arnst | Albert H Nguyen, Bryan Brown |  | Albert H Nguyen, Christopher Garcia, Larry Noble, Lindie Lorraine Lamar, Richard Keith Arnst |  |  | Baq Alsaedi, Clinton Bennett Deason, Devon LeMoine, Jeremiah Solomon, Jesus Gonzalez, Jose R. Duarte, Nathan Dao, Richard Keith Arnst |  |  | Lindie Lamar | TX-HOU | Prime Contractors | J00018010 | SJES & SLC | Closed | 100% | 54.63% | 199.08 | 105.33 | 18515.84 | 10231.25 | 52.91% | 18515.84 | 15 | 108.75 | 4136.25 | 0 |  | 10231.25 |  | 86162.78 | 25074.5 | 14843.25 | 59.2%
12/04/24 |  | 01/30/25 | Open | LaQisha Marshall | Christopher Puyear, Daniel Snyder |  | Christi D Hubbard, John Stephen Kurkjian, LaQisha Marshall |  |  | Alexander Chambless, John Stephen Kurkjian, LaQisha Marshall, Robert Jones, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200000182 | N/A | Closed | 100% | 34.43% | 181.53 | 119.03 | 18061.55 | 6895 | 65.57% | 18061.55 | 0 | 62.5 | 0 | 323.35 |  | 6895 |  | 73966.4 | 25826.8 | 18608.45 | 72.05%
12/13/24 |  | 01/30/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, LaQisha Marshall |  |  | Adam Felix, Grayson McClanahan, Grayson Rigsby, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200000267 | N/A | Closed | 100% | 86.29% | 39.69 | 5.44 | 2897.5 | 2526.25 | 13.71% | 2897.5 | 0 | 34.25 | 0 | 0 |  | 2526.25 |  | 0 | 4015.6 | 1489.35 | 37.09%
11/22/24 |  | 01/30/25 | Closed | Walter Clay Knight | N/A |  | David Escamilla, Jaclyn Pias, Kurt Sell, Mohammed Almoola, Saif Qaissi |  |  | Ahmed Jameel, Baq Alsaedi, Cory Bradfield, James Adams, Kevin Curtis, Kolawole Ayeni, Mohammed Almoola, Paul Serres, Saif Qaissi, Walter Clay Knight |  |  | Jaclyn Pias | TX-HOU | PNC Bank | J00019357 | 2024: Data Center Refresh Project | Closed | 100% | 111% | 171.78 | 14.78 | 20851.45 | 23710 | 8.604% | 20851.45 | 33.75 | 190.75 | 4346.25 | 0 |  | 23710 |  | 0 | 0 | -23710 | 0%
12/05/24 |  | 01/31/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, James Adams, Nicolas Garakani |  |  | N/A | N/A | Houston ISD | 200000211 | N/A | Closed | 0% | 0% | 0 | -15 | 0 | 2235 | 0% | 0 | 4.5 | 19.5 | 270 | 0 |  | 2235 |  | 24140.9 | 1600 | -635 | -39.69%
12/05/24 |  | 01/31/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Justin Smallwood, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | 200000225 | N/A | Closed | 0% | 0% | 0 | -17 | 0 | 1867.5 | 0% | 0 | 2.5 | 19.5 | 150 | 0 |  | 1867.5 |  | 3280 | 800 | -1067.5 | -133.4%
05/02/22 |  | 01/31/25 | Closed | Jim Blackwell | Albert H Nguyen, Mark J Chambliss |  | Ahmed Jameel, Albert H Nguyen, Aleksei Lavrushenkov, Ashley F Freeman, Jim Blackwell, Julio C Montoya, Kord Mullins, Larry Noble, Mark J Chambliss, Mustafa Al-Tamimi, Nathan Dao, Robert Brim, Syed Zaidi |  |  | Aaron Johns, Aleksei Lavrushenkov, Andy Alvarenga, Andy Pham, Baq Alsaedi, Bryant Bush, Carson Broussard, Craig St. Rose, David Dobbs, Devon LeMoine, Donald Muskaj, Hector Rivera, Jaime Flores, James Adams, Jeff Ogbor, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Jose R. Duarte, Julio C Montoya, Justin Higgins, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Mustafa Al-Tamimi, Nathan Dao, Ni |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00012760 | Crawford HS #12 - Network & Wireless | Closed | 100% | 265% | 452.22 | -640.03 | 29798.68 | 80105.2 | -141.5% | 29798.68 | 106.17 | 1198.42 | 72760 | 4981.081 |  | 80105.2 |  | 1398963.64 | 64687.64 | -20398.641 | -31.53%
10/30/23 |  | 01/31/25 | Closed | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Craig St. Rose, Craig St. Rose, Firas Abood, Jerald Garner, Jim Blackwell, Kord Mullins, Larry Noble, Leonid G Kamenker, Leonid Kamenker, Moe Izaks |  |  | Andy Pham, Cory Bradfield, Craig St. Rose, David Dobbs, Hector Rivera, Jaime Flores, James Adams, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Justin Cornish, Kord Mullins, Mohammed Al-Shaikhli, Nicolas Garakani |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016805 | Compute in Colo (New HX Cluster) | Closed | 100% | 183.5% | 98.08 | -40.92 | 12467.04 | 18105 | -41.72% | 12467.04 | 41 | 180 | 8880 | 0 |  | 18105 |  | 1012464.19 | 18755.2 | 650.2 | 3.467%
12/08/23 |  | 01/31/25 | Open | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Firas Abood, Jim Blackwell, Larry Noble |  |  | Ali Al-Haddad, Andy Pham, Anthony Lange, Bryant Bush, Cory Bradfield, David Dobbs, Hector Rivera, Jerald Garner, Jim Blackwell, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nicolas Garakani, Paul Serres |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016827 | Dell Powerscale Deployment | Closed | 100% | 87.09% | 182.2 | 70.03 | 21839.6 | 15891.45 | 38.44% | 21839.6 | 46.5 | 158.67 | 9928.95 | 136.5 |  | 15891.45 |  | 2758826.44 | 35341.2 | 19313.25 | 54.65%
04/15/24 |  | 01/31/25 | Open | Jim Blackwell | Aman Khan, Firas Abood |  | Aman Khan, Ashley F Freeman, Firas Abood, Jim Blackwell, Jorge Ortiz Cardozo, Larry Noble, Moe Izaks, Mohaymen Sodi |  |  | Jim Blackwell, Jorge Ortiz Cardozo, Mohaymen Sodi, Nicolas Garakani |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018027 | Cisco Core Network Refresh | Closed | 100% | 53.33% | 236.25 | 110.25 | 26411.25 | 15587.5 | 46.67% | 26411.25 | 0 | 126 | 14462.5 | 0 |  | 15587.5 |  | 306255.45 | 39640.64 | 24053.14 | 60.68%
04/29/24 |  | 01/31/25 | Closed | Jim Blackwell | Aman Khan, Firas Abood |  | Aman Khan, Ashley F Freeman, Cory Bradfield, Cory Bradfield, Firas Abood, Jim Blackwell, Jorge Ortiz Cardozo, Larry Noble, Moe Izaks, Mohammad Jilani, Mohaymen Sodi, Ron Loge |  |  | Andy Pham, Baq Alsaedi, Cory Bradfield, David Dobbs, Hector Rivera, James Adams, Jesus Gonzalez, Jim Blackwell, Jorge Ortiz Cardozo, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammad Jilani, Mohammed Al-Shaikhli, Mohaymen Sodi, Nathan Dao, Paul Serres, Ron Loge |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018191 | ACI - Cisco Core Network Refresh | Closed | 100% | 72.37% | 505.4 | 167.15 | 65839 | 41710 | 33.07% | 65839 | 27.5 | 365.75 | 28815 | 0 |  | 41710 |  | 6535.68 | 108359.6 | 66649.6 | 61.51%
09/20/23 |  | 01/31/25 | Open | Marshall Chuck Pugh | Christopher Puyear |  | Beau C. Devillier, Bryan Mullen, David Watkins, Jonathan Weir, Jonathan Weir, Kristy L Dice, Marshall Chuck Pugh |  |  | Bryan Mullen, Jonathan Weir, Marshall Chuck Pugh |  |  | Kristy L Dice | TX-DAL | Lewisville ISD | J00019386 | Ring Architecture – Redesign | Not started | 90% | 112.9% | 52.5 | -6.75 | 6247.5 | 7406.25 | -12.86% | 6247.5 | 0 | 59.25 | 0 | 0 |  | 7406.25 |  | 0 | 10335.6 | 2929.35 | 28.34%
05/20/24 |  | 01/31/25 | Open | Richard Keith Arnst | Mark J Chambliss |  | John Stephen Kurkjian, Monica Johnson, Richard Keith Arnst |  |  | John Stephen Kurkjian, Richard Keith Arnst |  |  | Monica Johnson | TX-HOU | Port of Houston Authority | J00018313 | Verizon SIP Migration | Closed | 100% | 104.7% | 75 | -3.5 | 10575 | 10712.5 | -4.667% | 10575 | 0 | 78.5 | 8762.5 | 0 |  | 10712.5 |  | 0 | 13879.6 | 3167.1 | 22.82%
06/28/24 |  | 01/31/25 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Wyley Johnson |  | Christopher Kutalek, Dhulfiqar Al Hashimi, Kord Mullins, Larry Noble, Shannon Marie Alvarado |  |  | Dhulfiqar Al Hashimi, Kord Mullins, Ron Loge, Shannon Marie Alvarado |  |  | Christopher Kutalek | TX-HOU | City of Webster | J00017307 | Firewall Implementation | Closed | 100% | 94.2% | 125.8 | 7.3 | 18466.49 | 17052.5 | 5.803% | 18466.49 | 0 | 118.5 | 17052.5 | 0 |  | 17052.5 |  | 39042.7 | 25041.48 | 7988.98 | 31.9%
05/27/24 |  | 01/31/25 | Open | Shannon Marie Alvarado | Mark J Chambliss |  | Larry Noble, Lindie Lorraine Lamar, Patrick Joseph Palermo, Shannon Marie Alvarado |  |  | Patrick Joseph Palermo, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Lumberton ISD | J00018320 | UC Upgrade | Closed | 100% | 95.34% | 91.25 | 4.25 | 12866.25 | 15652.5 | 4.658% | 12866.25 | 0 | 87 | 15277.5 | 0 |  | 15652.5 |  | 0 | 16786.8 | 1134.3 | 6.757%
11/05/24 |  | 02/05/25 | Closed | Joanna Herrera | Bryan Brown |  | Joanna Herrera, Steve J Rodriguez, Xavier A Trevino |  |  | Jeremiah Solomon, Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00019368 | Amplifier Replacement IDEA Hardy - Cafeteria | Closed | 100% | 29.07% | 6.88 | 4.88 | 585 | 200 | 70.93% | 585 | 0 | 2 | 0 | 0 |  | 200 |  | 579.54 | 986.8 | 786.8 | 79.73%
02/06/23 |  | 02/05/25 | Closed | Media Alsewaili | Emilio Carrillo, Timothy Ramsey |  | Ernesto Gonzalez, Hannah Paul, Ibrahim Altaweel, Larry Noble, Lonnie Owens, Media Alsewaili, Raul Velazquez, Rogelio Morgado-Perez, Ronan Empig, Tom Magboo |  |  | Ernesto Gonzalez, James Danner, Media Alsewaili, Raul Velazquez |  |  | Hannah Edmunds | TX-CEN | Edgewood ISD | J00014776 | Professional Services for Network Assessment | Closed | 0% | 0% | 0 | -255.4 | 0 | 31762.5 | 0% | 0 | 0 | 255.4 | 31762.5 | 0 |  | 31762.5 |  | 0 | 235305 | 203542.5 | 86.5%
12/17/24 |  | 02/07/25 | Open | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Ali Al-Haddad, James Adams, Mohammed Al-Shaikhli, Robert Brim |  |  | N/A | N/A | Houston ISD | 200000316 | N/A | Closed | 0% | 0% | 0 | -23 | 0 | 2725 | 0% | 0 | 4 | 27 | 240 | 0 |  | 2725 |  | 0 | 1350 | -1375 | -101.9%
04/01/24 |  | 02/07/25 | Open | Brian Willery | Majid Shirzadeh |  | Beau C. Devillier, Brian Willery, Lauren J Kennewell, Majid Shirzadeh, Sattar Mohseni, Vitalii Stepanchenko |  |  | Austen Howard, Bradley Buchanan, Brian Willery, Carlo Enriquez, Cason Spencer, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jeffery Alan Jorzig, Jhon Genao, Kebret Eshetu, Kirk O'Guinn, Michael McGee, Noah Castleberry, Noah Trump, Patrick Shea Thompson, Phillip Ma Lim, Quentin Sowels, Quy Le, Remijio Hernandez, Sean Cowhey, Tavis Jackson, Vitalii Stepanchenko, William Chris Roome |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00017669 | Evans MS & Finch ES Refresh | Closed | 100% | 130.5% | 410.91 | -98.84 | 38374.82 | 43945 | -24.05% | 38374.82 | 26.5 | 536.25 | 39453.75 | 0 |  | 43945 |  | 1179495.2 | 58936.44 | 14991.44 | 25.44%
05/13/24 |  | 02/07/25 | Open | Brian Willery | Majid Shirzadeh |  | Beau C. Devillier, Bradley Buchanan, Brian Willery, Dante Torres, Joshua Hubbard, Kirk O'Guinn, Lauren J Kennewell, Majid Shirzadeh, Patrick Shea Thompson, Patrick Thompson, Vitalii Stepanchenko |  |  | Brian Willery, Carlo Enriquez, Dante Torres, Devin Moreno, Dylan Pittsinger, Frank Jaimes, Kebret Eshetu, Michael McGee, Patrick Shea Thompson, Phillip Ma Lim, Quentin Sowels, Vitalii Stepanchenko, William Chris Roome |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00018312 | High School Gym Wireless | Closed | 100% | 84.92% | 139.08 | 24.98 | 12428.1 | 10944.75 | 17.96% | 12428.1 | 4 | 118.1 | 9767.25 | 0 |  | 10944.75 |  | 120102.62 | 19573.2 | 8628.45 | 44.08%
01/09/25 |  | 02/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez, Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200001559 | N/A | Closed | 0% | 0% | 0 | -20 | 0 | 600 | 0% | 0 | 0 | 20 | 0 | 0 |  | 600 |  | 222900 | 0 | -600 | 0%
12/04/24 |  | 02/07/25 | Open | Richard Keith Arnst | Bryan Brown |  | Lauren J Kennewell, Richard Keith Arnst, Robert Lavender |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | Medical City Healthcare | 200000179 | N/A | Closed | 100% | 30.63% | 84.06 | 62.31 | 9141.8 | 2993.75 | 74.13% | 9141.8 | 4 | 25.75 | 420 | 0 |  | 2993.75 |  | 5960.27 | 14806.4 | 11812.65 | 79.78%
07/12/24 |  | 02/07/25 | Open | Richard Keith Arnst | Mark J Chambliss |  | Mark J Chambliss, Monica Johnson, Richard Keith Arnst, Thomas Francis LoMonaco |  |  | Kristian Martell, Patrick Joseph Palermo, Richard Keith Arnst, Thomas Francis LoMonaco |  |  | Monica Johnson | TX-HOU | Port of Houston Authority | J00018659 | Webex Contact Center (CC) Implementation | Closed | 100% | 128.9% | 104.38 | -30.12 | 14717.5 | 23540 | -28.86% | 14717.5 | 0 | 134.5 | 17357.5 | 0 |  | 23540 |  | 14950.9 | 19201.2 | -4338.8 | -22.6%
11/18/24 |  | 02/10/25 | Open | Robert McIver | Warren Wilson |  | Daniel Saenz, Garrett Hart, Robert McIver, Warren Wilson |  |  | Garrett Hart, Robert McIver |  |  | Daniel Saenz | TX-SOUT | City Of Rio Grande | 200000127 | N/A | Closed | 100% | 142.9% | 9.8 | -4.2 | 1145.4 | 2150 | -42.86% | 1145.4 | 0 | 14 | 0 | 0 |  | 2150 |  | 610.1 | 4436.44 | 2286.44 | 51.54%
05/27/24 |  | 02/10/25 | Open | Tray Giddens | Mark J Chambliss |  | Ashley F Freeman, Larry Noble, Ming Chiu, Tray Giddens |  |  | Ming Chiu, Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00018350 | Attendant Console Advanced Installation | Closed | 100% | 145.3% | 23.75 | -10.75 | 3348.75 | 4695 | -45.26% | 3348.75 | 0 | 34.5 | 3037.5 | 0 |  | 4695 |  | 0 | 5226.92 | 531.92 | 10.18%
06/23/23 |  | 02/10/25 | Closed | Walter Clay Knight | Bryan Brown |  | Aaron Johns, Aaron Johns, Ashley F Freeman, Christopher Garcia, Jesus Gonzalez, Justin Higgins, Justin Higgins, Shiraz Humayun, Walter Clay Knight |  |  | Clinton Bennett Deason, Jeremiah Solomon, Walter Clay Knight |  |  | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00015633 | Correctional Health Video Plus Room Installation | Closed | 100% | 60.23% | 42.75 | 17 | 3751.24 | 2168.75 | 39.77% | 3751.24 | 0 | 25.75 | 468.75 | 0 |  | 2168.75 |  | 11177 | 4908.76 | 2740.01 | 55.82%
09/30/24 |  | 02/10/25 | Closed | Walter Clay Knight | Bryan Brown |  | Dennis Odneal |  |  | Clinton Bennett Deason, Jeremiah Solomon, Miguel Reed, Nathan Dao, Walter Clay Knight |  |  | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00019027 | LBJ Executive Conf Room – Interactive Display | Closed | 100% | 455.6% | 2.25 | -6.5 | 327.46 | 821.25 | -288.9% | 327.46 | 1.5 | 10.25 | 90 | 0 |  | 821.25 |  | 6513.94 | 1609.88 | 788.63 | 48.99%
09/30/24 |  | 02/10/25 | Closed | Walter Clay Knight | Bryan Brown |  | Dennis Odneal |  |  | Clinton Bennett Deason, Jeremiah Solomon, Miguel Reed, Nathan Dao, Walter Clay Knight |  |  | Dennis Odneal | TX-HOU | Harris County Hospital District | J00019027 | LBJ Executive Conf Room – Interactive Display | Closed | 0% | 0% | 0 | -2 | 0 | 150 | 0% | 0 | 0 | 2 | 150 | 0 |  | 150 |  | 6513.94 | 1609.88 | 1459.88 | 90.68%
06/19/24 |  | 02/11/25 | Closed | Joaquin Marroquin | Bryan Brown, Christopher Puyear |  | Amy Martinez-Nagy, Brian Newman, Brian Newman, David D Tijerina, Joaquin Marroquin, Joel Hubbard, Larry Noble, Rene Trejo |  |  | Brian Newman, Jennifer Soliz, Joanna Herrera, Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018343 | IP Speakers Implementation Elementary School 30 | Closed | 100% | 87.1% | 102.75 | 13.25 | 14487.75 | 12207.5 | 12.9% | 14487.75 | 0 | 89.5 | 12067.5 | 0 |  | 12207.5 |  | 206632.03 | 67046.41 | 54838.91 | 81.79%
06/10/24 |  | 02/11/25 | Closed | Joaquin Marroquin | Christopher Puyear |  | Brian Newman, Brian Newman, David D Tijerina, Joaquin Marroquin, Joel Hubbard, Larry Noble, Rene Trejo |  |  | Brian Newman, Joaquin Marroquin, Joel Hubbard, Julio Perez, Oscar Gonzalez, Rene Trejo, Robert Lavender, Steven Shipmon |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018430 | ACC IP Speakers Implementation | Closed | 100% | 94.18% | 122.11 | 27.61 | 14466.13 | 10552.5 | 22.61% | 14466.13 | 20.5 | 115 | 6300 | 0 |  | 10552.5 |  | 34927.35 | 18936 | 8383.5 | 44.27%
08/09/24 |  | 02/14/25 | Open | Christina Rice | David Watkins |  | Christina Rice, Christina Rice, David Watkins, Jayden Colon, Jesus Escobedo, Joan Brito, Jonathan Weir, Jonathan Weir, Juan Pomares, Samuel Gonzalez, Shawn Sutton |  |  | Caleb Henry, Carlo Enriquez, Christina Rice, Dante Torres, Gabriel Lantigua, Jacob Hill, Jayden Colon, Jesus Escobedo, Joan Brito, Juan Pomares, Justin Mitchell, Kendall Walls, Noah Trump, Phillip Ma Lim, Quy Le, Remijio Hernandez, Samuel Gonzalez, Sean Cowhey, Yonathan Fadel |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00018583 | Denton ISD: MIST AP Replacement - Multi-site | Closed | 100% | 61.22% | 651.3 | 277.55 | 58019.51 | 34171.25 | 42.61% | 58019.51 | 25 | 398.75 | 1885 | 0 |  | 34171.25 |  | 462003.5 | 85000 | 50828.75 | 59.8%
10/10/24 |  | 02/14/25 | Open | Christina Rice | William Birdsong |  | Christina Rice, Christina Rice, Conner MacDonnell, Lauren J Kennewell, William Birdsong |  |  | Christina Rice, Conner MacDonnell, Jhon Genao |  |  | Lauren J Kennewell | TX-DAL | Hudson Advisors | J00019183 | Hudson Advisors: Cable Work Cleanup - NY Office | Closed | 100% | 85.26% | 37.24 | 13.49 | 6458.39 | 2701.25 | 36.22% | 6458.39 | 8 | 31.75 | 1105 | 0 |  | 2701.25 |  | 0 | 6079.6 | 3378.35 | 55.57%
11/15/24 |  | 02/14/25 | Open | Marco Lish | Bryan Brown |  | Kristy L Dice, Marco Lish, Timothy Fain, William Davenport |  |  | Marco Lish, Robert Lavender |  |  | Kristy L Dice | TX-DAL | Aledo ISD | 200000137 | N/A | Closed | 100% | 70.16% | 20.31 | 11.06 | 2701.25 | 1901.25 | 54.46% | 2701.25 | 5 | 14.25 | 675 | 0 |  | 1901.25 |  | 1793.59 | 4450.88 | 2549.63 | 57.28%
01/15/25 |  | 02/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001604 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1005 | 0 | -30 | 0%
01/15/25 |  | 02/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Nathanael Morales, Samsoni Jean Claude, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200001606 | N/A | Closed | 0% | 0% | 0 | -16.5 | 0 | 495 | 0% | 0 | 0 | 16.5 | 0 | 0 |  | 495 |  | 53100 | 0 | -495 | 0%
01/15/25 |  | 02/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Nathanael Morales, Steffany Alvarez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200001607 | N/A | Closed | 0% | 0% | 0 | -18 | 0 | 540 | 0% | 0 | 0 | 18 | 0 | 0 |  | 540 |  | 53100 | 0 | -540 | 0%
01/15/25 |  | 02/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200001608 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 1240 | 0 | -45 | 0%
01/16/25 |  | 02/14/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Lorenzo Hernandez, Nathanael Morales, Pedro Cavazos, Steffany Alvarez |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200001616 | N/A | Closed | 0% | 0% | 0 | -80 | 0 | 2400 | 0% | 0 | 0 | 80 | 0 | 0 |  | 2400 |  | 0 | 4140 | 1740 | 42.03%
01/17/25 |  | 02/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001627 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 805.84 | 0 | -30 | 0%
01/17/25 |  | 02/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001628 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2500 | 0 | -30 | 0%
01/15/25 |  | 02/14/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | An Le, Blake Nadler, Celso Lopez, Isaiah Rosales, John Senkulics, Michael Torres |  |  | Gregory Tillett | TX-DAL | Whitley Penn | 200001603 | N/A | Closed | 0% | 0% | 0 | -30 | 0 | 1800 | 0% | 0 | 0 | 30 | 0 | 0 |  | 1800 |  | 0 | 2820 | 1020 | 36.17%
12/17/24 |  | 02/17/25 | Closed | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Ali Al-Haddad, Justin Smallwood, Kolawole Ayeni, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Robert Brim |  |  | N/A | N/A | Houston ISD | 200000315 | N/A | Closed | 100% | 0% | 0 | -26.25 | 12.97 | 1900 | 0% | 12.97 | 0 | 26.25 | 0 | 0 |  | 1900 |  | 0 | 1100 | -800 | -72.73%
11/18/24 |  | 02/17/25 | Closed | Walter Clay Knight | Bryan Brown |  | Christopher Garcia, Dennis Odneal |  |  | Clinton Bennett Deason, James Adams, Jeremiah Solomon, Miguel Reed, Walter Clay Knight |  |  | Dennis Odneal | TX-HOU | Harris Health System | 200000134 | N/A | Closed | 100% | 115.8% | 26.56 | -2.69 | 2642.5 | 2486.25 | -10.13% | 2642.5 | 1.5 | 30.75 | 90 | 0 |  | 2486.25 |  | 7315.34 | 4383.28 | 1897.03 | 43.28%
10/10/24 |  | 02/18/25 | Closed | LaQisha Marshall | Daniel Snyder |  | Christi D Hubbard, LaQisha Marshall, Larry Noble, Lori Endsley, Robert Jones |  |  | Adam Felix, Briliance Johnson, Dustin Aaron Lowrey, Ernesto Gonzalez, Grayson Rigsby, Julio Perez, LaQisha Marshall, Robert Jones |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00019176 | Wireless & Switch Refresh - Manor New Tech MS | Closed | 100% | 100.8% | 198.88 | -0.62 | 19441.16 | 17267.5 | -0.3117% | 19441.16 | 1 | 200.5 | 685 | 0 |  | 17267.5 |  | 348682.95 | 20492.4 | 3224.9 | 15.74%
11/20/23 |  | 02/18/25 | Open | Shannon Marie Alvarado | David Watkins, Kenneth Dieter |  | Beau C. Devillier, Mohammad Jilani, Mohaymen Sodi, Ron Loge, Saravanan Lakshmanan, Shannon Marie Alvarado, Shawn Sutton |  |  | Carlo Enriquez, Christina Rice, Mohammad Jilani, Mohaymen Sodi, Moises Rodriguez, Ron Loge, Saravanan Lakshmanan, Shannon Marie Alvarado |  |  | Shawn Sutton | TX-DAL | Ector County ISD | J00013551 | ECISD: DC Stretch & Move - Option 1 w\ WLCs (BBT) | Closed | 100% | 113.8% | 292.16 | -40.34 | 43309 | 46072.5 | -13.81% | 43309 | 0 | 332.5 | 33523.75 | 0 |  | 46072.5 |  | 284981.9 | 44741.24 | -1331.26 | -2.975%
01/20/25 |  | 02/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001633 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 918 | 0 | -15 | 0%
01/20/25 |  | 02/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001634 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 44600 | 0 | -30 | 0%
01/20/25 |  | 02/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001636 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 1155 | 0 | -15 | 0%
01/20/25 |  | 02/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001638 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 863 | 0 | -15 | 0%
01/20/25 |  | 02/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001642 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 5310 | 0 | -60 | 0%
01/21/25 |  | 02/20/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Josue Iglesias, Lorenzo Hernandez, Nathanael Morales, Pedro Cavazos, Steffany Alvarez |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200001646 | N/A | Closed | 0% | 0% | 0 | -164 | 0 | 4920 | 0% | 0 | 0 | 164 | 0 | 0 |  | 4920 |  | 0 | 5148 | 228 | 4.429%
05/16/24 |  | 02/21/25 | Open | Jennifer Soliz | Ahmed Al-Zubaidi, Timothy Ramsey, Wyley Johnson |  | Abdulrahman Farhan, Ahmed Al-Zubaidi, Diana Berger, Edgar Adolfo Sotelo Ramirez, Jennifer Soliz, Timothy Ramsey, Wyley Johnson, Xavier A Trevino |  |  | Abdulrahman Farhan, Carlos Carrillo, Dishabahen Bajpai, Edgar Adolfo Sotelo Ramirez, Felix Martinez, Jaime Galvan, Jennifer Soliz, Joaquin Garcia, Muhammad Ali Raza, Oscar Garcia, Rogelio Morgado-Perez, Ruben Cantu, Timothy Sean Marcyes, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Magic Valley Electric Cooperative | J00017975 | Fortinet FortiGate NGFW and FortiSwitch | Closed | 100% | 135.6% | 245.8 | -81.95 | 33795 | 28112.5 | -33.34% | 33795 | 5.5 | 333.25 | 13522.5 | 0 |  | 28112.5 |  | 57513 | 34303.2 | 6190.7 | 18.05%
10/25/24 |  | 02/21/25 | Open | Jennifer Soliz | Christopher Puyear, Emilio Carrillo, Timothy Ramsey |  | Hannah Paul, James O Sykes, Jason Espino, Jennifer Soliz, Robert Kelly, Robert Kelly |  |  | Jason Espino, Jennifer Soliz, Robert Kelly |  |  | Hannah Edmunds | TX-CEN | Texas Parks and Wildlife | J00015594 | TPWD Colocation Services | Closed | 100% | 103.8% | 499.58 | -5.17 | 66484.33 | 70373.75 | -1.035% | 66484.33 | 14 | 518.75 | 67828.75 | 178.72 |  | 70373.75 |  | 0 | 101291.6 | 30739.13 | 30.35%
12/19/22 |  | 02/21/25 | Closed | LaQisha Marshall | Timothy Ramsey |  | Jason Espino, LaQisha Marshall, Larry Noble, Lonnie Owens |  |  | James Danner, Jason Espino, Justin Smallwood, LaQisha Marshall |  |  | Lonnie Owens | TX-CEN | John Hagee Ministries | J00013750 | F5 Refresh | Closed | 100% | 153.2% | 154 | -72.75 | 1937.5 | 34632.5 | -47.24% | 1937.5 | 9.25 | 236 | 33335 | 122.62 |  | 34632.5 |  | 435060.76 | 32213.2 | -2541.92 | -7.891%
04/29/24 |  | 02/21/25 | Closed | Lauren Lanzini Coffey | Matthew Duncan |  | Juan Saenz, Lauren Lanzini Coffey, Matthew Duncan, Neel Shah |  |  | Juan Saenz, Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00018245 | AWS Landing Zone for Healthcare | Closed | 100% | 99.3% | 257.8 | 1.8 | 35104.78 | 34115 | 0.6982% | 35104.78 | 0 | 256 | 27772.5 | 0 |  | 34115 |  | 0 | 101557.6 | 67442.6 | 66.41%
10/23/24 |  | 02/21/25 | Closed | Lauren Lanzini Coffey | Mark J Chambliss |  | Adam Felix, Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah |  |  | Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00019105 | North Austin Texas PICU/CICU Expansion | Closed | 100% | 3.028% | 16.51 | 16.01 | 1553.6 | 62.5 | 96.97% | 1553.6 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 7595.5 | 2447.2 | 2384.7 | 97.45%
10/28/24 |  | 02/21/25 | Closed | Lauren Lanzini Coffey | Mark J Chambliss |  | Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah |  |  | Lauren Lanzini Coffey, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00019232 | InformaCast Paging North Austin Campus | Closed | 100% | 28.95% | 47.5 | 33.75 | 6697.5 | 1883.75 | 71.05% | 6697.5 | 0 | 13.75 | 31.25 | 0 |  | 1883.75 |  | 933.9 | 10548.4 | 8664.65 | 82.14%
01/29/24 |  | 02/21/25 | Closed | Lauren Lanzini Coffey | Mark J Chambliss |  | Larry Noble, Lauren Lanzini Coffey, Lindie Lorraine Lamar, Mark J Chambliss |  |  | Henry Pugsley, Lauren Lanzini Coffey, Michael Garcia |  |  | Lindie Lamar | TX-HOU | Westlake Corporation | J00017231 | MS Teams Migration | Closed | 100% | 109.9% | 52.5 | -5.2 | 7192.5 | 9256 | -9.905% | 7192.5 | 0 | 57.7 | 8643.5 | 2415 |  | 9256 |  | 13100.6 | 35419.61 | 23748.61 | 67.05%
08/26/24 |  | 02/21/25 | Open | Marco Lish | Christopher Puyear |  | Beau C. Devillier, Christopher Puyear, Kristy L Dice, Marco Lish |  |  | Brian Newman, Marco Lish |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00018876 | Olympus and Avigilon Access Control Integration | Closed | 100% | 66.25% | 20 | 6.75 | 2990.3 | 1828.75 | 33.75% | 2990.3 | 0 | 13.25 | 941.25 | 0 |  | 1828.75 |  | 0 | 9213.6 | 7384.85 | 80.15%
10/22/24 |  | 02/21/25 | Open | Marco Lish | Michael Brett Beggs |  | Beau C. Devillier, Kristy L Dice, Marco Lish |  |  | Joshua Hubbard, Luis Ovalles, Marco Lish, Phillip Ma Lim |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00019260 | Video Surveillance Server Deployment | Closed | 100% | 80% | 27.5 | 8.5 | 2982.5 | 2463.75 | 30.91% | 2982.5 | 3 | 22 | 1530 | 0 |  | 2463.75 |  | 32551.47 | 4697.44 | 2233.69 | 47.55%
07/22/24 |  | 02/21/25 | Open | Marco Lish | Michael Brett Beggs |  | Beau C. Devillier, Joshua Parker, Marco Lish, Michael Brett Beggs |  |  | Marco Lish |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00018693 | Dell ME for Video | Closed | 100% | 64.39% | 26.4 | 9.4 | 3340 | 2125 | 35.61% | 3340 | 0 | 17 | 1406.25 | 0 |  | 2125 |  | 483334.92 | 5260.4 | 3135.4 | 59.6%
01/22/25 |  | 02/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200001647 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2676 | 0 | -30 | 0%
01/22/25 |  | 02/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | N/A |  |  | N/A | N/A | Houston ISD | 200001652 | N/A | Closed | 100% | 0% | 0 | 0 | 70.82 | 0 | 0% | 70.82 | 0 | 0 | 0 | 0 |  | 0 |  | 9865 | 0 | 0 | 0%
01/22/25 |  | 02/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001659 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 986.64 | 0 | -30 | 0%
01/03/25 |  | 02/21/25 | Open | Richard Keith Arnst | Bryan Brown |  | Amani Tawfik, Beau C. Devillier, Christopher Garcia, Mark Forehand, Richard Keith Arnst |  |  | Caleb Baik, Jayden Colon, Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Mark Forehand | TX-DAL | CEC Entertainment | J00019304 | Webex Video Conferencing | Closed | 100% | 91.34% | 109.75 | 9.5 | 12645.4 | 10658.75 | 8.656% | 12645.4 | 0 | 100.25 | 187.5 | 0 |  | 10658.75 |  | 78017.31 | 17594.8 | 6936.05 | 39.42%
07/10/23 |  | 02/21/25 | Open | Richard Keith Arnst | Vernon Jackson |  | Garrett Curran, Richard Keith Arnst, Vernon Jackson, Yong Kim |  |  | Conner MacDonnell, Hamzeh Tahat, Henry Pugsley, Richard Keith Arnst |  |  | Garrett Curran | CA-LAX | Westside Union School District | J00015783 | UC Upgrade | Closed | 100% | 37.47% | 486.25 | 304.05 | 67078.25 | 28145 | 62.53% | 67078.25 | 0 | 182.2 | 22788.75 | 345 |  | 28145 |  | 293248.66 | 123669.68 | 95179.68 | 76.96%
10/23/24 |  | 02/24/25 | Closed | Jason Matthew Davis | Joshua Adam Engle, Majid Shirzadeh |  | Beau C. Devillier, Jason Matthew Davis, Joshua Adam Engle, Mark Forehand |  |  | Bryan Mullen, Jason Matthew Davis, Jeffery Alan Jorzig |  |  | Mark Forehand | TX-DAL | DR Horton | J00019268 | SD-WAN Implementation | Closed | 100% | 41.02% | 318.75 | 188 | 38348.75 | 16343.75 | 58.98% | 38348.75 | 0 | 130.75 | 2687.5 | 0 |  | 16343.75 |  | 660971.2 | 40266.2 | 23922.45 | 59.41%
07/17/23 |  | 02/24/25 | Closed | Joaquin Marroquin | Bryan Brown |  | Felix Martinez, Joaquin Marroquin, Michelle Bailey, Remi Martinez-Montenegro, Rene Trejo, Steve J Rodriguez, Xavier A Trevino |  |  | Clinton Bennett Deason, David Michael Castillo, Edgardo Lopez, Joaquin Marroquin, Juan Arturo Gonzalez Jr, Remi Martinez-Montenegro, Rene Trejo, Richard Colby, Rodney Sincere Robinson, Roger Guerra |  |  | Xavier A Trevino | TX-SOUT | Del Mar College | J00015848 | Culinary AV project | Closed | 100% | 143.6% | 952.5 | -321.75 | 129993.27 | 115736.25 | -33.78% | 129993.27 | 93.5 | 1367.75 | 107138.75 | 20785.58 |  | 115736.25 |  | 380555.07 | 261981.33 | 125459.5 | 47.89%
02/10/25 |  | 02/24/25 | Open | Robert McIver | Warren Wilson |  | Daniel Saenz, Robert McIver, Warren Wilson |  |  | Garrett Hart, Robert McIver |  |  | Daniel Saenz | TX-SOUT | City Of Rio Grande | 200001890 | N/A | Closed | 100% | 102% | 9.8 | -0.2 | 1145.4 | 1625 | -2.041% | 1145.4 | 0 | 10 | 0 | 0 |  | 1625 |  | 1618.34 | 3965.92 | 2340.92 | 59.03%
09/04/24 |  | 02/25/25 | Closed | Brian Willery | N/A |  | Abdalsattar Albaghdadi, Albert H Nguyen, Brian Willery, Christopher Butler, Susan Richardson |  |  | Abdalsattar Albaghdadi, Brian Willery, Jesus Gonzalez, Julio C Montoya, Justin Smallwood, Miguel Reed, Mohammed Al-Shaikhli |  |  | Susan Richardson | TX-HOU | Electra Link | J00018956 | Wireless Equipment and Implementation | Closed | 100% | 0% | 0 | -63.5 | 136.52 | 7787.5 | 0% | 136.52 | 10.5 | 74 | 4582.5 | 0 |  | 7787.5 |  | 0 | 0 | -7787.5 | 0%
11/01/23 |  | 02/25/25 | Closed | Joanna Herrera | Bryan Brown |  | Edward Padron, Joanna Herrera, Joshua Hubbard, Joshua Osgood, Robert Lavender, Steve J Rodriguez, Xavier A Trevino |  |  | Joanna Herrera, Joel Hubbard, Robert Lavender, Sophia Quinter |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00016462 | Regional Office/midland Conference Rooms | Closed | 100% | 84.93% | 86.25 | 24 | 8234.25 | 8263.75 | 27.83% | 8234.25 | 11 | 73.25 | 7108.75 | 0 |  | 8263.75 |  | 25360.67 | 11572.4 | 3308.65 | 28.59%
01/27/25 |  | 02/26/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200001675 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 6244 | 0 | -30 | 0%
05/06/24 |  | 02/27/25 | Open | Abiodun David Babasola | Steven Walker |  | Abiodun David Babasola, Beau C. Devillier, Christopher Brown, Christopher Brown, David Babasola, Liberty Reyes Tumibay, Mark Forehand, Steven Walker |  |  | Abiodun David Babasola, Christopher Brown, Liberty Reyes Tumibay |  |  | Mark Forehand | TX-DAL | City of Richardson | J00018287 | Active Directory (AD) Assessment Remediation | Closed | 100% | 112.1% | 70 | -8.5 | 9310 | 10457.5 | -12.14% | 9310 | 0 | 78.5 | 8125 | 0 |  | 10457.5 |  | 0 | 23885.68 | 13428.18 | 56.22%
07/03/23 |  | 02/28/25 | Open | Jason Esry | Chad Hart |  | David Neal Gravatt, Jason Esry, Kurt Sell, Mario Sanchez, Susan Richardson |  |  | Ahmed Jameel, Baq Alsaedi, David Neal Gravatt, Jason Esry, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Matthew D'Ambrosio, Moises Rodriguez |  |  | Susan Richardson | TX-HOU | Daikin Comfort Technologies Manufacturing, L.P. | J00014238 | QTY 2 Wireless Controller Installs | On HOLD | 25% | 396.4% | 69 | -198.5 | 8155 | 35095 | -287.7% | 8155 | 6 | 273.5 | 34735 | 0 |  | 35095 |  | 39673.96 | 13357.6 | -21737.4 | -162.7%
10/01/24 |  | 02/28/25 | Closed | Jim Blackwell | Aman Khan |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Aman Khan, Ashley F Freeman, Brandon McMillan, Jim Blackwell, Larry Noble |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Baq Alsaedi, Bryant Bush, Craig St. Rose, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Julio C Montoya, Justin Cornish, Justin Smallwood, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Nicolas Garakani, Paul Serres |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00019113 | Middle School LAN Switches Replacement | Closed | 100% | 219.2% | 806.3 | -739.45 | 75172.48 | 134703.75 | -91.71% | 75172.48 | 221.75 | 1767.5 | 25947.5 | 0 |  | 134703.75 |  | 5053742.4 | 119306.6 | -15397.15 | -12.91%
01/11/24 |  | 02/28/25 | Closed | Lauren Lanzini Coffey | Bryan Geoghan |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, Jhon Genao, Juan Pomares, Lauren Lanzini Coffey |  |  | Gena Robbins, Jhon Genao, Lauren Lanzini Coffey, Ming Chiu |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | J00017074 | Analog Premise Deployment | Closed | 100% | 81.17% | 135.83 | 25.58 | 16602.25 | 14826.25 | 18.83% | 16602.25 | 0 | 110.25 | 14826.25 | 0 |  | 14826.25 |  | 80149.5 | 35740.8 | 20914.55 | 58.52%
01/11/24 |  | 02/28/25 | Closed | Lauren Lanzini Coffey | Bryan Geoghan |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, Lauren Lanzini Coffey |  |  | Gena Robbins, Lauren Lanzini Coffey, Ming Chiu |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | J00017224 | Webex Calling | Closed | 100% | 81.92% | 140.08 | 33.33 | 17106.9 | 15618.75 | 23.79% | 17106.9 | 8 | 114.75 | 14327.5 | 0 |  | 15618.75 |  | 12139.9 | 36826 | 21207.25 | 57.59%
04/29/24 |  | 02/28/25 | Open | Marco Lish | Warren Wilson |  | Beau C. Devillier, Christopher Pheonix Preddy, Joshua Osgood, Kristy L Dice, Marco Lish |  |  | Bradley Buchanan, Christopher Pheonix Preddy, Joshua Osgood, Marco Lish |  |  | Joshua Parker | TX-DAL | Advanced Connections, Inc. (ACI) | J00018192 | Avigilon Access Control - McKinney ES | Closed | 100% | 0.8795% | 113.69 | 112.69 | 13335.5 | 175 | 99.12% | 13335.5 | 0 | 1 | 0 | 0 |  | 175 |  | 26261.71 | 24307.6 | 24132.6 | 99.28%
04/29/24 |  | 02/28/25 | Open | Marco Lish | Warren Wilson |  | Beau C. Devillier, Christopher Pheonix Preddy, Joshua Osgood, Kristy L Dice, Marco Lish |  |  | Bradley Buchanan, Christopher Pheonix Preddy, Joshua Osgood, Marco Lish |  |  | Kristy L Dice | TX-DAL | Advanced Connections, Inc. (ACI) | J00018192 | Avigilon Access Control - McKinney ES | Closed | 0% | 0% | 0 | -125.25 | 0 | 19516.25 | 0% | 0 | 8 | 133.25 | 19036.25 | 0 |  | 19516.25 |  | 26261.71 | 24307.6 | 4791.35 | 19.71%
01/29/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200001684 | N/A | Closed | 0% | 0% | 0 | -11.5 | 0 | 345 | 0% | 0 | 0 | 11.5 | 0 | 0 |  | 345 |  | 21336 | 0 | -345 | 0%
01/29/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001685 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 5320 | 0 | -60 | 0%
01/29/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Nathanael Morales, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200001686 | N/A | Closed | 0% | 0% | 0 | -14 | 0 | 420 | 0% | 0 | 0 | 14 | 0 | 0 |  | 420 |  | 39825 | 0 | -420 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001691 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 6244 | 0 | -45 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001692 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 6001 | 0 | -15 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001693 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 31860 | 0 | -30 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias, Lorenzo Hernandez, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001694 | N/A | Closed | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 21282 | 0 | -180 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez, Oscar Nunez, Pedro Cavazos, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001695 | N/A | Closed | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 23405 | 0 | -180 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001696 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 2676 | 0 | -45 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200001697 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 6296 | 140 | 110 | 78.57%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001700 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1686 | 0 | -30 | 0%
01/30/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200001704 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1350 | 0 | -30 | 0%
01/31/25 |  | 02/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001715 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1291 | 0 | -30 | 0%
10/31/24 |  | 02/28/25 | Open | Robert McIver | N/A |  | Christopher Prado, Craig St. Rose, Craig St. Rose, Kord Mullins, Robert McIver, Xavier A Trevino |  |  | N/A |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00016689 | UP - 3x MR46 Installation | Cancelled | 10% | 0% | 13.51 | 13.51 | 1483.85 | 0 | 100% | 1483.85 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
01/29/24 |  | 02/28/25 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Daniel Saenz, Diana Berger, Eric Rodriguez, Felix Martinez, Mario Sanchez, Robert McIver |  |  | Carlos Carrillo, Daniel Dominguez, Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Jorge Robert Rangel, Mario Sanchez, Oscar Garcia, Robert McIver, Roger Guerra, Trevor Galloso |  |  | Eric Rodriguez | TX-SOUT | Webb CISD | J00017348 | District-wide Network Replacement | Closed | 0% | 0% | 0 | -282.1 | 0 | 27705 | 0% | 0 | 64.65 | 346.75 | 23058.5 | 0 |  | 27705 |  | 379123.14 | 79812.16 | 52107.16 | 65.29%
01/29/24 |  | 02/28/25 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Daniel Saenz, Diana Berger, Eric Rodriguez, Felix Martinez, Mario Sanchez, Robert McIver |  |  | Carlos Carrillo, Daniel Dominguez, Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Jorge Robert Rangel, Mario Sanchez, Oscar Garcia, Robert McIver, Roger Guerra, Trevor Galloso |  |  | N/A | N/A | Webb CISD | J00017348 | District-wide Network Replacement | Closed | 100% | 47.78% | 287.8 | 174.8 | 33157.66 | 8990 | 60.74% | 33157.66 | 24.5 | 137.5 | 1470 | 0 |  | 8990 |  | 379123.14 | 79812.16 | 70822.16 | 88.74%
04/15/24 |  | 02/28/25 | Open | Shannon Marie Alvarado | Bryan Geoghan, David Watkins |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, Bryan Mullen, David Watkins, Jeffery Alan Jorzig, Jeffery Jorzig, John Stephen Kurkjian, Shannon Marie Alvarado, William Davenport |  |  | Bryan Mullen, John Stephen Kurkjian, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | J00018079 | Multicast Routing for Paging | Closed | 100% | 69.15% | 147.51 | 45.51 | 18848.75 | 13042.5 | 30.85% | 18848.75 | 0 | 102 | 10006.25 | 0 |  | 13042.5 |  | 0 | 30826.8 | 17784.3 | 57.69%
05/27/24 |  | 02/28/25 | Open | Shannon Marie Alvarado | Bryan Brown |  | Christi D Hubbard, Christopher Garcia, Kurt Sell, Robert Lavender, Shannon Marie Alvarado |  |  | Bryant Bush, Clinton Bennett Deason, David Dobbs, Jeremiah Solomon, Jesus Gonzalez, Joel Hubbard, Rene Trejo, Robert Lavender, Shannon Marie Alvarado |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018393 | Video Conferencing with Room Schedulers | Closed | 100% | 136.6% | 559.69 | -59.06 | 73727.43 | 69626.25 | -10.55% | 73727.43 | 146 | 764.75 | 56721.25 | 331.97 |  | 69626.25 |  | 478683.7 | 95772.88 | 25814.66 | 26.95%
09/09/24 |  | 02/28/25 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Albert H Nguyen, Wyley Johnson |  | Ahmed Al-Zubaidi, Albert H Nguyen, Wyley Johnson |  |  | Baq Alsaedi, Jeffery Alan Jorzig, Justin Smallwood, Kenneth Stevenson, Mohammed Al-Shaikhli, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Tejano Center for Community Concerns | J00018948 | Change order - Additional Juniper Equipment | Closed | 100% | 146.2% | 17.78 | -3.22 | 1665.7 | 1950 | -18.11% | 1665.7 | 5 | 26 | 600 | 0 |  | 1950 |  | 17449.88 | 2427 | 477 | 19.65%
12/17/24 |  | 02/28/25 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Jason Osuna, Jesus Escobedo, Shannon Marie Alvarado |  |  | Jesus Escobedo, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | 200000346 | N/A | Closed | 100% | 59.68% | 44.4 | 23.9 | 5258.22 | 2710 | 53.83% | 5258.22 | 6 | 26.5 | 360 | 0 |  | 2710 |  | 10037 | 10987.6 | 8277.6 | 75.34%
10/02/23 |  | 02/28/25 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Saif Qaissi, Wyley Johnson |  | Ahmed Al-Zubaidi, Jason Osuna, Jorge Ortiz Cardozo, Joshua Osgood, Larry Noble, Romar Roca, Saif Qaissi, Shannon Marie Alvarado, Tony Dean Skipworth, Wyley Johnson |  |  | Jorge Ortiz Cardozo, Kyle Linder, LaQisha Marshall, Romar Roca, Ron Loge, Shannon Marie Alvarado, Tony Dean Skipworth |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | J00016566 | Alpharetta DC Design | Closed | 100% | 103.6% | 645 | -23 | 89883.5 | 89490 | -3.566% | 89883.5 | 0 | 668 | 89490 | 0 |  | 89490 |  | 0 | 142505.6 | 53015.6 | 37.2%
06/05/24 |  | 02/28/25 | Closed | Tray Giddens | N/A |  | Ahmed Jameel, Chad Hart, Dustin Huffman, Larry Noble, Nelson Garcia, Tray Giddens |  |  | Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00018474 | Middle School Network Refresh | Cancelled | 5% | 0.9297% | 1613.26 | 1598.26 | 137262.15 | 1875 | 99.07% | 137262.15 | 0 | 15 | 1875 | 0 |  | 1875 |  | 0 | 0 | -1875 | 0%
01/31/25 |  | 03/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001712 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 5310 | 0 | -90 | 0%
01/31/25 |  | 03/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Josue Iglesias, Lorenzo Hernandez, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001713 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 16350 | 0 | -150 | 0%
01/31/25 |  | 03/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001714 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 16000 | 0 | -60 | 0%
02/03/25 |  | 03/05/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200001718 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 6662 | 105 | 75 | 71.43%
02/03/25 |  | 03/05/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001719 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2124 | 0 | -30 | 0%
02/03/25 |  | 03/05/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001725 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 892 | 0 | -45 | 0%
02/03/25 |  | 03/05/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001724 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4851 | 0 | -30 | 0%
02/04/25 |  | 03/06/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Anthony Balogun, Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001730 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 7125 | 0 | -90 | 0%
02/04/25 |  | 03/06/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gregory Posey, Josue Iglesias, Lorenzo Hernandez, Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200001732 | N/A | Closed | 0% | 0% | 0 | -9.5 | 0 | 285 | 0% | 0 | 0 | 9.5 | 0 | 0 |  | 285 |  | 35440 | 0 | -285 | 0%
10/02/23 |  | 03/07/25 | Open | Brian Willery | Joshua Adam Engle, Michael Brett Beggs |  | Brian Willery, Lauren J Kennewell, Shiraz Humayun |  |  | Brian Willery, Ron Loge |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00016545 | ACI Tenant Builds With Optics | Closed | 100% | 11.87% | 113.75 | 100.25 | 15128.75 | 1987.5 | 88.13% | 15128.75 | 0 | 13.5 | 1518.75 | 0 |  | 1987.5 |  | 3730.32 | 23792.8 | 21805.3 | 91.65%
02/10/25 |  | 03/07/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200001885 | N/A | Closed | 100% | 33.2% | 15.06 | 10.06 | 1804.7 | 625 | 66.8% | 1804.7 | 0 | 5 | 0 | 0 |  | 625 |  | 3496.8 | 4906.7 | 4281.7 | 87.26%
02/10/25 |  | 03/07/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Warren Wilson, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200001886 | N/A | Closed | 100% | 33.7% | 32.64 | 21.64 | 3905.5 | 1375 | 66.3% | 3905.5 | 0 | 11 | 0 | 0 |  | 1375 |  | 8742 | 10975.24 | 9600.24 | 87.47%
02/05/25 |  | 03/07/25 | Closed | LaQisha Marshall | Chad Hart |  | David Monasmith, David Monasmith, LaQisha Marshall, Tabais Prater |  |  | Briliance Johnson, LaQisha Marshall |  |  | David Monasmith | TX-HOU | Texas A&M System | 200001870 | N/A | Closed | 0% | 0% | 0 | -7 | 0 | 550 | 0% | 0 | 0 | 7 | 0 | 0 |  | 550 |  | 0 | 185 | -365 | -197.3%
10/21/24 |  | 03/07/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Christopher Garcia, Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah |  |  | Brian Newman, Carlo Enriquez, Clinton Bennett Deason, Kendall Walls, Lauren Lanzini Coffey, Yonathan Fadel |  |  | Neel Shah | TX-HOU | Brycomm | J00018709 | ATXNC IPTV & PX Expansion | Training/Knowledge Transfer/Documentation | 95% | 52.71% | 120 | 86.25 | 17377.02 | 7926.25 | 71.88% | 17377.02 | 29.5 | 63.25 | 4115 | 110.33 |  | 7926.25 |  | 56894.24 | 25542 | 17505.42 | 68.54%
07/03/24 |  | 03/07/25 | Open | Marco Lish | Bryan Brown |  | Beau C. Devillier, Christopher Garcia, Kristy L Dice, Marco Lish |  |  | Brian Newman, Marco Lish |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00018647 | Paging System - Lynn McKinney ES | Closed | 100% | 73.2% | 58.4 | 15.65 | 8232 | 5883.75 | 26.8% | 8232 | 0 | 42.75 | 5462.5 | 0 |  | 5883.75 |  | 4580 | 20348.4 | 14464.65 | 71.08%
02/05/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001734 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 1132 | 0 | -45 | 0%
02/05/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001735 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 3216 | 0 | -75 | 0%
02/05/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001736 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 6131 | 0 | -75 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Oscar Nunez, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200001787 | N/A | Closed | 0% | 0% | 0 | -28.5 | 0 | 855 | 0% | 0 | 0 | 28.5 | 0 | 0 |  | 855 |  | 125390 | 0 | -855 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001788 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 7599 | 0 | -60 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001789 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 9558 | 0 | -60 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001791 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 892 | 0 | -45 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001792 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 2589 | 0 | -60 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001799 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 1175 | 0 | -15 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001800 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 7742 | 0 | -30 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200001804 | N/A | Closed | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 5310 | 0 | -135 | 0%
02/06/25 |  | 03/07/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001806 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 20055.36 | 0 | -30 | 0%
02/07/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001807 | N/A | Closed | 0% | 0% | 0 | -34 | 0 | 1020 | 0% | 0 | 0 | 34 | 0 | 0 |  | 1020 |  | 55755 | 0 | -1020 | 0%
02/07/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200001808 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4445 | 0 | -30 | 0%
02/07/25 |  | 03/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001811 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 600 | 0 | -30 | 0%
11/06/23 |  | 03/07/25 | Open | Richard Keith Arnst | Albert H Nguyen, Mark J Chambliss |  | Monica Johnson, Richard Keith Arnst |  |  | Baq Alsaedi, James Adams, John Stephen Kurkjian, Nathan Dao, Nicolas Garakani, Richard Keith Arnst, Tray Giddens |  |  | Monica Johnson | TX-HOU | Port of Houston Authority | J00014662 | Antiquated Gear Refresh - Rack and Patch-In ONLY | Closed | 100% | 205% | 45 | -29.25 | 3025 | 8823.75 | -65% | 3025 | 18 | 92.25 | 5927.5 | 44.2 |  | 8823.75 |  | 609137.23 | 4158 | -4709.95 | -113.3%
01/27/25 |  | 03/07/25 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Jason Osuna, Jesus Escobedo, Shannon Marie Alvarado |  |  | Jesus Escobedo, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | 200001716 | N/A | Closed | 100% | 65% | 10 | 3.5 | 1290 | 840 | 35% | 1290 | 0 | 6.5 | 0 | 0 |  | 840 |  | 0 | 2221.2 | 1381.2 | 62.18%
12/09/24 |  | 03/10/25 | Open | Abiodun David Babasola | Steven Walker |  | Abiodun David Babasola, Christopher Brown, Christopher Brown, David Babasola, Joshua Parker |  |  | Abiodun David Babasola, Christopher Brown |  |  | Joshua Parker | TX-DAL | Richardson ISD | 200000271 | N/A | Closed | 100% | 80% | 43.75 | 8.75 | 5818.75 | 4635 | 20% | 5818.75 | 0 | 35 | 0 | 0 |  | 4635 |  | 0 | 9150.8 | 4515.8 | 49.35%
09/26/24 |  | 03/10/25 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Luis Ovalles, Michael Brett Beggs, William Davenport |  |  | Caleb Henry, Jason Esry, Luis Ovalles, Noah Trump |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00019064 | Veeam Repository Server Installation | Closed | 100% | 83.54% | 23.94 | 5.94 | 2584 | 2242.5 | 24.81% | 2584 | 2 | 20 | 120 | 0 |  | 2242.5 |  | 20750.4 | 4286.8 | 2044.3 | 47.69%
09/26/24 |  | 03/10/25 | Open | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Luis Ovalles, Michael Brett Beggs, William Davenport |  |  | Caleb Henry, Jason Esry, Luis Ovalles, Noah Trump |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00019064 | Veeam Repository Server Installation | Closed | 0% | 0% | 0 | -3 | 0 | 395 | 0% | 0 | 0 | 3 | 395 | 0 |  | 395 |  | 20750.4 | 4286.8 | 3891.8 | 90.79%
08/13/24 |  | 03/10/25 | Open | Jason Esry | Aman Khan |  | Aman Khan, David D Tijerina, Jason Esry, Larry Noble, Robert Kelly, Robert Kelly |  |  | An Le, Isaiah Rosales, Jason Esry, John Senkulics, Mohammed Almoola, Robert Kelly |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00018822 | Access Point (AP) Installation - 25000700 | Closed | 100% | 79.92% | 100.1 | 20.1 | 8354.73 | 6267.5 | 20.08% | 8354.73 | 0 | 80 | 5392.5 | 0 |  | 6267.5 |  | 5712.5 | 13742.4 | 7474.9 | 54.39%
10/09/23 |  | 03/10/25 | Open | Jason Esry | Aman Khan |  | Abdalsattar Albaghdadi, Aman Khan, David D Tijerina, Jason Esry, Kurt Sell, Mohammed Almoola, Mohammed Hussain, Robert Kelly, Robert Kelly |  |  | Jason Esry, Mohammed Almoola |  |  | David D Tijerina | TX-CEN | Travis County | J00016593 | DNAC Deployment | Closed | 100% | 88.78% | 159.38 | 17.88 | 19965 | 17687.5 | 11.22% | 19965 | 0 | 141.5 | 14437.5 | 59.8 |  | 17687.5 |  | 0 | 0 | -17747.3 | 0%
02/07/25 |  | 03/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001809 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 863 | 0 | -15 | 0%
02/12/25 |  | 03/12/25 | Closed | Lauren Lanzini Coffey | N/A |  | Lauren Lanzini Coffey, Neel Shah |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200001951 | N/A | Not started | 0% | 0% | 7.5 | 7.5 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 71994.96 | 2090.8 | 2090.8 | 100%
02/10/25 |  | 03/12/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Dedric Bowens, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Oscar Nunez, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001818 | N/A | Closed | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 25150 | 0 | -195 | 0%
02/10/25 |  | 03/12/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Anthony Balogun, David Lenihan, Dedric Bowens, Gregory Posey, Jarshawn Newsome, Nathanael Morales, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001820 | N/A | Closed | 0% | 0% | 0 | -5.5 | 0 | 165 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 165 |  | 7965 | 0 | -165 | 0%
09/05/23 |  | 03/13/25 | Open | Joanna Herrera | Jacob Parks, Jeffrey Holman |  | Abdulrahman Farhan, Austen New LN: Howard Cockerham, Garrett Curran, Jacob Parks, Jeffrey Holman, Joanna Herrera, Karyn Hubbard, Meray Doughly, Timothy Ramsey, Yong Kim |  |  | Abdulrahman Farhan, Austen Howard, Conner MacDonnell, Dante Torres, Devin Moreno, Joanna Herrera, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nick Varga, Timothy Sean Marcyes |  |  | Garrett Curran | CA-LAX | City of Claremont | J00016313 | Fortigate and Fortinet Switching | Closed | 100% | 264.5% | 319.3 | -441.2 | 44742.5 | 110591.25 | -138.2% | 44742.5 | 84 | 844.5 | 96911.25 | 227.05 |  | 110591.25 |  | 124838.48 | 130314.96 | 19496.66 | 14.96%
05/08/23 |  | 03/13/25 | Closed | LaQisha Marshall | David Escamilla |  | Chad Hart, Christopher Kutalek, David Escamilla, Jennifer Huie, John Randall Bailey, Jr., LaQisha Marshall, Ron Loge, Tony Dean Skipworth |  |  | Bryan Mullen, Bryant Bush, Craig St. Rose, David Dobbs, Hector Rivera, Jaime Flores, Jorge Ortiz Cardozo, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kyle Linder, LaQisha Marshall, Matthew D'Ambrosio, Nathan Dao, Paul Serres, Ron Loge, Sajjad Abo Dbs, Tony Dean Skipworth |  |  | Christopher Kutalek | TX-HOU | AlliantGroup | J00014081 | ACI Implementation | Closed | 100% | 143.5% | 410.51 | -117.24 | 52391.25 | 65877.5 | -28.56% | 52391.25 | 61.5 | 589.25 | 56372.5 | 1103.42 |  | 65877.5 |  | 1049545.84 | 62092.96 | -4887.96 | -7.872%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200001826 | N/A | Not started | 0% | 0% | 0 | -51.5 | 0 | 1545 | 0% | 0 | 0 | 51.5 | 0 | 0 |  | 1545 |  | 88900 | 0 | -1545 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001827 | N/A | Closed | 0% | 0% | 0 | -25.75 | 0 | 772.5 | 0% | 0 | 0 | 25.75 | 0 | 0 |  | 772.5 |  | 57110 | 0 | -772.5 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Anthony Balogun, David Lenihan, Dedric Bowens, Gregory Posey, Jarshawn Newsome, Nathanael Morales, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001828 | N/A | Closed | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 38232 | 0 | -195 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001829 | N/A | Closed | 0% | 0% | 0 | -8.5 | 0 | 255 | 0% | 0 | 0 | 8.5 | 0 | 0 |  | 255 |  | 56662 | 0 | -255 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gregory Posey, Kai Rose , Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200001830 | N/A | Closed | 0% | 0% | 0 | -10.5 | 0 | 315 | 0% | 0 | 0 | 10.5 | 0 | 0 |  | 315 |  | 17780 | 0 | -315 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Josue Iglesias, Kai Rose , Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001834 | N/A | Closed | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 4366 | 0 | -135 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Anthony Balogun, David Lenihan, Dedric Bowens, Gregory Posey, Jarshawn Newsome, Nathanael Morales, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001835 | N/A | Closed | 0% | 0% | 0 | -5.5 | 0 | 165 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 165 |  | 10089 | 0 | -165 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001837 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 1763 | 0 | -60 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001838 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2350 | 0 | -30 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, David Lenihan, Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200001846 | N/A | Closed | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 34660 | 0 | -180 | 0%
02/11/25 |  | 03/13/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001849 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1155 | 0 | -30 | 0%
09/07/22 |  | 03/13/25 | Open | Tray Giddens | N/A |  | Ashley F Freeman, Shiraz Humayun, Tray Giddens |  |  | Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00013856 | Clinic at HC Jail PC reimage | Cancelled | 5% | 5.42% | 369 | 349 | 16605 | 2500 | 94.58% | 16605 | 0 | 20 | 2500 | 0 |  | 2500 |  | 0 | 0 | -2500 | 0%
09/19/24 |  | 03/14/25 | Closed | Jason Matthew Davis | Christopher Ceykovsky |  | Beau C. Devillier, Christopher Ceykovsky, Jason Matthew Davis, Mark Forehand |  |  | Jason Matthew Davis, Michael Garcia, Samuel Newland |  |  | Mark Forehand | TX-DAL | DR Horton | J00019001 | Avaya to Cisco Migration | Closed | 100% | 59.06% | 245.5 | 100.5 | 3468.75 | 19760 | 40.94% | 3468.75 | 0 | 145 | 4580 | 3910 |  | 19760 |  | 0 | 21268 | -2402 | -11.29%
02/12/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Nathanael Morales, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001876 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 8500 | 0 | -75 | 0%
02/13/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001883 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3200 | 0 | -30 | 0%
02/13/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Oscar Nunez, Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001884 | N/A | Closed | 0% | 0% | 0 | -11.5 | 0 | 345 | 0% | 0 | 0 | 11.5 | 0 | 0 |  | 345 |  | 109768 | 0 | -345 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001900 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3173 | 0 | -30 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001901 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 889 | 0 | -60 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001902 | N/A | Closed | 0% | 0% | 0 | -16.5 | 0 | 495 | 0% | 0 | 0 | 16.5 | 0 | 0 |  | 495 |  | 53100 | 0 | -495 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001903 | N/A | Closed | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 28674 | 0 | -195 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Anthony Balogun, David Lenihan, Dedric Bowens, Gregory Posey, Jarshawn Newsome, Nathanael Morales, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001904 | N/A | Closed | 0% | 0% | 0 | -5.5 | 0 | 165 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 165 |  | 18585 | 0 | -165 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001905 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 6376 | 0 | -30 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Anthony Balogun, David Lenihan, Dedric Bowens, Gregory Posey, Jarshawn Newsome, Nathanael Morales, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200001906 | N/A | Closed | 0% | 0% | 0 | -5.5 | 0 | 165 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 165 |  | 6903 | 0 | -165 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001910 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 11200 | 0 | -60 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001916 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1612.8 | 0 | -30 | 0%
02/13/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001891 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2290 | 0 | -30 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001911 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1471 | 0 | -30 | 0%
02/14/25 |  | 03/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001914 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1309.81 | 0 | -30 | 0%
12/27/24 |  | 03/14/25 | Open | Tray Giddens | Albert H Nguyen |  | Albert H Nguyen, Dennis Odneal, Kolawole Ayeni, Matthew D'Ambrosio, Monica Johnson, Nelson Garcia, Paul F Phillips, Paul Phillips, Savitha Ramakrishnan, Tray Giddens |  |  | Hector Rivera, Jaime Flores, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nelson Garcia, Nicolas Garakani, Paul Serres, Tray Giddens |  |  | Dennis Odneal | TX-HOU | Dickinson ISD | 200000318 | N/A | Closed | 100% | 85.42% | 82.83 | 23.58 | 7257.8 | 6357.5 | 28.47% | 7257.8 | 11.5 | 70.75 | 690 | 0 |  | 6357.5 |  | 251622.54 | 9743.6 | 3386.1 | 34.75%
01/24/25 |  | 03/17/25 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Bryan Geoghan, David Babasola, Lauren J Kennewell |  |  | Abiodun David Babasola |  |  | Lauren J Kennewell | TX-DAL | City of Midlothian | 200001705 | N/A | Closed | 100% | 90% | 5 | 0.5 | 625 | 562.5 | 10% | 625 | 0 | 4.5 | 0 | 0 |  | 562.5 |  | 0 | 5422.01 | 4859.51 | 89.63%
11/08/24 |  | 03/17/25 | Open | Robert McIver | Edward Padron |  | Christopher Prado, Diana Berger, Edward Padron, Erick Nunez , Felix Martinez, Michelle Bailey, Robert McIver, Xavier A Trevino |  |  | Carlos Carrillo, Christopher Prado, Daniel Dominguez, Erick Nunez , Francisco Hernandez, Francisco Rosa, Garrett Hart, Jaime Galvan, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Mark Rosa, Oscar Garcia, Robert McIver, Roger Guerra, Trevor Galloso, William Brown |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018028 | Upper & Lower RGV Campus Installations | Closed | 100% | 123.8% | 584.41 | -44.09 | 47697.25 | 57514.8 | -7.544% | 47697.25 | 95.08 | 723.58 | 43005 | 1872 |  | 57514.8 |  | 1124911.63 | 62173.4 | 2786.6 | 4.482%
05/01/24 |  | 03/17/25 | Closed | Walter Clay Knight | William Birdsong |  | Camille Elizabeth Taber, Christopher Butler, Jeffery Alan Jorzig, Jeffery Jorzig |  |  | Jeffery Alan Jorzig, Walter Clay Knight |  |  | Camille Taber | FL | Leon County Schools | J00018255 | Core and Edge Internet Devices | Closed | 100% | 82.24% | 283.33 | 50.33 | 35619.69 | 29125 | 17.76% | 35619.69 | 0 | 233 | 21500 | 0 |  | 29125 |  | 0 | 72716.2 | 43591.2 | 59.95%
01/22/24 |  | 03/17/25 | Closed | Walter Clay Knight | Mark J Chambliss, William Birdsong |  | Aleksei Lavrushenkov, Christopher Ceykovsky, John Stephen Kurkjian, Joseph Boglino, Larry Noble |  |  | Aleksei Lavrushenkov, Craig St. Rose, John Stephen Kurkjian, Kendall Walls, Mustafa Al-Tamimi, Quy Le, Ryan Scott, Walter Clay Knight |  |  | Joseph Boglino | US-FED | National Park Service | J00013650 | Fort Stanwix National Monument UC Upgrade | Closed | 100% | 137.7% | 181.57 | -18.43 | 25973.06 | 29208.75 | -10.15% | 25973.06 | 50 | 250 | 17143.75 | 0 |  | 29208.75 |  | 27305.16 | 22943.11 | -6265.64 | -27.31%
11/18/24 |  | 03/18/25 | Closed | Joaquin Marroquin | Timothy Ramsey |  | Ashutosh Patel, Joaquin Marroquin, Timothy Ramsey, Xavier A Trevino |  |  | Ashutosh Patel, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Del Mar College | 200000135 | N/A | Closed | 100% | 159.6% | 24.75 | -14.75 | 3643.75 | 5862.5 | -59.6% | 3643.75 | 0 | 39.5 | 0 | 0 |  | 5862.5 |  | 0 | 5738.8 | -123.7 | -2.156%
07/24/24 |  | 03/18/25 | Closed | Joaquin Marroquin | Edward Padron |  | Diana Berger, Joaquin Marroquin, Ruben Cantu, Xavier A Trevino |  |  | Carlos Carrillo, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Jorge Robert Rangel, Ming Chiu, Roger Guerra, Ruben Cantu |  |  | Xavier A Trevino | TX-SOUT | Point Isabel ISD | J00018711 | CTE Building Network | Closed | 100% | 95.61% | 70.6 | 13.1 | 7058.8 | 6535 | 18.56% | 7058.8 | 10 | 67.5 | 5415 | 0 |  | 6535 |  | 82293.75 | 63368.24 | 56833.24 | 89.69%
11/08/24 |  | 03/18/25 | Open | Joaquin Marroquin | Bryan Brown |  | Christopher Garcia, Diana Berger, Joaquin Marroquin, Michelle Bailey, Ming Chiu, Xavier A Trevino |  |  | Felix Martinez, Joaquin Garcia, Joaquin Marroquin, Joel Hubbard, Jonathan Pina, Ming Chiu, Roger Guerra |  |  | Xavier A Trevino | TX-SOUT | Point Isabel ISD | J00019142 | CTE Building IP Speakers with data drops | Closed | 100% | 127.7% | 166.75 | -6.25 | 19466.48 | 15930 | -3.748% | 19466.48 | 40 | 213 | 3520 | 0 |  | 15930 |  | 43049.49 | 35939.12 | 20009.12 | 55.68%
09/26/24 |  | 03/18/25 | Closed | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, Kurt Sell, LaQisha Marshall |  |  | Briliance Johnson, John Stephen Kurkjian, LaQisha Marshall, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00019088 | Cisco IP Phone Installation – Vestibule Project | Closed | 100% | 75.22% | 116 | 28.75 | 11426 | 9546.25 | 24.78% | 11426 | 0 | 87.25 | 827.5 | 0 |  | 9546.25 |  | 23173.36 | 16744 | 7197.75 | 42.99%
09/30/24 |  | 03/19/25 | Closed | LaQisha Marshall | Mark J Chambliss |  | Beau C. Devillier, David Monasmith, David Monasmith, Hamzeh Tahat, LaQisha Marshall, Leonid G Kamenker, Leonid Kamenker |  |  | Hamzeh Tahat, LaQisha Marshall |  |  | David Monasmith | TX-HOU | West Texas A&M University | J00019042 | UC Upgrade | Closed | 100% | 106.6% | 79 | -5.25 | 1468.75 | 8806.25 | -6.646% | 1468.75 | 0 | 84.25 | 475 | 6727.5 |  | 8806.25 |  | 0 | 13783.64 | -1750.11 | -12.7%
02/17/25 |  | 03/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200001940 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1130 | 0 | -30 | 0%
02/17/25 |  | 03/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001942 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 10668 | 0 | -30 | 0%
02/17/25 |  | 03/19/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001943 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 10620 | 0 | -90 | 0%
01/06/25 |  | 03/20/25 | Open | Joaquin Marroquin | Aman Khan |  | David D Tijerina, Joaquin Marroquin |  |  | An Le, Celso Lopez, Joaquin Marroquin, Michael Torres |  |  | David D Tijerina | TX-CEN | San Antonio ISD | 200000874 | N/A | Closed | 100% | 115.1% | 12.81 | 1.56 | 935 | 950 | 12.18% | 935 | 3.5 | 14.75 | 210 | 0 |  | 950 |  | 3920.25 | 1416 | 466 | 32.91%
08/01/24 |  | 03/20/25 | Closed | Lauren Lanzini Coffey | George Edwin Jacob |  | Gearld Stanley McNiel, George Edwin Jacob, Jeff Barker, Jonathan Pendrich, Lauren Lanzini Coffey, Ron Loge, Stan McNiel |  |  | Bradley Buchanan, Bryce Evans, Calvin Darby, Carlo Enriquez, Conner MacDonnell, Eric Mitchell Frisby, Jacob Hill, Jalen Vecchitto, Jay Daniel De Leon, Joan Brito, Justin Mitchell, Kendall Walls, Lauren Lanzini Coffey, Osazee Eweka, Phillip Ma Lim, Ron Loge, Ryan Frankeberger, Takari Waddy, Taylor Poole, William Chris Roome |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | J00018797 | Cohesity Project | Closed | 100% | 169.2% | 785.4 | -539.95 | 57614.21 | 116832.25 | -68.75% | 57614.21 | 3.5 | 1328.85 | 70791 | 1560 |  | 116832.25 |  | 8030085.91 | 366922.5 | 248530.25 | 67.73%
02/18/25 |  | 03/20/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001947 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2676 | 0 | -30 | 0%
02/18/25 |  | 03/20/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001948 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2870 | 0 | -30 | 0%
02/18/25 |  | 03/20/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001950 | N/A | Closed | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 39825 | 0 | -195 | 0%
02/18/25 |  | 03/20/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001953 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3525 | 0 | -30 | 0%
02/18/25 |  | 03/20/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001954 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 10668 | 0 | -90 | 0%
02/18/25 |  | 03/20/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Lorenzo Hernandez, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001955 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 13964 | 0 | -90 | 0%
02/18/25 |  | 03/20/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001957 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2482 | 0 | -30 | 0%
08/09/23 |  | 03/20/25 | Open | Robert McIver | Edward Padron |  | Michelle Bailey, Robert McIver, Xavier A Trevino |  |  | Christopher Prado, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00015978 | Price Hill and VV Change order | Closed | 100% | 31.67% | 11.05 | 7.55 | 1540.1 | 422.5 | 68.33% | 1540.1 | 0 | 3.5 | 312.5 | 1063.09 |  | 422.5 |  | 13784.67 | 9410.43 | 7924.84 | 84.21%
12/23/24 |  | 03/21/25 | Closed | Joanna Herrera | Warren Wilson |  | Garrett Hart, Joanna Herrera, Michelle Bailey, Warren Wilson, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200001498 | N/A | Closed | 100% | 36.52% | 15.06 | 9.56 | 1804.7 | 687.5 | 63.48% | 1804.7 | 0 | 5.5 | 0 | 0 |  | 687.5 |  | 3937.84 | 4218.66 | 3531.16 | 83.7%
06/01/23 |  | 03/21/25 | Open | Joanna Herrera | Christopher Puyear |  | Christi D Hubbard, Joanna Herrera, Larry Noble |  |  | George McGann, Joanna Herrera |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | J00015660 | Imagicle Faxing Setup | Closed | 100% | 85% | 10 | 1.5 | 1370 | 1152.5 | 15% | 1370 | 0 | 8.5 | 1152.5 | 0 |  | 1152.5 |  | 21150 | 3372.4 | 2219.9 | 65.83%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Kai Rose |  |  | N/A | N/A | Houston ISD | 200001986 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 12488 | 0 | -90 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gregory Posey, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200001987 | N/A | Closed | 0% | 0% | 0 | -11 | 0 | 330 | 0% | 0 | 0 | 11 | 0 | 0 |  | 330 |  | 20581 | 0 | -330 | 0%
02/20/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001989 | N/A | Not started | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 8890 | 0 | -75 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200001990 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2412 | 100 | 70 | 70%
02/20/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200001991 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2667 | 0 | -30 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200001994 | N/A | Closed | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 13806 | 0 | -135 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Anthony Balogun, Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200001995 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 5400 | 0 | -150 | 0%
02/20/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200001997 | N/A | Not started | 0% | 0% | 0 | -12 | 0 | 360 | 0% | 0 | 0 | 12 | 0 | 0 |  | 360 |  | 21575 | 0 | -360 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, David Lenihan, Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200001999 | N/A | Closed | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 26229 | 0 | -180 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002000 | N/A | Closed | 0% | 0% | 0 | -13 | 0 | 390 | 0% | 0 | 0 | 13 | 0 | 0 |  | 390 |  | 53100 | 0 | -390 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Josue Iglesias, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002001 | N/A | Closed | 0% | 0% | 0 | -9.5 | 0 | 285 | 0% | 0 | 0 | 9.5 | 0 | 0 |  | 285 |  | 53100 | 0 | -285 | 0%
02/20/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002002 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8920 | 0 | -30 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002003 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4315 | 0 | -30 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, David Lenihan, Jarshawn Newsome, Josue Iglesias, Kai Rose , Oscar Nunez, Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002004 | N/A | Closed | 0% | 0% | 0 | -8.5 | 0 | 255 | 0% | 0 | 0 | 8.5 | 0 | 0 |  | 255 |  | 26220 | 0 | -255 | 0%
02/20/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002005 | N/A | Not started | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 15740 | 350 | 230 | 65.71%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, David Lenihan, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002006 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 17330 | 0 | -150 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, David Lenihan, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002007 | N/A | Closed | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 17330 | 0 | -120 | 0%
02/20/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Josue Iglesias, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002008 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 10620 | 0 | -150 | 0%
02/21/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Kai Rose , Oscar Nunez, Samsoni Jean Claude, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002013 | N/A | Not started | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 11596 | 0 | -195 | 0%
02/21/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002017 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2618 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002018 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 4779 | 0 | -60 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, Kai Rose , Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002019 | N/A | Closed | 0% | 0% | 0 | -6.25 | 0 | 187.5 | 0% | 0 | 0 | 6.25 | 0 | 0 |  | 187.5 |  | 31860 | 0 | -187.5 | 0%
02/21/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002020 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 11435 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002021 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4445 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002022 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 8890 | 0 | -90 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002023 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4200 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002024 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 7136 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002025 | N/A | Closed | 0% | 0% | 0 | -26.5 | 0 | 795 | 0% | 0 | 0 | 26.5 | 0 | 0 |  | 795 |  | 182165 | 0 | -795 | 0%
02/21/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002037 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3556 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002040 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 944 | 50 | 20 | 40%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002041 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3015 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002042 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4460 | 0 | -30 | 0%
02/21/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, David Lenihan, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Nathanael Morales, Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002043 | N/A | Closed | 0% | 0% | 0 | -7.5 | 0 | 225 | 0% | 0 | 0 | 7.5 | 0 | 0 |  | 225 |  | 14671 | 0 | -225 | 0%
02/21/25 |  | 03/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002047 | N/A | Not started | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 8225 | 0 | -45 | 0%
02/19/25 |  | 03/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | Neel Shah | TX-HOU | Lone Star College System | 200001971 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 4764 | 0 | -45 | 0%
01/06/25 |  | 03/21/25 | Closed | Richard Keith Arnst | David Escamilla |  | Ashley F Freeman, Richard Keith Arnst |  |  | Richard Keith Arnst |  |  | Ashley F Freeman | TX-HOU | Harris County Clerks Office | 200001544 | N/A | Cancelled | 0% | 4.103% | 36.56 | 35.06 | 4895 | 187.5 | 95.9% | 4895 | 0 | 1.5 | 0 | 0 |  | 187.5 |  | 0 | 8000 | 7812.5 | 97.66%
12/18/24 |  | 03/21/25 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Mark J Chambliss, Michelle Bailey, Patrick Joseph Palermo, Tray Giddens |  |  | Craig St. Rose, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Matthew D'Ambrosio, Patrick Joseph Palermo, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200000358 | N/A | Closed | 100% | 93.81% | 52.5 | 4.25 | 6552.5 | 7667.5 | 8.095% | 6552.5 | 1 | 49.25 | 60 | 0 |  | 7667.5 |  | 17264.94 | 10319.6 | 2652.1 | 25.7%
02/17/25 |  | 03/24/25 | Closed | Walter Clay Knight | Bryan Brown |  | Christopher Garcia, Dennis Odneal, Jeremiah Solomon, Walter Clay Knight |  |  | Clinton Bennett Deason, Hector Rivera, Jeremiah Solomon, Justin Cornish, Walter Clay Knight |  |  | Dennis Odneal | TX-HOU | Harris Health System | 200001998 | N/A | Closed | 100% | 90.97% | 15.94 | 3.44 | 0 | 1177.5 | 21.58% | 0 | 2 | 14.5 | 120 | 0 |  | 1177.5 |  | 11384.94 | 2366.8 | 1189.3 | 50.25%
11/18/24 |  | 03/25/25 | Open | Robert McIver | Edward Padron |  | Edward Padron, Erick Nunez , Robert McIver, Xavier A Trevino |  |  | Erick Nunez , Isaiah Rosales, James Danner, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200000129 | N/A | Closed | 100% | 156% | 21.8 | -12.2 | 2241.4 | 2690 | -55.96% | 2241.4 | 0 | 34 | 0 | 0 |  | 2690 |  | 24392.08 | 3077.6 | 387.6 | 12.59%
03/24/23 |  | 03/25/25 | Closed | Summer Abunaja | Jeremy Hoffpauir |  | Aaron Christopher Pfeifer, Christopher Butler, Jeremy Hoffpauir, Rafael Rodriguez-Vargas, Summer Abunaja, Susan Richardson, Zachary Short, Zachary Short |  |  | Aaron Christopher Pfeifer, Mohammed Almoola, Rafael Rodriguez-Vargas, Richard Keith Arnst |  |  | N/A | N/A | Centric Fiber Texas, LLC | J00015223 | WORK ORDER T&E Consultation | Closed | 0% | 0% | 0 | -34 | 0 | 4590 | 0% | 0 | 0 | 34 | 0 | 162.08 |  | 4590 |  | 0 | 175287.5 | 170535.42 | 97.29%
03/24/23 |  | 03/25/25 | Closed | Summer Abunaja | Jeremy Hoffpauir |  | Aaron Christopher Pfeifer, Christopher Butler, Jeremy Hoffpauir, Rafael Rodriguez-Vargas, Summer Abunaja, Susan Richardson, Zachary Short, Zachary Short |  |  | Aaron Christopher Pfeifer, Mohammed Almoola, Rafael Rodriguez-Vargas, Richard Keith Arnst |  |  | Susan Richardson | TX-HOU | Centric Fiber Texas, LLC | J00015223 | WORK ORDER T&E Consultation | Closed | 0% | 0% | 0 | -842 | 0 | 113635 | 0% | 0 | 0 | 842 | 113635 | 162.08 |  | 113635 |  | 0 | 175287.5 | 61490.42 | 35.08%
02/24/25 |  | 03/26/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002073 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 8630 | 0 | -60 | 0%
02/24/25 |  | 03/26/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002074 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 12744 | 0 | -45 | 0%
02/24/25 |  | 03/26/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002075 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 5600 | 0 | -60 | 0%
02/24/25 |  | 03/26/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002076 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3556 | 0 | -30 | 0%
02/24/25 |  | 03/26/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002077 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 11106 | 0 | -45 | 0%
02/24/25 |  | 03/26/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002078 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 892 | 0 | -30 | 0%
02/24/25 |  | 03/26/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002079 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 6372 | 0 | -45 | 0%
02/24/25 |  | 03/26/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002080 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 18695 | 175 | 85 | 48.57%
02/24/25 |  | 03/26/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002081 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 5500 | 0 | -30 | 0%
02/24/25 |  | 03/26/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002082 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4445 | 0 | -30 | 0%
02/17/25 |  | 03/27/25 | Open | Jennifer Soliz | Emilio Carrillo |  | Emilio Carrillo, Hannah Paul, Jennifer Soliz |  |  | An Le, Celso Lopez, Jennifer Soliz, Michael Torres |  |  | Hannah Edmunds | TX-CEN | Comal ISD | 200002038 | N/A | Closed | 100% | 80% | 44.69 | 8.94 | 0 | 2453.75 | 20% | 0 | 0 | 35.75 | 0 | 0 |  | 2453.75 |  | 50358 | 0 | -2453.75 | 0%
11/27/23 |  | 03/27/25 | Closed | Joaquin Marroquin | Daniel Snyder, Robert Berken |  | Christi D Hubbard, Joaquin Marroquin, Larry Noble, Robert Kelly, Robert Kelly |  |  | Adam Felix, Grayson Rigsby, Jeffrey Charles Primeaux, Joaquin Marroquin, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Oscar Gonzalez, Richard Shea, Robert Kelly, Robert Jones, Steven Shipmon, Tabais Prater |  |  | Christi D Hubbard | TX-CEN | Dripping Springs ISD | J00016872 | Erate Network Refresh Sycamore | Closed | 100% | 84.88% | 205.29 | 53.04 | 16088.1 | 12117.5 | 25.84% | 16088.1 | 22 | 174.25 | 8195 | 0 |  | 12117.5 |  | 916716.8 | 17294 | 5176.5 | 29.93%
02/25/25 |  | 03/27/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002092 | N/A | Closed | 0% | 0% | 0 | -13 | 0 | 390 | 0% | 0 | 0 | 13 | 0 | 0 |  | 390 |  | 45672 | 0 | -390 | 0%
02/25/25 |  | 03/27/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002093 | N/A | Not started | 0% | 0% | 0 | -40 | 0 | 1200 | 0% | 0 | 0 | 40 | 0 | 0 |  | 1200 |  | 88900 | 0 | -1200 | 0%
02/25/25 |  | 03/27/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Dedric Bowens, Josue Iglesias, Kai Rose , Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002094 | N/A | Not started | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 54580 | 0 | -150 | 0%
02/25/25 |  | 03/27/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002095 | N/A | Closed | 0% | 0% | 0 | -18.5 | 0 | 555 | 0% | 0 | 0 | 18.5 | 0 | 0 |  | 555 |  | 53100 | 0 | -555 | 0%
02/25/25 |  | 03/27/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Gregory Posey, Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200002097 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 123096 | 0 | -90 | 0%
02/25/25 |  | 03/27/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Gregory Posey, Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200002098 | N/A | Closed | 0% | 0% | 0 | -9.5 | 0 | 285 | 0% | 0 | 0 | 9.5 | 0 | 0 |  | 285 |  | 33600 | 0 | -285 | 0%
02/25/25 |  | 03/27/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Kai Rose , Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002099 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 2010 | 0 | -60 | 0%
02/25/25 |  | 03/27/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002103 | N/A | Not started | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 17595 | 0 | -120 | 0%
12/29/23 |  | 03/28/25 | Open | Jennifer Soliz | David Pena, George Delp, Joseph Hayes |  | Elizabeth Diaz, George Delp, Jason Espino, Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Aldo Cortes, Elizabeth Diaz, James Danner, Jason Espino, Jennifer Soliz, Jillian Townson, Kevin Curtis, Khoa Tran, Kolawole Ayeni, Kristopher Dwight, Matthew D'Ambrosio, Mohammed Almoola, Trevor Youngman |  |  | Lonnie Owens | TX-CEN | City of San Antonio | J00011103 | Optical WAN Network Refresh | Closed | 0% | 0% | 0 | -544.25 | 0 | 75267.5 | 0% | 0 | 20.5 | 564.75 | 72292.5 | 1765.55 |  | 75267.5 |  | 1799799.1 | 291125.52 | 214092.47 | 73.54%
12/29/23 |  | 03/28/25 | Open | Jennifer Soliz | David Pena, George Delp, Joseph Hayes |  | Elizabeth Diaz, George Delp, Jason Espino, Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Aldo Cortes, Elizabeth Diaz, James Danner, Jason Espino, Jennifer Soliz, Jillian Townson, Kevin Curtis, Khoa Tran, Kolawole Ayeni, Kristopher Dwight, Matthew D'Ambrosio, Mohammed Almoola, Trevor Youngman |  |  | N/A | N/A | City of San Antonio | J00011103 | Optical WAN Network Refresh | Closed | 100% | 0.3119% | 2324.43 | 2317.18 | 40148.9 | 943.75 | 99.69% | 40148.9 | 0 | 7.25 | 0 | 1765.55 |  | 943.75 |  | 1799799.1 | 291125.52 | 288416.22 | 99.07%
06/12/24 |  | 03/28/25 | Open | Jennifer Soliz | Christopher Ceykovsky |  | Jennifer Soliz, Patrick Joseph Palermo, Steve J Rodriguez, Xavier A Trevino |  |  | Jennifer Soliz, Patrick Joseph Palermo |  |  | Xavier A Trevino | TX-SOUT | University of Texas Rio Grande Valley | J00018318 | UC Upgrade from 11.x to 14.x | Closed | 100% | 75.64% | 239.63 | 58.38 | 32978.75 | 32893.75 | 24.36% | 32978.75 | 0 | 181.25 | 14168.75 | 0 |  | 32893.75 |  | 0 | 44077.6 | 11183.85 | 25.37%
12/17/24 |  | 03/28/25 | Open | Marco Lish | Bryan Brown |  | Christopher Garcia, Jeremiah Solomon, Marco Lish, Neel Shah |  |  | Jeremiah Solomon, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | 200000345 | N/A | Closed | 100% | 30.35% | 9.06 | 6.31 | 830 | 243.75 | 69.65% | 830 | 0 | 2.75 | 0 | 0 |  | 243.75 |  | 358.1 | 1370 | 1126.25 | 82.21%
10/04/21 |  | 03/28/25 | Open | Marco Lish | Billy Pearson, Pradeep Tyagi , Saif Qaissi, Wyley Johnson |  | Aaron Abshire, Abdulrahman Farhan, Christine A Hupe, Jason Espino, Larry Noble, Marco Lish, Mohammad Jilani, Neel Shah, Pradeep Tyagi , Saif Qaissi |  |  | Aaron Abshire, Andy Pham, Jason Espino, Jorge Ortiz Cardozo, Kord Mullins, Lauren Lanzini Coffey, Marco Lish, Mohammad Jilani, Saif Qaissi |  |  | Neel Shah | TX-HOU | City of Houston Police Dept | J00011508 | C1/Fannin HPD Migration - Reisner/Travis router | Closed | 100% | 101.6% | 1302.62 | 9.07 | 148192.2 | 154778.95 | 0.6963% | 148192.2 | 30 | 1323.55 | 149848.45 | 6801.62 |  | 154778.95 |  | 26580.6 | 235518.2 | 73937.63 | 31.39%
02/26/25 |  | 03/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez, Gregory Posey, Kai Rose , Pedro Cavazos, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002112 | N/A | Not started | 0% | 0% | 0 | -9.5 | 0 | 285 | 0% | 0 | 0 | 9.5 | 0 | 0 |  | 285 |  | 9730 | 0 | -285 | 0%
02/26/25 |  | 03/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002113 | N/A | Not started | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 8920 | 0 | -105 | 0%
02/26/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002115 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 27930 | 0 | -75 | 0%
02/26/25 |  | 03/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002116 | N/A | Not started | 0% | 0% | 0 | -24 | 0 | 720 | 0% | 0 | 0 | 24 | 0 | 0 |  | 720 |  | 62040 | 0 | -720 | 0%
02/26/25 |  | 03/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002117 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 7591 | 0 | -30 | 0%
02/26/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002118 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8890 | 0 | -30 | 0%
02/26/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Nathanael Morales, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002121 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 3600 | 0 | -75 | 0%
02/26/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002123 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 642 | 0 | -30 | 0%
02/26/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002125 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 140 | 0 | -30 | 0%
02/26/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002131 | N/A | Closed | 0% | 0% | 0 | -18 | 0 | 540 | 0% | 0 | 0 | 18 | 0 | 0 |  | 540 |  | 31860 | 0 | -540 | 0%
02/27/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002148 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 23450 | 0 | -30 | 0%
02/27/25 |  | 03/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002145 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1058.81 | 0 | -30 | 0%
11/08/24 |  | 03/28/25 | Open | Robert McIver | Edward Padron, Warren Wilson |  | Christopher Pheonix Preddy, Christopher Prado, Erick Nunez , Michelle Bailey, Robert McIver, Xavier A Trevino |  |  | Carlos Carrillo, Christopher Pheonix Preddy, Christopher Prado, Erick Nunez , Felix Martinez, Francisco Hernandez, Francisco Rosa, Garrett Hart, Jorge Robert Rangel, Kolawole Ayeni, Mark Rosa, Oscar Garcia, Robert McIver, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00017857 | Weslaco HQ Video Sv Access Cont & Network Refresh | Closed | 100% | 109.8% | 172.11 | -12.89 | 17057.88 | 19710 | -7.489% | 17057.88 | 4 | 189 | 16525 | 1014 |  | 19710 |  | 162111.6 | 34433.67 | 13709.67 | 39.81%
11/22/24 |  | 03/28/25 | Open | Robert McIver | Amanda Barney, Emilio Carrillo, Paul Garza, Wyley Johnson |  | Jason Espino, Larry Noble, Lonnie Owens, Michael Torres, Robert McIver |  |  | Aldo Cortes, Jacobo Padilla, Jason Espino, Kristopher Dwight, Michael Torres, Robert Kelly, Robert McIver, Romar Roca, Sarah Beatrice Williamson |  |  | Lonnie Owens | TX-CEN | John Hagee Ministries | J00011057 | NGFW - FirePower 4115 Appliance Install | Closed | 100% | 111% | 376.26 | -31.74 | 46006.7 | 57880 | -8.436% | 46006.7 | 9.75 | 417.75 | 56535 | 500.86 |  | 57880 |  | 537350.5 | 69168.4 | 10787.54 | 15.6%
12/09/24 |  | 03/28/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Tray Giddens |  |  | Christopher Brown, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200000254 | N/A | Closed | 100% | 96.47% | 42.5 | 1.5 | 5652.5 | 5460 | 3.529% | 5652.5 | 0 | 41 | 0 | 0 |  | 5460 |  | 0 | 7426 | 1966 | 26.47%
09/06/24 |  | 03/31/25 | Closed | Brittney Antoinette Hickman | Matthew Duncan |  | Brittney Antoinette Hickman, Carmen Isela Brandt, Jay Bucsa, Juan Saenz, Matthew Duncan, Yong Kim |  |  | Brittney Antoinette Hickman |  |  | Carmen Brandt | CA-LAX | Amazon Web Services | J00018949 | End User Compute (EUC) Proof of Concept (POC) | Cancelled | 0% | 0% | 0 | -4.5 | 0 | 562.5 | 0% | 0 | 0 | 4.5 | 562.5 | 0 |  | 562.5 |  | 0 | 22599.54 | 22037.04 | 97.51%
09/06/24 |  | 03/31/25 | Closed | Brittney Antoinette Hickman | Matthew Duncan |  | Brittney Antoinette Hickman, Carmen Isela Brandt, Jay Bucsa, Juan Saenz, Matthew Duncan, Yong Kim |  |  | Brittney Antoinette Hickman |  |  | N/A | N/A | Amazon Web Services | J00018949 | End User Compute (EUC) Proof of Concept (POC) | Cancelled | 20% | 0% | 109.25 | 109.25 | 14448.75 | 0 | 100% | 14448.75 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 22599.54 | 22599.54 | 100%
10/03/24 |  | 03/31/25 | Closed | Jason Matthew Davis | Kristian Martell |  | Jason Matthew Davis, Larry Noble, Neel Shah |  |  | Jason Matthew Davis, Kristian Martell, Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | City of Houston Health and Human Services Dept. | J00019057 | IVR Enhancements | Closed | 100% | 75.38% | 281.25 | 69.25 | 49781.25 | 37875 | 24.62% | 49781.25 | 0 | 212 | 2050 | 0 |  | 37875 |  | 3850 | 82138.8 | 44263.8 | 53.89%
02/03/25 |  | 03/31/25 | Open | Jennifer Soliz | N/A |  | Christopher Puyear, Hannah Paul, Jennifer Soliz |  |  | Jennifer Soliz |  |  | Hannah Edmunds | TX-CEN | Texas Real Estate Commission | 200001786 | N/A | Cancelled | 0% | 1.176% | 42.5 | 42 | 5992.5 | 62.5 | 98.82% | 5992.5 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 0 | 0 | -62.5 | 0%
10/21/24 |  | 03/31/25 | Closed | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Firas Abood, Jim Blackwell, Larry Noble, Moe Izaks |  |  | Bryant Bush, Cory Bradfield, David Dobbs, Hector Rivera, Jaime Flores, Jim Blackwell, Luis Alvarez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00019249 | Compute Infrastructure for VMS i-Pro Video Servers | Closed | 100% | 34.07% | 296.46 | 223.46 | 37625.29 | 10257.5 | 75.38% | 37625.29 | 28 | 101 | 3837.5 | 0 |  | 10257.5 |  | 2366146.96 | 75597.52 | 65340.02 | 86.43%
09/13/24 |  | 03/31/25 | Closed | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, Kurt Sell, LaQisha Marshall, Thomas Francis LoMonaco |  |  | John Stephen Kurkjian, LaQisha Marshall, Thomas Francis LoMonaco |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018963 | Cube and Contact Center | Closed | 100% | 71.7% | 220 | 62.25 | 31020 | 25971.25 | 28.3% | 31020 | 0 | 157.75 | 2075 | 0 |  | 25971.25 |  | 151066.6 | 52832.4 | 26861.15 | 50.84%
12/11/24 |  | 03/31/25 | Closed | LaQisha Marshall | Daniel Snyder, David Pena |  | Daniel Snyder, Darrell Walton, Darrell Walton, David Pena, LaQisha Marshall, Raul Velazquez, Thomas McClanahan |  |  | Darrell Walton, LaQisha Marshall, Oscar Gonzalez, Raul Velazquez |  |  | Thomas McClanahan | TX-CEN | Hutto ISD | 200000268 | N/A | Closed | 100% | 80% | 50.31 | 15.56 | 5223.75 | 5051.25 | 30.93% | 5223.75 | 5.5 | 40.25 | 622.5 | 0 |  | 5051.25 |  | 50390.32 | 7578 | 2526.75 | 33.34%
04/29/24 |  | 03/31/25 | Closed | LaQisha Marshall | Ahmed Al-Zubaidi, David Escamilla, Wyley Johnson |  | Ahmed Jameel, Christopher Glock, Christopher Kutalek, Jeffery Alan Jorzig, Jeffery Jorzig, Jennifer Huie, LaQisha Marshall, Larry Noble, Mohammad Jilani, Romar Roca |  |  | Ahmed Jameel, Dhulfiqar Al Hashimi, Jeffery Alan Jorzig, LaQisha Marshall, Mohammad Jilani, Ron Loge |  |  | Christopher Kutalek | TX-HOU | University of Houston Downtown | J00018239 | UHD – 9k Migration | Closed | 100% | 78.57% | 310.24 | 66.49 | 40015.1 | 36593.75 | 21.43% | 40015.1 | 0 | 243.75 | 18406.25 | 0 |  | 36593.75 |  | 0 | 47193.6 | 10599.85 | 22.46%
02/03/25 |  | 03/31/25 | Closed | Robert McIver | N/A |  | Christopher Garcia, Jason Osuna, Robert McIver |  |  | N/A |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200001798 | N/A | Cancelled | 0% | 0% | 26.25 | 26.25 | 2861.25 | 0 | 100% | 2861.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
11/11/24 |  | 03/31/25 | Closed | Summer Abunaja | David Watkins |  | David Watkins, David Neal Gravatt, Neel Shah, Summer Abunaja |  |  | David Neal Gravatt, Lauren Lanzini Coffey, Nathan Dao, Robert Kelly, Summer Abunaja |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00019381 | West & Woodlands Wifi | Closed | 100% | 89.69% | 345.63 | 45.63 | 36186.25 | 33945 | 13.2% | 36186.25 | 10 | 310 | 600 | 0 |  | 33945 |  | 0 | 57753.6 | 23808.6 | 41.22%
07/15/24 |  | 03/31/25 | Closed | Summer Abunaja | Steven Walker |  | Christopher Brown, Christopher Brown, Christopher Kutalek, Larry Noble, Lauren Lanzini Coffey, Summer Abunaja |  |  | Christopher Brown, Lauren Lanzini Coffey, Summer Abunaja |  |  | Christopher Kutalek | TX-HOU | University of Houston Downtown | J00018663 | Active Directory (AD) Assessment | Closed | 100% | 165.6% | 165 | -108.25 | 21120 | 35733.75 | -65.61% | 21120 | 0 | 273.25 | 17097.5 | 0 |  | 35733.75 |  | 0 | 27076.08 | -8657.67 | -31.98%
06/26/23 |  | 04/01/25 | Open | Joanna Herrera | David Escamilla |  | David D Tijerina, David Escamilla, Joanna Herrera, Juan Saenz, Kurt Sell |  |  | Joanna Herrera, Juan Saenz |  |  | David D Tijerina | TX-CEN | Bexar County | J00015835 | AWS PinPoint deployment WO 220050892 | Closed | 100% | 96.43% | 17.63 | 0.63 | 2353.75 | 2285 | 3.573% | 2353.75 | 0 | 17 | 877.5 | 0 |  | 2285 |  | 0 | 3843.2 | 1558.2 | 40.54%
11/19/24 |  | 04/02/25 | Open | Jennifer Soliz | Todd Melby |  | Jennifer Soliz, Lonnie Owens, Todd Melby |  |  | Jennifer Soliz |  |  | Lonnie Owens | TX-CEN | Texas State University | 200000150 | N/A | Closed | 100% | 57.14% | 17.5 | 7.5 | 0 | 1250 | 42.86% | 0 | 0 | 10 | 0 | 0 |  | 1250 |  | 0 | 33915.1 | 32665.1 | 96.31%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, LaQisha Marshall, Tony Dean Skipworth, Yong Kim |  |  | LaQisha Marshall, Nick Varga, Tony Dean Skipworth |  |  | Jay Bucsa | CA-LAX | Chaffey Joint Union High School District | J00017862 | Nexus 9336C-FX2-E Deployment | Closed | 0% | 0% | 0 | -87.25 | 0 | 11541.25 | 0% | 0 | 0 | 87.25 | 11541.25 | 0 |  | 11541.25 |  | 152510.72 | 19856.72 | 8315.47 | 41.88%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, Jeff Barker, Juan Pomares, Karl Houston, Karyn Hubbard, LaQisha Marshall, Luis Ovalles, Yong Kim |  |  | Juan Pomares, LaQisha Marshall, Luis Ovalles |  |  | Jay Bucsa | CA-LAX | Chaffey Joint Union High School District | J00017864 | Cisco Unified Computing System (UCS) | Closed | 0% | 0% | 0 | -178.75 | 0 | 24823.75 | 0% | 0 | 20 | 198.75 | 23023.75 | 0 |  | 24823.75 |  | 587800.38 | 39652.88 | 14829.13 | 37.4%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, LaQisha Marshall, Tony Dean Skipworth, Yong Kim |  |  | LaQisha Marshall, Nick Varga, Tony Dean Skipworth |  |  | N/A | N/A | Chaffey Joint Union High School District | J00017862 | Nexus 9336C-FX2-E Deployment | Closed | 100% | 20.79% | 93.78 | 74.28 | 12172.7 | 2617.5 | 79.21% | 12172.7 | 0 | 19.5 | 0 | 0 |  | 2617.5 |  | 152510.72 | 19856.72 | 17239.22 | 86.82%
04/01/24 |  | 04/02/25 | Closed | LaQisha Marshall | David Escamilla |  | Jay Bucsa, Jeff Barker, Juan Pomares, Karl Houston, Karyn Hubbard, LaQisha Marshall, Luis Ovalles, Yong Kim |  |  | Juan Pomares, LaQisha Marshall, Luis Ovalles |  |  | N/A | N/A | Chaffey Joint Union High School District | J00017864 | Cisco Unified Computing System (UCS) | Closed | 100% | 29.54% | 222.6 | 156.85 | 33488.09 | 8813.75 | 70.46% | 33488.09 | 0 | 65.75 | 0 | 0 |  | 8813.75 |  | 587800.38 | 39652.88 | 30839.13 | 77.77%
03/04/24 |  | 04/02/25 | Closed | LaQisha Marshall | Warren Wilson |  | Christi D Hubbard, Garrett Hart, LaQisha Marshall, Larry Noble, Lori Endsley |  |  | Garrett Hart, LaQisha Marshall, Robert Jones |  |  | Christi D Hubbard | TX-CEN | Satterfield & Pontikes | J00017743 | Transportation Facility - Verkada | Closed | 100% | 124% | 83.48 | -19.02 | 9665.2 | 13265 | -22.78% | 9665.2 | 1 | 103.5 | 11871.25 | 0 |  | 13265 |  | 126845.11 | 102676.08 | 89411.08 | 87.08%
03/03/25 |  | 04/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002173 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 5352 | 0 | -60 | 0%
03/03/25 |  | 04/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002174 | N/A | Closed | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 12020 | 0 | -105 | 0%
03/03/25 |  | 04/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002175 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 4076 | 0 | -60 | 0%
03/03/25 |  | 04/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002180 | N/A | Closed | 0% | 0% | 0 | -29.5 | 0 | 885 | 0% | 0 | 0 | 29.5 | 0 | 0 |  | 885 |  | 48000 | 0 | -885 | 0%
03/03/25 |  | 04/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002182 | N/A | Closed | 0% | 0% | 0 | -16.5 | 0 | 495 | 0% | 0 | 0 | 16.5 | 0 | 0 |  | 495 |  | 42480 | 0 | -495 | 0%
03/03/25 |  | 04/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002183 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 15930 | 0 | -75 | 0%
03/03/25 |  | 04/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002185 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 8371 | 0 | -60 | 0%
03/03/25 |  | 04/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Lorenzo Hernandez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002186 | N/A | Not started | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 24310 | 0 | -120 | 0%
03/03/25 |  | 04/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002189 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 9779 | 0 | -90 | 0%
03/03/25 |  | 04/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez, Kai Rose , Pedro Cavazos, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002191 | N/A | Not started | 0% | 0% | 0 | -15 | 0 | 450 | 0% | 0 | 0 | 15 | 0 | 0 |  | 450 |  | 17840 | 0 | -450 | 0%
03/03/25 |  | 04/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Nathanael Morales, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002194 | N/A | Closed | 0% | 0% | 0 | -13.5 | 0 | 405 | 0% | 0 | 0 | 13.5 | 0 | 0 |  | 405 |  | 35440 | 0 | -405 | 0%
03/03/25 |  | 04/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002195 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 15930 | 0 | -45 | 0%
01/29/25 |  | 04/02/25 | Open | Richard Keith Arnst | Bryan Brown |  | Christopher Garcia, Clinton Bennett Deason, Jeremiah Solomon, Richard Keith Arnst, Robert Lavender, Susan Richardson |  |  | Clinton Bennett Deason, Richard Keith Arnst, Robert Lavender |  |  | Susan Richardson | TX-HOU | Howard Hughes Management Co., LLC | 200001728 | N/A | Closed | 100% | 124.4% | 22.5 | 2.5 | 2512.5 | 3450 | 11.11% | 2512.5 | 8 | 28 | 1080 | 0 |  | 3450 |  | 2844.91 | 3537 | 87 | 2.46%
05/28/24 |  | 04/02/25 | Open | Ryan Scott | David Watkins |  | Beau C. Devillier, David Watkins, Karen Grant-Dennison, Mario Sanchez, Matthew Veach, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Carlo Enriquez, Conner MacDonnell, Joaquin Marroquin, Joshua Hubbard, Kendall Walls, Mario Sanchez, Matthew Veach, Moises Rodriguez, Quy Le, Ryan Scott, William Chris Roome, Yonathan Fadel |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | J00018440 | THOP – East Campus | Closed | 100% | 75.17% | 732.31 | 197.81 | 91499.76 | 66315 | 27.01% | 91499.76 | 16 | 550.5 | 13907.5 | 0 |  | 66315 |  | 2128.97 | 355076.5 | 288761.5 | 81.32%
03/04/25 |  | 04/03/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002199 | N/A | Closed | 0% | 0% | 0 | -13 | 0 | 390 | 0% | 0 | 0 | 13 | 0 | 0 |  | 390 |  | 30850 | 0 | -390 | 0%
12/06/24 |  | 04/03/25 | Open | Ryan Scott | David Watkins |  | David Watkins, Mario Sanchez, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Mario Sanchez, Matthew Veach, Moises Rodriguez, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200000193 | N/A | Closed | 100% | 188% | 25 | -22 | 3225 | 6157.5 | -88% | 3225 | 0 | 47 | 0 | 0 |  | 6157.5 |  | 0 | 4304.4 | -1853.1 | -43.05%
02/18/25 |  | 04/04/25 | Closed | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Jeremiah Solomon, Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002085 | N/A | Closed | 100% | 33.67% | 5.94 | 3.94 | 0 | 200 | 66.33% | 0 | 0 | 2 | 0 | 0 |  | 200 |  | 123.9 | 752.8 | 552.8 | 73.43%
06/13/24 |  | 04/04/25 | Closed | Joanna Herrera | Bryan Brown |  | Joanna Herrera, Steve J Rodriguez, Xavier A Trevino |  |  | Clinton Bennett Deason, James Danner, Joanna Herrera, John Senkulics, Rene Trejo |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018510 | PB BOY 24 Projector Installs | Closed | 100% | 76.37% | 212.13 | 74.63 | 25886.16 | 14752.5 | 35.18% | 25886.16 | 24.5 | 162 | 12005 | 0 |  | 14752.5 |  | 30148.39 | 31466.8 | 16714.3 | 53.12%
03/20/23 |  | 04/04/25 | Closed | Joaquin Marroquin | Rogelio Dominguez |  | David Avila, Felix Martinez, Garrett Hart, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Rogelio Dominguez, Roger Guerra |  |  | Carlos Carrillo, Francisco Hernandez, Garrett Hart, Ivan Uribe, Jesus Cantu, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel |  |  | David Avila | TX-SOUT | Geo Group | J00015014 | Brownsville Camera Solution Install | Closed | 0% | 0% | 0 | -110.1 | 0 | 15502.3 | 0% | 0 | 29.23 | 139.33 | 13423.5 | 324.25 |  | 15502.3 |  | 27573.04 | 34362.87 | 18536.32 | 53.94%
03/20/23 |  | 04/04/25 | Closed | Joaquin Marroquin | Rogelio Dominguez |  | David Avila, Felix Martinez, Garrett Hart, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Rogelio Dominguez, Roger Guerra |  |  | Carlos Carrillo, Francisco Hernandez, Garrett Hart, Ivan Uribe, Jesus Cantu, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel |  |  | N/A | N/A | Geo Group | J00015014 | Brownsville Camera Solution Install | Closed | 100% | 22.85% | 96.27 | 85.77 | 10327.55 | 1320 | 89.09% | 10327.55 | 11.5 | 22 | 690 | 324.25 |  | 1320 |  | 27573.04 | 34362.87 | 32718.62 | 95.22%
05/10/24 |  | 04/04/25 | Closed | LaQisha Marshall | Steven Walker |  | Christi D Hubbard, LaQisha Marshall, Larry Noble, Lori Endsley, Luis Ovalles |  |  | LaQisha Marshall, Luis Ovalles, Sophia Quinter |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00018043 | PKI Environment Reconfiguration | Closed | 100% | 55% | 116.36 | 52.36 | 1437.5 | 8597.5 | 45% | 1437.5 | 0 | 64 | 7048.75 | 0 |  | 8597.5 |  | 0 | 11527.6 | 2930.1 | 25.42%
03/05/25 |  | 04/04/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Dedric Bowens, Lorenzo Hernandez |  |  | Jaclyn Pias | TX-HOU | GOM Shelf / Commodore Offshore | 200002205 | N/A | Closed | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 39214.2 | 0 | -105 | 0%
03/05/25 |  | 04/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Samsoni Jean Claude, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002208 | N/A | Not started | 0% | 0% | 0 | -37 | 0 | 1110 | 0% | 0 | 0 | 37 | 0 | 0 |  | 1110 |  | 88900 | 0 | -1110 | 0%
03/05/25 |  | 04/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002209 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 1778 | 0 | -60 | 0%
03/05/25 |  | 04/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002213 | N/A | Not started | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 17780 | 0 | -105 | 0%
03/06/25 |  | 04/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Pedro Cavazos, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002220 | N/A | Not started | 0% | 0% | 0 | -18 | 0 | 540 | 0% | 0 | 0 | 18 | 0 | 0 |  | 540 |  | 28625 | 0 | -540 | 0%
03/06/25 |  | 04/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002229 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 5025 | 0 | -60 | 0%
03/06/25 |  | 04/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002231 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3277.98 | 0 | -30 | 0%
03/06/25 |  | 04/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002232 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3556 | 0 | -30 | 0%
03/07/25 |  | 04/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Pedro Cavazos, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002241 | N/A | Not started | 0% | 0% | 0 | -38 | 0 | 1140 | 0% | 0 | 0 | 38 | 0 | 0 |  | 1140 |  | 36390 | 0 | -1140 | 0%
03/07/25 |  | 04/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002246 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 4617 | 0 | -15 | 0%
03/07/25 |  | 04/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002255 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 3000 | 0 | -90 | 0%
03/07/25 |  | 04/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002251 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 351.91 | 0 | -30 | 0%
03/07/25 |  | 04/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002252 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1500 | 0 | -30 | 0%
11/18/24 |  | 04/04/25 | Open | Robert McIver | Edward Padron |  | Edward Padron, Erick Nunez , Robert McIver, Xavier A Trevino |  |  | Alexander Chambless, Briliance Johnson, Christopher Prado, Grayson McClanahan, LaQisha Marshall, Oscar Gonzalez, Steven Shipmon |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200000119 | N/A | Closed | 100% | 139.3% | 15.08 | -5.92 | 1473.55 | 1432.5 | -39.26% | 1473.55 | 0 | 21 | 0 | 0 |  | 1432.5 |  | 18294.06 | 1976.8 | 544.3 | 27.53%
01/07/25 |  | 04/04/25 | Open | Robert McIver | Bryan Brown |  | Rene Trejo, Robert McIver, Xavier A Trevino |  |  | Clinton Bennett Deason, Jonathan Pina, Rene Trejo, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Texas State Technical College Waco | 200001582 | N/A | Closed | 100% | 84.93% | 91.25 | 25.25 | 9260.56 | 6427.5 | 27.67% | 9260.56 | 11.5 | 77.5 | 840 | 0 |  | 6427.5 |  | 17419.08 | 15612.4 | 9184.9 | 58.83%
11/04/24 |  | 04/07/25 | Closed | Brittney Antoinette Hickman | William Birdsong |  | Brittney Antoinette Hickman, Ernesto Gonzalez, Larry Noble, Lauren J Kennewell, Raul Velazquez, William Birdsong |  |  | Alexander Chambless, Briliance Johnson, Brittney Antoinette Hickman, Ernesto Gonzalez, Grayson McClanahan, Grayson Rigsby, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nick Varga, Oscar Gonzalez, Paul Serres, Raul Velazquez, Robert Jones, Steven Shipmon, Wilangel Francis |  |  | Lauren J Kennewell | TX-DAL | Belton ISD | J00019333 | Network Equipment and Services(E-Rate Cat 2) | Closed | 100% | 77.98% | 645.38 | 201.63 | 60363 | 43666.25 | 31.24% | 60363 | 59.5 | 503.25 | 3851.25 | 0 |  | 43666.25 |  | 564746.35 | 99387.6 | 55721.35 | 56.06%
10/04/23 |  | 04/07/25 | Open | Christina Rice | Michael Brett Beggs |  | Austen New LN: Howard Cockerham, Beau C. Devillier, Christina Rice, Christina Rice, Cory Bradfield, Cory Bradfield, Devin Moreno, Gena Robbins, Jeffery Giles, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Michael Brett Beggs, Shawn Sutton |  |  | Austen Howard, Christina Rice, Conner MacDonnell, Cory Bradfield, Devin Moreno, Gena Robbins, Jackory Nash, Jeffery Giles, Jhon Genao, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Tony Dean Skipworth |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00016590 | Denton ISD: UCS-X & Dell - DC Refresh | Training/Knowledge Transfer/Documentation | 90% | 102.6% | 409.89 | 9.64 | 50465.25 | 51603.75 | 2.352% | 50465.25 | 20.5 | 420.75 | 46758.75 | 0 |  | 51603.75 |  | 727494.38 | 66283.56 | 14679.81 | 22.15%
10/24/24 |  | 04/08/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Khalid Abunaja, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Hector Rivera, Justin Smallwood, Luis Alvarez, Miguel Reed |  |  | N/A | N/A | Houston ISD | J00019295 | Coop ES - CCTV | Closed | 0% | 0% | 0 | -15 | 0 | 1525 | 0% | 0 | 5 | 20 | 300 | 0 |  | 1525 |  | 31998.3 | 200 | -1325 | -662.5%
03/03/25 |  | 04/08/25 | Open | Tray Giddens | Mark J Chambliss |  | Dustin Huffman, Mark J Chambliss, Tray Giddens |  |  | Patrick Joseph Palermo, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200002233 | N/A | Closed | 100% | 112.5% | 4 | -0.5 | 0 | 757.5 | -12.5% | 0 | 0 | 4.5 | 0 | 0 |  | 757.5 |  | 0 | 1110 | 352.5 | 31.76%
03/04/25 |  | 04/09/25 | Open | Abiodun David Babasola | George Edwin Jacob |  | Abiodun David Babasola, Alexander Gutman, David Babasola |  |  | Abiodun David Babasola, Jacob Hill, Noah Trump, Tavis Jackson |  |  | Alex Gutman | TX-DAL | Tyler Junior College | 200002215 | N/A | Closed | 100% | 55% | 20 | 12 | 0 | 887.5 | 60% | 0 | 3 | 11 | 180 | 0 |  | 887.5 |  | 0 | 2606 | 1718.5 | 65.94%
03/10/25 |  | 04/09/25 | Open | Ali Al-Haddad | N/A |  | Ali Al-Haddad, Meredith A Richardson |  |  | Ali Al-Haddad, Daniel Hernandez, Garrett Hart, Jose R. Duarte, Justin Smallwood, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao |  |  | N/A | N/A | Houston ISD | 200002272 | N/A | Planning/Design/Staging | 0% | 0% | 0 | -77.5 | 0 | 7325 | 0% | 0 | 10 | 87.5 | 600 | 0 |  | 7325 |  | 0 | 0 | -7325 | 0%
12/08/23 |  | 04/09/25 | Closed | Jim Blackwell | Firas Abood |  | Ashley F Freeman, Eric Firestone, Firas Abood, Jim Blackwell, Larry Noble |  |  | Cory Bradfield, Eric Firestone, Jim Blackwell, Justin Cornish |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016828 | ISE Deployment | Closed | 100% | 63.24% | 578.75 | 230.5 | 83918.75 | 54146.25 | 39.83% | 83918.75 | 17.75 | 366 | 41497.5 | 0 |  | 54146.25 |  | 165785.6 | 0 | -54146.25 | 0%
03/10/25 |  | 04/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002275 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 14934.22 | 0 | -30 | 0%
03/10/25 |  | 04/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002279 | N/A | Closed | 0% | 0% | 0 | -20 | 0 | 600 | 0% | 0 | 0 | 20 | 0 | 0 |  | 600 |  | 37170 | 0 | -600 | 0%
03/04/25 |  | 04/10/25 | Closed | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Ali Al-Haddad, James Adams, Jose R. Duarte, Justin Smallwood |  |  | N/A | N/A | Houston ISD | 200002298 | N/A | Closed | 0% | 0% | 0 | -15.25 | 0 | 1550 | 0% | 0 | 3 | 18.25 | 180 | 0 |  | 1550 |  | 0 | 4800 | 3250 | 67.71%
03/11/25 |  | 04/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002287 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 1062 | 0 | -45 | 0%
03/11/25 |  | 04/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002288 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 1062 | 0 | -45 | 0%
03/11/25 |  | 04/10/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Gerardo Ramirez, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002290 | N/A | Not started | 0% | 0% | 0 | -13 | 0 | 390 | 0% | 0 | 0 | 13 | 0 | 0 |  | 390 |  | 20945 | 0 | -390 | 0%
03/11/25 |  | 04/10/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002292 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 4690 | 0 | -60 | 0%
03/11/25 |  | 04/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002296 | N/A | Closed | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 27081 | 0 | -135 | 0%
03/11/25 |  | 04/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002297 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 3148 | 70 | -20 | -28.57%
03/11/25 |  | 04/10/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002301 | N/A | Not started | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 12488 | 0 | -195 | 0%
03/11/25 |  | 04/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002303 | N/A | Not started | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 12982 | 280 | 130 | 46.43%
03/11/25 |  | 04/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002304 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 370 | 0 | -15 | 0%
03/11/25 |  | 04/10/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002305 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 2220 | 0 | -15 | 0%
01/23/23 |  | 04/10/25 | Closed | Richard Keith Arnst | George Delp |  | Aaron Christopher Pfeifer, Garrett Curran, Richard Keith Arnst, Yong Kim |  |  | Aaron Christopher Pfeifer, Richard Keith Arnst |  |  | Garrett Curran | CA-LAX | City of Burbank | J00014721 | Core Network Equipment Upgrade | Closed | 100% | 317.3% | 184.5 | -401 | 24702.5 | 78180 | -217.3% | 24702.5 | 0 | 585.5 | 66035 | 702.62 |  | 78180 |  | 0 | 56801.6 | -22081.02 | -38.87%
07/17/23 |  | 04/11/25 | Closed | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Joanna Herrera, Steve J Rodriguez, Xavier A Trevino |  |  | An Le, Angel Alicea, Angel Alicea-Torres, Celso Lopez, Daniel Quade, Delton Childs, Isaiah Rosales, James Danner, Jason Andrews, Joanna Herrera, John Senkulics, Juan Carlos Flores, Michael Torres, Stephen Camacho |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00015807 | SA - BOY 23 Projector Install | Closed | 100% | 88.37% | 1111.5 | 151.25 | 83921.25 | 66280 | 13.61% | 83921.25 | 22 | 982.25 | 64050 | 3416.51 |  | 66280 |  | 172783.26 | 109164 | 39467.49 | 36.15%
10/24/22 |  | 04/11/25 | Closed | Joanna Herrera | Edward Padron, Timothy Ramsey |  | Amy Martinez-Nagy, Christopher Prado, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Jaime Cortez, Joanna Herrera, Timothy Ramsey, Timothy Sean Marcyes |  |  | Carlos Carrillo, Christopher Prado, Daniel Dominguez, Francisco Hernandez, Francisco Rosa, Jaime Cortez, Jennifer Soliz, Joanna Herrera, Joaquin Garcia, Jorge Robert Rangel, Kolawole Ayeni, Mark Rosa, Oscar Garcia, Roger Guerra, Timothy Sean Marcyes, Trevor Galloso, William Brown |  |  | Eric Rodriguez | TX-SOUT | Mission CISD | J00013575 | eRate 25 - Network Hardware, WLS, UPS & CBL | Closed | 0% | 0% | 0 | -748.5 | 0 | 77057.75 | 0% | 0 | 36.9 | 785.4 | 74843.75 | 1164.96 |  | 77057.75 |  | 1089703.82 | 96826.07 | 18603.36 | 19.21%
10/24/22 |  | 04/11/25 | Closed | Joanna Herrera | Edward Padron, Timothy Ramsey |  | Amy Martinez-Nagy, Christopher Prado, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Jaime Cortez, Joanna Herrera, Timothy Ramsey, Timothy Sean Marcyes |  |  | Carlos Carrillo, Christopher Prado, Daniel Dominguez, Francisco Hernandez, Francisco Rosa, Jaime Cortez, Jennifer Soliz, Joanna Herrera, Joaquin Garcia, Jorge Robert Rangel, Kolawole Ayeni, Mark Rosa, Oscar Garcia, Roger Guerra, Timothy Sean Marcyes, Trevor Galloso, William Brown |  |  | N/A | N/A | Mission CISD | J00013575 | eRate 25 - Network Hardware, WLS, UPS & CBL | Closed | 100% | 0.1525% | 491.75 | 491 | 41535.38 | 82.5 | 99.85% | 41535.38 | 0 | 0.75 | 0 | 1164.96 |  | 82.5 |  | 1089703.82 | 96826.07 | 95578.61 | 98.71%
11/20/24 |  | 04/11/25 | Open | Marco Lish | Bryan Brown |  | Clinton Bennett Deason, Jeremiah Solomon, Marco Lish |  |  | Clinton Bennett Deason, Jeremiah Solomon, Marco Lish |  |  | N/A | N/A | City of Houston Mayors Office | 200000153 | N/A | Closed | 100% | 67.43% | 43.75 | 14.25 | 4629.1 | 2512.5 | 32.57% | 4629.1 | 0 | 29.5 | 0 | 0 |  | 2512.5 |  | 38269.6 | 8914.8 | 6402.3 | 71.82%
03/12/25 |  | 04/11/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Kai Rose |  |  | N/A | N/A | Houston ISD | 200002325 | N/A | Closed | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 15053 | 0 | -180 | 0%
03/12/25 |  | 04/11/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002331 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 7136 | 0 | -90 | 0%
03/13/25 |  | 04/11/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002339 | N/A | Closed | 0% | 0% | 0 | -11 | 0 | 330 | 0% | 0 | 0 | 11 | 0 | 0 |  | 330 |  | 23364 | 0 | -330 | 0%
03/13/25 |  | 04/11/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200002343 | N/A | Not started | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 9782 | 0 | -15 | 0%
03/13/25 |  | 04/11/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002344 | N/A | Closed | 0% | 0% | 0 | -8 | 0 | 240 | 0% | 0 | 0 | 8 | 0 | 0 |  | 240 |  | 23479 | 0 | -240 | 0%
03/13/25 |  | 04/11/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002347 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1778 | 0 | -30 | 0%
03/13/25 |  | 04/11/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002348 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 140 | 0 | -15 | 0%
03/13/25 |  | 04/11/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002351 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 985 | 0 | -15 | 0%
03/14/25 |  | 04/11/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002355 | N/A | Not started | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 3842 | 0 | -15 | 0%
02/06/25 |  | 04/14/25 | Open | Jason Matthew Davis | N/A |  | Christopher Puyear, Dominic Harrison, Gregory Allen Tillett, Jason Matthew Davis, Samuel Newland |  |  | Jason Matthew Davis, Samuel Newland |  |  | Dominic Harrison | N/A | Cloud Revolution | 200001917 | N/A | Closed | 100% | 40% | 40 | 24 | 5640 | 2172.5 | 60% | 5640 | 0 | 16 | 0 | 0 |  | 2172.5 |  | 0 | 0 | -2172.5 | 0%
09/24/24 |  | 04/14/25 | Open | Tray Giddens | Mark J Chambliss |  | Larry Noble, Lindie Lorraine Lamar, Mark J Chambliss, Tray Giddens |  |  | Ming Chiu, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Lamar University | J00019067 | UC Upgrade | Closed | 100% | 64.58% | 207.5 | 73.5 | 29257.5 | 18227.5 | 35.42% | 29257.5 | 0 | 134 | 250 | 0 |  | 18227.5 |  | 0 | 42581.2 | 24353.7 | 57.19%
12/05/24 |  | 04/15/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Julio C Montoya, Justin Smallwood, Miguel Reed, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | 200000214 | N/A | Closed | 0% | 0% | 0 | -81 | 0 | 9622.5 | 0% | 0 | 5.5 | 86.5 | 502.5 | 0 |  | 9622.5 |  | 24140.9 | 1600 | -8022.5 | -501.4%
09/11/23 |  | 04/15/25 | Open | Tray Giddens | Aman Khan |  | Ahmed Jameel, Aman Khan, Craig St. Rose, Craig St. Rose, David Neal Gravatt, Dustin Huffman, Kord Mullins, Kurt Sell, Nathan Dao, Tray Giddens |  |  | Ahmed Jameel, Andy Pham, Ben Crouch, Bryant Bush, Craig St. Rose, David Dobbs, David Neal Gravatt, Hector Rivera, Jerald Garner, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mohaymen Sodi, Nathan Dao, Nicolas Garakani, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Apache Corporation | J00016276 | Briarlake - New Building Refresh and Expansion | Closed | 100% | 133.6% | 486.46 | -130.79 | 50403.34 | 60165 | -26.89% | 50403.34 | 32.5 | 649.75 | 54437.5 | 95.55 |  | 60165 |  | 1073558.11 | 65938.4 | 5677.85 | 8.611%
03/11/25 |  | 04/16/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002380 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 7450 | 0 | -90 | 0%
03/17/25 |  | 04/16/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200002381 | N/A | Not started | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 13335 | 0 | -75 | 0%
02/10/25 |  | 04/16/25 | Open | Robert McIver | Bryan Brown |  | Christopher Garcia, Clinton Bennett Deason, Jason Osuna, Robert McIver |  |  | Clinton Bennett Deason, Rene Trejo, Robert McIver, Valentin Vasquez |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200001824 | N/A | Closed | 100% | 72.73% | 24.06 | 8.56 | 0 | 1590 | 35.58% | 0 | 2 | 17.5 | 150 | 0 |  | 1590 |  | 15749.04 | 5843.12 | 4253.12 | 72.79%
02/24/25 |  | 04/16/25 | Open | Robert McIver | Bryan Brown |  | Christopher Garcia, Clinton Bennett Deason, Jason Osuna, Robert McIver |  |  | Clinton Bennett Deason, Rene Trejo, Robert McIver |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200002096 | N/A | Closed | 100% | 64.76% | 26.25 | 10.75 | 0 | 1625 | 40.95% | 0 | 1.5 | 17 | 112.5 | 0 |  | 1625 |  | 18745.56 | 5889.2 | 4264.2 | 72.41%
03/11/25 |  | 04/16/25 | Open | Robert McIver | Bryan Brown |  | Christopher Garcia, Clinton Bennett Deason, Jason Osuna, Robert McIver |  |  | Clinton Bennett Deason, Rene Trejo, Robert McIver |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200002389 | N/A | Closed | 100% | 69.09% | 27.5 | 10 | 0 | 1600 | 36.36% | 0 | 1.5 | 19 | 112.5 | 0 |  | 1600 |  | 13381.96 | 4887.32 | 3287.32 | 67.26%
03/11/25 |  | 04/16/25 | Open | Robert McIver | Bryan Brown |  | Christopher Garcia, Clinton Bennett Deason, Jason Osuna, Robert McIver |  |  | Rene Trejo, Robert McIver |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200002390 | N/A | Closed | 100% | 60% | 10 | 4 | 0 | 550 | 40% | 0 | 0 | 6 | 0 | 0 |  | 550 |  | 16281.86 | 2971.68 | 2421.68 | 81.49%
03/18/25 |  | 04/16/25 | Open | Robert McIver | Bryan Brown |  | Christopher Garcia, Clinton Bennett Deason, Jason Osuna, Robert McIver |  |  | Clinton Bennett Deason, Rene Trejo, Robert McIver |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200002391 | N/A | Closed | 100% | 47.06% | 26.56 | 16.06 | 0 | 1062.5 | 60.47% | 0 | 2 | 12.5 | 150 | 0 |  | 1062.5 |  | 19880.01 | 5890 | 4827.5 | 81.96%
03/31/25 |  | 04/16/25 | Open | Robert McIver | Bryan Brown |  | Christopher Garcia, Jason Osuna, Robert McIver |  |  | Clinton Bennett Deason, Rene Trejo, Robert McIver |  |  | Jason Osuna | TX-CEN | Texas Tech University Health Sciences Center - El | 200002507 | N/A | Closed | 0% | 0% | 0 | -9 | 0 | 725 | 0% | 0 | 0 | 9 | 0 | 0 |  | 725 |  | 15506.69 | 6186.8 | 5461.8 | 88.28%
03/12/25 |  | 04/17/25 | Open | Abiodun David Babasola | Bryan Brown |  | Abiodun David Babasola, David Babasola, Dominic Harrison, Joel Hubbard, Robert Lavender |  |  | Abiodun David Babasola, Joel Hubbard, Joshua Hubbard, Robert Lavender |  |  | Dominic Harrison | N/A | Concentric | 200002396 | N/A | Closed | 100% | 74.18% | 85.94 | 26.19 | 0 | 7216.25 | 30.47% | 0 | 4 | 63.75 | 285 | 0 |  | 7216.25 |  | 23623.99 | 13189.48 | 5973.23 | 45.29%
03/18/25 |  | 04/17/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez, Gregory Posey, Kai Rose |  |  | N/A | N/A | Houston ISD | 200002392 | N/A | Not started | 0% | 0% | 0 | -8 | 0 | 240 | 0% | 0 | 0 | 8 | 0 | 0 |  | 240 |  | 8890 | 0 | -240 | 0%
03/18/25 |  | 04/17/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Gregory Posey, Josue Iglesias, Oscar Nunez, Pedro Cavazos, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002393 | N/A | Not started | 0% | 0% | 0 | -17.5 | 0 | 525 | 0% | 0 | 0 | 17.5 | 0 | 0 |  | 525 |  | 69299 | 0 | -525 | 0%
03/18/25 |  | 04/17/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002394 | N/A | Not started | 0% | 0% | 0 | -30 | 0 | 900 | 0% | 0 | 0 | 30 | 0 | 0 |  | 900 |  | 86304.99 | 1225 | 325 | 26.53%
03/18/25 |  | 04/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002395 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 916 | 0 | -30 | 0%
03/18/25 |  | 04/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002397 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4200 | 0 | -30 | 0%
03/18/25 |  | 04/17/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Kai Rose , Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002399 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 51780 | 0 | -150 | 0%
03/18/25 |  | 04/17/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002401 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 6229 | 0 | -90 | 0%
10/25/24 |  | 04/18/25 | Open | Christina Rice | Jacob Parks, Jeffrey Holman |  | Christina Rice, Christina Rice, Jacob Parks, Jeffrey Holman, Shawn Sutton, Sophia Quinter |  |  | Christina Rice, Eric Firestone, Sophia Quinter |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00019239 | Denton ISD: ISE Upgrade and VM Migration - 2024 | Training/Knowledge Transfer/Documentation | 90% | 70.89% | 52.9 | 15.4 | 7762.5 | 5425 | 29.11% | 7762.5 | 0 | 37.5 | 912.5 | 0 |  | 5425 |  | 74708 | 12229.56 | 6804.56 | 55.64%
08/29/22 |  | 04/18/25 | Open | Jennifer Soliz | Timothy Ramsey |  | Eric Firestone, Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Eric Firestone, James Danner, Jennifer Soliz, Kristopher Dwight |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00013117 | Substation Firewall Refresh – NERC | Closed | 100% | 65.09% | 864.21 | 322.71 | 115013.75 | 71060 | 37.34% | 115013.75 | 21 | 562.5 | 66710 | 446.94 |  | 71060 |  | 542937.38 | 163960.4 | 92453.46 | 56.39%
04/03/25 |  | 04/18/25 | Closed | Joanna Herrera | N/A |  | Christopher Ceykovsky, Joanna Herrera, Xavier A Trevino |  |  | Joanna Herrera, John Stephen Kurkjian |  |  | Xavier A Trevino | TX-SOUT | Calallen ISD | 200002617 | N/A | Closed | 0% | 0% | 0 | -12.5 | 0 | 1742.5 | 0% | 0 | 0 | 12.5 | 0 | 0 |  | 1742.5 |  | 0 | 0 | -1742.5 | 0%
05/09/22 |  | 04/18/25 | Closed | Lauren Lanzini Coffey | Billy Pearson, Mark J Chambliss, Wyley Johnson |  | Billy Pearson, Christine A Hupe, Jason Espino, Lauren Lanzini Coffey, Neel Shah, Ron Loge, Shiraz Humayun, Wyley Johnson |  |  | Andy Alvarenga, Daniel Hernandez, Devon LeMoine, Jaime Flores, Jeff Ogbor, Jeffrey Charles Primeaux, Jorge Ortiz Cardozo, Jose R. Duarte, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Lauren Lanzini Coffey, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Paul Serres, Ron Loge, Tony Dean Skipworth |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00012363 | Datacenter Network Refresh | Closed | 100% | 125.7% | 465.79 | -9.8 | 59365.35 | 70441.25 | -2.104% | 59365.35 | 109.86 | 585.45 | 56063.4 | 4716.59 |  | 70441.25 |  | 4231308.92 | 205000 | 129842.16 | 63.34%
09/21/22 |  | 04/18/25 | Open | Lauren Lanzini Coffey | Chad Hart, Mark J Chambliss |  | Chad Hart, Christine A Hupe, Christopher Garcia, Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah, Robert Kelly, Robert Kelly, Shiraz Humayun, Taylar Hansen |  |  | Adam Felix, Aldo Cortes, Aleksei Lavrushenkov, Andy Pham, Arius Deautrè Yarborough, Briliance Johnson, Charles Knox, David Dobbs, Devon LeMoine, Grayson Rigsby, Hector Rivera, Isaiah Covington, Jaime Flores, James Adams, Jeffrey Charles Primeaux, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Kyle Linder, Lauren Lanzini Coffey, Luis Alvarez, Matthew D'Ambrosio, Micah Rendon, Miguel Reed, Mohammed Al-Shaikhli, Mohanad Hamid, Osc |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00013979 | North Campus Austin Hospital - Network | Training/Knowledge Transfer/Documentation | 95% | 102% | 1271.38 | 133.88 | 11731.91 | 93700.85 | 10.53% | 11731.91 | 158.81 | 1296.31 | 74127.25 | 3940.8 |  | 93700.85 |  | 473063.4 | 134682 | 37040.35 | 27.5%
01/06/25 |  | 04/18/25 | Open | Shannon Marie Alvarado | George Edwin Jacob, Michael Brett Beggs |  | Camille Elizabeth Taber, Cory Bradfield, Cory Bradfield, George Edwin Jacob, Michael Brett Beggs, Shannon Marie Alvarado |  |  | Cory Bradfield, Diego Asencio, Shannon Marie Alvarado |  |  | Camille Taber | FL | Hillsborough County Public Schools | 200000304 | N/A | Closed | 100% | 48.28% | 207.13 | 135.13 | 27051.05 | 12560 | 65.24% | 27051.05 | 28 | 100 | 3780 | 0 |  | 12560 |  | 1212759 | 44171.24 | 31611.24 | 71.57%
03/22/24 |  | 04/21/25 | Open | Christina Rice | Joshua Adam Engle |  | Arcangelo Fanelli, Christina Rice, Christina Rice, Jeffery Alan Jorzig, Jeffery Jorzig, Joshua Adam Engle, Mark Forehand, Vitalii Stepanchenko |  |  | Bryan Mullen, Christina Rice, Conner MacDonnell, Jeffery Alan Jorzig, Ron Loge, Vitalii Stepanchenko |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | J00017461 | UTSW: OOB Mgmt Network Redesign QTS DC | Implementation/Deployment | 85% | 95.51% | 208.05 | 9.35 | 21297.65 | 25280 | 4.494% | 21297.65 | 0 | 198.7 | 19873.75 | 0 |  | 25280 |  | 137820 | 32798 | 7518 | 22.92%
08/09/24 |  | 04/21/25 | Closed | Christina Rice | Joshua Adam Engle |  | Beau C. Devillier, Christina Rice, Christina Rice, Joshua Adam Engle, Mark Forehand, William Davenport |  |  | Austen Howard, Bryce Evans, Caleb Henry, Calvin Darby, Christina Rice, Dante Torres, Devin Moreno, Jacob Hill, Jayden Colon, Jhon Genao, Joan Brito, Joshua Hubbard, Justin Mitchell, Noah Castleberry, Noah Trump, Phillip Ma Lim, Remijio Hernandez, Ryan Frankeberger, Samuel Gonzalez, Tavis Jackson |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | J00018049 | UTSW: 2024 Switch Refresh - Sundays | Closed | 100% | 52.93% | 650.4 | 327.15 | 57818.79 | 27772.5 | 50.3% | 57818.79 | 21 | 344.25 | 6726.25 | 0 |  | 27772.5 |  | 2511213.16 | 78586.2 | 50813.7 | 64.66%
02/25/25 |  | 04/21/25 | Closed | Summer Abunaja | David Watkins |  | David Watkins, Neel Shah, Summer Abunaja |  |  | Nathan Dao, Robert Kelly, Summer Abunaja |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200002187 | N/A | Closed | 100% | 29.91% | 58.5 | 41 | 0 | 1920 | 70.09% | 0 | 0 | 17.5 | 0 | 0 |  | 1920 |  | 0 | 10704 | 8784 | 82.06%
04/06/22 |  | 04/22/25 | Open | Lauren Lanzini Coffey | Wyley Johnson |  | Abdulrahman Farhan, Christine A Hupe, Fadi Ashour, Jason Espino, Lauren Lanzini Coffey, Neel Shah, Shiraz Humayun, Wyley Johnson |  |  | Abdulrahman Farhan, David Dobbs, Jaime Flores, Jason Espino, Jennifer Soliz, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Lauren Lanzini Coffey, Matthew D'Ambrosio, Ron Loge |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00012378 | Firepower - Security Refresh & ISE | Closed | 100% | 60.37% | 534.38 | 214.78 | 76472.5 | 44877.5 | 40.19% | 76472.5 | 3 | 322.6 | 37273.75 | 73.17 |  | 44877.5 |  | 3194491.92 | 333430.28 | 288479.61 | 86.52%
02/10/25 |  | 04/22/25 | Open | Richard Keith Arnst | Bryan Brown |  | Christopher Garcia, David D Tijerina, Richard Keith Arnst, Robert Lavender |  |  | Rene Trejo, Richard Keith Arnst, Robert Lavender |  |  | David D Tijerina | TX-CEN | Williamson County | 200001878 | N/A | Closed | 100% | 84.82% | 41.56 | 15.81 | 4522.5 | 3996.25 | 38.04% | 4522.5 | 9.5 | 35.25 | 1042.5 | 0 |  | 3996.25 |  | 15770.46 | 7617.6 | 3621.35 | 47.54%
03/06/25 |  | 04/24/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Warren Wilson, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002326 | N/A | Closed | 100% | 36.97% | 17.58 | 11.08 | 0 | 812.5 | 63.03% | 0 | 0 | 6.5 | 0 | 0 |  | 812.5 |  | 5245.2 | 6115.29 | 5302.79 | 86.71%
03/25/25 |  | 04/24/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002438 | N/A | Not started | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 13650 | 0 | -135 | 0%
03/25/25 |  | 04/24/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002453 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 25295 | 0 | -30 | 0%
03/25/25 |  | 04/24/25 | Closed | Michelle Duenes | Collin Mazzeno |  | Collin Mazzeno |  |  | David Lenihan, Dedric Bowens, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Lorenzo Hernandez, Steffany Alvarez |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200002454 | N/A | Closed | 0% | 0% | 0 | -42 | 0 | 1260 | 0% | 0 | 0 | 42 | 0 | 0 |  | 1260 |  | 0 | -280 | -1540 | 550%
09/06/23 |  | 04/25/25 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Beau C. Devillier, Bryan Geoghan, Christopher Ceykovsky, David Babasola, John Stephen Kurkjian, Taylor Leger |  |  | Abiodun David Babasola, Christopher Ceykovsky, John Stephen Kurkjian, Patrick Shea Thompson, Sean Cowhey |  |  | Taylor Leger | TX-DAL | Pottsboro ISD | J00016274 | Singlewire and Wahsega Proof of Concept (POC) | Closed | 100% | 106.5% | 101.4 | -6.6 | 12782.5 | 14040 | -6.509% | 12782.5 | 0 | 108 | 11465 | 90.4 |  | 14040 |  | 24860.5 | 19996.4 | 5866 | 29.34%
10/02/23 |  | 04/25/25 | Open | Christina Rice | Joshua Adam Engle |  | Aleksei Lavrushenkov, Christina Rice, Christina Rice, Jason Osuna, Joshua Adam Engle, Juan Pomares, Larry Noble, Nick Varga, Tavis Jackson, William Barrett Chancellor |  |  | Aleksei Lavrushenkov, Christina Rice, Juan Pomares, Nick Varga, Tavis Jackson, Walter Clay Knight |  |  | Jason Osuna | TX-CEN | Tyson Foods Inc | J00016576 | Tyson Life Cycle Project | Training/Knowledge Transfer/Documentation | 95% | 92.99% | 546.32 | 131.57 | 73952.18 | 54565 | 24.08% | 73952.18 | 93.25 | 508 | 46427.5 | 2151.08 |  | 54565 |  | 0 | 292680.4 | 235964.32 | 80.62%
03/15/23 |  | 04/25/25 | Closed | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Conner MacDonnell, Craig St. Rose, Craig St. Rose, Dylan Pittsinger, Francisco Medrano, James Danner, Joanna Herrera, Michael Torres, Remi Martinez-Montenegro, Steve J Rodriguez, Xavier A Trevino |  |  | Aaron Johns, Aldo Cortes, Alexis Cantu, An Le, Antonio Rivera, Celso Lopez, Craig St. Rose, Daniel Quade, Dante Torres, Devinn Anthony Campbell, Dylan Pittsinger, Felix Martinez, Francisco Hernandez, James Danner, Jerald Garner, Jesus Angel Cantu, Jesus Cantu, Joanna Herrera, Joel Fleming, Joel Hubbard, John Senkulics, Jose Salazar, Joshua Hubbard, Juan Carlos Flores, Kord Mullins, Kristopher Dwight, Luis Alvarez, Nicolas Garakani, Remi Martinez-Montenegro, Rene Trejo, Richard Colby, Robert Lav |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00014885 | Autism Grant Projectors | Closed | 100% | 107.4% | 763.25 | 69 | 57243.75 | 52688.95 | 9.04% | 57243.75 | 125.84 | 820.09 | 44706.25 | 1585.42 |  | 52688.95 |  | 149096.64 | 62763.36 | 8488.99 | 13.53%
02/07/23 |  | 04/25/25 | Open | Lauren Lanzini Coffey | Chad Hart, Mark J Chambliss |  | Chad Hart, Jaime B Flores, Jaime Flores, James Adams, Jorge Ortiz Cardozo, Julio C Montoya, Justin Cornish, Lauren Lanzini Coffey, Mark J Chambliss, Mohammad Jilani, Neel Shah, Shiraz Humayun |  |  | Aleksei Lavrushenkov, Brian Willery, Bryant Bush, Devon LeMoine, Jaime Flores, Jesus Gonzalez, Jorge Ortiz Cardozo, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Lauren Lanzini Coffey, Matthew D'Ambrosio, Miguel Reed, Ming Chiu, Mohammad Jilani, Mohammed Al-Shaikhli, Nathan Dao, Nicolas Garakani |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00012893 | POC - SDWAN Routers | Implementation/Deployment | 90% | 18.01% | 1320.57 | 1092.76 | 144853.5 | 24113.45 | 82.75% | 144853.5 | 10.06 | 237.87 | 17763.6 | 0 |  | 24113.45 |  | 1041678.5 | 259686.4 | 235572.95 | 90.71%
10/17/22 |  | 04/25/25 | Open | Marshall Chuck Pugh | Jacob Parks, Jeffrey Holman, William Birdsong |  | Austen New LN: Howard Cockerham, Beau C. Devillier, Bradley Buchanan, Calvin Darby, Cason Spencer, Devin Moreno, Dylan Pittsinger, Jacob Parks, Jeffery Giles, Jeffrey Holman, Jhon Genao, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Thompson, Kirk O'Guinn, Lauren J Kennewell, Majid Shirzadeh, Marshall Chuck Pugh, Nazario Armenta Barraza, Noah Castleberry, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Sean Cowhey, Tavis Jackson, Timothy Fain, William Birdsong |  |  | Caleb Baik, Calvin Darby, Carlo Enriquez, Cason Spencer, Chase Davis, Dante Torres, Devin Moreno, Dylan Pittsinger, Eric Mitchell Frisby, Frank Jaimes, Gena Robbins, Jacob Hill, Jayden Colon, Jeffery Giles, Jhon Genao, Joan Brito, Joshua Osgood, Juan Pomares, Justin Thompson, Kebret Eshetu, Kirk O'Guinn, Marshall Chuck Pugh, Michael McGee, Nazario Armenta Barraza, Noah Castleberry, Noah Trump, Patrick Thompson, Phillip Ma Lim, Quentin Sowels, Quy Le, Remijio Hernandez, Sattar Mohseni, Sean Cow |  |  | Lauren J Kennewell | TX-DAL | Desoto ISD | J00014050 | District Wireless Refresh - ERATE CAT2 | Closed | 100% | 124.9% | 957.19 | -117.06 | 71978.39 | 98643.75 | -12.23% | 71978.39 | 121 | 1195.25 | 76410 | 2362.83 |  | 98643.75 |  | 1012425.5 | 89436.8 | -11569.78 | -12.94%
03/26/25 |  | 04/25/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002464 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 2360 | 0 | -60 | 0%
03/26/25 |  | 04/25/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Gerardo Ramirez |  |  | N/A | N/A | Houston ISD | 200002465 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 9229 | 0 | -60 | 0%
03/26/25 |  | 04/25/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002468 | N/A | Not started | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 1175 | 0 | -15 | 0%
03/26/25 |  | 04/25/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002469 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 8920 | 0 | -75 | 0%
03/26/25 |  | 04/25/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Kai Rose |  |  | N/A | N/A | Houston ISD | 200002470 | N/A | Not started | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 8920 | 0 | -150 | 0%
03/27/25 |  | 04/25/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002478 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 5310 | 0 | -90 | 0%
03/27/25 |  | 04/25/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002480 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 1400 | 0 | -60 | 0%
03/27/25 |  | 04/25/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Kai Rose , Nathanael Morales, Oscar Nunez, Pedro Cavazos, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002481 | N/A | Not started | 0% | 0% | 0 | -16 | 0 | 480 | 0% | 0 | 0 | 16 | 0 | 0 |  | 480 |  | 32004 | 0 | -480 | 0%
09/04/24 |  | 04/28/25 | Closed | Christina Rice | Christopher Puyear |  | Beau C. Devillier, Christina Rice, Christina Rice, Hamzeh Tahat, Shawn Sutton |  |  | Christina Rice, Hamzeh Tahat, Henry Pugsley, Tony Dean Skipworth |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00018930 | Denton ISD: UC Upgrade | Closed | 100% | 77.43% | 183.38 | 41.38 | 25856.5 | 15707.5 | 22.57% | 25856.5 | 0 | 142 | 3487.5 | 10177.5 |  | 15707.5 |  | 0 | 39587 | 13702 | 34.61%
12/30/24 |  | 04/28/25 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Bryan Geoghan, Camille Elizabeth Taber, Shannon Marie Alvarado |  |  | Shannon Marie Alvarado |  |  | Camille Taber | FL | Polk County Sheriffs Office | 200000554 | N/A | Closed | 100% | 50.57% | 21.75 | 10.75 | 2928.75 | 1375 | 49.43% | 2928.75 | 0 | 11 | 0 | 0 |  | 1375 |  | 12679.76 | 23548.8 | 22173.8 | 94.16%
12/01/23 |  | 04/28/25 | Closed | Walter Clay Knight | Timothy Ramsey, Wyley Johnson |  | Camille Elizabeth Taber, Christopher Butler, Eduardo Villavicencio, Justin Jimenez, Timothy Ramsey, Wyley Johnson |  |  | Ashutosh Patel, Jaime Cortez, Lauren Lanzini Coffey, Timothy Sean Marcyes, Walter Clay Knight |  |  | Camille Taber | FL | Noven Pharmaceuticals | J00014018 | Fortinet Migration | Closed | 100% | 130.7% | 931.33 | -286.17 | 127227.25 | 188912.5 | -30.73% | 127227.25 | 0 | 1217.5 | 185837.5 | 213.13 |  | 188912.5 |  | 56000 | 28000 | -161125.63 | -575.4%
04/30/24 |  | 04/29/25 | Open | Lauren Lanzini Coffey | N/A |  | Khalid Abunaja, Lauren Lanzini Coffey |  |  | Gena Robbins, Lauren Lanzini Coffey |  |  | N/A | N/A | Netsync Network Solutions | J00016409 | Process Triage - Internal - AAAQ408035 | Implementation/Deployment | 0% | 0% | 0 | -10.5 | 0 | 1312.5 | 0% | 0 | 0 | 10.5 | 1312.5 | 8.71 |  | 1312.5 |  | 0 | 0 | -1321.21 | 0%
02/19/25 |  | 04/29/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Steven Walker, Tray Giddens |  |  | Christopher Brown, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200002088 | N/A | Closed | 100% | 111.8% | 27.5 | -3.25 | 0 | 4101.25 | -11.82% | 0 | 0 | 30.75 | 0 | 0 |  | 4101.25 |  | 0 | 5760.4 | 1659.15 | 28.8%
04/08/25 |  | 04/30/25 | Closed | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Ali Al-Haddad, Hector Rivera, Justin Cornish, Kord Mullins, Luis Alvarez |  |  | N/A | N/A | Houston ISD | 200002630 | N/A | Closed | 0% | 0% | 0 | -23 | 0 | 2140 | 0% | 0 | 4 | 27 | 240 | 0 |  | 2140 |  | 0 | 3275 | 1135 | 34.66%
06/27/24 |  | 04/30/25 | Closed | Brian Willery | William Birdsong |  | Beau C. Devillier, Brian Willery, Jeffery Alan Jorzig, Jeffery Jorzig, Lauren J Kennewell, Vitalii Stepanchenko, William Birdsong |  |  | Austen Howard, Brian Willery, Dante Torres, Joshua Hubbard, Noah Castleberry, Remijio Hernandez, Ryan Frankeberger, Sophia Quinter, Vitalii Stepanchenko |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00018607 | LAN and Wireless Installation - CRC & JJAEP | Closed | 100% | 109.8% | 205.09 | -14.16 | 20931.7 | 23121.25 | -6.904% | 20931.7 | 6 | 225.25 | 12750 | 0 |  | 23121.25 |  | 127246.59 | 31269.2 | 8147.95 | 26.06%
02/18/25 |  | 04/30/25 | Open | Christina Rice | Bryan Geoghan |  | Arcangelo Fanelli, Bryan Geoghan, Christina Rice, Christina Rice |  |  | Christina Rice, Henry Pugsley |  |  | Arcangelo Fanelli | TX-DAL | United Regional Health Care System | 200001977 | N/A | Training/Knowledge Transfer/Documentation | 80% | 25.56% | 45 | 33.5 | 0 | 1937.5 | 74.44% | 0 | 0 | 11.5 | 0 | 0 |  | 1937.5 |  | 0 | 11992 | 10054.5 | 83.84%
01/23/25 |  | 04/30/25 | Open | Christina Rice | David Watkins |  | Arcangelo Fanelli, Christina Rice, Christina Rice, David Watkins, Jeffery Alan Jorzig, Jeffery Jorzig, Mark Forehand |  |  | Christina Rice, Jeffery Alan Jorzig, Vitalii Stepanchenko |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | 200001671 | N/A | Planning/Design/Staging | 65% | 17.12% | 147.5 | 122.25 | 17267.5 | 3156.25 | 82.88% | 17267.5 | 0 | 25.25 | 0 | 0 |  | 3156.25 |  | 0 | 30390.8 | 27234.55 | 89.61%
02/25/25 |  | 04/30/25 | Open | Jennifer Soliz | Christopher Puyear |  | Christopher Puyear, Hannah Paul, Jennifer Soliz |  |  | Jennifer Soliz, Ming Chiu |  |  | Hannah Edmunds | TX-CEN | Texas Parks and Wildlife | 200002188 | N/A | Closed | 100% | 101.7% | 30 | -0.5 | 0 | 4157.5 | -1.667% | 0 | 0 | 30.5 | 0 | 0 |  | 4157.5 |  | 0 | 6218 | 2060.5 | 33.14%
12/27/24 |  | 04/30/25 | Open | Jim Blackwell | Aman Khan |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Aman Khan, Ashley F Freeman, Christopher Ngang, Jim Blackwell |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Craig St. Rose, Jim Blackwell, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Paul Serres |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200001499 | N/A | Closed | 100% | 35.61% | 454.28 | 306.53 | 0 | 13355 | 67.48% | 0 | 14 | 161.75 | 840 | 0 |  | 13355 |  | 314437.2 | 66405.2 | 53050.2 | 79.89%
10/28/24 |  | 04/30/25 | Open | Robert McIver | Edward Padron |  | Daniel Saenz, Diana Berger, Edward Padron, Robert McIver, Ruben Cantu |  |  | Carlos Carrillo, Francisco Hernandez, Jaime Galvan, Jonathan Pina, Jorge Robert Rangel, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Oscar Garcia, Paul Serres, Robert McIver, Roger Guerra, Ruben Cantu, Trevor Galloso |  |  | N/A | N/A | Hidalgo ISD | J00019326 | E-Rate Network Equipment Maintenance & Services | Closed | 100% | 111.4% | 455.51 | 10.26 | 39295.25 | 39876.25 | 2.252% | 39295.25 | 62 | 507.25 | 3850 | 0 |  | 39876.25 |  | 416689.26 | 51513.4 | 11637.15 | 22.59%
11/27/23 |  | 04/30/25 | Open | Shannon Marie Alvarado | Jacob Parks, Jeffrey Holman |  | Ashutosh Patel, Beau C. Devillier, Christina Rice, Christina Rice, Shannon Marie Alvarado, Shawn Sutton |  |  | Ashutosh Patel, Carlo Enriquez, Christina Rice, Quy Le, Shannon Marie Alvarado |  |  | Shawn Sutton | TX-DAL | Ector County ISD | J00013818 | ECISD: DC - QTY 2 Palo Alto 5250 FW Installs | Closed | 100% | 36.67% | 135 | 85.5 | 19575 | 6632.5 | 63.33% | 19575 | 0 | 49.5 | 462.5 | 0 |  | 6632.5 |  | 466229.4 | 26016.4 | 19383.9 | 74.51%
05/20/24 |  | 04/30/25 | Open | Shannon Marie Alvarado | Mark J Chambliss |  | Larry Noble, Lindie Lorraine Lamar, Patrick Joseph Palermo, Shannon Marie Alvarado |  |  | Patrick Joseph Palermo, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Lumberton ISD | J00018334 | CUBE SIP Gateway Replacement | Closed | 100% | 96.92% | 32.5 | 1 | 4582.5 | 5627.5 | 3.077% | 4582.5 | 0 | 31.5 | 5152.5 | 0 |  | 5627.5 |  | 8625 | 5978.8 | 351.3 | 5.876%
06/19/24 |  | 04/30/25 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Albert H Nguyen, Wyley Johnson |  | Ahmed Al-Zubaidi, Albert H Nguyen, Haley Glasscock, Jeffery Alan Jorzig, Jeffery Jorzig, Julio C Montoya, Kurt Sell, Lindie Lorraine Lamar, Shannon Marie Alvarado, Wyley Johnson |  |  | Baq Alsaedi, Devon LeMoine, Francisco Hernandez, Jeffery Alan Jorzig, Jesus Gonzalez, Jose R. Duarte, Julio C Montoya, Justin Smallwood, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Oscar Garcia, Paul Serres, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Raul Yzaguirre Schools for Success | J00018535 | E-Rate Year 2024-2025 – RFP # 24-05JA | Closed | 100% | 84.59% | 282.05 | 94.3 | 32719.19 | 21465.4 | 33.43% | 32719.19 | 50.84 | 238.59 | 16925 | 0 |  | 21465.4 |  | 147686.63 | 141218.35 | 119752.95 | 84.8%
08/21/23 |  | 05/01/25 | Open | Christina Rice | Bryan Geoghan |  | Beau C. Devillier, Brian Newman, Brian Newman, Bryan Geoghan, Christina Rice, Christina Rice, Henry Pugsley, Joel Hubbard, Joshua Hubbard, Shawn Sutton, William Davenport |  |  | Blake Garibaldi, Brian Newman, Caleb Henry, Calvin Darby, Christina Rice, Conner MacDonnell, Dante Torres, Dylan Pittsinger, Jayden Colon, Joel Hubbard, Joshua Hubbard, Kebret Eshetu, Kendall Walls, Noah Trump, Rene Trejo, Ryan Frankeberger, Sean Cowhey, William Chris Roome |  |  | Shawn Sutton | TX-DAL | Northwest ISD | J00016299 | NISD: District Wide Alto for Media Devices | Implementation/Deployment | 90% | 100.8% | 493.75 | 45.45 | 301.36 | 38873.75 | 9.205% | 301.36 | 49.5 | 497.8 | 26742.5 | 278.04 |  | 38873.75 |  | 404879.55 | 138209 | 99057.21 | 71.67%
05/02/24 |  | 05/01/25 | Open | Shannon Marie Alvarado | Firas Abood, Mark J Chambliss |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Hamzeh Tahat, Karyn Hubbard, Leonid G Kamenker, Leonid Kamenker, Samuel Newland, Shannon Marie Alvarado |  |  | Cory Bradfield, Hamzeh Tahat, Michael Garcia, Osazee Eweka, Samuel Newland, Shannon Marie Alvarado |  |  | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00017292 | UC Infra Installation & Apps Upgrade | Closed | 100% | 57.41% | 592.25 | 260.25 | 81565.25 | 45447.5 | 43.94% | 81565.25 | 8 | 340 | 25967.5 | 3277.5 |  | 45447.5 |  | 387306.6 | 73499.4 | 24774.4 | 33.71%
10/02/24 |  | 05/02/25 | Open | Jason Esry | Steven Walker |  | Jason Esry, Jeff Barker, Steven Walker, William Davenport |  |  | Jason Esry, Luis Ovalles |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00019133 | SQL Physical to Virtual Migration | Closed | 100% | 389% | 36.25 | -104.75 | 4821.25 | 18975 | -289% | 4821.25 | 0 | 141 | 0 | 0 |  | 18975 |  | 0 | 7087.2 | -11887.8 | -167.7%
10/02/24 |  | 05/02/25 | Open | Jason Esry | Steven Walker |  | Jason Esry, Jeff Barker, Steven Walker, William Davenport |  |  | Jason Esry, Luis Ovalles |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00019133 | SQL Physical to Virtual Migration | Closed | 0% | 0% | 0 | -10 | 0 | 1330 | 0% | 0 | 0 | 10 | 1330 | 0 |  | 1330 |  | 0 | 7087.2 | 5757.2 | 81.23%
10/14/24 |  | 05/02/25 | Open | Jason Esry | Saif Qaissi |  | Jason Esry, Kurt Sell, Saif Qaissi, Susan Richardson |  |  | Abdalsattar Albaghdadi, David Dobbs, Gregory Posey, Hector Rivera, Jaime Flores, James Adams, Jason Esry, Justin Cornish, Kevin Curtis, Matthew D'Ambrosio, Mohaymen Sodi, Paul Serres, Saif Qaissi |  |  | Susan Richardson | TX-HOU | PetroChina International (America), Inc. | J00019221 | Router Recommendation for Data Center (DC) | Closed | 100% | 117.9% | 149.64 | -6.86 | 122.58 | 18977.5 | -4.584% | 122.58 | 20 | 176.5 | 3375 | 0 |  | 18977.5 |  | 237936.1 | 22647.4 | 3669.9 | 16.2%
06/19/23 |  | 05/02/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah, Shiraz Humayun |  |  | Adam Felix, Andrew Longcor, Andrew Nguyen Longcor, Brian Willery, Grayson Rigsby, Jeffrey Charles Primeaux, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kyle Linder, Lauren Lanzini Coffey, Matthew D'Ambrosio, Ming Chiu, Paul Serres, Richard Shea, Robert Jones, Steven Shipmon |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00015844 | Austin Voice Deployment | Implementation/Deployment | 85% | 57.58% | 3327 | 1498.95 | 369100 | 179094.25 | 45.05% | 369100 | 87.5 | 1915.55 | 168394.25 | 72167.19 |  | 179094.25 |  | 150757.64 | 795614.1 | 544352.66 | 68.42%
07/01/24 |  | 05/02/25 | Open | Lauren Lanzini Coffey | Amanda Barney |  | Amanda Barney, Lauren Lanzini Coffey, Neel Shah |  |  | Lauren Lanzini Coffey, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00018603 | SecureLogix | Training/Knowledge Transfer/Documentation | 95% | 42.14% | 35 | 20.25 | 4935 | 1881.25 | 57.86% | 4935 | 0 | 14.75 | 718.75 | 0 |  | 1881.25 |  | 0 | 7772.4 | 5891.15 | 75.8%
04/02/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002518 | N/A | Closed | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 16668 | 0 | -120 | 0%
04/02/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002519 | N/A | Closed | 0% | 0% | 0 | -12 | 0 | 360 | 0% | 0 | 0 | 12 | 0 | 0 |  | 360 |  | 37792 | 35 | -325 | -928.6%
04/02/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002521 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 6768 | 315 | 285 | 90.48%
04/02/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Dedric Bowens, Kai Rose |  |  | N/A | N/A | Houston ISD | 200002522 | N/A | Closed | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 9027 | 0 | -105 | 0%
04/02/25 |  | 05/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002524 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 4445 | 0 | -60 | 0%
04/02/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Gerardo Ramirez, Gregory Posey, Kai Rose |  |  | N/A | N/A | Houston ISD | 200002525 | N/A | Closed | 0% | 0% | 0 | -7.5 | 0 | 225 | 0% | 0 | 0 | 7.5 | 0 | 0 |  | 225 |  | 17840 | 0 | -225 | 0%
04/03/25 |  | 05/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002527 | N/A | Not started | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 4315 | 0 | -45 | 0%
04/03/25 |  | 05/02/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Kai Rose , Lorenzo Hernandez, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002532 | N/A | Not started | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 33065 | 0 | -195 | 0%
04/03/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002534 | N/A | Closed | 0% | 0% | 0 | -8.5 | 0 | 255 | 0% | 0 | 0 | 8.5 | 0 | 0 |  | 255 |  | 21778 | 420 | 165 | 39.29%
04/03/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez |  |  | N/A | N/A | Houston ISD | 200002547 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3186 | 0 | -30 | 0%
04/04/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002549 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 6114 | 0 | -60 | 0%
04/04/25 |  | 05/02/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002550 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1094.19 | 0 | -30 | 0%
02/22/23 |  | 05/02/25 | Open | Ryan Scott | Bryan Geoghan, David Watkins |  | Arcangelo Fanelli, Austen New LN: Howard Cockerham, Beau C. Devillier, Blake Garibaldi, Bradley Buchanan, Brandon McMillan, Dante Torres, David Watkins, Devin Moreno, Erick Sanchez, Jeffery Giles, Joshua Osgood, Kirk O'Guinn, Noah Castleberry, Noah Trump, Phillip Ma Lim, Prince Owusu, Ryan Scott, Sean Cowhey, Tabais Prater, Taylor Leger |  |  | Adam Ko, Adrian Cordero, Angelo Gallegos, Austen Howard, Blake Garibaldi, Bradley Buchanan, Bryan Mullen, Caleb Baik, Carlo Enriquez, Cason Spencer, Chase Davis, Conner MacDonnell, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelino, Dylan Pittsinger, Erick Sanchez, Frank Jaimes, Jacob Hill, Jeffery Alan Jorzig, Jeffery Giles, Jhon Genao, Joan Brito, Joel Fleming, Joel Hubbard, Jonathan Weir, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Thompson, Kairo Sauceda, Kanoa Parman, Ke |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00013261 | NPH Refresh - Phase 2 - Floor 9-1 | Closed | 100% | 373% | 1486.9 | -3925.15 | 114826.68 | 461113.75 | -264% | 114826.68 | 134 | 5546.05 | 374091.25 | 5899.362 |  | 461113.75 |  | 5472357 | 366213.12 | -100799.992 | -27.52%
03/11/25 |  | 05/02/25 | Closed | Walter Clay Knight | Jeremy Williams |  | Camille Elizabeth Taber, Jeremy Williams, Walter Clay Knight |  |  | Tony Dean Skipworth, Walter Clay Knight |  |  | Camille Taber | FL | Mainline | 200002359 | N/A | Closed | 100% | 48.91% | 18.4 | 9.4 | 0 | 1190 | 51.09% | 0 | 0 | 9 | 0 | 0 |  | 1190 |  | 0 | 4254.1 | 3064.1 | 72.03%
04/28/25 |  | 05/05/25 | Closed | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Ali Al-Haddad, Jose R. Duarte, Luis Alvarez, Mohammed Al-Shaikhli, Nathan Dao |  |  | N/A | N/A | Houston ISD | 200002903 | N/A | Closed | 0% | 0% | 0 | -10 | 0 | 975 | 0% | 0 | 3 | 13 | 180 | 0 |  | 975 |  | 0 | 1130 | 155 | 13.72%
10/07/24 |  | 05/06/25 | Open | Richard Keith Arnst | Eduardo Chavez |  | Eduardo Chavez, Garrett Curran, Karyn Hubbard, Nick Varga, Richard Keith Arnst, Yong Kim |  |  | Austen Howard, James Adams, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nick Varga, Paul Serres, Richard Keith Arnst |  |  | Garrett Curran | CA-LAX | Westside Union School District | J00019152 | District Office Switch Refresh & Cable Cleanup | Closed | 100% | 140.8% | 96.79 | -3.46 | 10750.8 | 13098.75 | -3.575% | 10750.8 | 36 | 136.25 | 2972.5 | 0 |  | 13098.75 |  | 43965.05 | 35958.06 | 22859.31 | 63.57%
01/06/25 |  | 05/06/25 | Open | Summer Abunaja | Wyley Johnson |  | Ibrahim Altaweel, Jennifer Huie, Joseph Boglino, Rogelio Morgado-Perez, Summer Abunaja, Wyley Johnson |  |  | Ibrahim Altaweel, Rogelio Morgado-Perez |  |  | Joseph Boglino | US-FED | Singhal @ Company Inc. | 200001567 | N/A | Planning/Design/Staging | 20% | 97.33% | 374 | 10 | 56000 | 54600 | 2.674% | 56000 | 0 | 364 | 0 | 0 |  | 54600 |  | 0 | 40000 | -14600 | -36.5%
04/07/25 |  | 05/07/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002556 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3015 | 0 | -30 | 0%
04/07/25 |  | 05/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Jarshawn Newsome, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002559 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 11970 | 0 | -90 | 0%
04/07/25 |  | 05/07/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002560 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 21575 | 0 | -60 | 0%
04/07/25 |  | 05/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002561 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 7870 | 175 | 115 | 65.71%
04/07/25 |  | 05/07/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002565 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 2800 | 0 | -45 | 0%
11/05/24 |  | 05/08/25 | Closed | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Joanna Herrera, Michelle Bailey, Steve J Rodriguez, Xavier A Trevino |  |  | Clinton Bennett Deason, Jeremiah Solomon, Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00019369 | Break-Fix Classroom Projectors IDEA Lake Houston | Closed | 100% | 88.14% | 31.2 | 4.7 | 2988.58 | 2537.5 | 15.06% | 2988.58 | 1 | 27.5 | 125 | 0 |  | 2537.5 |  | 3637.34 | 4517.67 | 1980.17 | 43.83%
04/08/25 |  | 05/08/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002567 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 1780 | 0 | -60 | 0%
04/08/25 |  | 05/08/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002568 | N/A | Not started | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 13335 | 0 | -75 | 0%
04/08/25 |  | 05/08/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002569 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 13275 | 0 | -60 | 0%
04/08/25 |  | 05/08/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002572 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 15399 | 0 | -75 | 0%
04/08/25 |  | 05/08/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Kai Rose , Nathanael Morales, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002573 | N/A | Closed | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 15930 | 0 | -180 | 0%
04/08/25 |  | 05/08/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Kai Rose , Nathanael Morales, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002575 | N/A | Not started | 0% | 0% | 0 | -12 | 0 | 360 | 0% | 0 | 0 | 12 | 0 | 0 |  | 360 |  | 44450 | 0 | -360 | 0%
04/03/25 |  | 05/09/25 | Closed | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Ali Al-Haddad, Jarshawn Newsome, Nathan Dao, Pedro Cavazos, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002578 | N/A | Closed | 0% | 0% | 0 | -28 | 0 | 2185 | 0% | 0 | 4 | 32 | 150 | 0 |  | 2185 |  | 0 | -140 | -2325 | 1661%
03/27/25 |  | 05/09/25 | Open | Christina Rice | Jacob Parks, Jeffrey Holman, Michael Brett Beggs |  | Christina Rice, Christina Rice, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Shawn Sutton, Sophia Quinter |  |  | Christina Rice, Joshua Osgood, Luis Ovalles, Sophia Quinter |  |  | Shawn Sutton | TX-DAL | Denton ISD | 200002157 | N/A | Training/Knowledge Transfer/Documentation | 95% | 134.3% | 17.5 | -4 | 0 | 2970 | -22.86% | 0 | 2 | 23.5 | 120 | 0 |  | 2970 |  | 138843.78 | 3660.32 | 690.32 | 18.86%
09/20/23 |  | 05/09/25 | Open | Jason Esry | Aman Khan |  | Aman Khan, Amy Martinez-Nagy, Brandon McMillan, David Watkins, David D Tijerina, James Danner, Jason Esry, Kolawole Ayeni, Kristan Crawford, Kristan Kimberly Crawford, Larry Noble, Lauren Lanzini Coffey, Robert Kelly, Robert Jones, Robert Kelly, Shae-Lynn Kelly |  |  | Abdalsattar Albaghdadi, Adam Felix, Albert Bernal, Aleksei Lavrushenkov, Alexander Chambless, An Le, Angel Alicea, Anthony Lange, Arius Deautrè Yarborough, Briliance Johnson, Daniel Quade, Dustin Aaron Lowrey, Dylan Pittsinger, Frank Jaimes, Grayson McClanahan, Grayson Rigsby, Hector Rivera, Jaime Flores, James Danner, Jason Esry, Jeffrey Charles Primeaux, John Senkulics, Joshua Osgood, Julio Perez, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kyle Linder, LaMarwin Alexander, Lauren Lanzini |  |  | David D Tijerina | TX-CEN | Leander ISD | J00016507 | FY23 E-Rate Network Electronics | Training/Knowledge Transfer/Documentation | 95% | 111.1% | 6818.4 | -79.35 | 547043.51 | 556594.5 | -1.164% | 547043.51 | 677.7 | 7575.45 | 471710 | 32436.95 |  | 556594.5 |  | 8486470.68 | 723041.58 | 134010.13 | 18.53%
02/10/25 |  | 05/09/25 | Closed | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Henry Pugsley, Joanna Herrera, Joel Hubbard, Lauren J Kennewell |  |  | Henry Pugsley, Joanna Herrera, Joel Hubbard |  |  | Lauren J Kennewell | TX-DAL | City of Waco | 200001875 | N/A | Closed | 100% | 93.85% | 32.5 | 5.5 | 3952.5 | 4162.5 | 16.92% | 3952.5 | 3.5 | 30.5 | 262.5 | 0 |  | 4162.5 |  | 9600.78 | 6250.4 | 2087.9 | 33.4%
04/28/25 |  | 05/09/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Warren Wilson, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002899 | N/A | Closed | 100% | 33.2% | 7.53 | 5.03 | 0 | 312.5 | 66.8% | 0 | 0 | 2.5 | 0 | 0 |  | 312.5 |  | 2826.82 | 1267.2 | 954.7 | 75.34%
11/20/24 |  | 05/09/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah |  |  | Andrew Nguyen Longcor, Henry Pugsley, Lauren Lanzini Coffey, Michael Garcia, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200000128 | N/A | Implementation/Deployment | 95% | 57.36% | 227.5 | 97 | 32077.5 | 18472.5 | 42.64% | 32077.5 | 0 | 130.5 | 0 | 6785 |  | 18472.5 |  | 0 | 52927.6 | 27670.1 | 52.28%
07/22/24 |  | 05/09/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Lauren Lanzini Coffey, Mark J Chambliss, Ming Chiu, Neel Shah |  |  | Carlos Montalvo, Lauren Lanzini Coffey, Ming Chiu, Patrick Joseph Palermo |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00018669 | Webex App Softphone POC | Planning/Design/Staging | 20% | 30% | 150 | 105 | 21150 | 6190 | 70% | 21150 | 0 | 45 | 673.75 | 0 |  | 6190 |  | 0 | 45441.2 | 39251.2 | 86.38%
04/11/25 |  | 05/09/25 | Closed | Michelle Duenes | Collin Mazzeno |  | Collin Mazzeno |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Harold Gomez, Jarshawn Newsome, Jesus Guadian, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200002614 | N/A | Closed | 0% | 0% | 0 | -261.5 | 0 | 7845 | 0% | 0 | 0 | 261.5 | 0 | 0 |  | 7845 |  | 0 | 64000 | 56155 | 87.74%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002577 | N/A | Closed | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 20516 | 0 | -180 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002579 | N/A | Closed | 0% | 0% | 0 | -10 | 0 | 300 | 0% | 0 | 0 | 10 | 0 | 0 |  | 300 |  | 31860 | 0 | -300 | 0%
04/09/25 |  | 05/09/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002581 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 6244 | 0 | -90 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Kai Rose , Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002582 | N/A | Closed | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 12213 | 0 | -120 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales, Oscar Nunez, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002583 | N/A | Closed | 0% | 0% | 0 | -6.5 | 0 | 195 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 195 |  | 8890 | 0 | -195 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002586 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 5334 | 0 | -30 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, Kai Rose , Nathanael Morales, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002591 | N/A | Closed | 0% | 0% | 0 | -9.5 | 0 | 285 | 0% | 0 | 0 | 9.5 | 0 | 0 |  | 285 |  | 21240 | 0 | -285 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Oscar Nunez, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002592 | N/A | Closed | 0% | 0% | 0 | -12 | 0 | 360 | 0% | 0 | 0 | 12 | 0 | 0 |  | 360 |  | 42480 | 0 | -360 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Dedric Bowens, Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002594 | N/A | Closed | 0% | 0% | 0 | -11.5 | 0 | 345 | 0% | 0 | 0 | 11.5 | 0 | 0 |  | 345 |  | 47790 | 0 | -345 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002595 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 7112 | 0 | -30 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002596 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 9812 | 0 | -60 | 0%
04/09/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002597 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3186 | 0 | -30 | 0%
04/10/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002603 | N/A | Closed | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 5310 | 0 | -105 | 0%
04/10/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Oscar Nunez, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002608 | N/A | Closed | 0% | 0% | 0 | -66 | 0 | 1980 | 0% | 0 | 0 | 66 | 0 | 0 |  | 1980 |  | 99190 | 0 | -1980 | 0%
04/11/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002619 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1490 | 0 | -30 | 0%
04/11/25 |  | 05/09/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002620 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 1850 | 0 | -60 | 0%
05/10/24 |  | 05/09/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Isaac Brown, Aboobiada Ali Abdalla, Ana Morales, Andrew Comeaux, Anthony Balogun, Arelly Revilla, Brisney Roblero, Conner MacDonnell, Daley Gil, Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Jennifer Mares, Joshua Jones, Josue Iglesias, Kai Rose , Mia Rose, Onyejebosa Okwumabua, Randall Jordan, Steffany Alvarez, Tamarron Sharpe, Victor Hernandez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | J00018403 | 8000481956 | Closed | 100% | 8.57% | 30000 | 27428.97 | 1053763.75 | 77100.9 | 91.43% | 1053763.75 | 0 | 2571.03 | 76035.9 | 0 |  | 77100.9 |  | 0 | 600000 | 522899.1 | 87.15%
05/10/24 |  | 05/09/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Adiel Alvarez, Ahmad Al-Dahoun, Ana Morales, Andrew Comeaux, Anjane Johnson, Anthony Balogun, Arelly Revilla, Brisney Roblero, Chad Bradford Smith, Cleophus Turner, Daniel Guadian, Daniela Revilla, David Balogun, David Lenihan, Dedric Bowens, Demetric Latigue, Detrick Bowens, Esmat Osman, Fahd Okla, Folasayo Adekanbi, Frank Bartunek, Gerardo Ramirez, Geremy Howard, Gregory Posey, Ismael Castillo, James Charvis, James Robertson, Jared Galvan, Jaren Smallwood, Jarshawn New |  |  | N/A | N/A | Houston ISD | J00018404 | 8000481956 | Closed | 100% | 33.52% | 20000 | 13296.32 | 704449.4 | 199641.1 | 66.48% | 704449.4 | 0 | 6703.68 | 145976.1 | 0 |  | 199641.1 |  | 0 | 600000 | 400358.9 | 66.73%
04/10/25 |  | 05/09/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | David Lenihan, Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Steffany Alvarez |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200002611 | N/A | Closed | 0% | 0% | 0 | -69.5 | 0 | 2085 | 0% | 0 | 0 | 69.5 | 0 | 0 |  | 2085 |  | 0 | 4104 | 2019 | 49.2%
03/04/25 |  | 05/09/25 | Open | Shannon Marie Alvarado | Albert H Nguyen |  | Lindie Lorraine Lamar, Magdalena Rodriguez, Moises Rodriguez, Nelson Garcia, Shannon Marie Alvarado |  |  | Moises Rodriguez, Nathan Dao, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | REPSOL INC | 200002248 | N/A | Closed | 100% | 55% | 20 | 9 | 0 | 1520 | 45% | 0 | 0 | 11 | 0 | 0 |  | 1520 |  | 0 | 6088 | 4568 | 75.03%
04/25/25 |  | 05/12/25 | Closed | LaQisha Marshall | Christopher Puyear |  | Christopher Puyear, David D Tijerina, LaQisha Marshall |  |  | LaQisha Marshall |  |  | David D Tijerina | TX-CEN | Travis County | 200002590 | N/A | Closed | 100% | 43.33% | 7.5 | 4.25 | 0 | 406.25 | 56.67% | 0 | 0 | 3.25 | 0 | 0 |  | 406.25 |  | 10000 | 984.4 | 578.15 | 58.73%
06/19/23 |  | 05/12/25 | Open | Richard Keith Arnst | Aman Khan, David Watkins, Joseph Hayes |  | Aman Khan, Craig St. Rose, Craig St. Rose, David Watkins, David Neal Gravatt, Joseph Hayes, Monica Johnson, Richard Keith Arnst |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Craig St. Rose, David Neal Gravatt, Hector Rivera, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio, Moises Rodriguez, Richard Keith Arnst |  |  | Monica Johnson | TX-HOU | Port of Houston Authority | J00015867 | Next Gen | Closed | 100% | 44.76% | 2659.19 | 1536.44 | 223171.81 | 144068.75 | 57.78% | 223171.81 | 67.5 | 1190.25 | 123551.25 | 692.53 |  | 144068.75 |  | 715143.17 | 248506.78 | 103745.5 | 41.75%
12/12/24 |  | 05/12/25 | Open | Robert McIver | Edward Padron |  | Conner MacDonnell, Edward Padron, Erick Nunez , Felix Martinez, Jonathan Pina, Robert McIver, Taylor Poole, Xavier A Trevino |  |  | Erick Nunez , Francisco Hernandez, Jonathan Pina, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200000290 | N/A | Closed | 100% | 117.3% | 50.52 | -4.23 | 4903.35 | 5570 | -8.373% | 4903.35 | 4.5 | 59.25 | 270 | 0 |  | 5570 |  | 0 | 6637.2 | 1067.2 | 16.08%
10/28/24 |  | 05/12/25 | Open | Ryan Scott | David Watkins |  | Beau C. Devillier, Christopher Prado, David Watkins, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Brian Willery, Christopher Prado, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | J00019328 | Wi-Fi Predictive- Huron Valley – Sinai Hospital | Closed | 100% | 75.09% | 66.25 | 16.5 | 8546.25 | 5596.25 | 24.91% | 8546.25 | 0 | 49.75 | 0 | 0 |  | 5596.25 |  | 0 | 11406.8 | 5810.55 | 50.94%
10/28/24 |  | 05/12/25 | Closed | Walter Clay Knight | George Delp |  | Aaron Christopher Pfeifer, George Delp, Jessica Anderson |  |  | Aaron Christopher Pfeifer, Carlo Enriquez, Conner MacDonnell, Walter Clay Knight |  |  | Jessica Anderson | US-SP | LTC Connect | J00019273 | LTC Egress Router Design | Closed | 100% | 81.54% | 97.5 | 18 | 12517.5 | 10350 | 18.46% | 12517.5 | 0 | 79.5 | 0 | 0 |  | 10350 |  | 50082.1 | 18400.4 | 8050.4 | 43.75%
11/05/24 |  | 05/13/25 | Open | Brian Willery | Mark J Chambliss |  | Brian Willery, Larry Noble, Mark J Chambliss, Monica Johnson |  |  | Anthony Towsley, Brian Willery |  |  | Monica Johnson | TX-HOU | Channelview ISD | J00019377 | UC Upgrade | Closed | 100% | 103.3% | 86.4 | -2.85 | 12240 | 12281.25 | -3.299% | 12240 | 0 | 89.25 | 0 | 0 |  | 12281.25 |  | 0 | 16347.2 | 4065.95 | 24.87%
06/12/24 |  | 05/14/25 | Open | Christina Rice | Christopher Puyear |  | Brian Newman, Brian Newman, Christi D Hubbard, Christina Rice, Christina Rice, Christopher Puyear, Larry Noble |  |  | Brian Newman, Christina Rice |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | J00018405 | Lake Travis ISD: Singlewire Fusion & Paging Gtwy | Training/Knowledge Transfer/Documentation | 80% | 27.71% | 38.26 | 27.66 | 5292.5 | 1400 | 72.29% | 5292.5 | 0 | 10.6 | 746.25 | 0 |  | 1400 |  | 137150.6 | 6606.4 | 5206.4 | 78.81%
10/14/24 |  | 05/14/25 | Open | Marco Lish | Bryan Geoghan |  | Alexander Gutman, Beau C. Devillier, Bryan Geoghan, Marco Lish |  |  | Henry Pugsley, Marco Lish |  |  | Alex Gutman | TX-DAL | North Texas Tollway Authority | J00019206 | RedSky E911 Deployment | Closed | 100% | 83.48% | 57.5 | 9.5 | 8107.5 | 7975 | 16.52% | 8107.5 | 0 | 48 | 800 | 0 |  | 7975 |  | 25988.4 | 12769.2 | 4794.2 | 37.55%
04/14/25 |  | 05/14/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002627 | N/A | Closed | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 2350 | 0 | -15 | 0%
10/30/24 |  | 05/15/25 | Closed | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Bryan Geoghan, David Babasola, Hamzeh Tahat, Jeff Barker, Taylor Leger |  |  | Abiodun David Babasola, Hamzeh Tahat |  |  | Taylor Leger | TX-DAL | Town of Little Elm | J00019210 | Collaboration IP Change | Closed | 100% | 118.3% | 58.13 | -10.62 | 8196.25 | 7168.75 | -18.27% | 8196.25 | 0 | 68.75 | 0 | 7360 |  | 7168.75 |  | 0 | 11186.8 | -3341.95 | -29.87%
05/02/25 |  | 05/15/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Warren Wilson, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002931 | N/A | Closed | 100% | 33.2% | 7.53 | 5.03 | 0 | 312.5 | 66.8% | 0 | 0 | 2.5 | 0 | 0 |  | 312.5 |  | 2793.84 | 1267.6 | 955.1 | 75.35%
04/15/25 |  | 05/15/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002632 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 4530 | 0 | -60 | 0%
04/17/25 |  | 05/15/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200002648 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 21240 | 0 | -60 | 0%
02/17/25 |  | 05/16/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Justin Smallwood, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | 200001993 | N/A | Closed | 0% | 0% | 0 | -17.5 | 0 | 1817.5 | 0% | 0 | 2 | 19.5 | 120 | 0 |  | 1817.5 |  | 3440 | 800 | -1017.5 | -127.2%
02/25/25 |  | 05/16/25 | Closed | Brian Willery | William Birdsong |  | Brian Willery, Mark Forehand, William Birdsong |  |  | Brian Willery |  |  | Mark Forehand | TX-DAL | RENT-A-CENTER, INC | 200002107 | N/A | Training/Knowledge Transfer/Documentation | 100% | 112.5% | 6 | -0.75 | 0 | 843.75 | -12.5% | 0 | 0 | 6.75 | 0 | 0 |  | 843.75 |  | 191633.46 | 1128 | 284.25 | 25.2%
01/24/22 |  | 05/16/25 | Open | Lauren Lanzini Coffey | Billy Pearson, Firas Abood |  | Firas Abood, Lauren Lanzini Coffey, Michael Hilton, Neel Shah, Ron Loge, Tony Dean Skipworth |  |  | Andy Pham, Devon LeMoine, Justin Cornish, Lauren Lanzini Coffey, Michael Hilton, Ron Loge, Tony Dean Skipworth |  |  | N/A | N/A | Sam Houston State University | J00011651 | ACI Deployment | Training/Knowledge Transfer/Documentation | 95% | 2.946% | 288.56 | 280.06 | 32286.7 | 980.5 | 97.05% | 32286.7 | 0 | 8.5 | 0 | 643.98 |  | 980.5 |  | 956677.52 | 94815.2 | 93190.72 | 98.29%
01/24/22 |  | 05/16/25 | Open | Lauren Lanzini Coffey | Billy Pearson, Firas Abood |  | Firas Abood, Lauren Lanzini Coffey, Michael Hilton, Neel Shah, Ron Loge, Tony Dean Skipworth |  |  | Andy Pham, Devon LeMoine, Justin Cornish, Lauren Lanzini Coffey, Michael Hilton, Ron Loge, Tony Dean Skipworth |  |  | Neel Shah | TX-HOU | Sam Houston State University | J00011651 | ACI Deployment | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -269.6 | 0 | 32092 | 0% | 0 | 21 | 290.6 | 29954 | 643.98 |  | 32092 |  | 956677.52 | 94815.2 | 62079.22 | 65.47%
04/16/25 |  | 05/16/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002639 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8528 | 0 | -30 | 0%
04/16/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | David Lenihan, Dedric Bowens, Gerardo Ramirez |  |  | N/A | N/A | Houston ISD | 200002641 | N/A | Closed | 0% | 0% | 0 | -8 | 0 | 240 | 0% | 0 | 0 | 8 | 0 | 0 |  | 240 |  | 10704 | 0 | -240 | 0%
04/16/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002643 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 10704 | 0 | -45 | 0%
04/17/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Andrew Comeaux, David Lenihan, Gerardo Ramirez, Kai Rose , Nathanael Morales, Oscar Nunez, Pedro Cavazos, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002647 | N/A | Closed | 0% | 0% | 0 | -41.5 | 0 | 1245 | 0% | 0 | 0 | 41.5 | 0 | 0 |  | 1245 |  | 85083 | 0 | -1245 | 0%
04/17/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002649 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 300 | 0 | -30 | 0%
04/17/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002650 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1778 | 0 | -30 | 0%
04/18/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002654 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8496 | 0 | -30 | 0%
04/18/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002656 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 8790 | 0 | -90 | 0%
04/18/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002657 | N/A | Closed | 0% | 0% | 0 | -15 | 0 | 450 | 0% | 0 | 0 | 15 | 0 | 0 |  | 450 |  | 58410 | 0 | -450 | 0%
04/18/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Jarshawn Newsome, Nathanael Morales, Steffany Alvarez |  |  | N/A | N/A | Houston ISD | 200002658 | N/A | Closed | 0% | 0% | 0 | -8 | 0 | 240 | 0% | 0 | 0 | 8 | 0 | 0 |  | 240 |  | 16600 | 0 | -240 | 0%
04/18/25 |  | 05/16/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002659 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 892 | 0 | -30 | 0%
04/18/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Jarshawn Newsome, Kai Rose , Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002663 | N/A | Closed | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 31860 | 0 | -120 | 0%
04/18/25 |  | 05/16/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002665 | N/A | Closed | 0% | 0% | 0 | -3.75 | 0 | 112.5 | 0% | 0 | 0 | 3.75 | 0 | 0 |  | 112.5 |  | 7965 | 0 | -112.5 | 0%
01/06/25 |  | 05/16/25 | Open | Richard Keith Arnst | Bryan Brown |  | Christopher Garcia, Joel Hubbard, Lauren J Kennewell, Richard Keith Arnst, Robert Lavender |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | Methodist Health System | 200000349 | N/A | Closed | 100% | 91.56% | 75.63 | 14.88 | 8333.75 | 8056.25 | 19.67% | 8333.75 | 8.5 | 69.25 | 907.5 | 0 |  | 8056.25 |  | 16446.87 | 14036.64 | 5980.39 | 42.61%
09/21/23 |  | 05/20/25 | Closed | Joaquin Marroquin | Vernon Jackson |  | Felix Martinez, Joaquin Marroquin, Samuel Newland, Vernon Jackson, Xavier A Trevino |  |  | Bryant Bush, Carlos Carrillo, Francisco Hernandez, Hector Rivera, Jesus Angel Cantu, Joaquin Marroquin, Jorge Robert Rangel, Juan Arturo Gonzalez Jr, Lance Daniel Waitschies, Luis Alvarez, Rodney Sincere Robinson, Samuel Newland, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | J00015883 | Voice Gateway Refresh | Closed | 100% | 101.7% | 393.44 | 19.49 | 50101.25 | 38588.25 | 4.954% | 50101.25 | 26.25 | 400.2 | 36115.75 | 5133.1 |  | 38588.25 |  | 474407.59 | 82765.98 | 39044.63 | 47.17%
04/21/25 |  | 05/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Nathanael Morales, Oscar Nunez, Steffany Alvarez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002669 | N/A | Not started | 0% | 0% | 0 | -13.5 | 0 | 405 | 0% | 0 | 0 | 13.5 | 0 | 0 |  | 405 |  | 17840 | 0 | -405 | 0%
04/21/25 |  | 05/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002670 | N/A | Closed | 0% | 0% | 0 | -6.75 | 0 | 202.5 | 0% | 0 | 0 | 6.75 | 0 | 0 |  | 202.5 |  | 26550 | 0 | -202.5 | 0%
04/21/25 |  | 05/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002671 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 15930 | 0 | -60 | 0%
04/21/25 |  | 05/21/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002676 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 2667 | 0 | -60 | 0%
04/21/25 |  | 05/21/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002680 | N/A | Closed | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 29352 | 0 | -135 | 0%
04/24/25 |  | 05/22/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Hector Rivera, Justin Cornish, Justin Smallwood, Kord Mullins, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | 200002602 | N/A | Closed | 0% | 0% | 0 | -27 | 0 | 3100 | 0% | 0 | 11 | 38 | 660 | 0 |  | 3100 |  | 24300.9 | 1500 | -1600 | -106.7%
04/22/25 |  | 05/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Dedric Bowens, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Samsoni Jean Claude, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002682 | N/A | Closed | 0% | 0% | 0 | -15 | 0 | 450 | 0% | 0 | 0 | 15 | 0 | 0 |  | 450 |  | 53100 | 0 | -450 | 0%
04/22/25 |  | 05/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002683 | N/A | Closed | 0% | 0% | 0 | -8.5 | 0 | 255 | 0% | 0 | 0 | 8.5 | 0 | 0 |  | 255 |  | 29736 | 0 | -255 | 0%
04/22/25 |  | 05/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Dedric Bowens, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002684 | N/A | Closed | 0% | 0% | 0 | -5.75 | 0 | 172.5 | 0% | 0 | 0 | 5.75 | 0 | 0 |  | 172.5 |  | 26550 | 0 | -172.5 | 0%
04/22/25 |  | 05/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Dedric Bowens, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002685 | N/A | Closed | 0% | 0% | 0 | -7 | 0 | 210 | 0% | 0 | 0 | 7 | 0 | 0 |  | 210 |  | 38232 | 0 | -210 | 0%
04/22/25 |  | 05/22/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Nathanael Morales |  |  | N/A | N/A | Houston ISD | 200002686 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 1062 | 0 | -90 | 0%
04/22/25 |  | 05/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002687 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 19200 | 175 | 145 | 82.86%
04/22/25 |  | 05/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002689 | N/A | Closed | 0% | 0% | 0 | -3.75 | 0 | 112.5 | 0% | 0 | 0 | 3.75 | 0 | 0 |  | 112.5 |  | 5310 | 0 | -112.5 | 0%
04/22/25 |  | 05/22/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002692 | N/A | Not started | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 1784 | 0 | -15 | 0%
04/22/25 |  | 05/22/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Steffany Alvarez, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002698 | N/A | Closed | 0% | 0% | 0 | -5.5 | 0 | 165 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 165 |  | 10620 | 0 | -165 | 0%
12/19/24 |  | 05/23/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, James Adams, Justin Smallwood, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | 200000555 | N/A | Closed | 0% | 0% | 0 | -19.5 | 0 | 2300 | 0% | 0 | 3 | 22.5 | 180 | 0 |  | 2300 |  | 3280 | 800 | -1500 | -187.5%
04/24/25 |  | 05/23/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Justin Smallwood, Kord Mullins |  |  | N/A | N/A | Houston ISD | 200002378 | N/A | Closed | 0% | 0% | 0 | -17.5 | 0 | 2070 | 0% | 0 | 2.5 | 20 | 150 | 0 |  | 2070 |  | 24300.9 | 1500 | -570 | -38%
09/11/24 |  | 05/23/25 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | Brian Willery |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00018979 | Cisco Catalyst 9136I Series x194 | Planning/Design/Staging | 50% | 15.08% | 124.31 | 105.56 | 9074.5 | 2343.75 | 84.92% | 9074.5 | 0 | 18.75 | 0 | 0 |  | 2343.75 |  | 0 | 14973.32 | 12629.57 | 84.35%
02/28/24 |  | 05/23/25 | Open | Christina Rice | Bryan Geoghan |  | Beau C. Devillier, Brian Newman, Brian Newman, Christina Rice, Christina Rice, Jayden Colon, Joel Hubbard, Karyn Hubbard, Shawn Sutton |  |  | Brian Newman, Christina Rice, Henry Pugsley, Jayden Colon, Joel Hubbard, Karyn Hubbard |  |  | Shawn Sutton | TX-DAL | Northwest ISD | J00014982 | NISD: WORK ORDER - Panic Button Installation | Implementation/Deployment | 25% | 17.12% | 160 | 135.1 | 12372.47 | 2882.5 | 84.44% | 12372.47 | 2.5 | 27.4 | 643.75 | 0 |  | 2882.5 |  | 42415 | 19462.8 | 16580.3 | 85.19%
04/23/25 |  | 05/23/25 | Open | Christina Rice | Joshua Adam Engle |  | Christina Rice, Christina Rice, Joshua Adam Engle, Mark Forehand, Ron Loge |  |  | Christina Rice, Ron Loge |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | 200001823 | N/A | Planning/Design/Staging | 15% | 6.757% | 122.1 | 113.85 | 15438.3 | 1343.75 | 93.24% | 15438.3 | 0 | 8.25 | 0 | 0 |  | 1343.75 |  | 81405 | 30567.6 | 29223.85 | 95.6%
01/08/24 |  | 05/23/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Carlos Montalvo, Christine A Hupe, Jaime B Flores, Jaime Flores, Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah, Shiraz Humayun, Summer Abunaja, Taylar Hansen |  |  | Adam Felix, Andrew Longcor, Andrew Nguyen Longcor, Andy Pham, Anthony Lange, Brian Willery, Briliance Johnson, Bryant Bush, Carlos Montalvo, Daniel Hernandez, David Dobbs, Devon LeMoine, Erick Nunez , Grayson Rigsby, Hector Rivera, Jaime Flores, Jason Matthew Davis, Jay Daniel De Leon, Jerald Garner, Jesus Gonzalez, John Hoyt, Jonathan Pina, Jorge Robert Rangel, Julio Perez, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Lauren |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00017234 | Cisco Migration Phase 2b | Training/Knowledge Transfer/Documentation | 95% | 77.81% | 7897 | 2407 | 896303.48 | 622755 | 30.48% | 896303.48 | 655 | 6145 | 495345 | 158832.91 |  | 622755 |  | 259671.93 | 2214457.09 | 1432869.18 | 64.71%
01/13/25 |  | 05/23/25 | Open | Lauren Lanzini Coffey | Chad Hart, Mark J Chambliss |  | Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah |  |  | Carlos Montalvo, Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00019244 | Specialty Pharmacy Phones, Headsets and PSE | Planning/Design/Staging | 25% | 30.73% | 116.35 | 80.6 | 12636.25 | 4690 | 69.27% | 12636.25 | 0 | 35.75 | 0 | 0 |  | 4690 |  | 189627.3 | 39774.36 | 35084.36 | 88.21%
04/23/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Gregory Posey, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002701 | N/A | Closed | 0% | 0% | 0 | -26 | 0 | 780 | 0% | 0 | 0 | 26 | 0 | 0 |  | 780 |  | 106200 | 0 | -780 | 0%
04/23/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002708 | N/A | Not started | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 8893 | 0 | -120 | 0%
04/24/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002713 | N/A | Closed | 0% | 0% | 0 | -5 | 0 | 150 | 0% | 0 | 0 | 5 | 0 | 0 |  | 150 |  | 14337 | 0 | -150 | 0%
04/24/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002715 | N/A | Closed | 0% | 0% | 0 | -1.25 | 0 | 37.5 | 0% | 0 | 0 | 1.25 | 0 | 0 |  | 37.5 |  | 5310 | 0 | -37.5 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Josue Iglesias, Rashaud Compton |  |  | N/A | N/A | Houston ISD | 200002716 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 2920.93 | 80 | -10 | -12.5%
04/24/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002718 | N/A | Closed | 0% | 0% | 0 | -2.25 | 0 | 67.5 | 0% | 0 | 0 | 2.25 | 0 | 0 |  | 67.5 |  | 5310 | 0 | -67.5 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200002721 | N/A | Not started | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 19600 | 0 | -135 | 0%
04/24/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002723 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 11370 | 0 | -75 | 0%
04/24/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002724 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 9846 | 0 | -60 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Gregory Posey, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002725 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 25874 | 35 | -55 | -157.1%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002727 | N/A | Not started | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 1778 | 0 | -105 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002728 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 12080 | 0 | -30 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002732 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1784 | 0 | -30 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002736 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 3568 | 0 | -30 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002737 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8890 | 0 | -30 | 0%
04/24/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002738 | N/A | Closed | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 5310 | 0 | -105 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002740 | N/A | Not started | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 5264 | 0 | -15 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002741 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 5352 | 0 | -30 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002742 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 4779 | 0 | -75 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002744 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 405 | 0 | -30 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002746 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2800 | 0 | -30 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002747 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 4374 | 35 | -25 | -71.43%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002748 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2373 | 50 | 20 | 40%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002751 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4345 | 0 | -30 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002752 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 5145 | 0 | -60 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002754 | N/A | Not started | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 30157 | 0 | -90 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002757 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 889 | 0 | -60 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gerardo Ramirez, Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002758 | N/A | Not started | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 3876 | 0 | -75 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002760 | N/A | Closed | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 14094 | 0 | -120 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002761 | N/A | Closed | 0% | 0% | 0 | -1.25 | 0 | 37.5 | 0% | 0 | 0 | 1.25 | 0 | 0 |  | 37.5 |  | 3717 | 0 | -37.5 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002762 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 4345 | 0 | -30 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Jarshawn Newsome |  |  | N/A | N/A | Houston ISD | 200002763 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 11690 | 0 | -30 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002764 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 15930 | 0 | -60 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200002766 | N/A | Not started | 0% | 0% | 0 | -6 | 0 | 180 | 0% | 0 | 0 | 6 | 0 | 0 |  | 180 |  | 17780 | 0 | -180 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002767 | N/A | Not started | 0% | 0% | 0 | -1.25 | 0 | 37.5 | 0% | 0 | 0 | 1.25 | 0 | 0 |  | 37.5 |  | 2309 | 0 | -37.5 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Samsoni Jean Claude, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002768 | N/A | Not started | 0% | 0% | 0 | -20.75 | 0 | 622.5 | 0% | 0 | 0 | 20.75 | 0 | 0 |  | 622.5 |  | 68434 | 0 | -622.5 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Kai Rose , Oscar Nunez, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002769 | N/A | Not started | 0% | 0% | 0 | -13.75 | 0 | 412.5 | 0% | 0 | 0 | 13.75 | 0 | 0 |  | 412.5 |  | 17840 | 0 | -412.5 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002770 | N/A | Closed | 0% | 0% | 0 | -14 | 0 | 420 | 0% | 0 | 0 | 14 | 0 | 0 |  | 420 |  | 48328 | 0 | -420 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002773 | N/A | Closed | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 26550 | 0 | -105 | 0%
04/25/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002774 | N/A | Closed | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 26550 | 0 | -135 | 0%
04/25/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002776 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 82496 | 0 | -30 | 0%
04/23/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002706 | N/A | Not started | 0% | 0% | 0 | -1.75 | 0 | 52.5 | 0% | 0 | 0 | 1.75 | 0 | 0 |  | 52.5 |  | 2602 | 0 | -52.5 | 0%
04/23/25 |  | 05/23/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002711 | N/A | Closed | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1258.81 | 0 | -30 | 0%
04/24/25 |  | 05/23/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002730 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1510 | 0 | -30 | 0%
07/12/23 |  | 05/27/25 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, Amy Martinez-Nagy, Daniel Saenz, David Avila, David Babasola, Diana Berger, Eric Rodriguez, Ruben Cantu |  |  | Abiodun David Babasola, Alexis Cantu, Antonio Rivera, Carlos Carrillo, Felix Martinez, Francisco Hernandez, Jorge Robert Rangel, Jose Salazar, Roger Guerra, Ruben Cantu, William Brown |  |  | Eric Rodriguez | TX-SOUT | Harlingen CISD | J00014784 | E-Rate C2 Services Network Upgrades | Closed | 0% | 0% | 0 | -258.25 | 0 | 25267.5 | 0% | 0 | 50 | 308.25 | 21845 | 753.21 |  | 25267.5 |  | 0 | 0 | -26020.71 | 0%
07/12/23 |  | 05/27/25 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, Amy Martinez-Nagy, Daniel Saenz, David Avila, David Babasola, Diana Berger, Eric Rodriguez, Ruben Cantu |  |  | Abiodun David Babasola, Alexis Cantu, Antonio Rivera, Carlos Carrillo, Felix Martinez, Francisco Hernandez, Jorge Robert Rangel, Jose Salazar, Roger Guerra, Ruben Cantu, William Brown |  |  | N/A | N/A | Harlingen CISD | J00014784 | E-Rate C2 Services Network Upgrades | Closed | 100% | 0% | 224.87 | 224.87 | 19812.8 | 0 | 100% | 19812.8 | 0 | 0 | 0 | 753.21 |  | 0 |  | 0 | 0 | -753.21 | 0%
04/28/25 |  | 05/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Aboobiada Ali Abdalla, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002779 | N/A | Closed | 0% | 0% | 0 | -8 | 0 | 240 | 0% | 0 | 0 | 8 | 0 | 0 |  | 240 |  | 29736 | 0 | -240 | 0%
04/28/25 |  | 05/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez, Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002780 | N/A | Not started | 0% | 0% | 0 | -5.5 | 0 | 165 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 165 |  | 33762.2 | 0 | -165 | 0%
04/28/25 |  | 05/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002783 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 400 | 0 | -30 | 0%
04/28/25 |  | 05/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Pedro Cavazos, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002785 | N/A | Closed | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 21240 | 0 | -120 | 0%
04/28/25 |  | 05/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens |  |  | N/A | N/A | Houston ISD | 200002786 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1784 | 0 | -30 | 0%
04/28/25 |  | 05/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002787 | N/A | Closed | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 13275 | 0 | -60 | 0%
04/28/25 |  | 05/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002788 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 2800 | 0 | -60 | 0%
04/28/25 |  | 05/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002789 | N/A | Not started | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 3288 | 0 | -75 | 0%
04/28/25 |  | 05/28/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002790 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8176 | 0 | -30 | 0%
04/28/25 |  | 05/28/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Kai Rose , Nathanael Morales, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002791 | N/A | Closed | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 9027 | 0 | -120 | 0%
12/04/24 |  | 05/29/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Michelle Bailey, Warren Wilson, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200000180 | N/A | Closed | 100% | 55.48% | 20.73 | 9.23 | 2468.15 | 1437.5 | 44.52% | 2468.15 | 0 | 11.5 | 0 | 0 |  | 1437.5 |  | 10490.4 | 11966.28 | 10528.78 | 87.99%
05/13/25 |  | 05/29/25 | Closed | Joanna Herrera | Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Felix Martinez, Joanna Herrera, Joaquin Garcia, Oscar Garcia |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002967 | N/A | Closed | 100% | 62.41% | 21.63 | 8.13 | 0 | 1037.5 | 37.59% | 0 | 0 | 13.5 | 0 | 0 |  | 1037.5 |  | 0 | 2810.4 | 1772.9 | 63.08%
04/29/25 |  | 05/29/25 | Open | LaQisha Marshall | Mark J Chambliss |  | Anthony Towsley, David Monasmith, David Monasmith, LaQisha Marshall, Mark J Chambliss |  |  | Anthony Towsley, LaQisha Marshall |  |  | David Monasmith | TX-HOU | Texas A&M University - Galveston | 200002814 | N/A | Planning/Design/Staging | 5% | 27.57% | 92.5 | 67 | 0 | 3382.5 | 72.43% | 0 | 0 | 25.5 | 0 | 0 |  | 3382.5 |  | 0 | 17098.8 | 13716.3 | 80.22%
04/29/25 |  | 05/29/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002797 | N/A | Closed | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 26550 | 0 | -75 | 0%
04/29/25 |  | 05/29/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002798 | N/A | Not started | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 31410 | 0 | -105 | 0%
04/29/25 |  | 05/29/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez, Nathanael Morales, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002801 | N/A | Not started | 0% | 0% | 0 | -7 | 0 | 210 | 0% | 0 | 0 | 7 | 0 | 0 |  | 210 |  | 58233 | 0 | -210 | 0%
04/29/25 |  | 05/29/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Camila Guzman, David Lenihan, Dedric Bowens, Eliana Guzman, Gerardo Ramirez, Jarshawn Newsome, Josue Iglesias, Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Steffany Alvarez, Walter Hanchett |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200002815 | N/A | Closed | 0% | 0% | 0 | -507.5 | 0 | 15225 | 0% | 0 | 0 | 507.5 | 0 | 0 |  | 15225 |  | 0 | 26136 | 10911 | 41.75%
12/11/24 |  | 05/29/25 | Open | Robert McIver | Edward Padron, Timothy Ramsey, Wyley Johnson |  | Ashutosh Patel, Daniel Saenz, Edward Padron, Robert McIver, Timothy Ramsey, Wyley Johnson |  |  | Ashutosh Patel, Jaime Galvan, Robert McIver, Roger Guerra |  |  | Daniel Saenz | TX-SOUT | City of Edinburg | 200000284 | N/A | Closed | 100% | 126.1% | 60.85 | -12.9 | 7236.85 | 9292.5 | -21.2% | 7236.85 | 3 | 76.75 | 180 | 0 |  | 9292.5 |  | 35062.07 | 9466.88 | 174.38 | 1.842%
10/24/24 |  | 05/29/25 | Open | Tray Giddens | Aman Khan |  | Ahmed Jameel, Aman Khan, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Craig St. Rose, Jerald Garner, Kord Mullins, Luis Alvarez, Nicolas Garakani, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Apache Corporation | J00019281 | Chassis Access Switch - Briarlake | Closed | 100% | 72.72% | 59.82 | 19.32 | 6127.56 | 3130 | 32.3% | 6127.56 | 3 | 43.5 | 430 | 0 |  | 3130 |  | 34338.6 | 2552.7 | -577.3 | -22.62%
05/01/25 |  | 05/30/25 | Closed | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Justin Smallwood, Kord Mullins, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | 200002771 | N/A | Closed | 0% | 0% | 0 | -24 | 0 | 2705 | 0% | 0 | 2 | 26 | 120 | 0 |  | 2705 |  | 24300.9 | 1600 | -1105 | -69.06%
11/02/22 |  | 05/30/25 | Open | Brian Willery | Joshua Adam Engle, Majid Shirzadeh |  | Brian Willery, Jean Pierre Obenda, Justin Thompson, Lauren J Kennewell, Shiraz Humayun, Timothy Fain |  |  | Brian Willery, Jean Pierre Obenda, Jeffery Giles, Justin Thompson |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014068 | Traffic Network Phase 2 Configs - Net-ProSrvc | Training/Knowledge Transfer/Documentation | 95% | 228.7% | 132.75 | -144.6 | 13178.75 | 35837.5 | -108.9% | 13178.75 | 26.25 | 303.6 | 22467.5 | 0 |  | 35837.5 |  | 0 | 17635.76 | -18201.74 | -103.2%
07/01/24 |  | 05/30/25 | Open | Brian Willery | Bryan Geoghan, Majid Shirzadeh |  | Brian Willery, Bryan Geoghan, Lauren J Kennewell, Majid Shirzadeh, Timothy Fain |  |  | Brian Willery, Juan Pomares |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00018619 | Fire Station 10 | Implementation/Deployment | 50% | 24.07% | 73.73 | 60.48 | 8044.33 | 1861.25 | 82.03% | 8044.33 | 4.5 | 17.75 | 270 | 0 |  | 1861.25 |  | 88379.17 | 13203.2 | 11341.95 | 85.9%
08/01/24 |  | 05/30/25 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Ashutosh Patel, Brian Willery, Jacob Parks, Jeffrey Holman, Lauren J Kennewell |  |  | Brian Willery, Eric Firestone |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00018792 | FTD to Palo Alto NGFW Migration | Training/Knowledge Transfer/Documentation | 95% | 100.1% | 252.4 | -0.35 | 37938 | 36975 | -0.1387% | 37938 | 0 | 252.75 | 16931.25 | 0 |  | 36975 |  | 314557.91 | 57951.2 | 20976.2 | 36.2%
09/30/24 |  | 05/30/25 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | Brian Willery, Noah Trump, Phillip Ma Lim, Tavis Jackson |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00019009 | AP install -Police Dept | Implementation/Deployment | 50% | 86.38% | 29.81 | 5.06 | 2241.91 | 2081.25 | 16.97% | 2241.91 | 1 | 25.75 | 270 | 0 |  | 2081.25 |  | 11254.72 | 3435.2 | 1353.95 | 39.41%
10/01/24 |  | 05/30/25 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | Brian Willery, Samuel Gonzalez |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00019092 | Cisco AP Replacement Quantity 27 | Implementation/Deployment | 80% | 32.34% | 40.2 | 28.7 | 2934.6 | 1300 | 71.39% | 2934.6 | 1.5 | 13 | 90 | 0 |  | 1300 |  | 38271.6 | 4304 | 3004 | 69.8%
04/16/25 |  | 05/30/25 | Open | Christina Rice | N/A |  | Christina Rice, Christina Rice, Conner MacDonnell, David Watkins, Jonathan Pendrich, Juan Pomares, Katharine McCarley, Katherine McCarley, Nick Varga, Tabais Prater |  |  | Briliance Johnson, Christina Rice, John Johnson, Juan Pomares, Nick Varga |  |  | Jonathan Pendrich | TX-DAL | Winstead PC | 200002472 | N/A | Planning/Design/Staging | 45% | 87.01% | 96.25 | 12.5 | 0 | 9298.75 | 12.99% | 0 | 0 | 83.75 | 0 | 0 |  | 9298.75 |  | 0 | 17801.68 | 8502.93 | 47.76%
11/19/24 |  | 05/30/25 | Open | Jennifer Soliz | Todd Melby |  | Jennifer Soliz, Lonnie Owens, Todd Melby |  |  | Jennifer Soliz |  |  | Lonnie Owens | TX-CEN | Texas State University | 200000151 | N/A | Closed | 100% | 105.7% | 8.75 | -0.5 | 1093.75 | 1156.25 | -5.714% | 1093.75 | 0 | 9.25 | 0 | 0 |  | 1156.25 |  | 0 | 15722.4 | 14566.15 | 92.65%
04/16/25 |  | 05/30/25 | Open | Jim Blackwell | Bryan Brown |  | Ali Al-Haddad, Bryan Brown, Christopher Garcia, Clinton Bennett Deason, Jeremiah Solomon, Jeremy R Freeman, Jim Blackwell, Meredith A Richardson |  |  | Ali Al-Haddad, James Adams, Jim Blackwell, Julio C Montoya, Justin Smallwood, Mohammed Al-Shaikhli |  |  | N/A | N/A | Houston ISD | 200002551 | N/A | Closed | 100% | 64.56% | 53.44 | 23.94 | 0 | 2395 | 44.8% | 0 | 5 | 34.5 | 300 | 0 |  | 2395 |  | 23400.13 | 6500 | 4105 | 63.15%
09/21/23 |  | 05/30/25 | Closed | Joanna Herrera | Warren Wilson |  | Joanna Herrera, Michelle Bailey, Steve J Rodriguez, Warren Wilson, Xavier A Trevino |  |  | Garrett Hart, Joanna Herrera, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, William Brown |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00016516 | FY24 BY Cameras SB507 | Closed | 100% | 54.2% | 671.61 | 308.61 | 79837 | 49245 | 45.95% | 79837 | 1 | 364 | 48247.5 | 0 |  | 49245 |  | 220668.84 | 191113.69 | 141868.69 | 74.23%
08/23/22 |  | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs |  |  | Gena Robbins, Luis Ovalles, Ron Loge |  |  | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012888 | SaaS/Parking NO HDWR - AAAQ361562 | Closed | 100% | 184% | 96.6 | -81.15 | 12915 | 24048.75 | -84.01% | 12915 | 0 | 177.75 | 24048.75 | 64.29 |  | 24048.75 |  | 0 | 0 | -24113.04 | 0%
07/11/22 |  | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Cory E Hopf, Cory Hopf, Joshua Adam Engle, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs |  |  | Gena Robbins, Luis Ovalles, Ron Loge |  |  | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012890 | HX Nodes for SAAB - AAAQ361558 | Closed | 100% | 196.6% | 38.78 | -35.47 | 4752.5 | 10301.25 | -91.46% | 4752.5 | 2 | 76.25 | 8681.25 | 0 |  | 10301.25 |  | 67944 | 0 | -10301.25 | 0%
01/14/25 |  | 05/30/25 | Open | LaQisha Marshall | Chad Hart |  | Chad Hart, David Monasmith, David Monasmith, LaQisha Marshall, Mario Sanchez |  |  | LaQisha Marshall, Mario Sanchez, Sophia Quinter |  |  | David Monasmith | TX-HOU | Texas A&M University - Galveston | 200001609 | N/A | Implementation/Deployment | 85% | 74.73% | 18.4 | 4.65 | 2540 | 1912.5 | 25.27% | 2540 | 0 | 13.75 | 0 | 0 |  | 1912.5 |  | 0 | 3335 | 1422.5 | 42.65%
01/08/25 |  | 05/30/25 | Open | Lauren Lanzini Coffey | N/A |  | Juan Saenz, Lauren Lanzini Coffey, Matthew Duncan, Neel Shah |  |  | Juan Saenz |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200001600 | N/A | Implementation/Deployment | 35% | 53.77% | 106 | 49 | 14020 | 7695 | 46.23% | 14020 | 0 | 57 | 0 | 0 |  | 7695 |  | 0 | 0 | -7695 | 0%
05/01/23 |  | 05/30/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Christine A Hupe, Khalid Abunaja, Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah, Sathish Somanathan, Shiraz Humayun |  |  | Brian Newman, Clinton Bennett Deason, Henry Pugsley, Jeffrey Charles Primeaux, Joel Hubbard, Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00015488 | Alto PX Proof of Concept & Austin Alto deployment | Planning/Design/Staging | 50% | 47.3% | 871.31 | 501.31 | 118155.32 | 39841 | 57.54% | 118155.32 | 42.1 | 412.1 | 31810 | 92.58 |  | 39841 |  | 0 | 270808.7 | 230875.12 | 85.25%
01/06/25 |  | 05/30/25 | Open | Lauren Lanzini Coffey | David Watkins |  | David Watkins, Lauren Lanzini Coffey, Neel Shah |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00018485 | Cores to Support Zero Trust | Not started | 0% | 0% | 143.75 | 143.75 | 12378.75 | 0 | 100% | 12378.75 | 0 | 0 | 0 | 0 |  | 0 |  | 443268.9 | 22096 | 22096 | 100%
04/28/25 |  | 05/30/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias, Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002792 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 5769 | 0 | -60 | 0%
04/29/25 |  | 05/30/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Valentin Vasquez, Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002796 | N/A | Closed | 0% | 0% | 0 | -1.5 | 0 | 45 | 0% | 0 | 0 | 1.5 | 0 | 0 |  | 45 |  | 5310 | 0 | -45 | 0%
04/30/25 |  | 05/30/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002820 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 9473 | 175 | 145 | 82.86%
04/30/25 |  | 05/30/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Josue Iglesias |  |  | N/A | N/A | Houston ISD | 200002821 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 16760 | 175 | 145 | 82.86%
04/30/25 |  | 05/30/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Jarshawn Newsome, Kai Rose , Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002822 | N/A | Not started | 0% | 0% | 0 | -8.5 | 0 | 255 | 0% | 0 | 0 | 8.5 | 0 | 0 |  | 255 |  | 44200 | 1000 | 745 | 74.5%
04/30/25 |  | 05/30/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002874 | N/A | Not started | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 2350 | 0 | -15 | 0%
04/30/25 |  | 05/30/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002872 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 2531 | 0 | -30 | 0%
11/08/24 |  | 05/30/25 | Open | Robert McIver | Edward Padron |  | Carlos Carrillo, Christopher Prado, Edward Padron, Erick Nunez , Francisco Hernandez, Michelle Bailey, Robert McIver, Xavier A Trevino |  |  | Alexander Chambless, An Le, Briliance Johnson, Christina Rice, Christopher Prado, Eric Straeter, Francisco Hernandez, Isaiah Rosales, Jaime Galvan, James Danner, Jhon Genao, John Senkulics, Jonathan Pina, Jorge Robert Rangel, Michael Torres, Oscar Garcia, Oscar Gonzalez, Robert McIver, Roger Guerra, Steven Shipmon, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018409 | E-Rate Cat 2 - UPS Installation - Multiple Areas | Closed | 100% | 108% | 197.83 | 15.08 | 15254.35 | 14368.75 | 7.623% | 15254.35 | 31 | 213.75 | 9383.75 | 0 |  | 14368.75 |  | 196518.44 | 19489.9 | 5121.15 | 26.28%
02/10/25 |  | 05/30/25 | Open | Shannon Marie Alvarado | Christopher Ceykovsky |  | Christopher Ceykovsky, George McGann, Mark Forehand, Shannon Marie Alvarado |  |  | George McGann, Shannon Marie Alvarado |  |  | Mark Forehand | TX-DAL | Heritage Auctions | 200001857 | N/A | Closed | 100% | 91.06% | 99.38 | 8.88 | 14012.5 | 12377.5 | 8.935% | 14012.5 | 0 | 90.5 | 0 | 0 |  | 12377.5 |  | 0 | 24520.76 | 12143.26 | 49.52%
12/30/24 |  | 05/30/25 | Open | Shannon Marie Alvarado | Bryan Geoghan, William Birdsong |  | Ahmed Jameel, Bryan Geoghan, Camille Elizabeth Taber, Hamzeh Tahat, Shannon Marie Alvarado, William Birdsong |  |  | Ahmed Jameel, Hamzeh Tahat, Shannon Marie Alvarado |  |  | Camille Taber | FL | Polk County Sheriffs Office | 200000339 | N/A | Closed | 100% | 87.08% | 43.64 | 5.64 | 5437.85 | 4450 | 12.92% | 5437.85 | 0 | 38 | 0 | 1495 |  | 4450 |  | 16913.79 | 30233.33 | 24288.33 | 80.34%
12/20/23 |  | 05/30/25 | Open | Summer Abunaja | David Watkins |  | Beau C. Devillier, David Watkins, Karyn Hubbard, Mark Forehand, Summer Abunaja |  |  | Carlo Enriquez, Kanoa Parman, Karyn Hubbard, Kebret Eshetu, Kendall Walls, Kenia Dimas, Lauren Lanzini Coffey, Quy Le, Ron Loge, William Chris Roome, Yonathan Fadel |  |  | Mark Forehand | TX-DAL | DR Horton | J00017118 | Office in a Box | Implementation/Deployment | 40% | 89.01% | 45.5 | 5 | 3226.78 | 3317.5 | 10.99% | 3226.78 | 0 | 40.5 | 2792.5 | 0 |  | 3317.5 |  | 13765.8 | 3753 | 435.5 | 11.6%
04/28/25 |  | 06/03/25 | Closed | Abiodun David Babasola | David Pena |  | Abiodun David Babasola, David Babasola, David Pena, Kristy L Dice |  |  | Abiodun David Babasola, Noah Trump, Tavis Jackson |  |  | Kristy L Dice | TX-DAL | Region 11 Education Service Center | 200002893 | N/A | Closed | 100% | 64.46% | 30.25 | 13.75 | 0 | 1592.5 | 45.45% | 0 | 3 | 19.5 | 180 | 0 |  | 1592.5 |  | 0 | 5309.6 | 3717.1 | 70.01%
02/25/25 |  | 06/03/25 | Open | Jennifer Soliz | N/A |  | Garrett Curran, Jennifer Soliz, Meray Doughly, Steven Walker |  |  | Christopher Brown, Jennifer Soliz |  |  | Garrett Curran | CA-LAX | San Bernardino County ERA | 200002153 | N/A | Closed | 100% | 17.59% | 95.25 | 78.5 | 0 | 2103.75 | 82.41% | 0 | 0 | 16.75 | 0 | 0 |  | 2103.75 |  | 0 | 0 | -2103.75 | 0%
03/04/25 |  | 06/03/25 | Open | Jennifer Soliz | Steven Walker |  | Garrett Curran, Jennifer Soliz, Steven Walker |  |  | Jennifer Soliz |  |  | Garrett Curran | CA-LAX | San Bernardino County ERA | 200002270 | N/A | Closed | 100% | 115% | 5 | -0.75 | 0 | 718.75 | -15% | 0 | 0 | 5.75 | 0 | 0 |  | 718.75 |  | 27523.56 | 0 | -718.75 | 0%
12/04/23 |  | 06/03/25 | Closed | Walter Clay Knight | Timothy Ramsey |  | Abdulrahman Farhan, Christopher Butler, Christopher Kutalek, Sophia Quinter, Timothy Ramsey, Timothy Sean Marcyes |  |  | Ashutosh Patel, Kenneth Stevenson, Kord Mullins, Sophia Quinter, Timothy Sean Marcyes, Walter Clay Knight |  |  | Christopher Kutalek | TX-HOU | Bradford Airport Logistics | J00016975 | Fortinet Configuration | Closed | 100% | 192% | 223.75 | -204.75 | 32249.75 | 69137.5 | -91.51% | 32249.75 | 1 | 429.5 | 58587.5 | 0 |  | 69137.5 |  | 6374.96 | 42308.72 | -26828.78 | -63.41%
09/25/24 |  | 06/04/25 | Closed | Joaquin Marroquin | Bryan Brown |  | Christopher Garcia, Diana Berger, Jason Osuna, Joaquin Marroquin |  |  | Joaquin Marroquin |  |  | Jason Osuna | TX-CEN | Sierra Blanca ISD | J00019082 | Promethean Boards | Closed | 100% | 75% | 4 | 1 | 500 | 375 | 25% | 500 | 0 | 3 | 125 | 0 |  | 375 |  | 5620.3 | 1622.58 | 1247.58 | 76.89%
02/03/25 |  | 06/04/25 | Closed | Joaquin Marroquin | N/A |  | Christopher Ceykovsky, Daniel Saenz, Joaquin Marroquin, Samuel Newland |  |  | Samuel Newland |  |  | Daniel Saenz | TX-SOUT | United ISD | 200001893 | N/A | Closed | 0% | 0% | 0 | -8.5 | 0 | 1190 | 0% | 0 | 0 | 8.5 | 0 | 0 |  | 1190 |  | 0 | 0 | -1190 | 0%
05/07/24 |  | 06/04/25 | Open | Joaquin Marroquin | Bryan Geoghan |  | Anthony Towsley, Bryan Geoghan, Daniel Saenz, Diana Berger, Joaquin Marroquin |  |  | Anthony Towsley, Joaquin Marroquin |  |  | Daniel Saenz | TX-SOUT | United ISD | J00018226 | Collaboration Upgrade | Closed | 100% | 77.67% | 75 | 16.75 | 10575 | 7941.25 | 22.33% | 10575 | 0 | 58.25 | 1921.25 | 0 |  | 7941.25 |  | 0 | 13795.2 | 5853.95 | 42.43%
06/10/24 |  | 06/04/25 | Open | Joaquin Marroquin | Vernon Jackson |  | Christopher Puyear, Daniel Saenz, Diana Berger, Joaquin Marroquin, Michael B Griffin, Samuel Newland, Vernon Jackson |  |  | Anthony Lange, Francisco Hernandez, Joaquin Marroquin, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres, Samuel Newland, Trevor Galloso |  |  | Daniel Saenz | TX-SOUT | United ISD | J00018487 | District ISR upgrades | Closed | 100% | 61.32% | 960.19 | 477.44 | 132669.36 | 59131.05 | 49.72% | 132669.36 | 106.08 | 588.83 | 23536.25 | 0 |  | 59131.05 |  | 654212.39 | 136935.48 | 77804.43 | 56.82%
07/01/24 |  | 06/04/25 | Open | Joaquin Marroquin | Christopher Ceykovsky |  | Amy Martinez-Nagy, Christopher Ceykovsky, Daniel Saenz, Diana Berger, Joaquin Marroquin, Samuel Newland |  |  | Carlos Carrillo, Joaquin Marroquin, Samuel Newland, Trevor Galloso |  |  | Daniel Saenz | TX-SOUT | United ISD | J00018628 | Connectivity Routers | Closed | 100% | 142.5% | 30 | -6.75 | 3550 | 4925 | -22.5% | 3550 | 6 | 42.75 | 805 | 0 |  | 4925 |  | 26761.22 | 4636 | -289 | -6.234%
05/05/25 |  | 06/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gerardo Ramirez, Jarshawn Newsome, Kai Rose , Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002904 | N/A | Closed | 0% | 0% | 0 | -5.5 | 0 | 165 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 165 |  | 17861 | 0 | -165 | 0%
05/05/25 |  | 06/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002907 | N/A | Not started | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 3805 | 0 | -75 | 0%
05/05/25 |  | 06/04/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200002916 | N/A | Not started | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 5600 | 0 | -120 | 0%
07/29/24 |  | 06/05/25 | Closed | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Michael Brett Beggs, Phillip Ma Lim, Tavis Jackson , William Davenport |  |  | Carlo Enriquez, Jason Esry, Jay Daniel De Leon, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Kendall Walls, Luis Ovalles, Phillip Ma Lim, Quy Le, Tavis Jackson, Yonathan Fadel |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00018726 | Data Center Network Refresh | Closed | 100% | 48.32% | 305.23 | 157.73 | 36770.62 | 16992.5 | 51.68% | 36770.62 | 0 | 147.5 | 0 | 0 |  | 16992.5 |  | 570092.93 | 42659.36 | 25666.86 | 60.17%
07/29/24 |  | 06/05/25 | Closed | Jason Esry | Michael Brett Beggs |  | Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Michael Brett Beggs, Phillip Ma Lim, Tavis Jackson , William Davenport |  |  | Carlo Enriquez, Jason Esry, Jay Daniel De Leon, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Kendall Walls, Luis Ovalles, Phillip Ma Lim, Quy Le, Tavis Jackson, Yonathan Fadel |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00018726 | Data Center Network Refresh | Closed | 0% | 0% | 0 | -74 | 0 | 7527.5 | 0% | 0 | 0 | 74 | 7527.5 | 0 |  | 7527.5 |  | 570092.93 | 42659.36 | 35131.86 | 82.35%
06/17/24 |  | 06/05/25 | Open | Jason Esry | Aman Khan, Christopher Puyear, Daniel Snyder |  | Aman Khan, Christopher Puyear, Daniel Snyder, David D Tijerina, Hamzeh Tahat, Jason Esry, Larry Noble |  |  | Adam Felix, Briliance Johnson, Dustin Aaron Lowrey, Grayson Rigsby, Hamzeh Tahat, Jason Esry, Julio Perez, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Robert Jones, Steven Shipmon, Wilangel Francis |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018524 | Elementary School 30 | Closed | 100% | 73.67% | 263 | 73.25 | 25024.35 | 16305 | 27.85% | 25024.35 | 4 | 193.75 | 13445 | 4600 |  | 16305 |  | 307748.14 | 38944 | 18039 | 46.32%
02/03/25 |  | 06/05/25 | Open | Richard Keith Arnst | Steven Walker |  | Richard Keith Arnst, Steven Walker, Susan Richardson |  |  | Richard Keith Arnst |  |  | Susan Richardson | TX-HOU | Howard Hughes Management Co., LLC | 200001810 | N/A | Closed | 100% | 20.13% | 202.4 | 161.65 | 5300 | 5093.75 | 79.87% | 5300 | 0 | 40.75 | 0 | 0 |  | 5093.75 |  | 0 | 81870 | 76776.25 | 93.78%
06/26/24 |  | 06/06/25 | Closed | Jason Esry | Aman Khan |  | Aman Khan, Amy Martinez-Nagy, David D Tijerina, Jason Esry, Larry Noble, Robert V Eubanks |  |  | An Le, Angel Alicea, Angel Alicea-Torres, Celso Lopez, Isaiah Rosales, James Danner, Jason Esry, John Senkulics, Michael Torres, Mohammed Almoola |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00018602 | Edison - Wireless HW Install | Closed | 100% | 106.1% | 175.71 | -10.79 | 14159.29 | 13562.5 | -6.141% | 14159.29 | 0 | 186.5 | 9400 | 0 |  | 13562.5 |  | 146906.6 | 19164 | 5601.5 | 29.23%
10/28/24 |  | 06/06/25 | Open | Jennifer Soliz | Steven Walker |  | Hannah Paul, Jennifer Soliz, Larry Noble, Lori Endsley, Steven Walker |  |  | Jennifer Soliz |  |  | Hannah Edmunds | TX-CEN | Edgewood ISD | J00019243 | VM Migration to Azure | Closed | 100% | 105% | 10 | -0.5 | 0 | 1312.5 | -5% | 0 | 0 | 10.5 | 0 | 0 |  | 1312.5 |  | 20047.25 | 1630.24 | 317.74 | 19.49%
02/13/23 |  | 06/06/25 | Open | Lauren Lanzini Coffey | Ahmed Al-Zubaidi, Wyley Johnson |  | Christine A Hupe, Jason Espino, Lauren Lanzini Coffey, Neel Shah, Shiraz Humayun |  |  | Eric Firestone, Jason Espino, Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00014935 | TCH Enterprise Security Architect | Planning/Design/Staging | 60% | 82.99% | 720 | 130 | 105000 | 89612.5 | 18.06% | 105000 | 7.5 | 597.5 | 81325 | 0 |  | 89612.5 |  | 0 | 133000 | 43387.5 | 32.62%
05/07/25 |  | 06/06/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Lorenzo Hernandez |  |  | Lindie Lamar | TX-HOU | Galveston ISD | 200002920 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 0 | 45.52 | -44.48 | -97.72%
05/02/25 |  | 06/06/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200002901 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1781 | 0 | -30 | 0%
05/07/25 |  | 06/06/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez, Nathanael Morales, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200002924 | N/A | Not started | 0% | 0% | 0 | -13 | 0 | 390 | 0% | 0 | 0 | 13 | 0 | 0 |  | 390 |  | 58941 | 0 | -390 | 0%
05/08/25 |  | 06/06/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200002936 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 8890 | 0 | -30 | 0%
05/09/25 |  | 06/06/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002937 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 30 | 0% | 0 | 0 | 1 | 0 | 0 |  | 30 |  | 1778 | 0 | -30 | 0%
05/09/25 |  | 06/06/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Pedro Cavazos |  |  | N/A | N/A | Houston ISD | 200002942 | N/A | Not started | 0% | 0% | 0 | -0.5 | 0 | 15 | 0% | 0 | 0 | 0.5 | 0 | 0 |  | 15 |  | 1175 | 0 | -15 | 0%
03/24/25 |  | 06/06/25 | Open | Summer Abunaja | Wyley Johnson |  | Camille Elizabeth Taber, Ibrahim Altaweel, Jerome Tanyag Mara, Mohammad Arman, Rogelio Morgado-Perez, Summer Abunaja, Tom Magboo, Wyley Johnson |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, Mohammad Arman, Rogelio Morgado-Perez, Summer Abunaja, Tom Magboo |  |  | Camille Taber | FL | Lake County School Board | 200002505 | N/A | Implementation/Deployment | 20% | 58.06% | 211 | 88.5 | 0 | 16325 | 41.94% | 0 | 0 | 122.5 | 0 | 0 |  | 16325 |  | 0 | 22524.6 | 6199.6 | 27.52%
12/09/24 |  | 06/09/25 | Closed | Brittney Antoinette Hickman | Christopher Puyear |  | Brittney Antoinette Hickman, Christopher Puyear, Henry Pugsley, Kristy L Dice |  |  | Brittney Antoinette Hickman, Carlo Enriquez, Henry Pugsley, Jacob Hill, Tavis Jackson |  |  | Kristy L Dice | TX-DAL | White Settlement ISD | 200000243 | N/A | Closed | 100% | 90% | 137.5 | 15.75 | 19387.5 | 19496.25 | 11.45% | 19387.5 | 2 | 123.75 | 120 | 0 |  | 19496.25 |  | 44168.34 | 36264.72 | 16768.47 | 46.24%
03/10/25 |  | 06/13/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, David Escamilla, Jaclyn Pias |  |  | Brian Willery, Cory Bradfield |  |  | Jaclyn Pias | TX-HOU | US Legal Support | 200002361 | N/A | Implementation/Deployment | 95% | 62.64% | 66.25 | 24.75 | 0 | 5467.5 | 37.36% | 0 | 0 | 41.5 | 0 | 0 |  | 5467.5 |  | 0 | 13856.84 | 8389.34 | 60.54%
07/17/24 |  | 06/13/25 | Open | Lauren Lanzini Coffey | Christopher Ceykovsky, Jacob Parks, Jeffrey Holman, Kenneth Dieter, William Birdsong |  | Beau C. Devillier, Bryan Mullen, Christopher Ceykovsky, Jacob Parks, Jeffrey Holman, Joshua Parker, Kenneth Dieter, Lauren Lanzini Coffey, William Birdsong |  |  | Anthony Towsley, Bryan Mullen, Lauren Lanzini Coffey |  |  | Joshua Parker | TX-DAL | Collin County - Texas | J00018662 | Cisco Equipment Assessment | On HOLD | 100% | 22.46% | 569.85 | 441.85 | 69351.25 | 16832.5 | 77.54% | 69351.25 | 0 | 128 | 10447.5 | 0 |  | 16832.5 |  | 0 | 169792.84 | 152960.34 | 90.09%
05/14/25 |  | 06/13/25 | Closed | Michelle Duenes | N/A |  | N/A |  |  | Andrew Comeaux, David Lenihan, Dedric Bowens, Gerardo Ramirez, Lorenzo Hernandez, Nathanael Morales, Oscar Nunez, Pedro Cavazos, Steffany Alvarez |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200002950 | N/A | Closed | 0% | 0% | 0 | -139 | 0 | 4170 | 0% | 0 | 0 | 139 | 0 | 0 |  | 4170 |  | 0 | 4248 | 78 | 1.836%
05/14/25 |  | 06/13/25 | Open | Michelle Duenes | N/A |  | N/A |  |  | David Lenihan, Dedric Bowens, Gerardo Ramirez, Gregory Posey, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Oscar Nunez, Pedro Cavazos, Steffany Alvarez, Walter Hanchett |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200002951 | N/A | Not started | 0% | 0% | 0 | -96 | 0 | 2880 | 0% | 0 | 0 | 96 | 0 | 0 |  | 2880 |  | 0 | 25416 | 22536 | 88.67%
03/24/25 |  | 06/13/25 | Open | Shannon Marie Alvarado | Mark J Chambliss |  | Lindie Lorraine Lamar, Mark J Chambliss, Shannon Marie Alvarado |  |  | Nathan Dao, Samuel Newland, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Westlake Corporation | 200002476 | N/A | Closed | 100% | 58.57% | 140 | 76 | 0 | 9165 | 54.29% | 0 | 18 | 82 | 2040 | 0 |  | 9165 |  | 0 | 22227 | 13062 | 58.77%
04/15/25 |  | 06/16/25 | Open | Richard Keith Arnst | Bryan Brown, Remi Martinez-Montenegro |  | Christopher Garcia, Remi Martinez-Montenegro, Richard Keith Arnst |  |  | Clinton Bennett Deason, Jeremiah Solomon, Richard Keith Arnst |  |  | N/A | N/A | Netsync Network Solutions | 200002638 | N/A | Closed | 0% | 0% | 0 | -20.5 | 0 | 1912.5 | 0% | 0 | 0 | 20.5 | 0 | 0 |  | 1912.5 |  | 0 | 0 | -1912.5 | 0%
10/07/24 |  | 06/16/25 | Open | Walter Clay Knight | Aman Khan, David Escamilla, Eduardo Chavez, Jacob Parks, Jeffrey Holman |  | Aman Khan, Carmen Isela Brandt, David Escamilla, Eduardo Chavez, Jacob Parks, Jeffrey Holman, Yong Kim |  |  | Luis Ovalles, Nick Varga, Walter Clay Knight |  |  | Carmen Brandt | CA-LAX | City of Manhattan Beach | J00019153 | Network Refresh and NetApp | Implementation/Deployment | 65% | 70.15% | 198.15 | 59.15 | 29446.73 | 17395 | 29.85% | 29446.73 | 0 | 139 | 125 | 0 |  | 17395 |  | 0 | 45340.08 | 27945.08 | 61.63%
09/12/24 |  | 06/16/25 | Closed | Walter Clay Knight | Bryan Brown |  | Ashley F Freeman, Christopher Garcia |  |  | Clinton Bennett Deason, Jeremiah Solomon, Walter Clay Knight |  |  | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00018987 | 4th Floor Conference Room Redesign | Closed | 100% | 287.4% | 15.31 | -28.69 | 2006.25 | 3600 | -187.4% | 2006.25 | 0 | 44 | 275 | 0 |  | 3600 |  | 5378.6 | 5274.28 | 1674.28 | 31.74%
02/10/25 |  | 06/18/25 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Tray Giddens |  |  | Cory Bradfield, Craig St. Rose, James Adams, Jose R. Duarte, Kord Mullins, Miguel Reed, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Galveston County | 200001831 | N/A | Closed | 100% | 73.12% | 218.13 | 98.63 | 23386.25 | 12895 | 45.22% | 23386.25 | 40 | 159.5 | 2400 | 0 |  | 12895 |  | 0 | 30708 | 17813 | 58.01%
07/10/23 |  | 06/20/25 | Open | Brian Willery | Joshua Adam Engle |  | Brian Willery, Dylan Pittsinger, Lauren J Kennewell, Phillip Ma Lim, Sean Cowhey, Shiraz Humayun, Tavis Jackson |  |  | Austen Howard, Brian Willery, Devin Moreno, Jeffery Giles, Noah Trump, Patrick Shea Thompson, Phillip Ma Lim |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00014775 | Police Dept. New HW - Remodel Project New | Training/Knowledge Transfer/Documentation | 90% | 27.83% | 213.8 | 159.3 | 20930.85 | 5260 | 74.51% | 20930.85 | 5 | 59.5 | 1710 | 79.4 |  | 5260 |  | 482847.9 | 34536 | 29196.6 | 84.54%
06/20/22 |  | 06/20/25 | Open | Jason Esry | Emilio Carrillo, Firas Abood, Kenneth Dieter, Mark J Chambliss, Timothy Ramsey |  | David D Tijerina, Jaime Cortez, Jason Esry, Larry Noble, Robert Kelly, Robert Kelly, Timothy Ramsey, Tony Dean Skipworth |  |  | Abdulrahman Farhan, Eric Firestone, Ernesto Gonzalez, Isaiah Covington, Jaime Cortez, James Danner, Jason Esry, Jeffrey Charles Primeaux, Kyle Linder, Micah Rendon, Mohammed Almoola, Ron Loge, Tony Dean Skipworth, Trevor Youngman |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00013237 | DC \ ACI \ Core Router and FW Work | Implementation/Deployment | 95% | 86.73% | 474.48 | 82.98 | 58472.5 | 50840 | 17.49% | 58472.5 | 20 | 411.5 | 43967.5 | 473.32 |  | 50840 |  | 637580.65 | 83092 | 31778.68 | 38.25%
04/29/24 |  | 06/20/25 | Open | Marco Lish | Mark J Chambliss |  | Larry Noble, Marco Lish, Mark J Chambliss, Neel Shah, Samuel Newland |  |  | Marco Lish, Samuel Newland |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00018251 | Cisco SME Deployment | On HOLD | 5% | 17.31% | 65 | 53.75 | 9165 | 1526.25 | 82.69% | 9165 | 0 | 11.25 | 1463.75 | 0 |  | 1526.25 |  | 0 | 14434.8 | 12908.55 | 89.43%
04/07/25 |  | 06/20/25 | Open | Marco Lish | Christopher Ceykovsky |  | Christopher Ceykovsky, Joshua Parker, Marco Lish |  |  | N/A |  |  | Joshua Parker | TX-DAL | Richardson ISD | 200002514 | N/A | Planning/Design/Staging | 0% | 0% | 62.5 | 62.5 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 59518.71 | 12029.04 | 12029.04 | 100%
02/13/25 |  | 06/20/25 | Closed | Marco Lish | William Birdsong |  | Jesus Escobedo, Marco Lish, Mark Forehand, William Birdsong |  |  | Jesus Escobedo, Marco Lish |  |  | Mark Forehand | TX-DAL | TD Industries | 200001981 | N/A | Closed | 100% | 73.33% | 52.5 | 14 | 0 | 4975 | 26.67% | 0 | 0 | 38.5 | 0 | 0 |  | 4975 |  | 0 | 11461.12 | 6486.12 | 56.59%
12/24/24 |  | 06/20/25 | Open | Marshall Chuck Pugh | Christopher Pheonix Preddy |  | Christopher Pheonix Preddy, Marshall Chuck Pugh , Taylor Leger |  |  | Caleb Henry, Christopher Pheonix Preddy, Marshall Chuck Pugh, Noah Trump, Ryan Frankeberger |  |  | Taylor Leger | TX-DAL | Rockwall ISD | 200000357 | N/A | Closed | 100% | 93.52% | 318.39 | 24.64 | 36116.2 | 46111.25 | 7.739% | 36116.2 | 4 | 297.75 | 240 | 0 |  | 46111.25 |  | 449808.1 | 56882.4 | 10771.15 | 18.94%
05/13/25 |  | 06/20/25 | Open | Michelle Duenes | Bryan Geoghan |  | Bryan Geoghan |  |  | Yonathan Fadel |  |  | Arcangelo Fanelli | TX-DAL | University Medical Center | 200002980 | N/A | Not started | 0% | 0% | 0 | -1 | 0 | 60 | 0% | 0 | 0 | 1 | 0 | 0 |  | 60 |  | 12931.1 | 224 | 164 | 73.21%
11/29/24 |  | 06/20/25 | Open | Robert McIver | Edward Padron |  | Christopher Prado, David Neal Gravatt, Edward Padron, Quoc Nguyen, Robert McIver, Xavier A Trevino |  |  | Christopher Prado, Daniel Hernandez, David Neal Gravatt, Hector Rivera, Justin Cornish, Kord Mullins, Miguel Reed, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018605 | UP Removal and Bridge reinstallation | Closed | 100% | 98.31% | 251.25 | 52.25 | 23988.84 | 24087.5 | 20.8% | 23988.84 | 48 | 247 | 10360 | 0 |  | 24087.5 |  | 0 | 33027.48 | 8939.98 | 27.07%
01/10/25 |  | 06/20/25 | Open | Tray Giddens | William Birdsong |  | Nelson Garcia, Rusty Bryan, Tray Giddens, William Birdsong |  |  | Nelson Garcia, Quy Le, Tray Giddens, Yonathan Fadel |  |  | Rusty Bryan | TX-DAL | Canadian ISD | 200001568 | N/A | Closed | 100% | 25.72% | 108.85 | 80.85 | 12576.25 | 3337.5 | 74.28% | 12576.25 | 0 | 28 | 0 | 0 |  | 3337.5 |  | 148027.2 | 10835.16 | 7497.66 | 69.2%
09/25/24 |  | 06/23/25 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Abdulrahman Farhan, Beau C. Devillier, Brian Willery, Jacob Parks, Jacob Sennett, Jeffrey Holman, Lauren J Kennewell |  |  | Abdulrahman Farhan, Brian Willery, Jacob Sennett, Raul Velazquez, Romar Roca |  |  | Lauren J Kennewell | TX-DAL | RENT-A-CENTER, INC | J00019080 | Corporate Office Firewall Installation | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -58.75 | 0 | 8006.25 | 0% | 0 | 0 | 58.75 | 8006.25 | 0 |  | 8006.25 |  | 0 | 40836.8 | 32830.55 | 80.39%
09/25/24 |  | 06/23/25 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Abdulrahman Farhan, Beau C. Devillier, Brian Willery, Jacob Parks, Jacob Sennett, Jeffrey Holman, Lauren J Kennewell |  |  | Abdulrahman Farhan, Brian Willery, Jacob Sennett, Raul Velazquez, Romar Roca |  |  | N/A | N/A | RENT-A-CENTER, INC | J00019080 | Corporate Office Firewall Installation | Training/Knowledge Transfer/Documentation | 95% | 90.12% | 181.7 | 17.95 | 25846.9 | 23106.25 | 9.879% | 25846.9 | 0 | 163.75 | 0 | 0 |  | 23106.25 |  | 0 | 40836.8 | 17730.55 | 43.42%
07/01/24 |  | 06/23/25 | Closed | Joaquin Marroquin | Edward Padron |  | Christopher Prado, Edward Padron, Joaquin Marroquin, Steve J Rodriguez, Xavier A Trevino |  |  | Adam Morataya, Christopher Prado, Felix Martinez, Joaquin Marroquin, Juan Arturo Gonzalez Jr, Lance Daniel Waitschies, Rodney Sincere Robinson, Sammie Simon Valero |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | J00018621 | Allen Elementary School Network Expansion | Closed | 100% | 268.5% | 46.19 | -75.31 | 4385.04 | 10967.5 | -163% | 4385.04 | 2.5 | 124 | 10267.5 | 3243 |  | 10967.5 |  | 43419.48 | 5604 | -8606.5 | -153.6%
04/01/25 |  | 06/23/25 | Closed | Walter Clay Knight | Bryan Brown |  | Christopher Garcia, Dennis Odneal, Walter Clay Knight |  |  | Clinton Bennett Deason, Jeremiah Solomon, Walter Clay Knight |  |  | Dennis Odneal | TX-HOU | Harris Health System | 200002529 | N/A | Closed | 100% | 57.31% | 20.94 | 8.94 | 0 | 1100 | 42.69% | 0 | 0 | 12 | 0 | 0 |  | 1100 |  | 5534.23 | 3101.6 | 2001.6 | 64.53%
10/28/24 |  | 06/24/25 | Open | Ryan Scott | David Watkins |  | Beau C. Devillier, David Watkins, Jesus Escobedo, Mohammed Almoola, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Christopher Prado, Jesus Escobedo, Mohammed Almoola, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | J00019327 | Wi-Fi Predictive- Harper Univ & Hutzel Women’s | Closed | 100% | 85.02% | 159.38 | 23.88 | 20560 | 16787.5 | 14.98% | 20560 | 0 | 135.5 | 0 | 0 |  | 16787.5 |  | 0 | 27590.4 | 10802.9 | 39.15%
05/12/25 |  | 06/26/25 | Open | Robert McIver | Edward Padron |  | Edward Padron, Robert McIver, Xavier A Trevino |  |  | An Le, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres, Quinn Wieland |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002959 | N/A | Closed | 100% | 232.2% | 8.72 | -11.53 | 0 | 1865 | -132.2% | 0 | 0 | 20.25 | 0 | 0 |  | 1865 |  | 8961.37 | 1289.2 | -575.8 | -44.66%
07/11/24 |  | 06/26/25 | Closed | Summer Abunaja | Matthew Duncan |  | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja |  |  | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja |  |  | N/A | N/A | Amazon Web Services | J00018637 | AWS AppStream POC | Closed | 100% | 72.08% | 148.8 | 41.55 | 19660.5 | 13988.75 | 27.92% | 19660.5 | 0 | 107.25 | 0 | 0 |  | 13988.75 |  | 0 | 31024 | 17035.25 | 54.91%
07/11/24 |  | 06/26/25 | Closed | Summer Abunaja | Matthew Duncan |  | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja |  |  | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja |  |  | Neel Shah | TX-HOU | Amazon Web Services | J00018637 | AWS AppStream POC | Closed | 0% | 0% | 0 | -90 | 0 | 11922.5 | 0% | 0 | 0 | 90 | 11922.5 | 0 |  | 11922.5 |  | 0 | 31024 | 19101.5 | 61.57%
01/31/25 |  | 06/27/25 | Open | Christina Rice | Bryan Geoghan |  | Bryan Geoghan, Christina Rice, Christina Rice, Patrick Joseph Palermo, Taylor Leger |  |  | Christina Rice, Conner MacDonnell, Patrick Joseph Palermo |  |  | Taylor Leger | TX-DAL | City of Sachse | 200000877 | N/A | Planning/Design/Staging | 30% | 27.75% | 190.06 | 137.31 | 26001.5 | 9258.75 | 72.25% | 26001.5 | 0 | 52.75 | 0 | 0 |  | 9258.75 |  | 48971.5 | 39493.2 | 30234.45 | 76.56%
01/15/25 |  | 06/27/25 | Open | Christina Rice | Christopher Puyear |  | Beau C. Devillier, Christina Rice, Christina Rice, Christopher Puyear, George McGann, Hamzeh Tahat, Shawn Sutton |  |  | Carlo Enriquez, Christina Rice, George McGann, Hamzeh Tahat, Jayden Colon, John Johnson, Juan Pomares, Kendall Walls, Quy Le, Samuel Gonzalez, Sean Cowhey |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00019179 | Denton ISD: Voice Gateway Replacement / Deploy | Implementation/Deployment | 30% | 69.91% | 322.19 | 117.94 | 41795 | 19891.25 | 36.61% | 41795 | 21 | 225.25 | 1416.25 | 5232.5 |  | 19891.25 |  | 248962.4 | 65296.6 | 40172.85 | 61.52%
04/28/23 |  | 06/27/25 | Open | Christina Rice | Joshua Adam Engle |  | Christina Rice, Christina Rice, Ivan Uribe, Jason Osuna, Joshua Adam Engle, Larry Noble |  |  | Christina Rice, Erick Sanchez, Ivan Uribe, Jim Blackwell, Kanoa Parman, Kebret Eshetu, Nick Varga, Prince Owusu, Taylor Poole, Walter Clay Knight, William Chris Roome |  |  | Jason Osuna | TX-CEN | Tyson Foods Inc | J00013662 | Tyson: Cisco DNA Deployment & Switches | Implementation/Deployment | 80% | 36.64% | 600.63 | 392.53 | 62841.25 | 26015 | 65.35% | 62841.25 | 12 | 220.1 | 25295 | 928.5 |  | 26015 |  | 6087077.6 | 0 | -26943.5 | 0%
04/22/25 |  | 06/27/25 | Open | Christina Rice | Joshua Adam Engle |  | Arcangelo Fanelli, Christina Rice, Christina Rice, Joshua Adam Engle, Mark Forehand |  |  | Christina Rice, Vitalii Stepanchenko |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | 200001822 | N/A | Planning/Design/Staging | 25% | 43.35% | 113.6 | 64.35 | 12192.8 | 6156.25 | 56.65% | 12192.8 | 0 | 49.25 | 0 | 0 |  | 6156.25 |  | 71972 | 23044 | 16887.75 | 73.28%
11/18/24 |  | 06/27/25 | Open | Jason Esry | Bryan Geoghan |  | Bryan Geoghan, Jason Esry, William Davenport |  |  | Alexander Liu, Anthony Towsley, Bradley Buchanan, Jason Esry, Kendall Walls, Quy Le, Sean Cowhey, William Chris Roome, Yonathan Fadel |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00019403 | Collaboration Upgrade and Refresh | Implementation/Deployment | 50% | 49.41% | 333.44 | 172.19 | 43211.25 | 18492.5 | 51.64% | 43211.25 | 3.5 | 164.75 | 210 | 0 |  | 18492.5 |  | 143078.98 | 65213.2 | 46720.7 | 71.64%
03/28/25 |  | 06/27/25 | Open | Jason Esry | Aman Khan |  | Aman Khan, David D Tijerina, Jason Esry |  |  | An Le, Celso Lopez, John Senkulics |  |  | David D Tijerina | TX-CEN | San Antonio ISD | 200002539 | N/A | Implementation/Deployment | 75% | 67.08% | 9.69 | 3.19 | 0 | 390 | 32.92% | 0 | 0 | 6.5 | 0 | 0 |  | 390 |  | 1851.02 | 1054.2 | 664.2 | 63.01%
01/06/25 |  | 06/27/25 | Open | Jason Matthew Davis | Kristian Martell |  | Jason Matthew Davis, Kristian Martell, Neel Shah |  |  | Carlos Montalvo, Jason Matthew Davis, Kristian Martell, Lauren Lanzini Coffey, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200001558 | N/A | Planning/Design/Staging | 50% | 37.64% | 259.06 | 161.56 | 45853.75 | 16112.5 | 62.36% | 45853.75 | 0 | 97.5 | 0 | 0 |  | 16112.5 |  | 0 | 72220 | 56107.5 | 77.69%
05/23/25 |  | 06/27/25 | Open | Jim Blackwell | Firas Abood |  | Cory Bradfield, Cory Bradfield, Firas Abood, Jeremy R Freeman, Jim Blackwell, Meredith A Richardson |  |  | Cory Bradfield, Jim Blackwell |  |  | N/A | N/A | Houston ISD | 200002987 | N/A | Implementation/Deployment | 50% | 13.86% | 79.35 | 68.35 | 0 | 1445 | 86.14% | 0 | 0 | 11 | 0 | 0 |  | 1445 |  | 0 | 11000 | 9555 | 86.86%
06/17/25 |  | 06/27/25 | Open | Joanna Herrera | N/A |  | Joanna Herrera, Michelle Bailey, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | IDEA FLORIDA INC. | 200003083 | N/A | Planning/Design/Staging | 0% | 4.348% | 23 | 22 | 0 | 125 | 95.65% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 0 | 187.2 | 62.2 | 33.23%
02/01/24 |  | 06/27/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, Hamzeh Tahat, LaQisha Marshall, Larry Noble |  |  | Hamzeh Tahat, Henry Pugsley, Kevin Curtis, Kolawole Ayeni, LaQisha Marshall, Matthew D'Ambrosio |  |  | Christi D Hubbard | TX-CEN | Pflugerville ISD | J00017275 | CUBE Implementation for Multiple Gateways | Implementation/Deployment | 75% | 170.4% | 70 | -49.25 | 9590 | 12927.5 | -70.36% | 9590 | 0 | 119.25 | 11890 | 8452.5 |  | 12927.5 |  | 50314.26 | 13058 | -8322 | -63.73%
04/05/24 |  | 06/27/25 | Open | Marco Lish | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Eric Firestone, Juan Saenz, Larry Noble, Marco Lish, Neel Shah, Wyley Johnson |  |  | Eric Firestone, Juan Saenz, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Public Works | J00017683 | AWS Security Project | Closed | 100% | 66.28% | 769.06 | 259.31 | 107238.75 | 70030 | 33.72% | 107238.75 | 0 | 509.75 | 43821.25 | 0 |  | 70030 |  | 1955.07 | 176944 | 106914 | 60.42%
02/17/25 |  | 06/27/25 | Open | Marshall Chuck Pugh | Christopher Puyear |  | Christopher Puyear, Joel Hubbard, Kristy L Dice, Marshall Chuck Pugh |  |  | Marshall Chuck Pugh |  |  | Kristy L Dice | TX-DAL | Trinity River Authority | 200002009 | N/A | Implementation/Deployment | 60% | 11.76% | 4.25 | 3.75 | 0 | 62.5 | 88.24% | 0 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 720.48 | 1000.8 | 938.3 | 93.75%
11/04/24 |  | 06/27/25 | Open | Marshall Chuck Pugh | Christopher Puyear |  | Beau C. Devillier, Christopher Puyear, Hamzeh Tahat, Henry Pugsley, Kristy L Dice, Marshall Chuck Pugh |  |  | Hamzeh Tahat, Henry Pugsley, Marshall Chuck Pugh, Ming Chiu |  |  | Kristy L Dice | TX-DAL | Trinity River Authority | J00019338 | UC System Implementation - TMCRWS | Planning/Design/Staging | 70% | 129.7% | 58.6 | -17.4 | 7911 | 8102.5 | -29.69% | 7911 | 0 | 76 | 156.25 | 6555 |  | 8102.5 |  | 0 | 13509.6 | -1147.9 | -8.497%
05/28/25 |  | 06/27/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Oscar Nunez, Samsoni Jean Claude |  |  | N/A | N/A | Houston ISD | 200002994 | N/A | Not started | 0% | 0% | 0 | -3.5 | 0 | 105 | 0% | 0 | 0 | 3.5 | 0 | 0 |  | 105 |  | 11027 | 0 | -105 | 0%
05/30/25 |  | 06/27/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Walter Hanchett |  |  | N/A | N/A | Houston ISD | 200003007 | N/A | Closed | 0% | 0% | 0 | -4.5 | 0 | 135 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 135 |  | 11596 | 0 | -135 | 0%
05/28/25 |  | 06/27/25 | Closed | Michelle Duenes | Bryan Geoghan |  | Bryan Geoghan |  |  | Yonathan Fadel |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200003000 | N/A | Closed | 0% | 0% | 0 | -5.5 | 0 | 330 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 330 |  | 83050 | 2700 | 2370 | 87.78%
02/03/25 |  | 06/27/25 | Open | Richard Keith Arnst | Bryan Brown |  | Arcangelo Fanelli, Christopher Garcia, Richard Keith Arnst, Ryan Scott, Taylor Leger |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200001805 | N/A | Training/Knowledge Transfer/Documentation | 90% | 143.2% | 17.81 | -7.69 | 2098.75 | 3047.5 | -43.18% | 2098.75 | 0 | 25.5 | 0 | 0 |  | 3047.5 |  | 4616.62 | 4017.6 | 970.1 | 24.15%
02/24/25 |  | 06/27/25 | Open | Ryan Scott | George Delp |  | George Delp, Jessica Anderson, Rafael Rodriguez-Vargas, Ryan Scott |  |  | Rafael Rodriguez-Vargas, Ryan Scott |  |  | Jessica Anderson | US-SP | Duo County Telephone Coop | 200001985 | N/A | Implementation/Deployment | 55% | 22.6% | 36.5 | 28.25 | 0 | 1091.25 | 77.4% | 0 | 0 | 8.25 | 0 | 0 |  | 1091.25 |  | 42936.8 | 7014.8 | 5923.55 | 84.44%
01/24/24 |  | 06/27/25 | Open | Shannon Marie Alvarado | N/A |  | Christi D Hubbard, Christopher Puyear, David Watkins, Jesus Escobedo, Larry Noble, Matthew Duncan, Shannon Marie Alvarado |  |  | Jesus Escobedo, Shannon Marie Alvarado, Sophia Quinter |  |  | Christi D Hubbard | TX-CEN | City of Austin - Aviation Dept | J00017493 | T&E - Wireless Survey & Troubleshoot | Closed | 0% | 0% | 0 | -41.5 | 0 | 5992.5 | 0% | 0 | 0 | 41.5 | 4642.5 | 0 |  | 5992.5 |  | 0 | 0 | -5992.5 | 0%
03/12/25 |  | 06/27/25 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Daniel Snyder, Jason Osuna, Shannon Marie Alvarado |  |  | Jesus Escobedo, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | 200002403 | N/A | Closed | 100% | 76% | 50 | 20 | 0 | 3700 | 40% | 0 | 8 | 38 | 480 | 0 |  | 3700 |  | 0 | 11006.8 | 7306.8 | 66.38%
03/10/25 |  | 06/27/25 | Open | Shannon Marie Alvarado | Mark J Chambliss |  | Lindie Lorraine Lamar, Mark J Chambliss, Shannon Marie Alvarado |  |  | Nathan Dao, Samuel Newland, Shannon Marie Alvarado, Thad Trusler |  |  | Lindie Lamar | TX-HOU | Westlake Corporation | 200002302 | N/A | Closed | 100% | 74.64% | 140 | 55.5 | 0 | 12365 | 39.64% | 0 | 20 | 104.5 | 2000 | 2625 |  | 12365 |  | 0 | 22226.4 | 7236.4 | 32.56%
02/17/25 |  | 06/30/25 | Open | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Ali Al-Haddad, Garrett Hart, Julio C Montoya, Mohammed Al-Shaikhli, Trenton Smith |  |  | N/A | N/A | Houston ISD | 200002014 | N/A | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -32 | 0 | 3075 | 0% | 0 | 2 | 34 | 110 | 0 |  | 3075 |  | 28242.9 | 3300 | 225 | 6.818%
01/30/23 |  | 06/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | Garrett Curran | CA-LAX | Amazon Web Services | J00014741 | AWS Funded - Control Tower Setup | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -14 | 0 | 1890 | 0% | 0 | 0 | 14 | 1890 | 0 |  | 1890 |  | 0 | 10000 | 8110 | 81.1%
01/30/23 |  | 06/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | Garrett Curran | CA-LAX | Amazon Web Services | J00014746 | WORK ORDER - AWS Funded Migration Evaluator | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -4 | 0 | 540 | 0% | 0 | 0 | 4 | 540 | 0 |  | 540 |  | 0 | 4800 | 4260 | 88.75%
01/30/23 |  | 06/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | N/A | N/A | Amazon Web Services | J00014741 | AWS Funded - Control Tower Setup | Training/Knowledge Transfer/Documentation | 95% | 4.179% | 41.88 | 40.13 | 4866.5 | 218.75 | 95.82% | 4866.5 | 0 | 1.75 | 0 | 0 |  | 218.75 |  | 0 | 10000 | 9781.25 | 97.81%
01/30/23 |  | 06/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim |  |  | Brian Willery, Juan Saenz |  |  | N/A | N/A | Amazon Web Services | J00014746 | WORK ORDER - AWS Funded Migration Evaluator | Training/Knowledge Transfer/Documentation | 95% | 9.352% | 24.06 | 21.81 | 2795.75 | 281.25 | 90.65% | 2795.75 | 0 | 2.25 | 0 | 0 |  | 281.25 |  | 0 | 4800 | 4518.75 | 94.14%
05/12/25 |  | 06/30/25 | Closed | Brian Willery | David Goss, Steven Walker |  | Brian Willery, David Goss, Jason Osuna, Steven Walker |  |  | N/A |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | 200002958 | N/A | Not started | 0% | 0% | 46.78 | 46.78 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 124583.8 | 9514.92 | 9514.92 | 100%
09/11/24 |  | 06/30/25 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | Brian Willery |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | J00018978 | City Hall Refresh | Implementation/Deployment | 50% | 13.54% | 142.18 | 122.93 | 12719.4 | 2406.25 | 86.46% | 12719.4 | 0 | 19.25 | 0 | 0 |  | 2406.25 |  | 0 | 20986.8 | 18580.55 | 88.53%
02/16/24 |  | 06/30/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, Cory Bradfield, Cory Bradfield, Jaime B Flores, Jaime Flores, Larry Noble, Maria De Kanter, Mohaymen Sodi, Susan Richardson |  |  | Abdalsattar Albaghdadi, Anthony Lange, Brian Willery, Bryant Bush, Cory Bradfield, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Luis Ovalles, Matthew D'Ambrosio, Mohaymen Sodi, Nathan Dao, Nicolas Garakani, Paul Serres |  |  | Susan Richardson | TX-HOU | Klein ISD | J00017378 | Datacenter Compute, Storage & Network Electronics | Training/Knowledge Transfer/Documentation | 95% | 416% | 346.13 | -986.17 | 46690.64 | 176731.55 | -284.9% | 46690.64 | 107.58 | 1439.88 | 103574.25 | 32.5 |  | 176731.55 |  | 6806687.42 | 164198.28 | -12565.77 | -7.653%
03/25/25 |  | 06/30/25 | Open | Brian Willery | Albert H Nguyen |  | Albert H Nguyen, Brian Willery, Susan Richardson |  |  | Brian Willery |  |  | Susan Richardson | TX-HOU | Pasadena ISD | 200002455 | N/A | Not started | 0% | 0.9708% | 77.25 | 76.5 | 0 | 93.75 | 99.03% | 0 | 0 | 0.75 | 0 | 0 |  | 93.75 |  | 44100.5 | 7808 | 7714.25 | 98.8%
12/11/24 |  | 06/30/25 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Brian Willery, Jacob Parks, Jeffrey Holman, Mark Forehand |  |  | Abdulrahman Farhan, Brian Willery, Dhulfiqar Al Hashimi, Sophia Quinter |  |  | Mark Forehand | TX-DAL | RENT-A-CENTER, INC | 200000276 | N/A | Planning/Design/Staging | 30% | 38.04% | 151.8 | 94.05 | 22275 | 8281.25 | 61.96% | 22275 | 0 | 57.75 | 0 | 0 |  | 8281.25 |  | 0 | 36196.8 | 27915.55 | 77.12%
08/27/24 |  | 06/30/25 | Open | Brittney Antoinette Hickman | N/A |  | Brittney Antoinette Hickman, Christopher Puyear, Henry Pugsley, Kurt Sell, Thomas McClanahan |  |  | Brittney Antoinette Hickman, Henry Pugsley |  |  | Thomas McClanahan | TX-CEN | Samsung Austin Semiconductor, LLC (SAS) | J00018888 | Webex Calling Implementation | Closed | 100% | 44.3% | 163.65 | 91.15 | 23074.65 | 11050 | 55.7% | 23074.65 | 0 | 72.5 | 3762.5 | 0 |  | 11050 |  | 0 | 0 | -11050 | 0%
11/27/23 |  | 06/30/25 | Open | Jim Blackwell | Mark J Chambliss |  | Ashley F Freeman, Hamzeh Tahat, Jim Blackwell, Karyn Hubbard, Larry Noble, Leonid G Kamenker, Leonid Kamenker, Mark J Chambliss, Ming Chiu, Moe Izaks |  |  | Garrett Hart, Hamzeh Tahat, Henry Pugsley, Jennifer Soliz, Jim Blackwell, Lauren Lanzini Coffey, Media Alsewaili, Ming Chiu |  |  | Ashley F Freeman | TX-HOU | Fort Bend County | J00016896 | UCCX, NovelVox, and Eleveo | Closed | 100% | 272.3% | 110.63 | -169.57 | 15156.25 | 39005 | -153.3% | 15156.25 | 21 | 301.2 | 26317.5 | 3565 |  | 39005 |  | 160495.68 | 24346.36 | -18223.64 | -74.85%
08/23/23 |  | 06/30/25 | Closed | Jim Blackwell | Albert H Nguyen, Aman Khan |  | Abdalsattar Albaghdadi, Albert H Nguyen, Aleksei Lavrushenkov, Aman Khan, Ashley F Freeman, Brandon McMillan, Jaime B Flores, Jaime Flores, Jim Blackwell, Jorge Ortiz Cardozo, Kolawole Ayeni, Kord Mullins, Larry Noble, Mustafa Al-Tamimi |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Anthony Lange, Baq Alsaedi, Ben Crouch, Bryant Bush, Craig St. Rose, David Dobbs, David Neal Gravatt, Devon LeMoine, Hector Rivera, Jerald Garner, Jesus Gonzalez, Jim Blackwell, Jorge Ortiz Cardozo, Jose R. Duarte, Julio C Montoya, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Mustafa Al-Tamimi, Nathan Dao, Nicola |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016075 | LAN Phase 1B High School AP Deployments | Closed | 100% | 74.04% | 2683.99 | 874.72 | 215486.37 | 146411 | 32.59% | 215486.37 | 177.83 | 1987.1 | 93291.2 | 68.75 |  | 146411 |  | 3792738.16 | 352420.18 | 205940.43 | 58.44%
04/29/24 |  | 06/30/25 | Open | Jim Blackwell | David Escamilla, Firas Abood |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, David Escamilla, Firas Abood, Jim Blackwell, Larry Noble, Luis A Alvarez, Luis Alvarez |  |  | Andy Pham, Cory Bradfield, Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018235 | UCSC Server Implementation | Closed | 100% | 64.64% | 105.2 | 49.45 | 1387.5 | 8605 | 47.01% | 1387.5 | 12.25 | 68 | 2718.75 | 0 |  | 8605 |  | 167484.44 | 19506.8 | 10901.8 | 55.89%
05/09/25 |  | 06/30/25 | Open | Jim Blackwell | Firas Abood |  | Firas Abood, Jesus Escobedo, Jim Blackwell, Juan Saenz, Meredith A Richardson |  |  | Jim Blackwell, Juan Saenz |  |  | N/A | N/A | Houston ISD | 200002956 | N/A | Closed | 0% | 0% | 0 | -20.5 | 0 | 2747.5 | 0% | 0 | 0 | 20.5 | 0 | 0 |  | 2747.5 |  | 0 | 4500 | 1752.5 | 38.94%
06/10/24 |  | 06/30/25 | Open | Marco Lish | Christopher Puyear |  | Beau C. Devillier, Christopher Puyear, Kristy L Dice, Marco Lish |  |  | Brian Newman, Marco Lish |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00018486 | Fire Control Panel Integration with Olympus | Planning/Design/Staging | 55% | 54.21% | 95 | 43.5 | 13579.45 | 7007.5 | 45.79% | 13579.45 | 0 | 51.5 | 218.75 | 0 |  | 7007.5 |  | 11257 | 20905.6 | 13898.1 | 66.48%
08/21/23 |  | 06/30/25 | Open | Marshall Chuck Pugh | Bryan Geoghan |  | Beau C. Devillier, Bryan Geoghan, Conner MacDonnell, Jeffery Giles, Marshall Chuck Pugh , Samuel Newland, Tavis Jackson, Taylor Leger |  |  | Conner MacDonnell, Jeffery Giles, Kirk O'Guinn, Marshall Chuck Pugh, Samuel Newland, Tavis Jackson, William Chris Roome |  |  | Taylor Leger | TX-DAL | Corsicana ISD | J00016106 | Singlewire Fusion Migration | Closed | 100% | 45.85% | 313 | 169.5 | 40163.06 | 18245 | 54.15% | 40163.06 | 0 | 143.5 | 10870 | 52.12 |  | 18245 |  | 76185.5 | 90675.2 | 72378.08 | 79.82%
04/17/25 |  | 06/30/25 | Open | Shannon Marie Alvarado | Mark J Chambliss |  | Lindie Lorraine Lamar, Mark J Chambliss, Shannon Marie Alvarado |  |  | Samuel Newland, Shannon Marie Alvarado |  |  | Lindie Lamar | TX-HOU | Westlake Corporation | 200002705 | N/A | Closed | 100% | 35.62% | 80 | 62.5 | 0 | 3810 | 78.12% | 0 | 11 | 28.5 | 1540 | 0 |  | 3810 |  | 0 | 13220 | 9410 | 71.18%
11/09/23 |  | 06/30/25 | Closed | Summer Abunaja | N/A |  | Arcangelo Fanelli, Beau C. Devillier, Darrell Walton, Darrell Walton, David Pena, Jonathan Weir, Jonathan Weir, Jose Gutierrez, Summer Abunaja, Timothy Rosser |  |  | Darrell Walton |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | J00016809 | Optical WAN Networking and Route/Switch T&E | Not started | 0% | 0% | 0 | -3 | 0 | 405 | 0% | 0 | 0 | 3 | 405 | 0 |  | 405 |  | 0 | 600 | 195 | 32.5%
12/14/23 |  | 06/30/25 | Closed | Summer Abunaja | Mark J Chambliss |  | Brian Newman, Brian Newman, Christopher Kutalek, Shiraz Humayun, Summer Abunaja |  |  | Lauren Lanzini Coffey |  |  | Christopher Kutalek | TX-HOU | Fugro USA, Inc. | J00017107 | T&E - Voice License | Closed | 0% | 0% | 0 | -0.5 | 0 | 62.5 | 0% | 0 | 0 | 0.5 | 62.5 | 0 |  | 62.5 |  | 0 | 0 | -62.5 | 0%
01/06/25 |  | 06/30/25 | Open | Summer Abunaja | Wyley Johnson |  | Ibrahim Altaweel, Jerome Tanyag Mara, Mohammad Arman, Rogelio Morgado-Perez, Summer Abunaja, Thomas McClanahan, Tom Magboo, Wyley Johnson |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, Rogelio Morgado-Perez, Summer Abunaja, Tom Magboo |  |  | Thomas McClanahan | TX-CEN | Killeen ISD | 200001513 | N/A | Training/Knowledge Transfer/Documentation | 100% | 99.28% | 208 | 1.5 | 31100 | 30850 | 0.7212% | 31100 | 0 | 206.5 | 0 | 0 |  | 30850 |  | 0 | 22795 | -8055 | -35.34%
10/26/22 |  | 06/30/25 | Open | Summer Abunaja | Jeremy Hoffpauir |  | Aaron Christopher Pfeifer, Jamie Lewis, Jeff Barker, Jessica Anderson, Summer Abunaja |  |  | Aaron Christopher Pfeifer |  |  | Jamie Lewis | US-SP | Riviera Utilities | J00014264 | T&E - Technical & Troubleshooting Support | Not started | 0% | 0% | 0 | -217 | 0 | 29295 | 0% | 0 | 0 | 217 | 29295 | 0 |  | 29295 |  | 0 | 49875 | 20580 | 41.26%
10/26/22 |  | 06/30/25 | Open | Summer Abunaja | Jeremy Hoffpauir |  | Aaron Christopher Pfeifer, Jamie Lewis, Jeff Barker, Jessica Anderson, Summer Abunaja |  |  | Aaron Christopher Pfeifer |  |  | N/A | N/A | Riviera Utilities | J00014264 | T&E - Technical & Troubleshooting Support | Not started | 0% | 0% | 0 | -5.75 | 0 | 776.25 | 0% | 0 | 0 | 5.75 | 0 | 0 |  | 776.25 |  | 0 | 49875 | 49098.75 | 98.44%
08/22/22 |  | 06/30/25 | Open | Summer Abunaja | Chad Hart |  | Neel Shah, Shiraz Humayun, Summer Abunaja |  |  | Devon LeMoine, Kord Mullins, Lauren Lanzini Coffey, Mohammed Al-Shaikhli |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00013645 | TCP Quote (Voice Project Phase 3 Budget) | On HOLD | 20% | 4.936% | 166.11 | 158.71 | 9856.5 | 648 | 95.55% | 9856.5 | 0.8 | 8.2 | 630 | 0 |  | 648 |  | 1936833.6 | 18223.6 | 17575.6 | 96.44%
07/31/23 |  | 06/30/25 | Open | Summer Abunaja | Christine A Hupe |  | Neel Shah, Shiraz Humayun, Summer Abunaja |  |  | Andy Alvarenga, Jose R. Duarte, Kord Mullins, Lauren Lanzini Coffey, Luis Alvarez |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00016121 | TCH Ambulance Routers | On HOLD | 25% | 49.7% | 84 | 44.25 | 5950 | 2553.75 | 52.68% | 5950 | 2 | 41.75 | 2433.75 | 526.44 |  | 2553.75 |  | 36770.4 | 9371.2 | 6291.01 | 67.13%
02/19/24 |  | 06/30/25 | Open | Summer Abunaja | Christine A Hupe |  | Jose E. Duarte Jr, Jose R Duarte, Jose R. Duarte, Neel Shah, Shiraz Humayun, Summer Abunaja |  |  | Jesus Gonzalez, Justin Smallwood, Miguel Reed, Mohammed Al-Shaikhli, Summer Abunaja |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00017591 | 8 Additional Ambulances | Implementation/Deployment | 20% | 7.5% | 120 | 111.5 | 8500 | 620 | 92.92% | 8500 | 0.5 | 9 | 380 | 0 |  | 620 |  | 61369.4 | 13706 | 13086 | 95.48%
05/09/24 |  | 06/30/25 | Open | Summer Abunaja | George Edwin Jacob |  | Joseph Boglino, Larry Noble, Summer Abunaja, Tony Dean Skipworth |  |  | Summer Abunaja, Tony Dean Skipworth |  |  | Joseph Boglino | US-FED | U.S. Peace Corps | J00018290 | APIC Cluster Project | Implementation/Deployment | 20% | 76.67% | 30 | 7 | 4050 | 3070 | 23.33% | 4050 | 0 | 23 | 3070 | 0 |  | 3070 |  | 140008.68 | 6075 | 3005 | 49.47%
01/31/25 |  | 06/30/25 | Open | Tray Giddens | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Ali Shinakho, Dustin Huffman, Tray Giddens, Wyley Johnson |  |  | Ali Shinakho, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200001803 | N/A | Planning/Design/Staging | 20% | 94.05% | 126 | 7.5 | 18750 | 17687.5 | 5.952% | 18750 | 0 | 118.5 | 0 | 0 |  | 17687.5 |  | 0 | 24672 | 6984.5 | 28.31%
03/12/25 |  | 06/30/25 | Open | Tray Giddens | Aman Khan, David Escamilla |  | Aman Khan, Dustin Huffman, Tray Giddens |  |  | Caleb Henry, Cory Bradfield, Craig St. Rose, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio, Noah Trump, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Gulf Capital Bank | 200002327 | N/A | Closed | 100% | 85.49% | 98.55 | 29.55 | 0 | 9661.25 | 29.98% | 0 | 15.25 | 84.25 | 1721.25 | 0 |  | 9661.25 |  | 527907.68 | 15272 | 5610.75 | 36.74%
02/25/25 |  | 06/30/25 | Open | Tray Giddens | Aman Khan, Mark J Chambliss |  | Aman Khan, Dustin Huffman, Mark J Chambliss, Tray Giddens |  |  | Ahmed Jameel, Kevin Curtis, Matthew D'Ambrosio, Miguel Reed, Nathan Dao, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Landry's Hotel Division | 200002129 | N/A | Closed | 100% | 82.43% | 104.64 | 31.39 | 0 | 8880 | 30% | 0 | 13 | 86.25 | 1040 | 0 |  | 8880 |  | 48715.25 | 14003.84 | 5123.84 | 36.59%
09/11/24 |  | 06/30/25 | Open | Walter Clay Knight | Bryan Brown |  | Ashley F Freeman, Christopher Garcia, Larry Noble |  |  | Clinton Bennett Deason, Walter Clay Knight |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00018965 | Correction Health Conf Room CO | Implementation/Deployment | 50% | 30% | 10 | 7 | 1410 | 325 | 70% | 1410 | 0 | 3 | 200 | 0 |  | 325 |  | 5347.06 | 2305.6 | 1980.6 | 85.9%
06/23/23 |  | 06/30/25 | Open | Walter Clay Knight | Bryan Brown |  | Aaron Johns, Aaron Johns, Ashley F Freeman, Christopher Garcia, Jesus Gonzalez, Justin Higgins, Justin Higgins, Shiraz Humayun, Walter Clay Knight |  |  | Clinton Bennett Deason, Jeremiah Solomon, Jesus Gonzalez, Walter Clay Knight |  |  | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00015634 | Correctional Health AV Room Installation | Implementation/Deployment | 50% | 50.4% | 46.13 | 24.88 | 3901.25 | 1666.25 | 53.93% | 3901.25 | 2 | 23.25 | 451.25 | 0 |  | 1666.25 |  | 52967.5 | 5218.12 | 3551.87 | 68.07%
03/06/25 |  | 07/01/25 | Open | Jennifer Soliz | N/A |  | Garrett Curran, Jennifer Soliz, Meray Doughly, Steven Walker |  |  | Assad Jumshyd, Elie Karkafi, Jennifer Soliz, Marianne Hajjar, Matthew Taylor |  |  | Garrett Curran | CA-LAX | San Bernardino County ERA | 200002312 | N/A | Closed | 0% | 0% | 0 | -375 | 0 | 37750 | 0% | 0 | 0 | 375 | 0 | 0 |  | 37750 |  | 0 | 0 | -37750 | 0%
04/28/25 |  | 07/01/25 | Open | Marco Lish | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Kristy L Dice, Marco Lish, Remi Martinez-Montenegro |  |  | Jayden Colon, John Johnson, Samuel Gonzalez |  |  | Kristy L Dice | TX-DAL | Aledo ISD | 200002900 | N/A | Implementation/Deployment | 50% | 155.9% | 24.05 | -5.45 | 0 | 2250 | -22.66% | 0 | 8 | 37.5 | 480 | 0 |  | 2250 |  | 5728.14 | 3365.2 | 1115.2 | 33.14%
08/25/23 |  | 07/01/25 | Closed | Marshall Chuck Pugh | Steven Walker |  | Beau C. Devillier, Christopher Brown, Christopher Brown, Lauren J Kennewell, Lee McChesney, Marshall Chuck Pugh , Steven Walker |  |  | Christopher Brown, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Carroll ISD | J00014805 | Microsoft Office 365 Migration | Closed | 85% | 116.5% | 46.13 | -7.62 | 6022.35 | 7208.75 | -16.52% | 6022.35 | 0 | 53.75 | 7208.75 | 0 |  | 7208.75 |  | 0 | 8128 | 919.25 | 11.31%
08/25/23 |  | 07/01/25 | Open | Marshall Chuck Pugh | Steven Walker |  | Beau C. Devillier, Christopher Brown, Christopher Brown, Lauren J Kennewell, Lee McChesney, Marshall Chuck Pugh, Steven Walker |  |  | Christopher Brown, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Carroll ISD | J00014807 | Microsoft Office 365 Migration | Closed | 100% | 41.13% | 105.75 | 62.25 | 13806.25 | 5762.5 | 58.87% | 13806.25 | 0 | 43.5 | 1375 | 0 |  | 5762.5 |  | 0 | 18635 | 12872.5 | 69.08%
02/27/25 |  | 07/01/25 | Closed | Marshall Chuck Pugh | William Birdsong |  | Lauren J Kennewell, Mark Forehand, Marshall Chuck Pugh , Vitalii Stepanchenko, William Birdsong |  |  | Carlo Enriquez, Marshall Chuck Pugh, Vitalii Stepanchenko |  |  | Mark Forehand | TX-DAL | RENT-A-CENTER, INC | 200002192 | N/A | Closed | 100% | 66.98% | 124.67 | 41.17 | 0 | 10340 | 33.02% | 0 | 0 | 83.5 | 0 | 0 |  | 10340 |  | 194116.14 | 20289.2 | 9949.2 | 49.04%
10/15/24 |  | 07/01/25 | Open | Ryan Scott | Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, Darrell Walton, Darrell Walton, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Ryan Scott, Taylor Leger |  |  | Darrell Walton, Devin Moreno, Jose Gutierrez, Noah Castleberry, Ryan Scott |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00019060 | WAN Processor and AMP Refresh | Closed | 100% | 54.67% | 56.25 | 26 | 7481.25 | 3102.5 | 46.22% | 7481.25 | 0.5 | 30.75 | 311.25 | 0 |  | 3102.5 |  | 0 | 15710.4 | 12607.9 | 80.25%
04/18/25 |  | 07/01/25 | Open | Summer Abunaja | Bryan Geoghan |  | Arcangelo Fanelli, Bryan Geoghan, Ming Chiu, Summer Abunaja |  |  | Summer Abunaja |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | 200002733 | N/A | Planning/Design/Staging | 15% | 4.706% | 42.5 | 40.5 | 0 | 200 | 95.29% | 0 | 0 | 2 | 0 | 0 |  | 200 |  | 3345.6 | 9496 | 9296 | 97.89%
06/16/25 |  | 07/03/25 | Open | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Justin Smallwood |  |  | N/A | N/A | Houston ISD | 200002673 | N/A | Planning/Design/Staging | 0% | 0% | 0 | 0 | 0 | 60 | 0% | 0 | 1 | 1 | 60 | 0 |  | 60 |  | 7126.2 | 750 | 690 | 92%
06/03/25 |  | 07/03/25 | Open | Joanna Herrera | Michael Brett Beggs |  | Arcangelo Fanelli, Joanna Herrera, Juan Saenz, Michael Brett Beggs |  |  | Joanna Herrera, Juan Saenz |  |  | Arcangelo Fanelli | TX-DAL | Cook Children's Health Care System | 200003046 | N/A | Training/Knowledge Transfer/Documentation | 95% | 113.7% | 10.55 | -1.45 | 0 | 1605 | -13.74% | 0 | 0 | 12 | 0 | 0 |  | 1605 |  | 0 | 1585 | -20 | -1.262%
08/29/22 |  | 07/03/25 | Open | Joanna Herrera | Christopher Kemsley |  | Joanna Herrera |  |  | Jillian Townson, Joanna Herrera |  |  | David D Tijerina | TX-CEN | Leander ISD | J00010138 | AP Wireless Gap Coverage | Planning/Design/Staging | 20% | 20.13% | 106.78 | 85.28 | 6669.2 | 2687.5 | 79.87% | 6669.2 | 0 | 21.5 | 2562.5 | 0 |  | 2687.5 |  | 99060.1 | 39250.4 | 36562.9 | 93.15%
02/24/25 |  | 07/03/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, LaQisha Marshall |  |  | Henry Pugsley, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200002146 | N/A | Training/Knowledge Transfer/Documentation | 90% | 77.33% | 18.75 | 4.25 | 0 | 2487.5 | 22.67% | 0 | 0 | 14.5 | 0 | 0 |  | 2487.5 |  | 0 | 2775.96 | 288.46 | 10.39%
03/05/25 |  | 07/03/25 | Open | Richard Keith Arnst | Bryan Brown, Christopher Garcia |  | Arcangelo Fanelli, Bryan Brown, Christopher Garcia, Richard Keith Arnst |  |  | Joel Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | 200002295 | N/A | Implementation/Deployment | 90% | 66.7% | 137.19 | 50.69 | 0 | 9067.5 | 36.95% | 0 | 5 | 91.5 | 625 | 0 |  | 9067.5 |  | 112738.26 | 24714.8 | 15647.3 | 63.31%
06/06/25 |  | 07/04/25 | Open | Michelle Duenes | Collin Mazzeno |  | Collin Mazzeno |  |  | Aboobiada Ali Abdalla, Adiel Alvarez, Ahmed Alolofi, Andrew Comeaux, Ariel Garcia, Camila Guzman, Daniel Munoz, David Lenihan, Dedric Bowens, Deonte Terrell, Edgar Rodriguez, Elfadil Elnour, Eliana Guzman, Esmat Osman, Folasayo Adekanbi, Frank Bartunek, George Izaguirre, Gerardo Ramirez, Gregory Posey, Harold Gomez, Jaden Williams, James Charvis, James Robertson, Jaren Smallwood, Jarshawn Newsome, Jesus Guadian, John Guadian, Jonathan McCoy, Joshua Jones, Josias Ajche, Josue Iglesias, Joyce Bir |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200003036 | N/A | Not started | 0% | 0% | 0 | -5364.5 | 0 | 158955 | 0% | 0 | 0 | 5364.5 | 0 | 0 |  | 158955 |  | 0 | 1336960 | 1178005 | 88.11%
06/06/25 |  | 07/04/25 | Open | Michelle Duenes | Collin Mazzeno |  | Collin Mazzeno |  |  | Dedric Bowens, Jaren Smallwood, Jarshawn Newsome, Jesus Guadian, Jonathan McCoy, Pedro Cavazos, Rashaud Compton, Steffany Alvarez, Walter Hanchett |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200003037 | N/A | Not started | 0% | 0% | 0 | -59.75 | 0 | 1792.5 | 0% | 0 | 0 | 59.75 | 0 | 0 |  | 1792.5 |  | 0 | 175000 | 173207.5 | 98.98%
06/05/25 |  | 07/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez, Nathanael Morales, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200003031 | N/A | Closed | 0% | 0% | 0 | -11 | 0 | 330 | 0% | 0 | 0 | 11 | 0 | 0 |  | 330 |  | 69030 | 0 | -330 | 0%
06/06/25 |  | 07/04/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Samsoni Jean Claude, Valentin Vasquez |  |  | N/A | N/A | Houston ISD | 200003040 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 2800 | 0 | -90 | 0%
02/25/25 |  | 07/10/25 | Closed | Ryan Scott | David Watkins |  | David Watkins, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | N/A |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200002163 | N/A | Implementation/Deployment | 75% | 0% | 4 | 4 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 48756.4 | 48756.4 | 100%
06/04/25 |  | 07/11/25 | Open | Brian Willery | N/A |  | Brian Willery, David Escamilla, Jaclyn Pias |  |  | Brian Willery |  |  | Jaclyn Pias | TX-HOU | Hogan Data Operations | 200003006 | N/A | Planning/Design/Staging | 5% | 4.571% | 43.75 | 41.75 | 0 | 250 | 95.43% | 0 | 0 | 2 | 0 | 0 |  | 250 |  | 251413.55 | 11000 | 10750 | 97.73%
03/25/25 |  | 07/11/25 | Open | Brian Willery | Ahmed Al-Zubaidi, Chad Hart |  | Ahmed Al-Zubaidi, Brian Willery, Chad Hart, Jaclyn Pias, Mohammed Almoola |  |  | Brian Willery, James Adams, Kolawole Ayeni, Mohammed Almoola |  |  | Jaclyn Pias | TX-HOU | Houston Zoo | 200002506 | N/A | Planning/Design/Staging | 50% | 45.01% | 78.87 | 44.37 | 0 | 4112.5 | 56.26% | 0 | 1 | 35.5 | 60 | 0 |  | 4112.5 |  | 26004.1 | 12088.4 | 7975.9 | 65.98%
02/04/25 |  | 07/11/25 | Open | Jennifer Soliz | Daniel Snyder |  | Daniel Snyder, David Neal Gravatt, Ernesto Gonzalez, Jennifer Soliz, Lonnie Owens, Mohammed Almoola, Quoc Nguyen |  |  | David Neal Gravatt, Ernesto Gonzalez, Jennifer Soliz, Mohammed Almoola, Moises Rodriguez |  |  | Lonnie Owens | TX-CEN | McCoy Corporation | 200001819 | N/A | Training/Knowledge Transfer/Documentation | 95% | 86.52% | 483.13 | 66.13 | 62365.93 | 52450 | 13.69% | 62365.93 | 1 | 418 | 125 | 0 |  | 52450 |  | 0 | 104395.6 | 51945.6 | 49.76%
11/13/24 |  | 07/11/25 | Open | Jennifer Soliz | Christopher Puyear |  | Christopher Puyear, Hannah Paul, Jennifer Soliz |  |  | Jennifer Soliz, John Stephen Kurkjian |  |  | Hannah Edmunds | TX-CEN | Texas Parks and Wildlife | J00019415 | N/A | Implementation/Deployment | 75% | 81.25% | 80 | 15 | 11280 | 8965 | 18.75% | 11280 | 0 | 65 | 0 | 0 |  | 8965 |  | 9865.84 | 16581.6 | 7616.6 | 45.93%
03/10/25 |  | 07/11/25 | Open | Jim Blackwell | Mark J Chambliss |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Henry Pugsley, Jim Blackwell, Mark J Chambliss, Moe Izaks |  |  | Craig St. Rose, Henry Pugsley, Jim Blackwell, Justin Cornish, Kord Mullins, Luis Alvarez |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200002340 | N/A | Training/Knowledge Transfer/Documentation | 100% | 52.11% | 142.5 | 72.25 | 0 | 10663.75 | 50.7% | 0 | 4 | 74.25 | 240 | 0 |  | 10663.75 |  | 0 | 31361.4 | 20697.65 | 66%
06/12/25 |  | 07/11/25 | Open | Joanna Herrera | N/A |  | Alexander Gutman, George Edwin Jacob, Joanna Herrera |  |  | Joanna Herrera |  |  | Alex Gutman | TX-DAL | Tyler Junior College | 200003087 | N/A | Planning/Design/Staging | 5% | 6.25% | 8 | 7.5 | 0 | 62.5 | 93.75% | 0 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 0 | 768.4 | 705.9 | 91.87%
03/10/25 |  | 07/11/25 | Open | Joaquin Marroquin | Bryan Brown, Christopher Ceykovsky |  | Christopher Ceykovsky, Christopher Garcia, Joaquin Marroquin, Ming Chiu, Samuel Newland, Xavier A Trevino |  |  | Joaquin Marroquin, Samuel Newland |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | 200002350 | N/A | Planning/Design/Staging | 5% | 27.35% | 73.13 | 53.13 | 0 | 2687.5 | 72.65% | 0 | 0 | 20 | 0 | 0 |  | 2687.5 |  | 0 | 12146 | 9458.5 | 77.87%
07/03/23 |  | 07/11/25 | Open | Joaquin Marroquin | N/A |  | Diana Berger, Joaquin Marroquin, Michelle Bailey, Warren Wilson, Xavier A Trevino |  |  | Garrett Hart |  |  | Xavier A Trevino | TX-SOUT | Gulf Coast Federal Credit Union | J00015864 | Port A - Security Camera installation | On HOLD | 5% | 7.66% | 26.11 | 24.11 | 3006.9 | 350 | 92.34% | 3006.9 | 0 | 2 | 350 | 0 |  | 350 |  | 0 | 0 | -350 | 0%
01/20/25 |  | 07/11/25 | Closed | Joaquin Marroquin | Christopher Puyear |  | Christopher Puyear, David D Tijerina, Joaquin Marroquin, Samuel Newland |  |  | N/A |  |  | David D Tijerina | TX-CEN | Leander ISD | 200001635 | N/A | On HOLD | 90% | 0% | 9 | 9 | 1245 | 0 | 100% | 1245 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 1786.04 | 1786.04 | 100%
02/12/24 |  | 07/11/25 | Open | Joaquin Marroquin | Edward Padron |  | Diana Berger, Edward Padron, Joaquin Marroquin, Michelle Bailey, Ruben Cantu, Xavier A Trevino |  |  | Mario Sanchez, Ruben Cantu |  |  | Xavier A Trevino | TX-SOUT | Security First Credit Union | J00017489 | BGP Configuration Primary and DR Sites | On HOLD | 0% | 6.856% | 21.88 | 20.38 | 2735 | 190 | 93.14% | 2735 | 0 | 1.5 | 190 | 0 |  | 190 |  | 0 | 4306.4 | 4116.4 | 95.59%
09/08/23 |  | 07/11/25 | Open | Joaquin Marroquin | Edward Padron |  | Amy Martinez-Nagy, Christopher Prado, Daniel Saenz, David Avila, Edward Padron, Felix Martinez, Joaquin Marroquin, Michelle Bailey, Xavier A Trevino |  |  | Felix Martinez, Joaquin Marroquin |  |  | N/A | N/A | Texas A&M International University | J00015044 | Tennis Court UPS Install | On HOLD | 50% | 0% | 12.29 | 12.29 | 946.45 | 0 | 100% | 946.45 | 0 | 0 | 0 | 1015.67 |  | 0 |  | 9361.44 | 1083.2 | 67.53 | 6.234%
09/08/23 |  | 07/11/25 | Open | Joaquin Marroquin | Edward Padron |  | Amy Martinez-Nagy, Christopher Prado, Daniel Saenz, David Avila, Edward Padron, Felix Martinez, Joaquin Marroquin, Michelle Bailey, Xavier A Trevino |  |  | Felix Martinez, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Texas A&M International University | J00015044 | Tennis Court UPS Install | On HOLD | 0% | 0% | 0 | -3.5 | 0 | 372.5 | 0% | 0 | 0 | 3.5 | 372.5 | 1015.67 |  | 372.5 |  | 9361.44 | 1083.2 | -304.97 | -28.15%
05/23/24 |  | 07/11/25 | Open | LaQisha Marshall | Bryan Brown, Christopher Puyear |  | Christi D Hubbard, Christopher Garcia, Christopher Puyear, John Stephen Kurkjian, Kurt Sell, LaQisha Marshall, Lori Endsley, Oscar Gonzalez |  |  | Briliance Johnson, Carlo Enriquez, Jacob Hill, John Stephen Kurkjian, Kendall Walls, LaQisha Marshall, Noah Trump, Oscar Gonzalez, Robert Jones, Steven Shipmon, Wilangel Francis |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018373 | District Analog VG Replacement | Training/Knowledge Transfer/Documentation | 90% | 174.8% | 213.76 | -138.49 | 4553.25 | 32583.75 | -64.79% | 4553.25 | 21.5 | 373.75 | 2007.5 | 0 |  | 32583.75 |  | 314631 | 29056.8 | -3526.95 | -12.14%
04/25/25 |  | 07/11/25 | Open | LaQisha Marshall | Mark J Chambliss |  | David Monasmith, David Monasmith, Henry Pugsley, LaQisha Marshall, Mark J Chambliss |  |  | Henry Pugsley, LaQisha Marshall |  |  | David Monasmith | TX-HOU | Texas A&M University | 200002882 | N/A | Planning/Design/Staging | 5% | 65% | 20 | 7 | 0 | 1825 | 35% | 0 | 0 | 13 | 0 | 0 |  | 1825 |  | 0 | 4401.6 | 2576.6 | 58.54%
04/24/25 |  | 07/11/25 | Open | Marco Lish | Michael Brett Beggs |  | Jonathan Pendrich, Marco Lish, Michael Brett Beggs |  |  | Luis Ovalles, Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Coblentz Patch Duffy & Bass LLP | 200002887 | N/A | Planning/Design/Staging | 20% | 17.74% | 77.5 | 63.75 | 0 | 1808.75 | 82.26% | 0 | 0 | 13.75 | 0 | 0 |  | 1808.75 |  | 0 | 16209.92 | 14401.17 | 88.84%
06/11/25 |  | 07/11/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Dedric Bowens, Rashaud Compton |  |  | N/A | N/A | Houston ISD | 200003056 | N/A | Not started | 0% | 0% | 0 | -2 | 0 | 60 | 0% | 0 | 0 | 2 | 0 | 0 |  | 60 |  | 33598 | 0 | -60 | 0%
06/11/25 |  | 07/11/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Oscar Nunez |  |  | N/A | N/A | Houston ISD | 200003057 | N/A | Not started | 0% | 0% | 0 | -2.5 | 0 | 75 | 0% | 0 | 0 | 2.5 | 0 | 0 |  | 75 |  | 10620 | 0 | -75 | 0%
06/12/25 |  | 07/11/25 | Open | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey, Lorenzo Hernandez |  |  | N/A | N/A | Houston ISD | 200003061 | N/A | Not started | 0% | 0% | 0 | -4 | 0 | 120 | 0% | 0 | 0 | 4 | 0 | 0 |  | 120 |  | 37050 | 0 | -120 | 0%
06/13/25 |  | 07/11/25 | Closed | Michelle Duenes | Mark J Chambliss |  | Mark J Chambliss |  |  | Gregory Posey |  |  | N/A | N/A | Houston ISD | 200003067 | N/A | Closed | 0% | 0% | 0 | -3 | 0 | 90 | 0% | 0 | 0 | 3 | 0 | 0 |  | 90 |  | 28576 | 1330 | 1240 | 93.23%
05/31/24 |  | 07/11/25 | Open | Richard Keith Arnst | Ahmed Al-Zubaidi, David Escamilla, Joshua Adam Engle, Wyley Johnson |  | Ashutosh Patel, Christopher Butler, Maria De Kanter, Randy Schamberger, Raul Velazquez, Richard Keith Arnst, Tony Dean Skipworth |  |  | Ashutosh Patel, Kreshnik Memaj, Raul Velazquez, Richard Keith Arnst, Romar Roca, Tony Dean Skipworth |  |  | Randy Schamberger | FL | Charlotte County Clerk of the Circuit Court | J00014845 | Core Upgrade & Net-Pro-3rd Party Srvcs | Implementation/Deployment | 85% | 120.7% | 548.85 | -81.4 | 87146.41 | 89143.75 | -14.83% | 87146.41 | 32 | 662.25 | 65992.5 | 50 |  | 89143.75 |  | 271377.04 | 112684.24 | 23490.49 | 20.85%
01/27/25 |  | 07/11/25 | Open | Robert McIver | Daniel Snyder |  | Daniel Snyder, Lonnie Owens, Mohammed Almoola, Robert McIver |  |  | An Le, Celso Lopez, Isaiah Rosales, James Danner, John Senkulics, Michael Torres, Mohammed Almoola, Robert McIver |  |  | Lonnie Owens | TX-CEN | John Hagee Ministries | 200001687 | N/A | Training/Knowledge Transfer/Documentation | 85% | 126.5% | 192.95 | -51.05 | 0 | 22830 | -26.46% | 0 | 0 | 244 | 0 | 0 |  | 22830 |  | 219066.27 | 34892.48 | 12062.48 | 34.57%
03/04/25 |  | 07/11/25 | Open | Robert McIver | Christopher Ceykovsky |  | Anthony Towsley, Christopher Ceykovsky, Daniel Saenz, Robert McIver |  |  | Anthony Towsley, Joaquin Garcia, Robert McIver, Roger Guerra |  |  | Daniel Saenz | TX-SOUT | Los Fresnos CISD | 200002285 | N/A | Implementation/Deployment | 60% | 29.03% | 116.25 | 82.75 | 0 | 4350 | 71.18% | 0 | 0.25 | 33.75 | 15 | 0 |  | 4350 |  | 20911.4 | 21164 | 16814 | 79.45%
05/05/25 |  | 07/11/25 | Open | Robert McIver | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro, Rene Trejo, Robert McIver, Xavier A Trevino |  |  | Clinton Bennett Deason, Francisco Hernandez, Rene Trejo, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Rio Bank | 200002913 | N/A | Training/Knowledge Transfer/Documentation | 80% | 146.5% | 49.5 | -10.5 | 0 | 6015 | -21.21% | 0 | 12.5 | 72.5 | 930 | 0 |  | 6015 |  | 19701.51 | 11410.4 | 5395.4 | 47.28%
05/05/25 |  | 07/11/25 | Open | Robert McIver | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro, Robert McIver, Xavier A Trevino |  |  | Clinton Bennett Deason, Rene Trejo |  |  | Xavier A Trevino | TX-SOUT | Texas State Technical College Waco | 200002932 | N/A | Implementation/Deployment | 40% | 86.6% | 46.19 | 16.19 | 0 | 3000 | 35.05% | 0 | 10 | 40 | 750 | 0 |  | 3000 |  | 5248.34 | 6945.6 | 3945.6 | 56.81%
05/18/23 |  | 07/11/25 | Open | Ryan Scott | George Delp |  | George Delp, Jeff Barker, Jessica Anderson, Rafael Rodriguez-Vargas, Ryan Scott, Shannon Rico, Thomas Haag, Tom Haag, William Chris Roome |  |  | Aaron Christopher Pfeifer, Carlo Enriquez, Christina Rice, Darrell Walton, Kebret Eshetu, Rafael Rodriguez-Vargas, Ryan Scott, Tabais Prater, William Chris Roome |  |  | Jessica Anderson | US-SP | Bluegrass Network | J00014628 | Bluegrass Network: Optical Transport | Training/Knowledge Transfer/Documentation | 90% | 45.9% | 1256.66 | 690.31 | 156995 | 73238.75 | 54.93% | 156995 | 10.5 | 576.85 | 53135 | 0 |  | 73238.75 |  | 4560977.84 | 309553.2 | 236314.45 | 76.34%
11/04/24 |  | 07/11/25 | Open | Ryan Scott | George Delp |  | George Delp, Jeff Barker, Jessica Anderson, Rafael Rodriguez-Vargas, Ryan Scott |  |  | Rafael Rodriguez-Vargas, Ryan Scott |  |  | Jessica Anderson | US-SP | Bluegrass Network | J00018981 | Router Configuration Implementation | Training/Knowledge Transfer/Documentation | 95% | 85% | 40 | 6 | 5320 | 4520 | 15% | 5320 | 0 | 34 | 2815 | 0 |  | 4520 |  | 0 | 7820.4 | 3300.4 | 42.2%
12/10/24 |  | 07/11/25 | Open | Ryan Scott | David Watkins |  | Conner MacDonnell, David Watkins, Devin Moreno, Jeffery Giles, Joshua Hubbard, Karen Grant-Dennison, Mario Sanchez, Matthew Veach, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Carlo Enriquez, Conner MacDonnell, David Neal Gravatt, Devin Moreno, Jeffery Giles, Joshua Hubbard, Kendall Walls, Mario Sanchez, Matthew Veach, Noah Castleberry, Quy Le, Ryan Scott, William Chris Roome, Yonathan Fadel |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200000226 | N/A | Implementation/Deployment | 70% | 91.14% | 437.24 | 99.99 | 46806.35 | 42930 | 22.87% | 46806.35 | 61.25 | 398.5 | 4715 | 0 |  | 42930 |  | 172781.8 | 69042 | 26112 | 37.82%
02/24/25 |  | 07/11/25 | Open | Ryan Scott | David Watkins |  | Ahmed Jameel, David Watkins, David Neal Gravatt, Devin Moreno, Karen Grant-Dennison, Mario Sanchez, Matthew Veach, Quoc Nguyen, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Ahmed Jameel, Dante Torres, David Neal Gravatt, Devin Moreno, Kevin Curtis, Kolawole Ayeni, Mario Sanchez, Matthew D'Ambrosio, Matthew Veach, Paul Serres, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200000228 | N/A | Planning/Design/Staging | 45% | 76.84% | 416.78 | 131.53 | 41756 | 33490 | 31.56% | 41756 | 35 | 320.25 | 2100 | 0 |  | 33490 |  | 74782.78 | 70073.6 | 36583.6 | 52.21%
05/14/25 |  | 07/11/25 | Open | Walter Clay Knight | Jeremy Hoffpauir |  | Camille Elizabeth Taber, Jeremy Hoffpauir, Walter Clay Knight |  |  | Jesus Escobedo, Walter Clay Knight |  |  | Camille Taber | FL | Leon County Schools | 200002968 | N/A | Implementation/Deployment | 55% | 32.89% | 45.6 | 30.6 | 0 | 1922.5 | 67.11% | 0 | 0 | 15 | 0 | 0 |  | 1922.5 |  | 0 | 9280.76 | 7358.26 | 79.29%
01/28/25 |  | 07/14/25 | Open | Robert McIver | Bryan Brown, Christopher Ceykovsky, Edward Padron |  | Christopher Ceykovsky, Christopher Garcia, Daniel Saenz, Edward Padron, Rene Trejo, Robert McIver, Ruben Cantu |  |  | Carlos Carrillo, Jaime Galvan, Kolawole Ayeni, Rene Trejo, Robert McIver, Roger Guerra, Ruben Cantu |  |  | Daniel Saenz | TX-SOUT | City of Edinburg | 200001717 | N/A | Implementation/Deployment | 65% | 59.18% | 104.35 | 46.1 | 10026.95 | 6595 | 44.18% | 10026.95 | 3.5 | 61.75 | 340 | 0 |  | 6595 |  | 64054.96 | 13061.83 | 6466.83 | 49.51%
04/14/25 |  | 07/14/25 | Open | Robert McIver | Bryan Brown, Remi Martinez-Montenegro |  | Amy Martinez-Nagy, Bryan Brown, Christopher Garcia, Daniel Saenz, Remi Martinez-Montenegro, Robert McIver |  |  | N/A |  |  | Daniel Saenz | TX-SOUT | LAREDO ISD | 200002589 | N/A | On HOLD | 5% | 0% | 62.19 | 62.19 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27290.95 | 7917.6 | 7917.6 | 100%
07/29/24 |  | 07/15/25 | Closed | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Julio C Montoya, Khalid Abunaja, Mark J Chambliss, Meredith A Richardson, Nathan Dao |  |  | Ali Al-Haddad, Andrew Comeaux, Andy Pham, Anthony Balogun, Baq Alsaedi, Bryant Bush, David Lenihan, Devon LeMoine, Gerardo Ramirez, Gregory Posey, Hector Rivera, Jaime Flores, James Adams, Jarshawn Newsome, Jennifer Mares, Jesus Gonzalez, Jesus Guadian, Jim Blackwell, Jose R. Duarte, Josue Iglesias, Julio C Montoya, Justin Cornish, Justin Smallwood, Kai Rose , Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Natha |  |  | N/A | N/A | Houston ISD | J00018733 | HISD CTE CCNA lab project | Training/Knowledge Transfer/Documentation | 95% | 0% | 0 | -1455.25 | 2715 | 118850 | 0% | 2715 | 145.25 | 1600.5 | 60170 | 0 |  | 118850 |  | 1065895.82 | 50400 | -68450 | -135.8%
05/13/24 |  | 07/15/25 | Open | Marco Lish | Ahmed Al-Zubaidi, Wyley Johnson |  | Abdulrahman Farhan, Ahmed Al-Zubaidi, Dhulfiqar Al Hashimi, Larry Noble, Marco Lish, Neel Shah, Wyley Johnson |  |  | Dhulfiqar Al Hashimi, Eric Firestone, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00018297 | HPD - VPN Migration and MFA Implementation | Training/Knowledge Transfer/Documentation | 85% | 75.2% | 276.25 | 68.5 | 40056.25 | 29812.5 | 24.8% | 40056.25 | 0 | 207.75 | 21181.25 | 0 |  | 29812.5 |  | 0 | 67594.8 | 37782.3 | 55.9%
02/13/23 |  | 07/15/25 | Open | Marco Lish | Ahmed Al-Zubaidi, Pradeep Tyagi , Wyley Johnson |  | Christine A Hupe, Jason Espino, Jorge Ortiz Cardozo, Larry Noble, Marco Lish, Neel Shah |  |  | Jason Espino, Jorge Ortiz Cardozo, Justin Higgins, Lauren Lanzini Coffey, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Police Dept | J00014851 | HPD Azure VPN | On HOLD | 60% | 36.34% | 231.15 | 147.15 | 32043.75 | 10960 | 63.66% | 32043.75 | 0 | 84 | 10960 | 0 |  | 10960 |  | 0 | 45951.6 | 34991.6 | 76.15%
11/25/24 |  | 07/15/25 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Conner MacDonnell, Daniel Saenz, Edward Padron, Felix Martinez, Francisco Hernandez, Jaime Galvan, Jesse Gonzalez, Jonathan Pina, Jorge Robert Rangel, Mario Sanchez, Robert McIver, Taylor Poole |  |  | Carlos Carrillo, Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Mario Sanchez, Robert McIver, Roger Guerra, Trevor Galloso |  |  | Daniel Saenz | TX-SOUT | Los Fresnos CISD | 200000169 | N/A | Implementation/Deployment | 70% | 119.4% | 387.63 | 22.88 | 32662.25 | 34280 | 5.903% | 32662.25 | 98 | 462.75 | 6010 | 0 |  | 34280 |  | 651712.34 | 54856.2 | 20576.2 | 37.51%
02/10/25 |  | 07/18/25 | Open | Brittney Antoinette Hickman | William Birdsong |  | Brittney Antoinette Hickman, Erick Sanchez, Kristy L Dice, Matthew Veach, William Birdsong |  |  | Brittney Antoinette Hickman, Matthew Veach |  |  | Kristy L Dice | TX-DAL | Irving ISD | 200001843 | N/A | Planning/Design/Staging | 25% | 13.88% | 135.11 | 116.36 | 13442.9 | 2343.75 | 86.12% | 13442.9 | 0 | 18.75 | 0 | 0 |  | 2343.75 |  | 63592.55 | 21172.4 | 18828.65 | 88.93%
02/10/25 |  | 07/18/25 | Open | Brittney Antoinette Hickman | William Birdsong |  | Brittney Antoinette Hickman, Erick Sanchez, Kristy L Dice, Matthew Veach, William Birdsong |  |  | Brittney Antoinette Hickman, Carlo Enriquez, Conner MacDonnell, Frank Jaimes, Jalen Vecchitto, Matthew Veach, Quy Le |  |  | Kristy L Dice | TX-DAL | Irving ISD | 200001848 | N/A | Planning/Design/Staging | 75% | 36.54% | 136.16 | 87.41 | 13519.55 | 5081.25 | 64.2% | 13519.55 | 1 | 49.75 | 60 | 0 |  | 5081.25 |  | 66473.19 | 21292.8 | 16211.55 | 76.14%
05/08/25 |  | 07/18/25 | Open | Christina Rice | Jacob Parks, Jeffrey Holman |  | Arcangelo Fanelli, Christina Rice, Christina Rice, Jacob Parks, Jeffrey Holman |  |  | Christina Rice |  |  | Arcangelo Fanelli | TX-DAL | Cook Children's Health Care System | 200002400 | N/A | Implementation/Deployment | 45% | 22.73% | 11 | 8.5 | 0 | 312.5 | 77.27% | 0 | 0 | 2.5 | 0 | 0 |  | 312.5 |  | 0 | 30014.8 | 29702.3 | 98.96%
10/01/24 |  | 07/18/25 | Open | Jason Matthew Davis | Kristian Martell |  | Cory E Hopf, Cory Hopf, Jason Matthew Davis, Kristian Martell, Larry Noble, Michael B Griffin, Neel Shah |  |  | Jason Matthew Davis, Kristian Martell, Patrick Joseph Palermo, Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00019090 | UW Health Hospitals & Clinics Queue Redesign | Planning/Design/Staging | 95% | 154.3% | 35 | -19 | 6195 | 9837.5 | -54.29% | 6195 | 0 | 54 | 600 | 0 |  | 9837.5 |  | 0 | 7700 | -2137.5 | -27.76%
02/07/25 |  | 07/18/25 | Open | Jennifer Soliz | Christopher Puyear |  | Christopher Puyear, Hannah Paul, Jennifer Soliz, Lori Endsley, Patrick Joseph Palermo |  |  | Jennifer Soliz, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Patrick Joseph Palermo, Paul Serres |  |  | Hannah Edmunds | TX-CEN | Texas Real Estate Commission | 200001812 | N/A | Implementation/Deployment | 55% | 60.94% | 80 | 31.25 | 0 | 8190 | 39.06% | 0 | 0 | 48.75 | 0 | 0 |  | 8190 |  | 55125.52 | 16578 | 8388 | 50.6%
08/03/22 |  | 07/18/25 | Open | Joanna Herrera | Edward Padron |  | Amy Martinez-Nagy, Christopher Prado, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Joanna Herrera |  |  | Antonio Rivera, Carlos Carrillo, Christopher Prado, Felix Martinez, Francisco Hernandez, Jesus Angel Cantu, Jesus Cantu, Joanna Herrera, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Rene Trejo, Richard Colby, Roger Guerra, William Brown |  |  | Eric Rodriguez | TX-SOUT | Mission CISD | J00012224 | ERATE - District Upgrade | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -605.61 | 0 | 43802.65 | 0% | 0 | 17.66 | 623.27 | 42879.45 | 955.17 |  | 43802.65 |  | 127494.8 | 200613.3 | 155855.48 | 77.69%
08/03/22 |  | 07/18/25 | Open | Joanna Herrera | Edward Padron |  | Amy Martinez-Nagy, Christopher Prado, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Joanna Herrera |  |  | Antonio Rivera, Carlos Carrillo, Christopher Prado, Felix Martinez, Francisco Hernandez, Jesus Angel Cantu, Jesus Cantu, Joanna Herrera, Joaquin Garcia, Jorge Robert Rangel, Jose Salazar, Rene Trejo, Richard Colby, Roger Guerra, William Brown |  |  | N/A | N/A | Mission CISD | J00012224 | ERATE - District Upgrade | Training/Knowledge Transfer/Documentation | 100% | 0.1401% | 356.78 | 356.28 | 25766.5 | 62.5 | 99.86% | 25766.5 | 0 | 0.5 | 0 | 955.17 |  | 62.5 |  | 127494.8 | 200613.3 | 199595.63 | 99.49%
02/10/25 |  | 07/18/25 | Open | Joaquin Marroquin | Bryan Brown |  | Bryan Brown, Christopher Garcia, Conner MacDonnell, Felix Martinez, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Laura Herrera, Michelle Bailey, Ming Chiu, Taylor Poole, Trevor Galloso, Xavier A Trevino |  |  | Carlos Carrillo, Christian Pena, Felix Martinez, Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Ming Chiu, Oscar Garcia, Roger Guerra, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Point Isabel ISD | 200001888 | N/A | Implementation/Deployment | 95% | 129.5% | 316.56 | -12.69 | 29207.5 | 27177.5 | -4.009% | 29207.5 | 80.75 | 410 | 4845 | 0 |  | 27177.5 |  | 78782.03 | 65962.85 | 38785.35 | 58.8%
02/10/25 |  | 07/18/25 | Open | Joaquin Marroquin | Bryan Brown |  | Bryan Brown, Christopher Garcia, Conner MacDonnell, Joaquin Marroquin, Laura Herrera, Michelle Bailey, Ming Chiu, Remi Martinez-Montenegro, Robert McIver, Xavier A Trevino |  |  | Carlos Carrillo, Christian Pena, Erick Nunez , Felix Martinez, Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Ming Chiu, Oscar Garcia, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Point Isabel ISD | 200001889 | N/A | Implementation/Deployment | 95% | 129.9% | 267.69 | -4.81 | 25291.75 | 23152.5 | -1.797% | 25291.75 | 75.25 | 347.75 | 4515 | 0 |  | 23152.5 |  | 64218.07 | 55254.74 | 32102.24 | 58.1%
03/11/25 |  | 07/18/25 | Open | Joaquin Marroquin | Edward Padron |  | Edward Padron, Erick Nunez , Joaquin Marroquin, Xavier A Trevino |  |  | Carlos Carrillo, Christian Pena, Erick Nunez , Felix Martinez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Point Isabel ISD | 200002384 | N/A | Implementation/Deployment | 75% | 141% | 39.72 | -11.28 | 0 | 4432.5 | -28.4% | 0 | 5 | 56 | 300 | 0 |  | 4432.5 |  | 53309.38 | 4839.6 | 407.1 | 8.412%
03/18/25 |  | 07/18/25 | Open | Joaquin Marroquin | Bryan Brown |  | Bryan Brown, Christopher Garcia, Conner MacDonnell, Joaquin Marroquin, Laura Herrera, Michelle Bailey, Ming Chiu, Xavier A Trevino |  |  | Carlos Carrillo, Christian Pena, Felix Martinez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Ming Chiu, Oscar Garcia, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Point Isabel ISD | 200002432 | N/A | Implementation/Deployment | 95% | 91.98% | 249.25 | 62.25 | 0 | 15335 | 24.97% | 0 | 42.25 | 229.25 | 2535 | 0 |  | 15335 |  | 64618.06 | 53368.43 | 38033.43 | 71.27%
12/09/24 |  | 07/18/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, John Stephen Kurkjian, LaQisha Marshall |  |  | Alexander Chambless, Grayson McClanahan, Jeffrey Charles Primeaux, John Stephen Kurkjian, Kolawole Ayeni, LaQisha Marshall, Robert Jones |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200000251 | N/A | Training/Knowledge Transfer/Documentation | 100% | 105.6% | 64.15 | -1.6 | 5145.35 | 5456.25 | -2.494% | 5145.35 | 2 | 67.75 | 120 | 0 |  | 5456.25 |  | 47617.2 | 7810.4 | 2354.15 | 30.14%
03/17/25 |  | 07/18/25 | Open | Marco Lish | Bryan Brown |  | Bryan Brown, Christopher Garcia, Marco Lish, Neel Shah, Richard Keith Arnst |  |  | Clinton Bennett Deason, Craig St. Rose, Hector Rivera, Jeremiah Solomon, Joel Hubbard, Justin Cornish, Marco Lish, Rene Trejo, Richard Keith Arnst, Robert Lavender |  |  | Neel Shah | TX-HOU | City of Houston Public Works | 200002422 | N/A | Training/Knowledge Transfer/Documentation | 85% | 89.04% | 915.31 | 212.31 | 0 | 82980 | 23.2% | 0 | 112 | 815 | 11545 | 0 |  | 82980 |  | 338934.53 | 182813.2 | 99833.2 | 54.61%
04/25/25 |  | 07/18/25 | Open | Marco Lish | N/A |  | Jonathan Pendrich, Majid Shirzadeh, Marco Lish |  |  | Jorge Ortiz Cardozo, Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Coblentz Patch Duffy & Bass LLP | 200002894 | N/A | Planning/Design/Staging | 45% | 13.12% | 40 | 34.75 | 0 | 656.25 | 86.88% | 0 | 0 | 5.25 | 0 | 0 |  | 656.25 |  | 0 | 8648.8 | 7992.55 | 92.41%
11/08/22 |  | 07/18/25 | Open | Marco Lish | Michael Brett Beggs |  | Jeff Barker, Jonathan Pendrich, Marco Lish, Michael Brett Beggs |  |  | Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | J00014358 | Staff Aug Backlog | Training/Knowledge Transfer/Documentation | 100% | 573.1% | 52 | -246 | 6500 | 37250 | -473.1% | 6500 | 0 | 298 | 37250 | 0 |  | 37250 |  | 750440.34 | 0 | -37250 | 0%
03/18/25 |  | 07/18/25 | Open | Richard Keith Arnst | Steven Walker |  | Daniel Saenz, Eric Rodriguez, Richard Keith Arnst, Steven Walker |  |  | Christopher Brown, Richard Keith Arnst |  |  | Daniel Saenz | TX-SOUT | Great Hearts Texas | 200002434 | N/A | Planning/Design/Staging | 75% | 116.6% | 43.75 | -7.25 | 0 | 6770 | -16.57% | 0 | 0 | 51 | 0 | 0 |  | 6770 |  | 473 | 7187.84 | 417.84 | 5.813%
06/02/25 |  | 07/18/25 | Open | Richard Keith Arnst | William Birdsong |  | Bryan Brown, Christopher Garcia, Joel Hubbard, Mark Forehand, Richard Keith Arnst, Robert Lavender |  |  | Richard Keith Arnst |  |  | Mark Forehand | TX-DAL | Hilltop Holdings Inc | 200003035 | N/A | Planning/Design/Staging | 20% | 35.75% | 11.19 | 7.19 | 0 | 500 | 64.25% | 0 | 0 | 4 | 0 | 0 |  | 500 |  | 145502.2 | 1370.52 | 870.52 | 63.52%
02/25/25 |  | 07/18/25 | Open | Richard Keith Arnst | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joel Hubbard, Lauren J Kennewell, Remi Martinez-Montenegro, Richard Keith Arnst, Robert Lavender |  |  | Frank Jaimes, Joel Hubbard, Joshua Hubbard, Richard Keith Arnst, Robert Lavender |  |  | Lauren J Kennewell | TX-DAL | Methodist Health System | 200002132 | N/A | Implementation/Deployment | 80% | 147.7% | 28.44 | -8.81 | 0 | 3833.75 | -30.98% | 0 | 4.75 | 42 | 300 | 0 |  | 3833.75 |  | 26180.75 | 4684.6 | 850.85 | 18.16%
12/04/24 |  | 07/18/25 | Open | Robert McIver | Edward Padron |  | Christopher Prado, Edward Padron, Robert McIver, Xavier A Trevino |  |  | An Le, Briliance Johnson, Carlo Enriquez, Christopher Prado, Kendall Walls, Quy Le, Robert McIver, Yonathan Fadel |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200000221 | N/A | Implementation/Deployment | 70% | 61.63% | 142.79 | 75.79 | 13918.55 | 6877.5 | 53.08% | 13918.55 | 21 | 88 | 1260 | 0 |  | 6877.5 |  | 150247.78 | 24243.18 | 17365.68 | 71.63%
01/28/25 |  | 07/18/25 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Carlos Carrillo, Conner MacDonnell, Edward Padron, Erick Nunez , Felix Martinez, Jaime Galvan, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Michelle Bailey, Oscar Garcia, Robert McIver, Roger Guerra, Taylor Poole, Xavier A Trevino |  |  | Carlos Carrillo, Erick Nunez , Francisco Hernandez, Jaime Galvan, James Danner, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Oscar Garcia, Robert McIver, Roger Guerra |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200001689 | N/A | Implementation/Deployment | 65% | 53.66% | 1216.38 | 593.63 | 0 | 51092.5 | 48.8% | 0 | 30 | 652.75 | 1800 | 0 |  | 51092.5 |  | 1934474.32 | 133362.88 | 82270.38 | 61.69%
05/03/24 |  | 07/18/25 | Open | Robert McIver | Edward Padron, Rogelio Dominguez |  | Christopher Prado, Edward Padron, Erick Nunez , Michelle Bailey, Robert McIver, Rogelio Dominguez, Xavier A Trevino |  |  | Alexander Chambless, An Le, Angel Alicea, Angel Alicea-Torres, Briliance Johnson, Celso Lopez, Christopher Prado, Devon LeMoine, Eric Straeter, Erick Nunez , Grayson Rigsby, Harley Garcia, Isaiah Rosales, James Adams, James Danner, Jesus Gonzalez, John Senkulics, Jose R. Duarte, Julio C Montoya, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Michael Torres, Oscar Gonzalez, Paul Serres, Robert McIver, Steven Shipmon, Wilangel Francis |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018032 | Austin, Houston & San Antonio Campus Installations | Training/Knowledge Transfer/Documentation | 95% | 144.4% | 427.75 | -180.5 | 7032.84 | 50677.6 | -42.2% | 7032.84 | 9.46 | 617.71 | 27312.5 | 0 |  | 50677.6 |  | 829113.21 | 44892.14 | -5785.46 | -12.89%
03/12/25 |  | 07/18/25 | Open | Robert McIver | Edward Padron |  | Daniel Saenz, Edward Padron, Robert McIver, Ruben Cantu |  |  | N/A |  |  | Daniel Saenz | TX-SOUT | Rio Grande City Grulla ISD | 200000171 | N/A | Planning/Design/Staging | 30% | 0% | 47.5 | 47.5 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 15214.59 | 175133.92 | 175133.92 | 100%
10/28/24 |  | 07/18/25 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Daniel Saenz, Diana Berger, Edward Padron, Erick Nunez , Felix Martinez, Robert McIver |  |  | Carlos Carrillo, Erick Nunez , Francisco Hernandez, Jaime Galvan, Joanna Herrera, Joaquin Garcia, Jonathan Pina, Oscar Garcia, Robert McIver, Roger Guerra, Trevor Galloso |  |  | Eric Rodriguez | TX-SOUT | Vanguard Academy | J00019329 | Category 2 Network Upgrades SW_AP | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -1 | 0 | 125 | 0% | 0 | 0 | 1 | 125 | 0 |  | 125 |  | 162603.39 | 69372.38 | 69247.38 | 99.82%
10/28/24 |  | 07/18/25 | Open | Robert McIver | Edward Padron |  | Amy Martinez-Nagy, Daniel Saenz, Diana Berger, Edward Padron, Erick Nunez , Felix Martinez, Robert McIver |  |  | Carlos Carrillo, Erick Nunez , Francisco Hernandez, Jaime Galvan, Joanna Herrera, Joaquin Garcia, Jonathan Pina, Oscar Garcia, Robert McIver, Roger Guerra, Trevor Galloso |  |  | N/A | N/A | Vanguard Academy | J00019329 | Category 2 Network Upgrades SW_AP | Training/Knowledge Transfer/Documentation | 85% | 114.6% | 162.32 | -17.93 | 15172.88 | 16035 | -11.05% | 15172.88 | 5.75 | 186 | 345 | 0 |  | 16035 |  | 162603.39 | 69372.38 | 53337.38 | 76.89%
01/20/25 |  | 07/18/25 | Open | Ryan Scott | David Watkins |  | Christopher Prado, David Watkins, Mario Sanchez, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Christopher Prado, Mario Sanchez, Ryan Scott |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200001670 | N/A | Training/Knowledge Transfer/Documentation | 90% | 69.67% | 135.63 | 41.13 | 17496.25 | 11847.5 | 30.33% | 17496.25 | 0 | 94.5 | 0 | 0 |  | 11847.5 |  | 0 | 28882.68 | 17035.18 | 58.98%
04/22/25 |  | 07/18/25 | Open | Summer Abunaja | Jeremy Williams |  | Garrett Curran, Jeremy Williams, Summer Abunaja |  |  | Juan Saenz, Summer Abunaja |  |  | Garrett Curran | CA-LAX | Santa Ana Unified School District | 200002778 | N/A | On HOLD | 15% | 2.775% | 144.12 | 140.12 | 0 | 435 | 97.22% | 0 | 0 | 4 | 0 | 0 |  | 435 |  | 0 | 33348 | 32913 | 98.7%
04/16/25 |  | 07/21/25 | Open | Brian Willery | Bryan Geoghan |  | Brian Willery, Bryan Geoghan, Lauren J Kennewell |  |  | Brian Willery, Frank Jaimes, Joshua Osgood |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | 200002691 | N/A | Not started | 0% | 50.39% | 19.35 | 9.6 | 0 | 1023.75 | 49.61% | 0 | 0 | 9.75 | 0 | 0 |  | 1023.75 |  | 7906.62 | 2224.4 | 1200.65 | 53.98%
06/17/24 |  | 07/21/25 | Open | Walter Clay Knight | Christopher Puyear |  | Christopher Puyear, Hannah Paul, James O Sykes, John Stephen Kurkjian |  |  | John Stephen Kurkjian, Walter Clay Knight |  |  | Hannah Edmunds | TX-CEN | Texas Parks and Wildlife | J00018518 | UC Upgrade - Nuance 1-Year Option | Implementation/Deployment | 65% | 102.6% | 229.95 | -6.05 | 32831.75 | 32687.5 | -2.631% | 32831.75 | 0 | 236 | 7207.5 | 0 |  | 32687.5 |  | 33651 | 46383.2 | 13695.7 | 29.53%
07/15/24 |  | 07/21/25 | Open | Walter Clay Knight | Christopher Puyear |  | Christopher Puyear, Hannah Paul, James O Sykes |  |  | John Stephen Kurkjian, Patrick Joseph Palermo, Thomas Francis LoMonaco, Walter Clay Knight |  |  | Hannah Edmunds | TX-CEN | Texas Parks and Wildlife | J00018664 | Webex Contact Center Chatbot Implementation | Implementation/Deployment | 55% | 67.86% | 140 | 45 | 19740 | 15370 | 32.14% | 19740 | 0 | 95 | 3060 | 0 |  | 15370 |  | 2791.36 | 26944.8 | 11574.8 | 42.96%
04/01/25 |  | 07/22/25 | Open | Marco Lish | William Birdsong |  | Karen Grant-Dennison, Marco Lish, Vitalii Stepanchenko, William Birdsong, William Davenport |  |  | Carlo Enriquez, Jayden Colon, Juan Pomares, Kendall Walls, Marco Lish, Vitalii Stepanchenko, Yonathan Fadel |  |  | William Davenport | TX-DAL | Prosper ISD | 200001643 | N/A | Implementation/Deployment | 70% | 68.05% | 139.6 | 45.6 | 13570.8 | 9177.5 | 32.66% | 13570.8 | 1 | 95 | 60 | 0 |  | 9177.5 |  | 112560.08 | 19948.8 | 10771.3 | 53.99%
07/25/24 |  | 07/22/25 | Open | Walter Clay Knight | George Delp |  | George Delp, Rafael Rodriguez-Vargas, William Isaac Sears |  |  | Rafael Rodriguez-Vargas, Walter Clay Knight |  |  | Anthony Hildebrand | US-SP | Navajo County, AZ | J00018716 | Navajo County Greenfield Fiber | Implementation/Deployment | 50% | 16.65% | 268.75 | 224 | 33046.25 | 5683.75 | 83.35% | 33046.25 | 0 | 44.75 | 4153.75 | 0 |  | 5683.75 |  | 299771.62 | 49570.8 | 43887.05 | 88.53%
03/24/25 |  | 07/23/25 | Open | Joaquin Marroquin | Mark J Chambliss |  | Anthony Towsley, Joaquin Marroquin, Lonnie Owens, Mark J Chambliss |  |  | Anthony Towsley, Joaquin Marroquin, Michael Torres |  |  | Lonnie Owens | TX-CEN | Boerne ISD | 200002484 | N/A | Planning/Design/Staging | 5% | 4.368% | 457.9 | 437.9 | 0 | 2645 | 95.63% | 0 | 0 | 20 | 0 | 0 |  | 2645 |  | 156645.94 | 69001.6 | 66356.6 | 96.17%
07/25/23 |  | 07/24/25 | Closed | Summer Abunaja | Todd Melby |  | Grant Jacobs, Liberty Reyes Tumibay, Summer Abunaja, Todd Melby, Yong Kim |  |  | Liberty Reyes Tumibay, Todd Melby |  |  | Grant Jacobs | CA-LAX | Fresno Unified School District | J00016169 | Consulting T&E for Private LTE | Closed | 0% | 0% | 0 | -16 | 0 | 2160 | 0% | 0 | 0 | 16 | 2160 | 0 |  | 2160 |  | 0 | 360 | -1800 | -500%
07/25/23 |  | 07/24/25 | Closed | Summer Abunaja | Todd Melby |  | Grant Jacobs, Liberty Reyes Tumibay, Summer Abunaja, Todd Melby, Yong Kim |  |  | Liberty Reyes Tumibay, Todd Melby |  |  | N/A | N/A | Fresno Unified School District | J00016169 | Consulting T&E for Private LTE | Closed | 100% | 0% | 1.25 | 1.25 | 166.25 | 0 | 100% | 166.25 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 360 | 360 | 100%
02/17/25 |  | 07/24/25 | Open | Tray Giddens | Chad Hart |  | Chad Hart, Dustin Huffman, Tray Giddens |  |  | Abdalsattar Albaghdadi, Ahmed Jameel, Craig St. Rose, Justin Cornish, Kevin Curtis, Kord Mullins, Matthew D'Ambrosio, Paul Serres, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200001988 | N/A | Closed | 100% | 81.52% | 64.71 | 15.96 | 0 | 5505 | 24.66% | 0 | 4 | 52.75 | 305 | 0 |  | 5505 |  | 58214.2 | 10309.6 | 4804.6 | 46.6%
12/20/24 |  | 07/25/25 | Open | Brian Willery | George Delp, Jeremy Hoffpauir |  | Brian Willery, George Delp, Jeremy Hoffpauir |  |  | Brian Willery |  |  | N/A | N/A | Hayneville Telephone Company | 200000884 | N/A | Implementation/Deployment | 40% | 115.9% | 11 | -1.75 | 1375 | 1593.75 | -15.91% | 1375 | 0 | 12.75 | 0 | 0 |  | 1593.75 |  | 698360.99 | 76563.5 | 74969.75 | 97.92%
03/01/23 |  | 07/25/25 | Open | Jason Esry | Joshua Adam Engle, Majid Shirzadeh |  | Alexander Gutman, Austen New LN: Howard Cockerham, Beau C. Devillier, Conner MacDonnell, Devin Moreno, Dylan Pittsinger, Jason Esry, Jeffery Giles, Jhon Genao, Joshua Adam Engle, Joshua Osgood, Juan Pomares, Justin Thompson, Kairo Sauceda, Kirk O'Guinn, Magdalena Rodriguez, Majid Shirzadeh, Mohammad Jilani, Moises Rodriguez, Nazario Armenta Barraza, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Prince Owusu, Quoc Nguyen, Sean Cowhey, Shawn Sutton, Tavis Jackson, Timothy M |  |  | Austen Howard, Bradley Buchanan, Carlo Enriquez, Chase Davis, Conner MacDonnell, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelino, Dylan Pittsinger, Frank Jaimes, Jalen Vecchitto, Jason Esry, Jeffery Giles, Jhon Genao, Joel Hubbard, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Mitchell, Justin Thompson, Kanoa Parman, Karyn Hubbard, Kebret Eshetu, Kirk O'Guinn, Luis Hernandez, Moises Rodriguez, Nazario Armenta Barraza, Noah Trump, Pablo Bernal, Patrick Shea Thompson, Patrick Th |  |  | N/A | N/A | Dallas ISD | J00015072 | Dallas ISD Switch, UPS, Wireless Install | Implementation/Deployment | 85% | 63.43% | 632.6 | 257.1 | 53679.6 | 29782.5 | 40.64% | 53679.6 | 25.75 | 401.25 | 2290 | 1400.11 |  | 29782.5 |  | 2735418.96 | 168611 | 137428.39 | 81.51%
03/01/23 |  | 07/25/25 | Open | Jason Esry | Joshua Adam Engle, Majid Shirzadeh |  | Alexander Gutman, Austen New LN: Howard Cockerham, Beau C. Devillier, Conner MacDonnell, Devin Moreno, Dylan Pittsinger, Jason Esry, Jeffery Giles, Jhon Genao, Joshua Adam Engle, Joshua Osgood, Juan Pomares, Justin Thompson, Kairo Sauceda, Kirk O'Guinn, Magdalena Rodriguez, Majid Shirzadeh, Mohammad Jilani, Moises Rodriguez, Nazario Armenta Barraza, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Prince Owusu, Quoc Nguyen, Sean Cowhey, Shawn Sutton, Tavis Jackson, Timothy M |  |  | Austen Howard, Bradley Buchanan, Carlo Enriquez, Chase Davis, Conner MacDonnell, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelino, Dylan Pittsinger, Frank Jaimes, Jalen Vecchitto, Jason Esry, Jeffery Giles, Jhon Genao, Joel Hubbard, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Mitchell, Justin Thompson, Kanoa Parman, Karyn Hubbard, Kebret Eshetu, Kirk O'Guinn, Luis Hernandez, Moises Rodriguez, Nazario Armenta Barraza, Noah Trump, Pablo Bernal, Patrick Shea Thompson, Patrick Th |  |  | Shawn Sutton | TX-DAL | Dallas ISD | J00015072 | Dallas ISD Switch, UPS, Wireless Install | Implementation/Deployment | 0% | 0% | 0 | -1111.28 | 0 | 105527.3 | 0% | 0 | 41 | 1152.28 | 102104.8 | 1400.11 |  | 105527.3 |  | 2735418.96 | 168611 | 61683.59 | 36.58%
03/14/25 |  | 07/25/25 | Open | Jason Esry | David Goss |  | David D Tijerina, David Goss, Jason Esry |  |  | Cory Bradfield, Jason Esry |  |  | David D Tijerina | TX-CEN | Leander ISD | 200002407 | N/A | Planning/Design/Staging | 25% | 18.76% | 130.63 | 106.13 | 0 | 3172.5 | 81.24% | 0 | 0 | 24.5 | 0 | 0 |  | 3172.5 |  | 547590.15 | 29141.2 | 25968.7 | 89.11%
02/26/24 |  | 07/25/25 | Open | Jason Esry | David Escamilla, Michael Brett Beggs |  | Cory Bradfield, Cory Bradfield, David D Tijerina, David Escamilla, Jason Esry, Larry Noble, Michael Brett Beggs, Ron Loge |  |  | Cory Bradfield, Jason Esry, Ron Loge |  |  | David D Tijerina | TX-CEN | University of Texas - Austin | J00017214 | UT Austin VXRail Apex DC Refresh | Implementation/Deployment | 65% | 32.75% | 474.88 | 327.38 | 65336.87 | 23597.5 | 68.94% | 65336.87 | 8 | 155.5 | 15172.5 | 0 |  | 23597.5 |  | 2059242.16 | 110000 | 86402.5 | 78.55%
05/06/25 |  | 07/25/25 | Open | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Joanna Herrera, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002948 | N/A | Planning/Design/Staging | 10% | 60% | 5 | 2 | 0 | 375 | 40% | 0 | 0 | 3 | 0 | 0 |  | 375 |  | 3703.5 | 780 | 405 | 51.92%
06/12/24 |  | 07/25/25 | Open | Joaquin Marroquin | Edward Padron |  | Conner MacDonnell, Diana Berger, Edward Padron, Eric Rodriguez, Erick Nunez , Felix Martinez, Joaquin Garcia, Joaquin Marroquin, Taylor Poole |  |  | Carlos Carrillo, Erick Nunez , Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Oscar Garcia, Roger Guerra |  |  | Eric Rodriguez | TX-SOUT | La Feria ISD | J00018421 | E-Rate Year 26 Switches & UPS | Implementation/Deployment | 0% | 0% | 0 | -37 | 0 | 4625 | 0% | 0 | 0 | 37 | 4625 | 0 |  | 4625 |  | 0 | 0 | -4625 | 0%
06/12/24 |  | 07/25/25 | Open | Joaquin Marroquin | Edward Padron |  | Conner MacDonnell, Diana Berger, Edward Padron, Eric Rodriguez, Erick Nunez , Felix Martinez, Joaquin Garcia, Joaquin Marroquin, Taylor Poole |  |  | Carlos Carrillo, Erick Nunez , Francisco Hernandez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Oscar Garcia, Roger Guerra |  |  | N/A | N/A | La Feria ISD | J00018421 | E-Rate Year 26 Switches & UPS | Implementation/Deployment | 60% | 126.9% | 149.77 | -12.23 | 12715.44 | 13155 | -8.166% | 12715.44 | 28 | 190 | 1680 | 0 |  | 13155 |  | 0 | 0 | -13155 | 0%
02/20/25 |  | 07/25/25 | Open | Joaquin Marroquin | Bryan Brown |  | Brian Newman, Brian Newman, Christopher Garcia, David D Tijerina, Joaquin Marroquin, Joel Hubbard |  |  | Brian Newman, Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | 200002126 | N/A | Planning/Design/Staging | 5% | 35.47% | 50.75 | 32.75 | 0 | 2295 | 64.53% | 0 | 0 | 18 | 0 | 0 |  | 2295 |  | 48944.11 | 25961.89 | 23666.89 | 91.16%
10/31/22 |  | 07/25/25 | Open | LaQisha Marshall | Chad Hart |  | Ahmed Jameel, Chad Hart, Daniel Hernandez, Daniel R Hernandez, David Monasmith, David Monasmith, Jaime B Flores, Jaime Flores, Justin Cornish, Kord Mullins, LaQisha Marshall, Larry Noble, Lauren Lanzini Coffey, Miguel Reed, Mohammad Jilani, Mohaymen Sodi, Robert Jones, Sajjad Abo Dbs, Taylor Poole |  |  | Aaron Johns, Abdalsattar Albaghdadi, Adam Felix, Ahmed Jameel, Albert Bernal, Aleksei Lavrushenkov, Alexander Chambless, Andy Alvarenga, Andy Pham, Anthony Lange, Arius Deautrè Yarborough, Austen Howard, Briliance Johnson, Bryant Bush, Charles Knox, Daniel Hernandez, Dante Torres, David Dobbs, Devin Moreno, Devon LeMoine, Ethan Monasmith, Ethan Thomas George, Grayson McClanahan, Grayson Rigsby, Hector Rivera, Isaiah Covington, Jaime Flores, James Adams, Jeffrey Charles Primeaux, Jerald Garner, J |  |  | David Monasmith | TX-HOU | Texas A&M University | J00014198 | Zones 1-12 - Campus Switch Refresh | Training/Knowledge Transfer/Documentation | 95% | 31.83% | 27365.39 | 20050.24 | 2437087.14 | 658088 | 73.27% | 2437087.14 | 1394.5 | 8709.65 | 499841.75 | 52543.365 |  | 658088 |  | 8436696.7 | 1376000 | 665368.635 | 48.36%
01/30/23 |  | 07/25/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Christopher Ceykovsky, Khalid Abunaja, Lauren Lanzini Coffey, Ming Chiu, Neel Shah, Shiraz Humayun |  |  | Christopher Ceykovsky, Lauren Lanzini Coffey, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00014769 | Voice Architect consultant | Planning/Design/Staging | 75% | 90.58% | 300 | 28.25 | 41250 | 37703.75 | 9.417% | 41250 | 0 | 271.75 | 32103.75 | 1448.73 |  | 37703.75 |  | 0 | 66937.2 | 27784.72 | 41.51%
02/19/25 |  | 07/25/25 | Open | Richard Keith Arnst | Bryan Brown |  | Arcangelo Fanelli, Bryan Brown, Christopher Garcia, Richard Keith Arnst |  |  | Joel Hubbard, Rene Trejo, Richard Keith Arnst, Robert Lavender |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | 200002105 | N/A | Implementation/Deployment | 80% | 83.44% | 72.81 | 18.06 | 0 | 6773.75 | 24.8% | 0 | 6 | 60.75 | 450 | 0 |  | 6773.75 |  | 29348.45 | 17866.4 | 11092.65 | 62.09%
11/07/22 |  | 07/25/25 | Open | Richard Keith Arnst | David Escamilla |  | Alexander Gutman, Beau C. Devillier, Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge, Shawn Sutton |  |  | Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge |  |  | Shawn Sutton | TX-DAL | City of Dallas | J00014229 | AWS - DRaaS Implementation | Implementation/Deployment | 75% | 55.88% | 880.08 | 388.33 | 101771 | 66506.25 | 44.12% | 101771 | 0 | 491.75 | 59935 | 1005.53 |  | 66506.25 |  | 0 | 225027.68 | 157515.9 | 70%
05/13/24 |  | 07/25/25 | Open | Richard Keith Arnst | Albert H Nguyen, Wyley Johnson |  | Albert H Nguyen, Larry Noble, Monica Johnson, Richard Keith Arnst, Wyley Johnson |  |  | Devon LeMoine, Hector Rivera, Jose R. Duarte, Justin Smallwood, Mohammed Al-Shaikhli, Nathan Dao, Phillip Ma Lim, Richard Keith Arnst, Tavis Jackson |  |  | Monica Johnson | TX-HOU | Harmony Public Schools El Paso | J00018317 | Wireless Access Point (AP) Installation | On HOLD | 95% | 142.3% | 300 | -124 | 38145.51 | 51587.5 | -41.33% | 38145.51 | 3 | 427 | 39026.25 | 0 |  | 51587.5 |  | 11905.74 | 236345.16 | 184757.66 | 78.17%
04/09/25 |  | 07/25/25 | Open | Richard Keith Arnst | Mark J Chambliss |  | Mark J Chambliss, Monica Johnson, Richard Keith Arnst, Thomas Francis LoMonaco |  |  | Richard Keith Arnst, Thomas Francis LoMonaco |  |  | Monica Johnson | TX-HOU | Port of Houston Authority | 200002635 | N/A | Planning/Design/Staging | 30% | 35% | 60 | 39 | 0 | 3145 | 65% | 0 | 0 | 21 | 0 | 0 |  | 3145 |  | 0 | 11563.6 | 8418.6 | 72.8%
07/22/24 |  | 07/25/25 | Open | Robert McIver | Edward Padron |  | Christopher Prado, Edward Padron, Erick Nunez , Felix Martinez, Robert McIver, Xavier A Trevino |  |  | Christopher Prado, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018692 | AW Brown Installation | Planning/Design/Staging | 35% | 6.703% | 253.62 | 236.62 | 5305 | 1967.5 | 93.3% | 5305 | 0 | 17 | 877.5 | 0 |  | 1967.5 |  | 8466 | 29744.76 | 27777.26 | 93.39%
01/15/25 |  | 07/25/25 | Open | Robert McIver | Firas Abood |  | Cory Bradfield, Cory Bradfield, Firas Abood, Robert McIver, Xavier A Trevino |  |  | Cory Bradfield, Francisco Hernandez, Jonathan Pina, Robert McIver, Roger Guerra |  |  | Eric Rodriguez | TX-SOUT | McAllen ISD | 200001640 | N/A | Implementation/Deployment | 65% | 18.33% | 144.58 | 119.33 | 18622.04 | 2887.5 | 82.54% | 18622.04 | 1.25 | 26.5 | 75 | 0 |  | 2887.5 |  | 205113.02 | 25656.4 | 22768.9 | 88.75%
01/03/24 |  | 07/25/25 | Open | Shannon Marie Alvarado | George Delp |  | Aaron Christopher Pfeifer, George Delp, Joseph Boglino, Larry Noble, Shannon Marie Alvarado |  |  | Aaron Christopher Pfeifer, Jose Gutierrez, Shannon Marie Alvarado |  |  | Joseph Boglino | US-FED | Impres Technology Soluitons, Inc. | J00016942 | NCS 4200 Device Installation | Implementation/Deployment | 85% | 73.22% | 368.75 | 98.75 | 56484.88 | 35850 | 26.78% | 56484.88 | 0 | 270 | 27497.5 | 0 |  | 35850 |  | 0 | 83320.8 | 47470.8 | 56.97%
07/26/24 |  | 07/25/25 | Open | Summer Abunaja | Timothy Ramsey |  | Daniel Saenz, Diana Berger, Summer Abunaja, Timothy Ramsey |  |  | Romar Roca |  |  | Daniel Saenz | TX-SOUT | Rio Grande City Grulla ISD | J00018825 | 24008985 | Not started | 0% | 0% | 0 | -16 | 0 | 2400 | 0% | 0 | 0 | 16 | 2400 | 0 |  | 2400 |  | 0 | 0 | -2400 | 0%
02/12/24 |  | 07/25/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Kurt Sell, Luis Ovalles, Steven Walker, Tray Giddens |  |  | Christopher Brown, Luis Ovalles, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Houston Federal Credit Union | J00017474 | Domain Upgrade & O365 Migration | Implementation/Deployment | 0% | 0% | 0 | -139 | 0 | 18570 | 0% | 0 | 0 | 139 | 18570 | 0 |  | 18570 |  | 0 | 47282.8 | 28712.8 | 60.73%
02/12/24 |  | 07/25/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Kurt Sell, Luis Ovalles, Steven Walker, Tray Giddens |  |  | Christopher Brown, Luis Ovalles, Tray Giddens |  |  | N/A | N/A | Houston Federal Credit Union | J00017474 | Domain Upgrade & O365 Migration | Implementation/Deployment | 70% | 13.4% | 238.75 | 206.75 | 31753.75 | 4190 | 86.6% | 31753.75 | 0 | 32 | 0 | 0 |  | 4190 |  | 0 | 47282.8 | 43092.8 | 91.14%
12/04/24 |  | 07/29/25 | Open | Marco Lish | Bryan Geoghan |  | Bryan Geoghan, Henry Pugsley, Jonathan Pendrich, Marco Lish |  |  | Henry Pugsley, Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Oncor Electric Delivery Company LLC | 200000184 | N/A | Implementation/Deployment | 70% | 36.6% | 250 | 158.5 | 35250 | 14337.5 | 63.4% | 35250 | 0 | 91.5 | 0 | 0 |  | 14337.5 |  | 9799.68 | 57640 | 43302.5 | 75.13%
12/28/23 |  | 07/29/25 | Open | Marco Lish | Christopher Ceykovsky |  | Jeff Barker, Jonathan Pendrich, Marco Lish |  |  | Marco Lish |  |  | Jonathan Pendrich | TX-DAL | Oncor Electric Delivery Company LLC | J00017212 | Appspace On-Premise Server Upgrade | Implementation/Deployment | 45% | 70% | 5 | 1.5 | 625 | 437.5 | 30% | 625 | 0 | 3.5 | 343.75 | 0 |  | 437.5 |  | 18000 | 988 | 550.5 | 55.72%
02/19/24 |  | 07/29/25 | Open | Walter Clay Knight | George Delp, Jeremy Hoffpauir |  | George Delp, Jay David Carothers, Jeremy Hoffpauir, Jessica Anderson, William Isaac Sears |  |  | Aaron Christopher Pfeifer, Walter Clay Knight |  |  | Jay Carothers | US-SP | Celito Communications, LLC | J00017495 | Edge Router Solution | Implementation/Deployment | 0% | 0% | 0 | -207.25 | 0 | 29531.25 | 0% | 0 | 16 | 223.25 | 27371.25 | 0 |  | 29531.25 |  | 0 | 56614.4 | 27083.15 | 47.84%
02/19/24 |  | 07/29/25 | Open | Walter Clay Knight | George Delp, Jeremy Hoffpauir |  | George Delp, Jay David Carothers, Jeremy Hoffpauir, Jessica Anderson, William Isaac Sears |  |  | Aaron Christopher Pfeifer, Walter Clay Knight |  |  | N/A | N/A | Celito Communications, LLC | J00017495 | Edge Router Solution | Implementation/Deployment | 65% | 25.13% | 314.38 | 235.38 | 44637.63 | 10665 | 74.87% | 44637.63 | 0 | 79 | 0 | 0 |  | 10665 |  | 0 | 56614.4 | 45949.4 | 81.16%
12/04/24 |  | 07/29/25 | Open | Walter Clay Knight | Robert V Eubanks, Todd Melby |  | Dennis Odneal, Robert Kelly, Robert Kelly, Robert V Eubanks, Todd Melby |  |  | Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres, Robert Kelly, Walter Clay Knight |  |  | Dennis Odneal | TX-HOU | McCormick Place/ MPEA | 200000232 | N/A | Implementation/Deployment | 75% | 85.63% | 372.23 | 53.48 | 0 | 34532.5 | 14.37% | 0 | 0 | 318.75 | 0 | 0 |  | 34532.5 |  | 2110327.36 | 83591.6 | 49059.1 | 58.69%
01/13/25 |  | 07/29/25 | Open | Walter Clay Knight | Christopher Puyear |  | Christopher Puyear, Hannah Paul, John Stephen Kurkjian |  |  | Hector Rivera, John Stephen Kurkjian, Kevin Curtis, Luis Alvarez, Matthew D'Ambrosio, Paul Serres, Walter Clay Knight |  |  | Hannah Edmunds | TX-CEN | Texana Center | 200001614 | N/A | Implementation/Deployment | 75% | 87.13% | 133.13 | 20.13 | 18431.25 | 14952.5 | 15.12% | 18431.25 | 3 | 116 | 180 | 0 |  | 14952.5 |  | 84925.79 | 27092.8 | 12140.3 | 44.81%
03/17/25 |  | 07/30/25 | Open | Joaquin Marroquin | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, Joaquin Marroquin |  |  | Briliance Johnson, Joaquin Marroquin, Oscar Gonzalez, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Dripping Springs ISD | 200002358 | N/A | Planning/Design/Staging | 5% | 27.53% | 108.99 | 81.99 | 0 | 1995 | 75.23% | 0 | 3 | 30 | 180 | 0 |  | 1995 |  | 453051 | 11359.6 | 9364.6 | 82.44%
05/22/25 |  | 07/30/25 | Open | Summer Abunaja | N/A |  | David Watkins, Neel Shah, Summer Abunaja |  |  | Nathan Dao, Robert Kelly, Summer Abunaja |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200002999 | N/A | Planning/Design/Staging | 50% | 82.21% | 13.38 | 2.88 | 0 | 1230 | 21.52% | 0 | 0.5 | 11 | 30 | 0 |  | 1230 |  | 0 | 5212.8 | 3982.8 | 76.4%
02/21/25 |  | 07/31/25 | Open | Ali Al-Haddad | Warren Wilson |  | Ali Al-Haddad, Meredith A Richardson, Warren Wilson |  |  | Justin Smallwood, Nathan Dao |  |  | N/A | N/A | Houston ISD | 200002016 | N/A | Implementation/Deployment | 0% | 0% | 0 | -3 | 0 | 240 | 0% | 0 | 1 | 4 | 60 | 0 |  | 240 |  | 19642.9 | 1300 | 1060 | 81.54%
06/23/25 |  | 07/31/25 | Open | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Mark J Chambliss, Meredith A Richardson |  |  | Nathan Dao |  |  | N/A | N/A | Houston ISD | 200003113 | N/A | Implementation/Deployment | 0% | 0% | 0 | -1 | 0 | 90 | 0% | 0 | 0.5 | 1.5 | 30 | 0 |  | 90 |  | 0 | 275 | 185 | 67.27%
04/01/25 |  | 07/31/25 | Open | Brian Willery | Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | Brian Willery, Vitalii Stepanchenko |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | 200002421 | N/A | Planning/Design/Staging | 5% | 12.45% | 224.97 | 196.97 | 0 | 3500 | 87.55% | 0 | 0 | 28 | 0 | 0 |  | 3500 |  | 0 | 31972 | 28472 | 89.05%
01/30/25 |  | 07/31/25 | Open | Brittney Antoinette Hickman | Steven Walker |  | Brittney Antoinette Hickman, Christopher Brown, Christopher Brown, Luis Ovalles, Mark Forehand, Steven Walker |  |  | Brittney Antoinette Hickman, Christopher Brown, Luis Ovalles |  |  | Mark Forehand | TX-DAL | City of Richardson | 200001737 | N/A | Planning/Design/Staging | 55% | 116.1% | 140 | -22.5 | 18620 | 21637.5 | -16.07% | 18620 | 0 | 162.5 | 0 | 0 |  | 21637.5 |  | 19743.14 | 30078.44 | 8440.94 | 28.06%
04/22/25 |  | 07/31/25 | Open | Brittney Antoinette Hickman | Jacob Parks, Jeffrey Holman |  | Brittney Antoinette Hickman, Garrett Curran, Jacob Parks, Jeffrey Holman, Sophia Quinter |  |  | Brittney Antoinette Hickman, Sophia Quinter |  |  | Garrett Curran | CA-LAX | CONFIRE | 200002794 | N/A | Planning/Design/Staging | 15% | 6.106% | 131.01 | 123.01 | 0 | 1012.5 | 93.89% | 0 | 0 | 8 | 0 | 0 |  | 1012.5 |  | 48080.5 | 35134.08 | 34121.58 | 97.12%
05/13/25 |  | 07/31/25 | Open | Brittney Antoinette Hickman | William Birdsong |  | Brittney Antoinette Hickman, Kristy L Dice, Matthew Veach, Thai Truong, William Birdsong |  |  | Brittney Antoinette Hickman, Carlo Enriquez, Conner MacDonnell, Frank Jaimes, Jalen Vecchitto, Kendall Walls, Matthew Veach, Thai Truong, Yonathan Fadel |  |  | Kristy L Dice | TX-DAL | Irving ISD | 200002954 | N/A | Planning/Design/Staging | 50% | 58.12% | 95.5 | 42.75 | 0 | 4971.25 | 44.76% | 0 | 2.75 | 55.5 | 165 | 0 |  | 4971.25 |  | 198924.52 | 15825.48 | 10854.23 | 68.59%
10/07/24 |  | 07/31/25 | Open | Brittney Antoinette Hickman | Jacob Parks, Jeffrey Holman, William Birdsong |  | Beau C. Devillier, Brittney Antoinette Hickman, Jacob Parks, Jeffrey Holman, Matthew Veach, Noah Trump, Phillip Ma Lim, Saravanan Lakshmanan, Sophia Quinter, Taylor Leger, William Birdsong |  |  | Brittney Antoinette Hickman, Caleb Baik, Caleb Henry, Calvin Darby, Carlo Enriquez, Conner MacDonnell, Dante Torres, Eric Firestone, Jacob Hill, Kendall Walls, Matthew Veach, Moises Rodriguez, Noah Castleberry, Noah Trump, Phillip Ma Lim, Quy Le, Ryan Frankeberger, Saravanan Lakshmanan, Sophia Quinter, Tavis Jackson, Yonathan Fadel |  |  | Taylor Leger | TX-DAL | Parker University | J00019143 | Wireless Refresh and ISE Deployment | Implementation/Deployment | 85% | 100.1% | 867.64 | 35.64 | 93240.91 | 93403.75 | 4.108% | 93240.91 | 36.25 | 868.25 | 3205 | 0 |  | 93403.75 |  | 254958.5 | 122872 | 29468.25 | 23.98%
01/10/25 |  | 07/31/25 | Open | Brittney Antoinette Hickman | David Goss |  | Brittney Antoinette Hickman, David Goss, Luis Ovalles, Rusty Bryan |  |  | Brittney Antoinette Hickman, David Goss, Jacob Hill, Luis Ovalles, Noah Trump |  |  | Rusty Bryan | TX-DAL | Region 17 Education Service Center | 200001587 | N/A | Planning/Design/Staging | 85% | 116.9% | 197.8 | -7.45 | 23159.04 | 28383.75 | -3.766% | 23159.04 | 26 | 231.25 | 1560 | 0 |  | 28383.75 |  | 732573.72 | 0 | -28383.75 | 0%
05/07/25 |  | 07/31/25 | Open | Christina Rice | William Birdsong |  | Christina Rice, Christina Rice, Kristy L Dice, Thai Truong, William Birdsong |  |  | Christina Rice, Joshua Osgood, Matthew Veach, Thai Truong |  |  | Kristy L Dice | TX-DAL | City of Southlake | 200002853 | N/A | Not started | 0% | 14.72% | 137.53 | 117.28 | 0 | 2106.25 | 85.28% | 0 | 0 | 20.25 | 0 | 0 |  | 2106.25 |  | 307904.19 | 23633.2 | 21526.95 | 91.09%
04/04/25 |  | 07/31/25 | Open | Christina Rice | Matthew Duncan, Michael Brett Beggs |  | Christina Rice, Christina Rice, Juan Saenz, Matthew Duncan, Michael Brett Beggs, Shawn Sutton |  |  | Christina Rice, Juan Saenz |  |  | Shawn Sutton | TX-DAL | Denton ISD | 200002612 | N/A | Not started | 0% | 21.65% | 151.25 | 118.5 | 0 | 4326.25 | 78.35% | 0 | 0 | 32.75 | 0 | 0 |  | 4326.25 |  | 0 | 24667.24 | 20340.99 | 82.46%
12/12/24 |  | 07/31/25 | Open | Christina Rice | Timothy Rosser |  | Beau C. Devillier, Christina Rice, Christina Rice, Darrell Walton, Darrell Walton, Jose Gutierrez, Karyn Hubbard, Shawn Sutton |  |  | Christina Rice, Darrell Walton, Karyn Hubbard |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00015356 | Denton ISD: SFPs for Campus WAN Additions | On HOLD | 5% | 27.69% | 27.81 | 20.11 | 3661.25 | 977.5 | 72.31% | 3661.25 | 0 | 7.7 | 587.5 | 332.24 |  | 977.5 |  | 44122.2 | 0 | -1309.74 | 0%
06/06/24 |  | 07/31/25 | Open | Jason Esry | Joshua Adam Engle |  | Alexander Gutman, Beau C. Devillier, Bradley Buchanan, Jason Esry, Joshua Adam Engle, Joshua Osgood, Justin Thompson, Nazario Armenta Barraza, Sean Cowhey |  |  | Bradley Buchanan, Conner MacDonnell, Devin Moreno, Frank Jaimes, Jalen Vecchitto, Jason Esry, Jesus Escobedo, Joshua Osgood, Justin Mitchell, Justin Thompson, Moises Rodriguez, Nazario Armenta Barraza, Sean Cowhey, Taylor Poole, William Chris Roome |  |  | Alex Gutman | TX-DAL | Dallas ISD | J00018480 | Wireless Surveys | Implementation/Deployment | 25% | 62.78% | 1995.5 | 758.75 | 224995.5 | 125010 | 38.02% | 224995.5 | 16 | 1252.75 | 62917.5 | 0 |  | 125010 |  | 0 | 1285159.9 | 1160149.9 | 90.27%
05/19/25 |  | 07/31/25 | Closed | Jason Esry | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Jason Esry, Romar Roca, Susan Richardson, Wyley Johnson |  |  | N/A |  |  | Susan Richardson | TX-HOU | PetroChina International (America), Inc. | 200002984 | N/A | Not started | 0% | 0% | 56.4 | 56.4 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 7627.92 | 10914.4 | 10914.4 | 100%
09/30/24 |  | 07/31/25 | Open | Jason Matthew Davis | Mark J Chambliss |  | Dustin Huffman, Jason Matthew Davis, Larry Noble, Mark J Chambliss, Thomas Francis LoMonaco |  |  | Henry Pugsley, Jason Matthew Davis, Thomas Francis LoMonaco |  |  | Dustin Huffman | TX-HOU | Landry's Restaurants | J00019073 | UCCX Migration & Calabrio Deployment | Planning/Design/Staging | 90% | 100.3% | 297.06 | -0.94 | 0 | 52870 | -0.3164% | 0 | 0 | 298 | 2965 | 0 |  | 52870 |  | 0 | 112131.92 | 59261.92 | 52.85%
12/18/24 |  | 07/31/25 | Open | Jim Blackwell | Aman Khan |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Aman Khan, Ashley F Freeman, Daniel Hernandez, Daniel R Hernandez, Jim Blackwell |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Baq Alsaedi, Jim Blackwell, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Nathan Dao, Paul Serres |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200000356 | N/A | Implementation/Deployment | 75% | 44.91% | 218.22 | 131.22 | 22169.8 | 8440 | 60.13% | 22169.8 | 11 | 98 | 890 | 0 |  | 8440 |  | 508801.2 | 28442.08 | 20002.08 | 70.33%
03/27/25 |  | 07/31/25 | Open | Jim Blackwell | Ahmed Al-Zubaidi, Aman Khan, Wyley Johnson |  | Ahmed Al-Zubaidi, Aman Khan, Ashley F Freeman, Ben Crouch, Cory Bradfield, Cory Bradfield, Jim Blackwell, Wyley Johnson |  |  | Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200002487 | N/A | Planning/Design/Staging | 5% | 2.494% | 641.65 | 625.65 | 0 | 2000 | 97.51% | 0 | 0 | 16 | 0 | 0 |  | 2000 |  | 0 | 0 | -2000 | 0%
04/11/25 |  | 07/31/25 | Open | Jim Blackwell | Aman Khan |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Aman Khan, Ashley F Freeman, Jim Blackwell |  |  | Aleksei Lavrushenkov, Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200002621 | N/A | Planning/Design/Staging | 5% | 20.72% | 45.86 | 36.36 | 0 | 1180 | 79.28% | 0 | 0 | 9.5 | 0 | 0 |  | 1180 |  | 52649.02 | 12608.08 | 11428.08 | 90.64%
05/16/25 |  | 07/31/25 | Open | Jim Blackwell | N/A |  | Ashley F Freeman, Jim Blackwell, Mark J Chambliss |  |  | Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200002981 | N/A | Planning/Design/Staging | 5% | 37.59% | 18.62 | 11.62 | 0 | 875 | 62.41% | 0 | 0 | 7 | 0 | 0 |  | 875 |  | 24160 | 1629.16 | 754.16 | 46.29%
01/31/25 |  | 07/31/25 | Open | Jim Blackwell | Aman Khan |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Aman Khan, Ashley F Freeman, Jim Blackwell, Larry Noble, Moe Izaks |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Baq Alsaedi, Craig St. Rose, Daniel Hernandez, Hector Rivera, Jaime Flores, Jim Blackwell, Julio C Montoya, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Nathan Dao, Paul Serres, Russell James Bugarin, Trenton Smith |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00019344 | Mission Bend ES - Greenfield Network Deployment | Training/Knowledge Transfer/Documentation | 100% | 77.56% | 314.92 | 97.67 | 30908.9 | 17387.5 | 31.01% | 30908.9 | 27 | 244.25 | 2130 | 0 |  | 17387.5 |  | 550796.9 | 38407.6 | 21020.1 | 54.73%
11/01/23 |  | 07/31/25 | Open | Jim Blackwell | Mark J Chambliss |  | Ashley F Freeman, James Adams, Jim Blackwell, Jorge Ortiz Cardozo, Larry Noble, Mohammed Almoola |  |  | Baq Alsaedi, Devon LeMoine, James Adams, Jesus Gonzalez, Jim Blackwell, Mohammed Almoola |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00016764 | Endpoints + DNA Appliance | On HOLD | 50% | 63.7% | 86.88 | 35.88 | 10472.5 | 6375.4 | 41.3% | 10472.5 | 4.34 | 55.34 | 6115 | 0 |  | 6375.4 |  | 187173.68 | 8826.32 | 2450.92 | 27.77%
02/17/25 |  | 07/31/25 | Open | Jim Blackwell | Mark J Chambliss |  | Ben Crouch, Jeremy R Freeman, Jim Blackwell, Mark J Chambliss, Meredith A Richardson, Michael Garcia, Thad Trusler |  |  | Henry Pugsley, Jim Blackwell, Thad Trusler |  |  | N/A | N/A | Houston ISD | 200001956 | N/A | On HOLD | 25% | 24.12% | 242.5 | 184 | 0 | 8192.5 | 75.88% | 0 | 0 | 58.5 | 0 | 4625 |  | 8192.5 |  | 0 | 35902 | 23084.5 | 64.3%
04/15/25 |  | 07/31/25 | Open | Joaquin Marroquin | N/A |  | Christopher Ceykovsky, Christopher Prado, Joaquin Marroquin, John Stephen Kurkjian, Xavier A Trevino |  |  | Christopher Prado, Joaquin Marroquin, John Stephen Kurkjian |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | 200002615 | N/A | Planning/Design/Staging | 5% | 3.823% | 222.32 | 213.82 | 0 | 1062.5 | 96.18% | 0 | 0 | 8.5 | 0 | 0 |  | 1062.5 |  | 0 | 0 | -1062.5 | 0%
04/15/25 |  | 07/31/25 | Open | Joaquin Marroquin | Christopher Ceykovsky |  | Christopher Ceykovsky, Joaquin Marroquin, John Stephen Kurkjian, Xavier A Trevino |  |  | Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | 200002616 | N/A | Planning/Design/Staging | 5% | 2.024% | 222.32 | 217.82 | 0 | 562.5 | 97.98% | 0 | 0 | 4.5 | 0 | 0 |  | 562.5 |  | 596985.06 | 53577.6 | 53015.1 | 98.95%
12/01/22 |  | 07/31/25 | Open | Joaquin Marroquin | Edward Padron |  | Christopher Prado, Conner MacDonnell, Edward Padron, Felix Martinez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Michelle Bailey, Ruben Cantu, Taylor Poole, Trevor Galloso, Xavier A Trevino |  |  | Abdalsattar Albaghdadi, Adam Morataya, Aleksei Lavrushenkov, Alexis Cantu, Anthony Lange, Bryant Bush, Carlos Carrillo, Christopher Prado, David Michael Castillo, Edgardo Lopez, Felix Martinez, Francisco Hernandez, Hector Rivera, Jaime Flores, Jaime Galvan, Jesus Angel Cantu, Jesus Gonzalez, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Jose Salazar, Juan Arturo Gonzalez Jr, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Lance Daniel Waitschies, Matthew D'Ambrosio, Oscar Ga |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | J00013344 | ER2020 - x29 ES Campus HW Upgrades | Implementation/Deployment | 70% | 212.9% | 2349.92 | -2184.03 | 142574.19 | 384591.85 | -92.94% | 142574.19 | 468.6 | 5002.55 | 286495.85 | 70771.3 |  | 384591.85 |  | 3286118.51 | 677676.16 | 222313.01 | 32.81%
07/10/23 |  | 07/31/25 | Open | Joaquin Marroquin | Edward Padron, Vernon Jackson |  | Amy Martinez-Nagy, Christopher Prado, Conner MacDonnell, Edward Padron, Felix Martinez, Jaime Galvan, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Michelle Bailey, Oscar Garcia, Samuel Newland, Taylor Poole, Trevor Galloso, Vernon Jackson, Xavier A Trevino |  |  | Adam Morataya, Alexis Cantu, Carlos Carrillo, Christopher Prado, David Michael Castillo, Edgardo Lopez, Felix Martinez, Francisco Hernandez, Jaime Galvan, Jesus Angel Cantu, Joaquin Garcia, Joaquin Marroquin, Jonathan Pina, Jorge Robert Rangel, Juan Arturo Gonzalez Jr, Kolawole Ayeni, Lance Daniel Waitschies, Oscar Garcia, Rodney Sincere Robinson, Roger Guerra, Ruben Cantu, Sammie Simon Valero, Samuel Newland, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | J00015906 | ER25 Network Refresh | Implementation/Deployment | 50% | 249.4% | 1431.1 | -1611.51 | 142345.56 | 263061.15 | -112.6% | 142345.56 | 526.43 | 3569.04 | 90172.85 | 26391.5 |  | 263061.15 |  | 1180029.67 | 165564.31 | -123888.34 | -74.83%
12/09/24 |  | 07/31/25 | Open | Joaquin Marroquin | Daniel Snyder, David Goss, Wyley Johnson |  | Amy Martinez-Nagy, Daniel Snyder, David D Tijerina, David Goss, Joaquin Marroquin, Sophia Quinter, Wyley Johnson |  |  | Cory Bradfield, Joaquin Marroquin, Kevin Curtis, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Sophia Quinter, Timothy Sean Marcyes |  |  | David D Tijerina | TX-CEN | Leander ISD | 200000177 | N/A | Implementation/Deployment | 50% | 29.43% | 593.75 | 419 | 84633.75 | 23146.25 | 70.57% | 84633.75 | 0 | 174.75 | 0 | 0 |  | 23146.25 |  | 239314.87 | 135009.72 | 111863.47 | 82.86%
02/26/25 |  | 07/31/25 | Open | Joaquin Marroquin | Bryan Brown |  | Amy Martinez-Nagy, Brian Newman, Brian Newman, Christopher Garcia, David D Tijerina, Joaquin Marroquin, Joel Hubbard |  |  | Brian Newman, Grayson Rigsby, Joaquin Marroquin, Steven Shipmon, Wilangel Francis |  |  | David D Tijerina | TX-CEN | Leander ISD | 200002128 | N/A | Planning/Design/Staging | 5% | 39.09% | 66.51 | 42.01 | 0 | 2370 | 63.16% | 0 | 1.5 | 26 | 90 | 0 |  | 2370 |  | 123330.15 | 76668.85 | 74298.85 | 96.91%
04/28/25 |  | 07/31/25 | Closed | Joaquin Marroquin | Bryan Brown |  | Christopher Garcia, David D Tijerina, Joaquin Marroquin |  |  | N/A |  |  | David D Tijerina | TX-CEN | Leander ISD | 200002890 | N/A | Not started | 0% | 0% | 57.63 | 57.63 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 115364.82 | 82574.44 | 82574.44 | 100%
03/04/25 |  | 07/31/25 | Open | Joaquin Marroquin | Bryan Brown, Edward Padron |  | Bryan Brown, Christopher Garcia, Edward Padron, Joaquin Marroquin, Laura Herrera, Michelle Bailey, Ming Chiu, Ruben Cantu, Xavier A Trevino |  |  | Carlos Carrillo, Christian Pena, Felix Martinez, Jaime Galvan, Joaquin Marroquin, Ming Chiu, Oscar Garcia, Ruben Cantu, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Point Isabel ISD | 200002253 | N/A | Implementation/Deployment | 95% | 77.33% | 309.39 | 113.64 | 0 | 16190 | 36.73% | 0 | 43.5 | 239.25 | 2610 | 0 |  | 16190 |  | 81448.16 | 63088.84 | 46898.84 | 74.34%
01/07/25 |  | 07/31/25 | Open | LaQisha Marshall | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, LaQisha Marshall, Raul Velazquez |  |  | Alexander Chambless, Briliance Johnson, Grayson McClanahan, Grayson Rigsby, LaQisha Marshall, LaTaveon Champ, Oscar Gonzalez, Raul Velazquez, Steven Shipmon, Tommy Percivill, Wilangel Francis |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200001557 | N/A | Implementation/Deployment | 90% | 57.95% | 1082 | 482 | 83698.5 | 47857.5 | 44.55% | 83698.5 | 27 | 627 | 1620 | 0 |  | 47857.5 |  | 966698.89 | 98956 | 51098.5 | 51.64%
04/16/25 |  | 07/31/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, John Stephen Kurkjian, LaQisha Marshall |  |  | John Stephen Kurkjian, LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200002695 | N/A | Training/Knowledge Transfer/Documentation | 85% | 28.56% | 324.75 | 232 | 0 | 12636.25 | 71.44% | 0 | 0 | 92.75 | 0 | 0 |  | 12636.25 |  | 0 | 14974 | 2337.75 | 15.61%
04/23/25 |  | 07/31/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, LaQisha Marshall |  |  | N/A |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200002795 | N/A | Planning/Design/Staging | 5% | 0% | 40.35 | 40.35 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1537.5 | 897.6 | 897.6 | 100%
06/05/24 |  | 07/31/25 | Open | LaQisha Marshall | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, Ernesto Gonzalez, Kurt Sell, LaQisha Marshall, Lori Endsley |  |  | Adam Felix, Alexander Chambless, Briliance Johnson, Ernesto Gonzalez, Grayson Rigsby, Kevin Curtis, Kolawole Ayeni, LaQisha Marshall, LaTaveon Champ, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Robert Jones, Steven Shipmon, Wilangel Francis |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018475 | Multi-Campus Cisco Meraki Wireless Deployment | Training/Knowledge Transfer/Documentation | 85% | 79.47% | 619.45 | 136.2 | 57399.85 | 47198.75 | 21.99% | 57399.85 | 9 | 492.25 | 3352.5 | 0 |  | 47198.75 |  | 485647.61 | 56727.2 | 9528.45 | 16.8%
07/22/24 |  | 07/31/25 | Open | LaQisha Marshall | Christopher Puyear, Daniel Snyder |  | Briliance Johnson, Christi D Hubbard, Christopher Puyear, Daniel Snyder, Ernesto Gonzalez, John Stephen Kurkjian, Kurt Sell, LaQisha Marshall, Lori Endsley, Raul Velazquez, Robert Jones |  |  | Alexander Chambless, Ernesto Gonzalez, Grayson McClanahan, Grayson Rigsby, John Stephen Kurkjian, Kevin Curtis, LaQisha Marshall, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Raul Velazquez, Robert Jones, Steven Shipmon, Wilangel Francis |  |  | Christi D Hubbard | TX-CEN | Austin ISD | J00018684 | Network Refresh - Sims Elementary School | Training/Knowledge Transfer/Documentation | 95% | 113.6% | 156.97 | -14.78 | 14360.59 | 16700 | -9.416% | 14360.59 | 6.5 | 178.25 | 2070 | 0 |  | 16700 |  | 193035.7 | 20157.28 | 3457.28 | 17.15%
05/20/25 |  | 07/31/25 | Open | LaQisha Marshall | Ahmed Al-Zubaidi, Steven Walker |  | Ahmed Al-Zubaidi, Ashutosh Patel, David Monasmith, David Monasmith, Ibrahim Altaweel, Jerome Tanyag Mara, LaQisha Marshall, Mohammad Arman, Rogelio Morgado-Perez, Steven Walker, Tom Magboo |  |  | Ashutosh Patel, Ibrahim Altaweel, Jerome Tanyag Mara, LaQisha Marshall, Tom Magboo |  |  | David Monasmith | TX-HOU | College Station ISD | 200002989 | N/A | Planning/Design/Staging | 5% | 11.22% | 263 | 233.5 | 0 | 4337.5 | 88.78% | 0 | 0 | 29.5 | 0 | 0 |  | 4337.5 |  | 0 | 33990 | 29652.5 | 87.24%
09/02/24 |  | 07/31/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, Henry Pugsley, LaQisha Marshall, Larry Noble, Lori Endsley |  |  | Henry Pugsley, LaQisha Marshall, Raul Velazquez |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00018448 | Singlewire | Implementation/Deployment | 75% | 84.32% | 110 | 17.25 | 15110 | 13893.75 | 15.68% | 15110 | 0 | 92.75 | 5225 | 0 |  | 13893.75 |  | 228996.18 | 22627.2 | 8733.45 | 38.6%
04/25/25 |  | 07/31/25 | Open | LaQisha Marshall | David D Tijerina, David Goss |  | David D Tijerina, David Escamilla, David Goss, LaQisha Marshall, Tony Dean Skipworth |  |  | LaQisha Marshall, Tony Dean Skipworth |  |  | David D Tijerina | TX-CEN | Travis County | 200002593 | N/A | Planning/Design/Staging | 5% | 15.15% | 33 | 28 | 0 | 635 | 84.85% | 0 | 0 | 5 | 0 | 0 |  | 635 |  | 89560.52 | 19724 | 19089 | 96.78%
06/11/24 |  | 07/31/25 | Open | Marco Lish | Bryan Brown, Christopher Pheonix Preddy, Christopher Puyear, Warren Wilson |  | Beau C. Devillier, Christopher Garcia, Christopher Pheonix Preddy, Christopher Puyear, Conner MacDonnell, Dylan Pittsinger, Joel Hubbard, Kristy L Dice, Marco Lish, Warren Wilson |  |  | Angelo Gallegos, Bradley Buchanan, Brian Newman, Carlo Enriquez, Christina Rice, Conner MacDonnell, Corey Lamon Walker, Dante Torres, Darryl Ronald Hamilton, Dylan Pittsinger, Gabriel Lantigua, Hamzeh Tahat, Jacob Hill, Jayden Colon, Joan Brito, Joel Hubbard, Joshua Hubbard, Joshua Osgood, Luis Ovalles, Marco Lish, Michael McGee, Noah Trump, Phillip Ma Lim, Raymond Phan, Remijio Hernandez, Samuel Earl Parks Jr, Samuel Gonzalez, Twight Peaks |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00018477 | Aledo ISD: Safety and Security Upgrades | Implementation/Deployment | 80% | 172.5% | 1160.12 | -694.93 | 148137.04 | 146138.75 | -59.9% | 148137.04 | 146.2 | 2001.25 | 99405.5 | 23816.75 |  | 146138.75 |  | 688789.41 | 359961.8 | 190006.3 | 52.79%
02/10/25 |  | 07/31/25 | Open | Marco Lish | Jacob Parks, Jeffrey Holman |  | Ibrahim Altaweel, Jeffrey Holman, Jerome Tanyag Mara, Marco Lish, Mark Forehand, Mohammad Arman, Rogelio Morgado-Perez, Tom Magboo |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, Marco Lish, Rogelio Morgado-Perez, Tom Magboo |  |  | Mark Forehand | TX-DAL | TD Industries | 200001854 | N/A | Planning/Design/Staging | 80% | 97.9% | 321 | 6.75 | 0 | 47081.25 | 2.103% | 0 | 0 | 314.25 | 0 | 0 |  | 47081.25 |  | 0 | 34092.68 | -12988.57 | -38.1%
05/13/24 |  | 07/31/25 | Open | Marshall Chuck Pugh | Bryan Geoghan |  | Beau C. Devillier, Bryan Geoghan, Marshall Chuck Pugh, Patrick Joseph Palermo, Tavis Jackson, Taylor Leger |  |  | Bryce Evans, Dante Torres, Jacob Hill, Joan Brito, Joshua Hubbard, Marshall Chuck Pugh, Patrick Joseph Palermo, Phillip Ma Lim, Remijio Hernandez, Tavis Jackson, William Chris Roome |  |  | Taylor Leger | TX-DAL | Corsicana ISD | J00018288 | Collaboration Upgrade | Implementation/Deployment | 90% | 186.1% | 162.05 | -109.45 | 19432.1 | 38040 | -67.54% | 19432.1 | 30 | 301.5 | 31497.5 | 0 |  | 38040 |  | 28213.3 | 26599.2 | -11440.8 | -43.01%
02/19/24 |  | 07/31/25 | Open | Marshall Chuck Pugh | Bryan Geoghan |  | Beau C. Devillier, Brian Newman, Brian Newman, Lauren J Kennewell, Marshall Chuck Pugh , Sean Cowhey, Tavis Jackson, Timothy Fain |  |  | Brian Newman, Henry Pugsley, Joel Hubbard, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Midlothian ISD | J00017448 | Olympus POC (3 campuses) | Implementation/Deployment | 80% | 44.93% | 365.03 | 205.03 | 39306.53 | 22387.5 | 56.17% | 39306.53 | 4 | 164 | 12823.75 | 0 |  | 22387.5 |  | 0 | 10894.32 | -11493.18 | -105.5%
10/25/24 |  | 07/31/25 | Open | Marshall Chuck Pugh | Christopher Pheonix Preddy, Warren Wilson |  | Beau C. Devillier, Christopher Pheonix Preddy, Lauren J Kennewell, Marshall Chuck Pugh , Warren Wilson |  |  | Christopher Pheonix Preddy, Conner MacDonnell, Dante Torres, Jayden Colon, Marshall Chuck Pugh, Remijio Hernandez, Samuel Gonzalez |  |  | Lauren J Kennewell | TX-DAL | Midlothian ISD | J00019212 | Service Center - Avigilon Unity Video and ACM | Planning/Design/Staging | 80% | 107.2% | 135.78 | 0.28 | 14608.96 | 19437.5 | 0.2062% | 14608.96 | 10 | 145.5 | 1025 | 0 |  | 19437.5 |  | 0 | 16621.68 | -2815.82 | -16.94%
10/21/24 |  | 07/31/25 | Open | Marshall Chuck Pugh | Bryan Brown, Bryan Geoghan |  | Beau C. Devillier, Brian Newman, Brian Newman, Bryan Geoghan, Christopher Garcia, Joel Hubbard, Lauren J Kennewell, Marshall Chuck Pugh, Timothy Fain |  |  | Austen Howard, Brian Newman, Carlo Enriquez, Dante Torres, Joel Hubbard, Joshua Hubbard, Kendall Walls, Marshall Chuck Pugh, Quy Le, Remijio Hernandez, Yonathan Fadel |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | J00019251 | Atlas/Singlewire Implementation - Memorial MS | Implementation/Deployment | 90% | 122.2% | 154.25 | -24.25 | 1826.72 | 19791.25 | -15.72% | 1826.72 | 10 | 188.5 | 725 | 0 |  | 19791.25 |  | 82033.59 | 47488.29 | 27697.04 | 58.32%
02/24/25 |  | 07/31/25 | Open | Richard Keith Arnst | Bryan Geoghan |  | Arcangelo Fanelli, Brian Newman, Brian Newman, Bryan Geoghan, Richard Keith Arnst |  |  | Brian Newman, Joel Hubbard, Richard Keith Arnst |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | 200002149 | N/A | Planning/Design/Staging | 50% | 40.34% | 60.12 | 35.87 | 0 | 3123.75 | 59.66% | 0 | 0 | 24.25 | 0 | 0 |  | 3123.75 |  | 24533.88 | 13349.2 | 10225.45 | 76.6%
05/05/25 |  | 07/31/25 | Open | Robert McIver | David Escamilla |  | Arpine Ramirez, Daniel Saenz, David Escamilla, Juan Saenz, Robert McIver, Ron Loge |  |  | Juan Saenz, Robert McIver, Ron Loge |  |  | Daniel Saenz | TX-SOUT | City of Mission | 200002941 | N/A | Implementation/Deployment | 60% | 51.18% | 127.5 | 62.25 | 0 | 9808.75 | 48.82% | 0 | 0 | 65.25 | 0 | 0 |  | 9808.75 |  | 0 | 11672.56 | 1863.81 | 15.97%
03/21/25 |  | 07/31/25 | Open | Robert McIver | Edward Padron |  | Edward Padron, Erick Nunez , Robert McIver, Xavier A Trevino |  |  | Briliance Johnson, Diego Asencio, Erick Nunez , James Espinosa, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres, Phillip Capozzi, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002486 | N/A | Implementation/Deployment | 65% | 73.99% | 178.06 | 62.31 | 0 | 9362.5 | 34.99% | 0 | 16 | 131.75 | 480 | 0 |  | 9362.5 |  | 194585.2 | 28782.8 | 19420.3 | 67.47%
08/26/24 |  | 07/31/25 | Open | Ryan Scott | Mark J Chambliss |  | Anthony Towsley, Dustin Huffman, Larry Noble, Mark J Chambliss, Ryan Scott |  |  | Anthony Towsley, Carlo Enriquez, Henry Pugsley, Jarshawn Newsome, Jesus Gonzalez, Jose R. Duarte, Julio C Montoya, Justin Cornish, Kendall Walls, Kenneth Stevenson, Kolawole Ayeni, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Quy Le, Ryan Scott, Walter Hanchett, Yonathan Fadel |  |  | Dustin Huffman | TX-HOU | Landry's Restaurants | J00018735 | Webex Calling Implementation | Training/Knowledge Transfer/Documentation | 90% | 190.1% | 274.25 | -194 | 31927.27 | 54548.75 | -70.74% | 31927.27 | 53 | 521.25 | 15402.5 | 0 |  | 54548.75 |  | 5162.39 | 49256.8 | -5291.95 | -10.74%
04/14/25 |  | 07/31/25 | Open | Ryan Scott | Chad Hart, Joshua Adam Engle |  | Chad Hart, Dennis Odneal, Jeffery Alan Jorzig, Jeffery Jorzig, Joshua Adam Engle, Ryan Scott, Warren Llewellyn Flynn |  |  | Daniel Hernandez, Jeffery Alan Jorzig, Lauren Lanzini Coffey, Ryan Scott, Taylor Poole |  |  | Dennis Odneal | TX-HOU | Ochsner Health | 200002651 | N/A | Implementation/Deployment | 75% | 106.9% | 125.4 | 34.4 | 0 | 9697.5 | 27.43% | 0 | 43 | 134 | 2580 | 0 |  | 9697.5 |  | 0 | 12000 | 2302.5 | 19.19%
06/07/24 |  | 07/31/25 | Open | Ryan Scott | David Watkins |  | Arcangelo Fanelli, Beau C. Devillier, Conner MacDonnell, David Watkins, Devin Moreno, Erick Sanchez, Jesus Escobedo, Ryan Scott |  |  | Bradley Buchanan, Caleb Baik, Carlo Enriquez, Dante Torres, Devin Moreno, Jeffery Giles, Jesus Escobedo, John Johnson, Kendall Walls, Noah Castleberry, Noah Trump, Phillip Ma Lim, Quy Le, Remijio Hernandez, Ryan Scott, Tavis Jackson, Yonathan Fadel |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00018298 | Remote Site AP Refresh - x400APs | Training/Knowledge Transfer/Documentation | 95% | 69.33% | 911.25 | 346.5 | 88141.22 | 51148.75 | 38.02% | 88141.22 | 67 | 631.75 | 30101.25 | 0 |  | 51148.75 |  | 375240 | 192392.4 | 141243.65 | 73.41%
03/27/25 |  | 07/31/25 | Open | Shannon Marie Alvarado | Jacob Parks, Jeffrey Holman |  | Arcangelo Fanelli, Eric Firestone, Jacob Parks, Jeffrey Holman, Shannon Marie Alvarado |  |  | Eric Firestone, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | 200002526 | N/A | Implementation/Deployment | 50% | 42.55% | 80.5 | 46.25 | 0 | 4962.5 | 57.45% | 0 | 0 | 34.25 | 0 | 0 |  | 4962.5 |  | 0 | 27641.2 | 22678.7 | 82.05%
07/16/24 |  | 07/31/25 | Open | Summer Abunaja | Jacob Parks, Jeffrey Holman |  | Beau C. Devillier, Ibrahim Altaweel, Jacob Parks, Jeffrey Holman, Rogelio Morgado-Perez, Rusty Bryan, Summer Abunaja, Tom Magboo |  |  | Ibrahim Altaweel, Rogelio Morgado-Perez |  |  | Rusty Bryan | TX-DAL | Amarillo ISD | J00018668 | Monthly Vulnerability Scans | Implementation/Deployment | 80% | 59.51% | 263 | 106.5 | 39250 | 23475 | 40.49% | 39250 | 0 | 156.5 | 7125 | 0 |  | 23475 |  | 0 | 21842 | -1633 | -7.476%
05/14/25 |  | 07/31/25 | Open | Summer Abunaja | Bryan Geoghan |  | Arcangelo Fanelli, Bryan Geoghan, Summer Abunaja |  |  | Summer Abunaja |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | 200002971 | N/A | Planning/Design/Staging | 15% | 1.877% | 133.19 | 130.69 | 0 | 250 | 98.12% | 0 | 0 | 2.5 | 0 | 0 |  | 250 |  | 7140.7 | 26722.8 | 26472.8 | 99.06%
04/07/25 |  | 07/31/25 | Open | Summer Abunaja | Jacob Parks, Jeffrey Holman |  | Ibrahim Altaweel, Jacob Parks, Jeffrey Holman, Jerome Tanyag Mara, Kristy L Dice, Mohammad Arman, Rogelio Morgado-Perez, Summer Abunaja, Tom Magboo |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, Rogelio Morgado-Perez, Summer Abunaja, Tom Magboo |  |  | Kristy L Dice | TX-DAL | City of Southlake | 200002622 | N/A | Planning/Design/Staging | 20% | 11.45% | 203 | 179.75 | 0 | 3437.5 | 88.55% | 0 | 0 | 23.25 | 0 | 0 |  | 3437.5 |  | 0 | 21160 | 17722.5 | 83.75%
03/11/25 |  | 07/31/25 | Open | Tray Giddens | Aman Khan, Mark J Chambliss |  | Ahmed Jameel, Aman Khan, Anthony Towsley, Dustin Huffman, George McGann, Mark J Chambliss, Michelle Bailey, Tray Giddens |  |  | Ahmed Jameel, Anthony Towsley, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Landry's Hotel Division | 200002247 | N/A | Planning/Design/Staging | 25% | 8.749% | 342.9 | 312.9 | 0 | 3885 | 91.25% | 0 | 0 | 30 | 0 | 0 |  | 3885 |  | 46384.94 | 62324.8 | 58439.8 | 93.77%
03/25/25 |  | 07/31/25 | Open | Walter Clay Knight | Ahmed Al-Zubaidi |  | Ahmed Al-Zubaidi, Christopher Kutalek, Timothy Sean Marcyes, Walter Clay Knight |  |  | Timothy Sean Marcyes |  |  | Christopher Kutalek | TX-HOU | Bradford Airport Logistics | 200002509 | N/A | Planning/Design/Staging | 30% | 10% | 30 | 27 | 0 | 525 | 90% | 0 | 0 | 3 | 0 | 0 |  | 525 |  | 44850.92 | 4210.37 | 3685.37 | 87.53%
05/06/25 |  | 07/31/25 | Open | Walter Clay Knight | George Delp |  | Aaron Christopher Pfeifer, George Delp, Rafael Rodriguez-Vargas, Walter Clay Knight, Zachary Short, Zachary Short |  |  | Aaron Christopher Pfeifer, Walter Clay Knight |  |  | Zachary Short | US-SP | Segra | 200002947 | N/A | Planning/Design/Staging | 5% | 2.083% | 168 | 164.5 | 0 | 452.5 | 97.92% | 0 | 0 | 3.5 | 0 | 0 |  | 452.5 |  | 977595.75 | 28901.2 | 28448.7 | 98.43%
03/25/25 |  | 07/31/25 | Open | Walter Clay Knight | Timothy Ramsey, Wyley Johnson |  | Hannah Paul, Timothy Ramsey, Timothy Sean Marcyes, Walter Clay Knight, Wyley Johnson |  |  | Timothy Sean Marcyes, Walter Clay Knight |  |  | Hannah Edmunds | TX-CEN | Texas Water Development Board | 200002184 | N/A | Implementation/Deployment | 50% | 47.16% | 200.4 | 105.9 | 0 | 15312.5 | 52.84% | 0 | 0 | 94.5 | 0 | 0 |  | 15312.5 |  | 57.04 | 40318 | 25005.5 | 62.02%
05/27/25 |  | 07/31/25 | Open | Walter Clay Knight | David Goss |  | David D Tijerina, David Goss, Tony Dean Skipworth, Walter Clay Knight |  |  | Tony Dean Skipworth, Walter Clay Knight |  |  | David D Tijerina | TX-CEN | Williamson County | 200003014 | N/A | Planning/Design/Staging | 5% | 3.095% | 64.63 | 62.63 | 0 | 260 | 96.91% | 0 | 0 | 2 | 0 | 0 |  | 260 |  | 59519.92 | 8772.88 | 8512.88 | 97.04%
04/24/25 |  | 08/01/25 | Closed | Brian Willery | Jacob Parks, Jeffrey Holman |  | Brian Willery, Eric Firestone, Jacob Parks, Jeffrey Holman, Lauren J Kennewell |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | 200002873 | N/A | Cancelled | 0% | 0% | 169.75 | 169.75 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 223232.56 | 34514 | 34514 | 100%
06/05/25 |  | 08/01/25 | Closed | Brian Willery | Amanda Barney, George Edwin Jacob, Majid Shirzadeh |  | Brian Willery, Lauren J Kennewell, Majid Shirzadeh |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | 200003058 | N/A | Not started | 0% | 0% | 123.75 | 123.75 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 206853.5 | 20165.6 | 20165.6 | 100%
05/21/25 |  | 08/01/25 | Closed | Brian Willery | N/A |  | Brian Willery, Chad Hart, Jaclyn Pias |  |  | N/A |  |  | Jaclyn Pias | TX-HOU | Houston Zoo | 200002993 | N/A | Not started | 0% | 0% | 68.13 | 68.13 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 16254.81 | 10834.4 | 10834.4 | 100%
04/10/25 |  | 08/01/25 | Closed | Brian Willery | Jeremy Williams, Michael Brett Beggs |  | Brian Willery, Camille Elizabeth Taber, Jeremy Williams, Michael Brett Beggs |  |  | N/A |  |  | Camille Taber | FL | Lake County School Board | 200002580 | N/A | Not started | 0% | 0% | 188.88 | 188.88 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 938041.19 | 42461.52 | 42461.52 | 100%
04/03/25 |  | 08/01/25 | Open | Brittney Antoinette Hickman | William Birdsong |  | Brittney Antoinette Hickman, Lauren J Kennewell, Saravanan Lakshmanan, William Birdsong |  |  | Brittney Antoinette Hickman, Conner MacDonnell, Kendall Walls, Saravanan Lakshmanan, Yonathan Fadel |  |  | Lauren J Kennewell | TX-DAL | Cedar Hill ISD | 200002457 | N/A | Implementation/Deployment | 50% | 19.42% | 677 | 545.5 | 0 | 16507.5 | 80.58% | 0 | 0 | 131.5 | 0 | 0 |  | 16507.5 |  | 589593.58 | 111784.8 | 95277.3 | 85.23%
04/25/25 |  | 08/01/25 | Open | Brittney Antoinette Hickman | Matthew Duncan |  | Brittney Antoinette Hickman, Carmen Isela Brandt, Garrett Curran, Juan Saenz, Matthew Duncan, Osazee Eweka |  |  | Brittney Antoinette Hickman, Juan Saenz, Osazee Eweka |  |  | Garrett Curran | CA-LAX | Los Angeles Community College District | 200002640 | N/A | Implementation/Deployment | 50% | 33.87% | 109.25 | 72.25 | 0 | 4840 | 66.13% | 0 | 0 | 37 | 0 | 0 |  | 4840 |  | 0 | 22598.8 | 17758.8 | 78.58%
04/21/25 |  | 08/01/25 | Open | Jason Esry | Aman Khan |  | Aman Khan, David D Tijerina, Emilio Carrillo, Jason Esry, Mohammed Almoola |  |  | An Le, Celso Lopez, Dustin Aaron Lowrey, Eric Straeter, Isaiah Rosales, James Danner, Jason Esry, John Senkulics, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Michael Torres, Mohammed Almoola, Paul Serres, Quinn Wieland, Robert Kelly |  |  | David D Tijerina | TX-CEN | San Antonio ISD | 200002782 | N/A | Implementation/Deployment | 75% | 84.76% | 640.35 | 97.6 | 0 | 44767.5 | 15.24% | 0 | 0 | 542.75 | 0 | 0 |  | 44767.5 |  | 684977.66 | 49875 | 5107.5 | 10.24%
05/19/25 |  | 08/01/25 | Open | Jennifer Soliz | Daniel Snyder |  | Daniel Snyder, Ernesto Gonzalez, Jennifer Soliz, Lonnie Owens |  |  | Ernesto Gonzalez, Jennifer Soliz, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres |  |  | Lonnie Owens | TX-CEN | McCoy Corporation | 200002969 | N/A | Planning/Design/Staging | 40% | 15.08% | 220.53 | 187.28 | 0 | 3425 | 84.92% | 0 | 0 | 33.25 | 0 | 0 |  | 3425 |  | 126244.5 | 310982 | 307557 | 98.9%
06/06/25 |  | 08/01/25 | Open | Jim Blackwell | N/A |  | Abdalsattar Albaghdadi, Aman Khan, Ashley F Freeman, Jim Blackwell, Jorge Ortiz Cardozo |  |  | Abdalsattar Albaghdadi, Jim Blackwell, Jorge Ortiz Cardozo |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200003060 | N/A | Implementation/Deployment | 50% | 76.36% | 110 | 37 | 0 | 10500 | 33.64% | 0 | 11 | 84 | 1375 | 0 |  | 10500 |  | 0 | 0 | -10500 | 0%
06/26/25 |  | 08/01/25 | Open | Jim Blackwell | N/A |  | Ashley F Freeman, Jim Blackwell, Mark J Chambliss |  |  | Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200003122 | N/A | Planning/Design/Staging | 5% | 5.452% | 18.34 | 17.34 | 0 | 125 | 94.55% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 0 | 1604.52 | 1479.52 | 92.21%
06/26/25 |  | 08/01/25 | Open | Jim Blackwell | N/A |  | Ashley F Freeman, Jim Blackwell, Mark J Chambliss |  |  | Jim Blackwell |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200003123 | N/A | Planning/Design/Staging | 5% | 6.006% | 16.65 | 15.65 | 0 | 125 | 93.99% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 0 | 1456.88 | 1331.88 | 91.42%
03/11/25 |  | 08/01/25 | Open | Joanna Herrera | Mark J Chambliss |  | Jason Osuna, Joanna Herrera, Karen Grant-Dennison, Mark J Chambliss |  |  | Anthony Towsley, Joanna Herrera |  |  | Jason Osuna | TX-CEN | Cobre Consolidated School District | 200002363 | N/A | Implementation/Deployment | 90% | 36.13% | 10.38 | 6.63 | 0 | 498.75 | 63.87% | 0 | 0 | 3.75 | 0 | 0 |  | 498.75 |  | 26839.8 | 1612.8 | 1114.05 | 69.08%
04/09/25 |  | 08/01/25 | Open | Joanna Herrera | Steven Walker |  | Jason Osuna, Joanna Herrera, Steven Walker |  |  | Christopher Brown, Joanna Herrera |  |  | Jason Osuna | TX-CEN | Cobre Consolidated School District | 200002613 | N/A | Implementation/Deployment | 75% | 40.67% | 75 | 44.5 | 0 | 4027.5 | 59.33% | 0 | 0 | 30.5 | 0 | 0 |  | 4027.5 |  | 0 | 14663.2 | 10635.7 | 72.53%
06/26/24 |  | 08/01/25 | Open | Joanna Herrera | Edward Padron |  | Amy Martinez-Nagy, Carlos Carrillo, Conner MacDonnell, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Francisco Hernandez, Jaime Galvan, Joanna Herrera, Jonathan Pina, Jorge Robert Rangel, Michelle Bailey, Oscar Garcia, Robert McIver, Roger Guerra, Ruben Cantu, Taylor Poole, Trevor Galloso, Xavier A Trevino |  |  | Carlos Carrillo, Felix Martinez, Jaime Galvan, Joanna Herrera, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Oscar Garcia, Roger Guerra, Ruben Cantu, Trevor Galloso |  |  | Eric Rodriguez | TX-SOUT | Mission CISD | J00018582 | E-Rate Round 26 Internal Connections | Implementation/Deployment | 0% | 0% | 0 | -24 | 0 | 2445 | 0% | 0 | 0.5 | 24.5 | 2415 | 0 |  | 2445 |  | 1029785.5 | 51223.91 | 48778.91 | 95.23%
06/26/24 |  | 08/01/25 | Open | Joanna Herrera | Edward Padron |  | Amy Martinez-Nagy, Carlos Carrillo, Conner MacDonnell, Diana Berger, Edward Padron, Eric Rodriguez, Felix Martinez, Francisco Hernandez, Jaime Galvan, Joanna Herrera, Jonathan Pina, Jorge Robert Rangel, Michelle Bailey, Oscar Garcia, Robert McIver, Roger Guerra, Ruben Cantu, Taylor Poole, Trevor Galloso, Xavier A Trevino |  |  | Carlos Carrillo, Felix Martinez, Jaime Galvan, Joanna Herrera, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Oscar Garcia, Roger Guerra, Ruben Cantu, Trevor Galloso |  |  | N/A | N/A | Mission CISD | J00018582 | E-Rate Round 26 Internal Connections | Implementation/Deployment | 90% | 154.1% | 390.82 | -158.43 | 30597.9 | 44617.5 | -40.54% | 30597.9 | 53 | 602.25 | 3635 | 0 |  | 44617.5 |  | 1029785.5 | 51223.91 | 6606.41 | 12.9%
07/16/24 |  | 08/01/25 | Open | Joaquin Marroquin | David Escamilla |  | David D Tijerina, David Escamilla, Joaquin Marroquin, Juan Saenz, Larry Noble |  |  | Joaquin Marroquin, Juan Saenz |  |  | David D Tijerina | TX-CEN | Amazon Web Services | J00018667 | AWS DRS Migration & Control Tower Deployment | Implementation/Deployment | 0% | 0% | 0 | -16.5 | 0 | 2147.5 | 0% | 0 | 0 | 16.5 | 2147.5 | 0 |  | 2147.5 |  | 0 | 15710.4 | 13562.9 | 86.33%
07/16/24 |  | 08/01/25 | Open | Joaquin Marroquin | David Escamilla |  | David D Tijerina, David Escamilla, Joaquin Marroquin, Juan Saenz, Larry Noble |  |  | Joaquin Marroquin, Juan Saenz |  |  | N/A | N/A | Amazon Web Services | J00018667 | AWS DRS Migration & Control Tower Deployment | Implementation/Deployment | 70% | 13.53% | 77.63 | 67.13 | 10393.75 | 1407.5 | 86.47% | 10393.75 | 0 | 10.5 | 0 | 0 |  | 1407.5 |  | 0 | 15710.4 | 14302.9 | 91.04%
04/01/25 |  | 08/01/25 | Open | Joaquin Marroquin | Christopher Puyear |  | Anthony Towsley, Christi D Hubbard, Christopher Puyear, Hamzeh Tahat, Joaquin Marroquin |  |  | Joaquin Marroquin, Samuel Newland |  |  | Christi D Hubbard | TX-CEN | Dripping Springs ISD | 200002398 | N/A | Implementation/Deployment | 75% | 9.655% | 36.25 | 32.75 | 0 | 452.5 | 90.34% | 0 | 0 | 3.5 | 0 | 0 |  | 452.5 |  | 12006.63 | 7513.2 | 7060.7 | 93.98%
07/12/24 |  | 08/01/25 | Open | Joaquin Marroquin | Christopher Puyear |  | Anthony Towsley, Christi D Hubbard, Christopher Puyear, Hamzeh Tahat, Henry Pugsley, Joaquin Marroquin, Larry Noble |  |  | Anthony Towsley, Hamzeh Tahat, Henry Pugsley, Joaquin Marroquin, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Paul Serres |  |  | Christi D Hubbard | TX-CEN | Dripping Springs ISD | J00018657 | Cisco Unified Communications (UC) Upgrade | Implementation/Deployment | 70% | 90.2% | 169.63 | 16.63 | 23322.75 | 16427.5 | 9.804% | 23322.75 | 0 | 153 | 2187.5 | 12190 |  | 16427.5 |  | 178185.8 | 71287.3 | 42669.8 | 59.86%
04/04/25 |  | 08/01/25 | Open | Joaquin Marroquin | Daniel Snyder |  | Amy Martinez-Nagy, Daniel Snyder, David D Tijerina, David Pena, Joaquin Marroquin, Oscar Gonzalez |  |  | Dustin Aaron Lowrey, Joaquin Marroquin, Oscar Gonzalez, Robert Jones |  |  | David D Tijerina | TX-CEN | Leander ISD | 200002607 | N/A | Planning/Design/Staging | 15% | 21.34% | 133.56 | 105.06 | 0 | 3122.5 | 78.66% | 0 | 0 | 28.5 | 0 | 0 |  | 3122.5 |  | 242544.04 | 22804 | 19681.5 | 86.31%
09/24/24 |  | 08/01/25 | Open | Joaquin Marroquin | David Pena |  | Amy Martinez-Nagy, Darrell Walton, Darrell Walton, David D Tijerina, David Pena, Joaquin Marroquin, Larry Noble |  |  | Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | J00018620 | Cat 1 - WAN Network Equipment and Fiber Repair | Implementation/Deployment | 25% | 123.7% | 14.95 | -3.55 | 1868.75 | 2312.5 | -23.75% | 1868.75 | 0 | 18.5 | 750 | 0 |  | 2312.5 |  | 1340424.5 | 117961.76 | 115649.26 | 98.04%
02/12/25 |  | 08/01/25 | Open | Lauren Lanzini Coffey | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Lauren Lanzini Coffey, Neel Shah, Wyley Johnson |  |  | Ashutosh Patel, Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200001869 | N/A | Planning/Design/Staging | 15% | 58.14% | 53.75 | 22.5 | 7793.75 | 4556.25 | 41.86% | 7793.75 | 0 | 31.25 | 0 | 0 |  | 4556.25 |  | 0 | 12274.8 | 7718.55 | 62.88%
06/11/25 |  | 08/01/25 | Open | Marco Lish | William Birdsong |  | Kristy L Dice, Marco Lish, William Birdsong |  |  | Marco Lish |  |  | Kristy L Dice | TX-DAL | Aledo ISD | 200003082 | N/A | Planning/Design/Staging | 0% | 0.3717% | 134.51 | 134.01 | 0 | 62.5 | 99.63% | 0 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 114690 | 17060 | 16997.5 | 99.63%
10/07/24 |  | 08/01/25 | Open | Marco Lish | Christopher Puyear |  | Anthony Towsley, Beau C. Devillier, Christopher Puyear, Kristy L Dice, Marco Lish |  |  | Anthony Towsley, Henry Pugsley, Kendall Walls, Marco Lish, Phillip Ma Lim, Tavis Jackson |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00019104 | Cisco Collaboration System Upgrade | Implementation/Deployment | 85% | 53.49% | 107.5 | 50 | 15157.5 | 7722.5 | 46.51% | 15157.5 | 0 | 57.5 | 592.5 | 0 |  | 7722.5 |  | 26240.1 | 25148.52 | 17426.02 | 69.29%
10/31/24 |  | 08/01/25 | Open | Marco Lish | Bryan Brown, Christopher Pheonix Preddy, Christopher Puyear, Warren Wilson |  | Beau C. Devillier, Christopher Garcia, Christopher Pheonix Preddy, Christopher Puyear, Kristy L Dice, Marco Lish, Warren Wilson |  |  | Marco Lish |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00019346 | Install 6 Strobes at Vandagriff Elem | Planning/Design/Staging | 10% | 9.479% | 10.55 | 9.55 | 1365.95 | 125 | 90.52% | 1365.95 | 0 | 1 | 0 | 0 |  | 125 |  | 2138.1 | 3389.2 | 3264.2 | 96.31%
09/12/23 |  | 08/01/25 | Open | Marco Lish | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Christine A Hupe, Jason Espino, Larry Noble, Marco Lish, Neel Shah, Wyley Johnson |  |  | Jason Espino, Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00015227 | Ochin VPN | Implementation/Deployment | 0% | 0% | 0 | -36.5 | 0 | 5406.25 | 0% | 0 | 0 | 36.5 | 5406.25 | 0 |  | 5406.25 |  | 0 | 10250 | 4843.75 | 47.26%
02/14/24 |  | 08/01/25 | Open | Marco Lish | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Larry Noble, Marco Lish, Neel Shah, Sophia Quinter, Wyley Johnson |  |  | James Adams, Marco Lish, Mohammed Al-Shaikhli, Sophia Quinter |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00017473 | ISE Pilot | Implementation/Deployment | 70% | 29.36% | 841.25 | 597.25 | 121441.25 | 32841.25 | 71% | 121441.25 | 3 | 247 | 12473.75 | 0 |  | 32841.25 |  | 142139.8 | 218594 | 185752.75 | 84.98%
03/04/25 |  | 08/01/25 | Open | Marco Lish | Matthew Duncan |  | Marco Lish, Matthew Duncan, Neel Shah |  |  | Erick Nunez , Juan Saenz, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Public Works | 200002286 | N/A | Implementation/Deployment | 55% | 50.97% | 161.85 | 79.35 | 0 | 10910 | 49.03% | 0 | 0 | 82.5 | 0 | 0 |  | 10910 |  | 0 | 33830.4 | 22920.4 | 67.75%
04/28/25 |  | 08/01/25 | Open | Marco Lish | Ahmed Al-Zubaidi |  | Ahmed Al-Zubaidi, Marco Lish, Neel Shah |  |  | Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Public Works | 200002896 | N/A | Planning/Design/Staging | 5% | 2.425% | 10.31 | 10.06 | 0 | 31.25 | 97.58% | 0 | 0 | 0.25 | 0 | 0 |  | 31.25 |  | 2297.7 | 1909.2 | 1877.95 | 98.36%
08/12/24 |  | 08/01/25 | Open | Marco Lish | Kristian Martell, Mark J Chambliss |  | Kristian Martell, Larry Noble, Marco Lish, Mark J Chambliss, Neel Shah |  |  | Kristian Martell, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Public Works | J00018809 | COH- HITS HPW HPC IVR | Implementation/Deployment | 50% | 38.73% | 253.06 | 155.06 | 44791.75 | 16280 | 61.27% | 44791.75 | 0 | 98 | 8718.75 | 0 |  | 16280 |  | 110462 | 73906 | 57626 | 77.97%
04/01/25 |  | 08/01/25 | Open | Marco Lish | William Birdsong |  | John Johnson, Juan Pomares, Marco Lish, Vitalii Stepanchenko, William Birdsong, William Davenport |  |  | Caleb Henry, Carlo Enriquez, Gabriel Lantigua, Jayden Colon, John Johnson, Juan Pomares, Marco Lish, Quy Le, Samuel Gonzalez, Sean Cowhey, Vitalii Stepanchenko, Yonathan Fadel |  |  | William Davenport | TX-DAL | Prosper ISD | 200001644 | N/A | Implementation/Deployment | 70% | 113.1% | 892.95 | -71.3 | 74425.35 | 72022.5 | -7.985% | 74425.35 | 46 | 1010.25 | 2760 | 0 |  | 72022.5 |  | 1488888.69 | 111139.3 | 39116.8 | 35.2%
02/17/25 |  | 08/01/25 | Open | Marshall Chuck Pugh | Bryan Geoghan |  | Bryan Geoghan, Conner MacDonnell, John Stephen Kurkjian, Lauren J Kennewell, Marshall Chuck Pugh |  |  | Austen Howard, Carlo Enriquez, John Stephen Kurkjian, Kendall Walls, Marshall Chuck Pugh, Ryan Frankeberger, Yonathan Fadel |  |  | Lauren J Kennewell | TX-DAL | Lancaster ISD | 200001915 | N/A | Implementation/Deployment | 55% | 22.02% | 935.54 | 735.54 | 104819.9 | 26405 | 78.62% | 104819.9 | 6 | 206 | 360 | 0 |  | 26405 |  | 202335.47 | 181043.43 | 154638.43 | 85.42%
03/10/25 |  | 08/01/25 | Open | Marshall Chuck Pugh | Jacob Parks, Jeffrey Holman |  | Jacob Parks, Jeffery Alan Jorzig, Jeffery Jorzig, Jeffrey Holman, Lauren J Kennewell, Marshall Chuck Pugh , Romar Roca, Timothy Sean Marcyes |  |  | Jeffery Alan Jorzig, Marshall Chuck Pugh, Romar Roca, Timothy Sean Marcyes |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | 200002357 | N/A | Not started | 25% | 21.05% | 128.25 | 101.25 | 0 | 3475 | 78.95% | 0 | 0 | 27 | 0 | 0 |  | 3475 |  | 73026.8 | 30560 | 27085 | 88.63%
11/01/23 |  | 08/01/25 | Open | Marshall Chuck Pugh | Joshua Adam Engle, Majid Shirzadeh |  | Austen New LN: Howard Cockerham, Beau C. Devillier, Bradley Buchanan, Cason Spencer, Conner MacDonnell, Dante Torres, Dylan Pittsinger, Frank Jaimes, Jhon Genao, Joshua Adam Engle, Joshua Osgood, Juan Pomares, Karyn Hubbard, Kirk O'Guinn, Lauren J Kennewell, Majid Shirzadeh, Marshall Chuck Pugh , Noah Castleberry, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Tavis Jackson , Taylor Poole, Timothy Fain, Vitalii Stepanchenko, William Birdsong |  |  | Austen Howard, Bradley Buchanan, Bryce Evans, Carlo Enriquez, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Joan Brito, Joshua Hubbard, Joshua Osgood, Juan Pomares, Kebret Eshetu, Kirk O'Guinn, Marshall Chuck Pugh, Moises Rodriguez, Noah Castleberry, Noah Trump, Phillip Ma Lim, Quentin Sowels, Quy Le, Remijio Hernandez, Ryan Scott, Sean Cowhey, Vitalii Stepanchenko, William Chris Roome |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | J00016223 | Phase 1 - PESH & PWSH - C2 Network Equipment | Implementation/Deployment | 40% | 88.51% | 2095.46 | 313.03 | 173071.53 | 154943.3 | 14.94% | 173071.53 | 72.25 | 1854.68 | 133777.05 | 0 |  | 154943.3 |  | 4102124.01 | 269605.6 | 114662.3 | 42.53%
04/28/25 |  | 08/01/25 | Open | Marshall Chuck Pugh | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joel Hubbard, Kristy L Dice, Marshall Chuck Pugh , Remi Martinez-Montenegro, Richard Keith Arnst, Robert Lavender |  |  | Marshall Chuck Pugh, Richard Keith Arnst |  |  | Kristy L Dice | TX-DAL | Trinity River Authority | 200002895 | N/A | Planning/Design/Staging | 25% | 8.333% | 30 | 27.5 | 0 | 312.5 | 91.67% | 0 | 0 | 2.5 | 0 | 0 |  | 312.5 |  | 9568.46 | 4581.2 | 4268.7 | 93.18%
04/30/25 |  | 08/01/25 | Open | Marshall Chuck Pugh | Bryan Brown, Remi Martinez-Montenegro |  | Brian Newman, Brian Newman, Bryan Brown, Christopher Garcia, Joshua Osgood, Kristy L Dice, Marshall Chuck Pugh , Remi Martinez-Montenegro |  |  | N/A |  |  | Kristy L Dice | TX-DAL | Trinity River Authority | 200002914 | N/A | Planning/Design/Staging | 15% | 0% | 47.69 | 47.69 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 10896.05 | 8182 | 8182 | 100%
05/12/25 |  | 08/01/25 | Open | Richard Keith Arnst | Bryan Brown |  | Arcangelo Fanelli, Christopher Garcia, Richard Keith Arnst |  |  | Richard Keith Arnst |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200002963 | N/A | Planning/Design/Staging | 30% | 13.93% | 104.06 | 89.56 | 0 | 1812.5 | 86.07% | 0 | 0 | 14.5 | 0 | 0 |  | 1812.5 |  | 55819.93 | 18077.2 | 16264.7 | 89.97%
04/29/24 |  | 08/01/25 | Open | Robert McIver | Edward Padron |  | Christopher Prado, Diana Berger, Edward Padron, Erick Nunez , Michelle Bailey, Robert McIver, Xavier A Trevino |  |  | Anthony Lange, Bodie Schmidt, Christopher Prado, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, LaCraig Hollis, Matthew D'Ambrosio, Max Vaughn, Paul Serres, Phillip Capozzi, Reynaldo Del Valle, Robert McIver |  |  | Xavier A Trevino | TX-SOUT | IDEA FLORIDA INC. | J00018029 | 23-24 New Construction - IDEA Florida | Planning/Design/Staging | 35% | 193.2% | 107.94 | -89.56 | 13345.96 | 15410 | -82.97% | 13345.96 | 11 | 208.5 | 13465 | 391 |  | 15410 |  | 157496.97 | 16350.4 | 549.4 | 3.36%
11/01/24 |  | 08/01/25 | Open | Robert McIver | Edward Padron |  | Christopher Prado, Edward Padron, Robert McIver, Steve J Rodriguez, Xavier A Trevino |  |  | Christopher Prado |  |  | Xavier A Trevino | TX-SOUT | IDEA FLORIDA INC. | J00019351 | Lakeland Campus - Addl HW & Survey | Planning/Design/Staging | 35% | 8.969% | 44.6 | 40.6 | 5956.45 | 440 | 91.03% | 5956.45 | 0 | 4 | 0 | 0 |  | 440 |  | 19915.08 | 7902.4 | 7462.4 | 94.43%
06/18/25 |  | 08/01/25 | Open | Summer Abunaja | Mark J Chambliss |  | Mark J Chambliss, Neel Shah, Summer Abunaja |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200003100 | N/A | Planning/Design/Staging | 10% | 0% | 18.44 | 18.44 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1710 | 3257 | 3257 | 100%
08/01/23 |  | 08/01/25 | Open | Tray Giddens | David Escamilla |  | Aman Khan, Austen New LN: Howard Cockerham, Bradley Buchanan, Conner MacDonnell, Dante Torres, David Escamilla, Devin Moreno, Dustin Huffman, Frank Jaimes, Jeffery Giles, Jhon Genao, Juan Pomares, Kirk O'Guinn, Kurt Sell, Mohaymen Sodi, Noah Castleberry, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Ron Loge, Sean Cowhey, Tabais Prater, Tavis Jackson, Tray Giddens |  |  | Austen Howard, Carlo Enriquez, Devin Moreno, Jhon Genao, Justin Mitchell, Kanoa Parman, Kebret Eshetu, Kevin Curtis, Kirk O'Guinn, Kolawole Ayeni, Matthew D'Ambrosio, Mohaymen Sodi, Nicolas Garakani, Noah Trump, Patrick Shea Thompson, Phillip Ma Lim, Quy Le, Ron Loge, Sean Cowhey, Tabais Prater, Tray Giddens, William Chris Roome, Yonathan Fadel |  |  | Dustin Huffman | TX-HOU | Apache Corporation | J00016147 | Nexus Refresh | Implementation/Deployment | 50% | 130.9% | 373.4 | -95.85 | 49610.75 | 58927.5 | -25.67% | 49610.75 | 19.5 | 488.75 | 47760 | 20 |  | 58927.5 |  | 866896 | 78495 | 19547.5 | 24.9%
04/16/25 |  | 08/01/25 | Open | Tray Giddens | Chad Hart |  | Chad Hart, Dustin Huffman, Tray Giddens |  |  | Ahmed Jameel, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200002644 | N/A | Implementation/Deployment | 35% | 21.79% | 82.6 | 65.6 | 0 | 2250 | 79.42% | 0 | 1 | 18 | 125 | 0 |  | 2250 |  | 142220.2 | 10309.6 | 8059.6 | 78.18%
05/12/25 |  | 08/01/25 | Open | Tray Giddens | N/A |  | Chad Hart, Dustin Huffman, Tray Giddens |  |  | Abdalsattar Albaghdadi, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200002962 | N/A | Planning/Design/Staging | 20% | 13.02% | 57.62 | 50.12 | 0 | 937.5 | 86.98% | 0 | 0 | 7.5 | 0 | 0 |  | 937.5 |  | 20518.1 | 6875.2 | 5937.7 | 86.36%
09/26/24 |  | 08/01/25 | Open | Tray Giddens | David Escamilla |  | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Kurt Sell, Tray Giddens |  |  | Cory Bradfield, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Galveston County | J00019097 | VMware Services | Implementation/Deployment | 50% | 77.65% | 106.25 | 23.75 | 14981.25 | 10987.5 | 22.35% | 14981.25 | 0 | 82.5 | 800 | 0 |  | 10987.5 |  | 0 | 23711.6 | 12724.1 | 53.66%
05/27/24 |  | 08/01/25 | Open | Tray Giddens | Mark J Chambliss |  | Ashley F Freeman, Larry Noble, Mark J Chambliss, Ming Chiu, Tray Giddens |  |  | Ming Chiu, Tray Giddens |  |  | Ashley F Freeman | TX-HOU | Harris County Auditor | J00018351 | UC Upgrade | Implementation/Deployment | 50% | 55.74% | 117.5 | 52 | 16567.5 | 8937.5 | 44.26% | 16567.5 | 0 | 65.5 | 6787.5 | 0 |  | 8937.5 |  | 0 | 25859.4 | 16921.9 | 65.44%
04/14/25 |  | 08/01/25 | Closed | William Chris Roome | George Edwin Jacob |  | George Edwin Jacob, Jonathan Pendrich, William Chris Roome, William Roome |  |  | N/A |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | 200002653 | N/A | Not started | 0% | 0% | 84 | 84 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2894478.68 | 1812972.64 | 1812972.64 | 100%
03/11/25 |  | 08/05/25 | Open | Robert McIver | Christopher Ceykovsky |  | Christopher Ceykovsky, Daniel Saenz, George McGann, Hamzeh Tahat, Robert McIver |  |  | George McGann, Hamzeh Tahat, Robert McIver |  |  | Daniel Saenz | TX-SOUT | City of Laredo | 200002365 | N/A | Planning/Design/Staging | 35% | 50% | 40 | 20 | 0 | 2360 | 50% | 0 | 0 | 20 | 0 | 1265 |  | 2360 |  | 13911.72 | 7691.76 | 4066.76 | 52.87%
02/06/25 |  | 08/06/25 | Open | Abiodun David Babasola | Bryan Geoghan |  | Abiodun David Babasola, Bryan Geoghan, David Babasola, Thomas Francis LoMonaco, William Davenport |  |  | Abiodun David Babasola, Anthony Towsley, Luis Ovalles, Thomas Francis LoMonaco |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | 200001711 | N/A | Training/Knowledge Transfer/Documentation | 95% | 103.5% | 72 | -2.5 | 10152 | 12882.5 | -3.472% | 10152 | 0 | 74.5 | 0 | 0 |  | 12882.5 |  | 0 | 13857.2 | 974.7 | 7.034%
03/12/25 |  | 08/07/25 | Open | Robert McIver | Edward Padron |  | Daniel Saenz, Edward Padron, Robert McIver, Ruben Cantu |  |  | Felix Martinez, Francisco Hernandez, Robert McIver, Ruben Cantu |  |  | Daniel Saenz | TX-SOUT | Cameron County | 200002349 | N/A | Planning/Design/Staging | 30% | 33.5% | 64.92 | 45.17 | 0 | 2572.5 | 69.58% | 0 | 2 | 21.75 | 185 | 0 |  | 2572.5 |  | 34458.06 | 8724.8 | 6152.3 | 70.52%
03/20/25 |  | 08/07/25 | Open | Robert McIver | Edward Padron |  | Daniel Saenz, Edward Padron, Robert McIver, Ruben Cantu |  |  | Felix Martinez, Francisco Hernandez, Robert McIver, Ruben Cantu |  |  | Daniel Saenz | TX-SOUT | Cameron County | 200002433 | N/A | Planning/Design/Staging | 30% | 46.62% | 71.32 | 40.07 | 0 | 4010 | 56.18% | 0 | 2 | 33.25 | 185 | 0 |  | 4010 |  | 35288.57 | 45831.76 | 41821.76 | 91.25%
06/04/25 |  | 08/08/25 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, David Babasola, Joshua Parker, Michael Brett Beggs, Tony Dean Skipworth |  |  | Abiodun David Babasola, Tony Dean Skipworth |  |  | Joshua Parker | TX-DAL | Waxahachie ISD | 200002983 | N/A | Planning/Design/Staging | 5% | 29.12% | 58.38 | 41.38 | 0 | 2280 | 70.88% | 0 | 0 | 17 | 0 | 0 |  | 2280 |  | 21242.52 | 10994.8 | 8714.8 | 79.26%
06/09/25 |  | 08/08/25 | Open | Brian Willery | David Escamilla |  | Brian Willery, David Escamilla, Jaclyn Pias |  |  | Brian Willery, Frank Jaimes, Jalen Vecchitto, Ron Loge |  |  | Jaclyn Pias | TX-HOU | AIS Portfolio Services | 200003066 | N/A | Planning/Design/Staging | 5% | 40% | 43.75 | 30.25 | 0 | 1901.25 | 69.14% | 0 | 4 | 17.5 | 470 | 0 |  | 1901.25 |  | 251413.55 | 11000 | 9098.75 | 82.72%
03/10/25 |  | 08/08/25 | Open | Brian Willery | Jacob Parks, Jeffrey Holman, Majid Shirzadeh |  | Brian Willery, Jacob Parks, Jeffrey Holman, Lauren J Kennewell, Majid Shirzadeh, Sophia Quinter, William Birdsong |  |  | Brian Willery, Luis Ovalles, Saravanan Lakshmanan, Sophia Quinter, Vitalii Stepanchenko |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | 200002342 | N/A | Planning/Design/Staging | 20% | 27.33% | 362.23 | 263.23 | 0 | 13047.5 | 72.67% | 0 | 0 | 99 | 0 | 0 |  | 13047.5 |  | 0 | 83019.2 | 69971.7 | 84.28%
06/26/25 |  | 08/08/25 | Closed | Jason Esry | Albert H Nguyen |  | Albert H Nguyen, Jason Esry, Susan Richardson |  |  | N/A |  |  | Susan Richardson | TX-HOU | Pasadena ISD | 200003119 | N/A | Not started | 0% | 0% | 84.83 | 84.83 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 87551.4 | 9021.28 | 9021.28 | 100%
10/21/24 |  | 08/08/25 | Open | Jennifer Soliz | Jacob Parks |  | Jacob Parks, Jason Espino, Jennifer Soliz, Larry Noble, Lonnie Owens |  |  | Jason Espino, Jennifer Soliz, Marshall Chuck Pugh |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00019254 | VPN Encryption Enhancement | Implementation/Deployment | 75% | 29.52% | 105 | 74 | 15225 | 4181.25 | 70.48% | 15225 | 0 | 31 | 0 | 0 |  | 4181.25 |  | 0 | 23979.2 | 19797.95 | 82.56%
06/25/25 |  | 08/08/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002976 | N/A | Planning/Design/Staging | 5% | 2.5% | 20 | 19.5 | 0 | 62.5 | 97.5% | 0 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 3950.04 | 2509.6 | 2447.1 | 97.51%
05/20/24 |  | 08/08/25 | Open | Joaquin Marroquin | Emilio Carrillo, Timothy Ramsey |  | Emilio Carrillo, Ernesto Gonzalez, Jacob Parks, Joaquin Marroquin, Larry Noble, Lonnie Owens, Quoc Nguyen, Romar Roca, Timothy Ramsey |  |  | An Le, Celso Lopez, Cory Bradfield, Dustin Aaron Lowrey, Eric Firestone, Ernesto Gonzalez, Joaquin Marroquin, John Senkulics, Kevin Curtis, Kolawole Ayeni, Michael Torres, Mohammed Almoola, Paul Serres, Romar Roca |  |  | Lonnie Owens | TX-CEN | Boerne ISD | J00018325 | IDF Additions | On HOLD | 65% | 71.66% | 521.92 | 147.92 | 54679.02 | 42576.25 | 28.34% | 54679.02 | 0 | 374 | 8005 | 0 |  | 42576.25 |  | 193206.93 | 83021.96 | 40445.71 | 48.72%
06/03/25 |  | 08/08/25 | Open | Marshall Chuck Pugh | Jacob Parks, Jeffrey Holman |  | Abdulrahman Farhan, Conner MacDonnell, Jacob Parks, Jeffrey Holman, Kristy L Dice, Marshall Chuck Pugh, Romar Roca |  |  | Marshall Chuck Pugh, Romar Roca |  |  | Kristy L Dice | TX-DAL | Highland Park ISD | 200003043 | N/A | Implementation/Deployment | 50% | 41.83% | 76.5 | 44.5 | 0 | 4700 | 58.17% | 0 | 0 | 32 | 0 | 0 |  | 4700 |  | 288252.91 | 15168.28 | 10468.28 | 69.01%
05/19/25 |  | 08/08/25 | Open | Marshall Chuck Pugh | Bryan Geoghan |  | Brian Newman, Brian Newman, Bryan Geoghan, Lauren J Kennewell, Marshall Chuck Pugh |  |  | Brian Newman, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | 200002986 | N/A | Planning/Design/Staging | 10% | 2.603% | 576.25 | 561.25 | 0 | 1920 | 97.4% | 0 | 0 | 15 | 0 | 0 |  | 1920 |  | 0 | 94664.88 | 92744.88 | 97.97%
04/15/25 |  | 08/08/25 | Open | Richard Keith Arnst | Bryan Brown, Remi Martinez-Montenegro |  | Arcangelo Fanelli, Christopher Garcia, Remi Martinez-Montenegro, Richard Keith Arnst |  |  | Richard Keith Arnst |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200002677 | N/A | Implementation/Deployment | 50% | 17.61% | 68.13 | 56.13 | 0 | 1500 | 82.39% | 0 | 0 | 12 | 0 | 0 |  | 1500 |  | 29940.67 | 14907.2 | 13407.2 | 89.94%
06/12/23 |  | 08/08/25 | Open | Robert McIver | Edward Padron, Rogelio Dominguez |  | Aldo Cortes, Christopher Prado, Robert McIver, Xavier A Trevino |  |  | N/A |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00015786 | River Bluff- Gym AP | On HOLD | 5% | 0% | 45.68 | 45.68 | 4970.7 | 0 | 100% | 4970.7 | 0 | 0 | 0 | 2944.55 |  | 0 |  | 0 | 7475.2 | 4530.65 | 60.61%
04/28/25 |  | 08/08/25 | Open | Tray Giddens | Aman Khan |  | Aman Khan, Dustin Huffman, Tray Giddens |  |  | Daniel Hernandez, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Gunvor USA LLC | 200002875 | N/A | Planning/Design/Staging | 5% | 13.71% | 43.75 | 38.75 | 0 | 620 | 88.57% | 0 | 1 | 6 | 60 | 0 |  | 620 |  | 983.92 | 6463.2 | 5843.2 | 90.41%
03/24/25 |  | 08/08/25 | Open | Walter Clay Knight | David Escamilla |  | Ashley F Freeman, Cory Bradfield, Cory Bradfield, David Escamilla, Moe Izaks, Walter Clay Knight |  |  | Cory Bradfield, Craig St. Rose, Justin Cornish, Walter Clay Knight |  |  | Ashley F Freeman | TX-HOU | Harris County Toll Road Authority | 200002488 | N/A | Implementation/Deployment | 85% | 50.01% | 296.94 | 164.94 | 0 | 17115 | 55.55% | 0 | 16.5 | 148.5 | 1852.5 | 0 |  | 17115 |  | 2498811.16 | 61174 | 44059 | 72.02%
10/23/24 |  | 08/11/25 | Open | Ryan Scott | Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Ryan Scott, Tony Dean Skipworth |  |  | Bryan Mullen, Devin Moreno, Noah Castleberry, Ryan Scott, Tony Dean Skipworth |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00019061 | DC: ACI - APIC Refresh | On HOLD | 20% | 43.33% | 67.5 | 39.25 | 7575.69 | 3676.25 | 58.15% | 7575.69 | 1 | 29.25 | 247.5 | 0 |  | 3676.25 |  | 0 | 16532.8 | 12856.55 | 77.76%
03/24/25 |  | 08/11/25 | Open | Summer Abunaja | Jacob Parks, Jeffrey Holman |  | Ibrahim Altaweel, Jacob Parks, Jeffrey Holman, Jerome Tanyag Mara, Rogelio Morgado-Perez, Summer Abunaja, Taylor Leger, Tom Magboo |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, Mohammad Arman, Rogelio Morgado-Perez, Summer Abunaja, Tom Magboo |  |  | Taylor Leger | TX-DAL | Forney ISD | 200002461 | N/A | Training/Knowledge Transfer/Documentation | 100% | 96.18% | 131 | 5 | 0 | 17550 | 3.817% | 0 | 0 | 126 | 0 | 0 |  | 17550 |  | 0 | 12256.8 | -5293.2 | -43.19%
05/06/24 |  | 08/15/25 | Open | Abiodun David Babasola | Bryan Geoghan, Edward Padron |  | Abiodun David Babasola, Bryan Geoghan, Daniel Saenz, David Babasola, Diana Berger, Edward Padron, Eric Rodriguez, Samuel Newland |  |  | Abiodun David Babasola, Samuel Newland |  |  | Eric Rodriguez | TX-SOUT | Harlingen CISD | J00018244 | Singlewire & Speaker Deploy Ph II | Implementation/Deployment | 0% | 0% | 0 | -1.5 | 0 | 210 | 0% | 0 | 0 | 1.5 | 210 | 0 |  | 210 |  | 229204.6 | 75039 | 74829 | 99.72%
05/06/24 |  | 08/15/25 | Open | Abiodun David Babasola | Bryan Geoghan, Edward Padron |  | Abiodun David Babasola, Bryan Geoghan, Daniel Saenz, David Babasola, Diana Berger, Edward Padron, Eric Rodriguez, Samuel Newland |  |  | Abiodun David Babasola, Samuel Newland |  |  | N/A | N/A | Harlingen CISD | J00018244 | Singlewire & Speaker Deploy Ph II | Implementation/Deployment | 40% | 14.02% | 171.21 | 147.21 | 24140.65 | 3075 | 85.98% | 24140.65 | 0 | 24 | 0 | 0 |  | 3075 |  | 229204.6 | 75039 | 71964 | 95.9%
06/10/25 |  | 08/15/25 | Closed | Brian Willery | Wyley Johnson |  | Brian Willery, Jessica Anderson, Wyley Johnson |  |  | N/A |  |  | Jessica Anderson | US-SP | Bluegrass Network | 200003071 | N/A | Not started | 0% | 0% | 43.7 | 43.7 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 9426 | 9426 | 100%
05/16/25 |  | 08/15/25 | Open | Brian Willery | David Goss, Steven Walker |  | Brian Willery, David Goss, Jason Osuna, Steven Walker |  |  | Brian Willery |  |  | Jason Osuna | TX-CEN | Buc-ee's, LTD | 200002979 | N/A | Planning/Design/Staging | 5% | 3.296% | 106.2 | 102.7 | 0 | 437.5 | 96.7% | 0 | 0 | 3.5 | 0 | 0 |  | 437.5 |  | 349374.3 | 153470.56 | 153033.06 | 99.71%
07/16/24 |  | 08/15/25 | Open | Jennifer Soliz | Daniel Snyder |  | Daniel Snyder, Jennifer Soliz, Larry Noble, Lonnie Owens, Raul Velazquez, Shannon Marie Alvarado |  |  | Jennifer Soliz, Raul Velazquez |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00018291 | Cisco Nexus 7718 Switch Decommission | Implementation/Deployment | 65% | 85.3% | 318.6 | 56.1 | 5387.5 | 33968.75 | 17.61% | 5387.5 | 9.25 | 271.75 | 22781.25 | 0 |  | 33968.75 |  | 0 | 55830 | 21861.25 | 39.16%
06/19/25 |  | 08/15/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003107 | N/A | Planning/Design/Staging | 5% | 9.524% | 10.5 | 9.5 | 0 | 125 | 90.48% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 14429.08 | 5490.67 | 5365.67 | 97.72%
02/10/25 |  | 08/15/25 | Open | Lauren Lanzini Coffey | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Ashutosh Patel, Lauren Lanzini Coffey, Neel Shah, Wyley Johnson |  |  | Ashutosh Patel, Lauren Lanzini Coffey |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200001918 | N/A | Planning/Design/Staging | 10% | 38.77% | 657 | 402.25 | 96725 | 38143.75 | 61.23% | 96725 | 0 | 254.75 | 0 | 0 |  | 38143.75 |  | 0 | 144724.4 | 106580.65 | 73.64%
10/21/24 |  | 08/15/25 | Open | Marshall Chuck Pugh | Bryan Brown, Bryan Geoghan |  | Beau C. Devillier, Brian Newman, Brian Newman, Bryan Geoghan, Christopher Garcia, Joel Hubbard, Karyn Hubbard, Lauren J Kennewell, Marshall Chuck Pugh |  |  | Brian Newman, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | J00019252 | Atlas/Singlewire Implementation - Bowman MS | Planning/Design/Staging | 25% | 20.85% | 106.69 | 84.44 | 13918.05 | 3051.25 | 79.15% | 13918.05 | 0 | 22.25 | 125 | 0 |  | 3051.25 |  | 94553.56 | 57513.4 | 54462.15 | 94.69%
08/30/21 |  | 08/15/25 | Open | Ryan Scott | David Watkins |  | Arcangelo Fanelli, Bryan Mullen, Jonathan Weir, Jonathan Weir, Mohaymen Sodi, Ryan Scott, Taylor Leger |  |  | Bryan Mullen, Jonathan Weir, Mohaymen Sodi, Ryan Scott |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00011276 | NPH - SDA Deployment | Implementation/Deployment | 70% | 672.9% | 139.7 | -800.3 | 13271.5 | 89300 | -572.9% | 13271.5 | 0 | 940 | 62201.25 | 57.71 |  | 89300 |  | 46138.2 | 68756 | -20601.71 | -29.96%
05/22/25 |  | 08/15/25 | Open | Walter Clay Knight | N/A |  | Alexander Gutman, Bryan Geoghan, John Stephen Kurkjian, Walter Clay Knight |  |  | John Stephen Kurkjian, Walter Clay Knight |  |  | Alex Gutman | TX-DAL | Tyler Junior College | 200003003 | N/A | Planning/Design/Staging | 30% | 8.675% | 103.75 | 94.75 | 0 | 1230 | 91.33% | 0 | 0 | 9 | 0 | 0 |  | 1230 |  | 0 | 24576 | 23346 | 95%
04/07/25 |  | 08/18/25 | Closed | Ryan Scott | David Watkins |  | David Watkins, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | N/A |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200002159 | N/A | Planning/Design/Staging | 25% | 0% | 4 | 4 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 180653.1 | 180653.1 | 100%
02/17/25 |  | 08/19/25 | Open | Ryan Scott | David Watkins |  | Christopher Prado, David Watkins, Karen Grant-Dennison, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Ahmed Jameel, David Neal Gravatt, Devin Moreno, Jeffery Giles, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Matthew Veach, Paul Serres, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200000260 | N/A | Planning/Design/Staging | 30% | 16.55% | 1302.13 | 1086.63 | 131653.15 | 25948.75 | 83.45% | 131653.15 | 0 | 215.5 | 0 | 0 |  | 25948.75 |  | 376872.1 | 214264.8 | 188316.05 | 87.89%
04/03/25 |  | 08/21/25 | Open | Abiodun David Babasola | George Edwin Jacob |  | Abiodun David Babasola, David Babasola, George Edwin Jacob, Lauren J Kennewell, Ron Loge, Timothy Fain |  |  | Abiodun David Babasola, Austen Howard, Brycen Dimas, Dante Torres, Remijio Hernandez, Ron Loge |  |  | Lauren J Kennewell | TX-DAL | Duncanville ISD | 200002471 | N/A | Planning/Design/Staging | 50% | 31.18% | 242.97 | 171.72 | 0 | 9826.25 | 70.68% | 0 | 4.5 | 75.75 | 442.5 | 0 |  | 9826.25 |  | 992618.73 | 50096.3 | 40270.05 | 80.39%
04/30/25 |  | 08/22/25 | Open | Abiodun David Babasola | N/A |  | Abiodun David Babasola, David Babasola, Joshua Parker |  |  | Aboobiada Ali Abdalla, Andrew Comeaux, David Lenihan, Gerardo Ramirez, Gregory Posey, Harold Gomez, Jarshawn Newsome, Josue Iglesias, Kai Rose , Lorenzo Hernandez, Nathanael Morales, Pedro Cavazos, Samsoni Jean Claude, Steffany Alvarez, Valentin Vasquez, Walter Hanchett |  |  | Joshua Parker | TX-DAL | Richardson ISD | 200002702 | N/A | Implementation/Deployment | 0% | 0% | 0 | -759.75 | 0 | 22792.5 | 0% | 0 | 0 | 759.75 | 0 | 0 |  | 22792.5 |  | 2806090 | 879340 | 856547.5 | 97.41%
08/20/24 |  | 08/22/25 | Open | Christina Rice | David Watkins, Jacob Parks, Jeffrey Holman |  | Calvin Darby, Carlo Enriquez, Christina Rice, Christina Rice, Christopher Puyear, Conner MacDonnell, David Watkins, Jacob Parks, Jeffrey Holman, Jonathan Weir, Jonathan Weir, Juan Pomares, Schfronda Ford, Shawn Sutton, Taylor Poole, Zachary Neal Newman, Zachary Newman |  |  | Austen Howard, Bryan Mullen, Caleb Henry, Calvin Darby, Carlo Enriquez, Christina Rice, Dante Torres, Frank Jaimes, Gabriel Lantigua, Jacob Hill, Jalen Vecchitto, Jayden Colon, Jhon Genao, John Johnson, Jonathan Weir, Juan Pomares, Kendall Walls, Noah Trump, Quy Le, Ryan Frankeberger, Samuel Gonzalez, Sean Cowhey, Tavis Jackson, Yonathan Fadel, Zachary Neal Newman |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00018592 | Denton ISD: 2024 ERate/Bond SW Refresh - ESs | Implementation/Deployment | 55% | 60.48% | 2619.98 | 1094.48 | 230278.21 | 141386.25 | 41.77% | 230278.21 | 59 | 1584.5 | 24926.25 | 0 |  | 141386.25 |  | 3471058.42 | 286287.1 | 144900.85 | 50.61%
10/28/24 |  | 08/22/25 | Open | Jason Matthew Davis | Kristian Martell |  | Cory E Hopf, Cory Hopf, Jason Matthew Davis, Kristian Martell, Larry Noble, Michael B Griffin, Neel Shah |  |  | Jason Matthew Davis, Kalim Qamar, Patrick Joseph Palermo |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00019325 | PCCE Upgrade - Mitchell 1 | Planning/Design/Staging | 35% | 34.73% | 390.1 | 254.6 | 0 | 24250 | 65.27% | 0 | 0 | 135.5 | 315 | 0 |  | 24250 |  | 0 | 81144.4 | 56894.4 | 70.12%
02/07/25 |  | 08/22/25 | Open | Jason Matthew Davis | Mark J Chambliss |  | Jason Matthew Davis, Lonnie Owens, Mark J Chambliss, Patrick Joseph Palermo, Thomas Francis LoMonaco |  |  | Jason Matthew Davis, Patrick Joseph Palermo |  |  | Lonnie Owens | TX-CEN | John Hagee Ministries | 200001669 | N/A | Planning/Design/Staging | 60% | 34.28% | 414.24 | 272.24 | 62834.65 | 25777.5 | 65.72% | 62834.65 | 0 | 142 | 0 | 0 |  | 25777.5 |  | 55808.42 | 98964 | 73186.5 | 73.95%
05/22/25 |  | 08/22/25 | Open | Jim Blackwell | Ahmed Al-Zubaidi |  | Ahmed Al-Zubaidi, Ashley F Freeman, Ibrahim Altaweel, Jim Blackwell, Moe Izaks, Rogelio Morgado-Perez |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, Jim Blackwell, Rogelio Morgado-Perez, Tom Magboo |  |  | Ashley F Freeman | TX-HOU | Katy ISD | 200002996 | N/A | Implementation/Deployment | 10% | 15.84% | 221 | 186 | 0 | 5125 | 84.16% | 0 | 0 | 35 | 0 | 0 |  | 5125 |  | 0 | 23574.6 | 18449.6 | 78.26%
02/27/25 |  | 08/22/25 | Open | Marshall Chuck Pugh | William Birdsong |  | Mark Forehand, Marshall Chuck Pugh , Vitalii Stepanchenko, William Birdsong |  |  | Marshall Chuck Pugh, Vitalii Stepanchenko |  |  | Mark Forehand | TX-DAL | RENT-A-CENTER, INC | 200002193 | N/A | Planning/Design/Staging | 20% | 8.947% | 181.63 | 165.38 | 0 | 2031.25 | 91.05% | 0 | 0 | 16.25 | 0 | 0 |  | 2031.25 |  | 319306.5 | 29348.8 | 27317.55 | 93.08%
03/17/25 |  | 08/22/25 | Open | Robert McIver | Warren Wilson |  | Conner MacDonnell, Daniel Saenz, Edward Padron, Felix Martinez, Garrett Hart, Jaime Galvan, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Kolawole Ayeni, Oscar Garcia, Quoc Nguyen, Robert McIver, Roger Guerra, Taylor Poole, Trevor Galloso |  |  | Francisco Hernandez, Garrett Hart, Jaime Galvan, Joaquin Garcia, Jonathan Pina, Jorge Robert Rangel, Robert McIver, Roger Guerra, Trevor Galloso |  |  | Daniel Saenz | TX-SOUT | La Joya ISD | 200002413 | N/A | Implementation/Deployment | 95% | 26.17% | 1277.14 | 943.14 | 0 | 25552.5 | 73.85% | 0 | 0.25 | 334.25 | 15 | 0 |  | 25552.5 |  | 690363.73 | 694073.6 | 668521.1 | 96.32%
12/10/24 |  | 08/22/25 | Open | Ryan Scott | David Watkins |  | David Watkins, Mario Sanchez, Matthew Veach, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Conner MacDonnell, Jeffery Giles, Joshua Hubbard, Mario Sanchez, Matthew Veach, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200000154 | N/A | Planning/Design/Staging | 35% | 20.54% | 1854.5 | 1475 | 188046.44 | 45312.5 | 79.54% | 188046.44 | 1.5 | 381 | 90 | 0 |  | 45312.5 |  | 0 | 312150 | 266837.5 | 85.48%
08/23/24 |  | 08/22/25 | Open | Summer Abunaja | N/A |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, Summer Abunaja |  |  | Henry Pugsley, Ming Chiu |  |  | Arcangelo Fanelli | TX-DAL | BEPCO, LP | J00018895 | AAAQ435235-04 | Not started | 0% | 0% | 0 | -10 | 0 | 1435 | 0% | 0 | 0 | 10 | 280 | 0 |  | 1435 |  | 0 | 0 | -1435 | 0%
04/04/25 |  | 08/22/25 | Open | Tray Giddens | Steven Walker |  | Christopher Brown, Christopher Brown, Dustin Huffman, Steven Walker, Tray Giddens |  |  | Christopher Brown, Tray Giddens |  |  | Dustin Huffman | TX-HOU | City of League City | 200002600 | N/A | Planning/Design/Staging | 5% | 45.45% | 55 | 30 | 0 | 3295 | 54.55% | 0 | 0 | 25 | 0 | 0 |  | 3295 |  | 0 | 11520.8 | 8225.8 | 71.4%
08/01/24 |  | 08/25/25 | Open | Ryan Scott | Bryan Geoghan |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, Christopher Garcia, Ryan Scott, Samuel Newland |  |  | Ryan Scott, Samuel Newland |  |  | Arcangelo Fanelli | TX-DAL | Fossil Group, Inc | J00018648 | Voice Gateway Replacement and Refresh | Implementation/Deployment | 70% | 77.7% | 76.25 | 17 | 10751.25 | 8111.25 | 22.3% | 10751.25 | 0 | 59.25 | 3923.75 | 0 |  | 8111.25 |  | 0 | 22577.6 | 14466.35 | 64.07%
06/21/23 |  | 08/25/25 | Open | Walter Clay Knight | Robert V Eubanks, Todd Melby |  | Eduardo Chavez, Garrett Curran, Liberty Reyes Tumibay, Robert V Eubanks, Todd Melby, Yong Kim |  |  | LaQisha Marshall, Lauren Lanzini Coffey, Liberty Reyes Tumibay, Nick Varga, Rafael Rodriguez-Vargas, Todd Melby, Walter Clay Knight |  |  | Garrett Curran | CA-LAX | City of Perris | J00015764 | Private LTE | Training/Knowledge Transfer/Documentation | 95% | 75.54% | 855.48 | 209.23 | 71941.46 | 83141.25 | 24.46% | 71941.46 | 0 | 646.25 | 64993.75 | 253.78 |  | 83141.25 |  | 783852.42 | 425288.58 | 341893.55 | 80.39%
06/26/25 |  | 08/26/25 | Closed | Shannon Marie Alvarado | Mark J Chambliss |  | Lindie Lorraine Lamar, Mark J Chambliss, Shannon Marie Alvarado |  |  | N/A |  |  | Lindie Lamar | TX-HOU | Westlake Corporation | 200003126 | N/A | Not started | 0% | 0% | 85 | 85 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 16690.52 | 14943.6 | 14943.6 | 100%
08/29/23 |  | 08/28/25 | Closed | Summer Abunaja | N/A |  | Jeff Barker, Mark Forehand, Sophia Quinter, Summer Abunaja, William Davenport |  |  | Sophia Quinter |  |  | Mark Forehand | TX-DAL | Prosper ISD | J00016408 | NO PO AAAQ408032 | Closed | 0% | 0% | 0 | -14.5 | 0 | 2175 | 0% | 0 | 0 | 14.5 | 2175 | 0 |  | 2175 |  | 0 | 0 | -2175 | 0%
06/02/25 |  | 08/29/25 | Closed | Brian Willery | N/A |  | Brian Willery, Jacob Parks, Jeffrey Holman, Lauren J Kennewell |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | 200003041 | N/A | Not started | 0% | 0% | 85.8 | 85.8 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 106764 | 18572.8 | 18572.8 | 100%
06/02/25 |  | 08/29/25 | Closed | Brian Willery | N/A |  | Aaron Christopher Pfeifer, Brian Willery, George Delp, Jessica Anderson, Rafael Rodriguez-Vargas |  |  | N/A |  |  | Jessica Anderson | US-SP | Duo County Telephone Coop | 200003033 | N/A | Not started | 0% | 0% | 50.4 | 50.4 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 9878.4 | 9878.4 | 100%
07/29/24 |  | 08/29/25 | Open | Brian Willery | Bryan Geoghan |  | Beau C. Devillier, Brian Willery, Bryan Geoghan, Lauren J Kennewell |  |  | Austen Howard, Brian Willery, Dante Torres, Joshua Hubbard, Kendall Walls, Noah Trump, Patrick Joseph Palermo, Remijio Hernandez, Ryan Frankeberger, Thomas Francis LoMonaco, Vitalii Stepanchenko |  |  | Lauren J Kennewell | TX-DAL | McKinney ISD | J00018759 | Cloud Calling Migration | Planning/Design/Staging | 40% | 33.5% | 1588.65 | 1057.4 | 194173.15 | 85885 | 66.56% | 194173.15 | 1 | 532.25 | 20806.25 | 0 |  | 85885 |  | 4995.13 | 303539.2 | 217654.2 | 71.71%
06/03/25 |  | 08/29/25 | Open | Brittney Antoinette Hickman | Bryan Geoghan, David Watkins |  | Arcangelo Fanelli, Brittney Antoinette Hickman, Bryan Geoghan, Bryan Mullen, David Watkins, Erick Sanchez |  |  | Brittney Antoinette Hickman, Bryan Mullen, Noah Trump |  |  | Arcangelo Fanelli | TX-DAL | Fort Worth ISD | 200003023 | N/A | Planning/Design/Staging | 10% | 2.697% | 1575.97 | 1533.47 | 0 | 3687.5 | 97.3% | 0 | 0 | 42.5 | 0 | 0 |  | 3687.5 |  | 1833518.1 | 257428.1 | 253740.6 | 98.57%
03/17/25 |  | 08/29/25 | Open | Brittney Antoinette Hickman | Ahmed Al-Zubaidi, David Watkins, Wyley Johnson |  | Ahmed Al-Zubaidi, Ahmed Jameel, Ben Crouch, Brittney Antoinette Hickman, Christine A Hupe, David Watkins, Eric Firestone, Magdalena Rodriguez, Moises Rodriguez, Neel Shah, Nelson Garcia, Wyley Johnson |  |  | Ahmed Jameel, Ben Crouch, Brittney Antoinette Hickman, Craig St. Rose, Eric Firestone, James Adams, Justin Cornish, Kevin Curtis, Matthew D'Ambrosio, Moises Rodriguez, Nathan Dao, Nelson Garcia, Paul Serres |  |  | Neel Shah | TX-HOU | Lone Star College System | 200002372 | N/A | Planning/Design/Staging | 25% | 12.25% | 3461.25 | 3046.75 | 0 | 57312.5 | 88.02% | 0 | 9.5 | 424 | 570 | 0 |  | 57312.5 |  | 1000272 | 630012 | 572699.5 | 90.9%
06/03/25 |  | 08/29/25 | Open | Christina Rice | N/A |  | Christina Rice, Christina Rice, Christopher Puyear, David Watkins, Shawn Sutton |  |  | Christina Rice |  |  | Shawn Sutton | TX-DAL | Denton ISD | 200003059 | N/A | Planning/Design/Staging | 0% | 1.979% | 151.63 | 148.63 | 0 | 375 | 98.02% | 0 | 0 | 3 | 0 | 0 |  | 375 |  | 70273.88 | 24455.32 | 24080.32 | 98.47%
04/29/25 |  | 08/29/25 | Open | Christina Rice | Bryan Geoghan |  | Bryan Geoghan, Christina Rice, Christina Rice, Shawn Sutton |  |  | Dante Torres, Ryan Frankeberger |  |  | Shawn Sutton | TX-DAL | Northwest ISD | 200002645 | N/A | Implementation/Deployment | 10% | 6.861% | 120.25 | 114.25 | 0 | 495 | 95.01% | 0 | 2.25 | 8.25 | 135 | 0 |  | 495 |  | 75668.4 | 16690.6 | 16195.6 | 97.03%
05/19/25 |  | 08/29/25 | Open | Christina Rice | Joshua Adam Engle |  | Christina Rice, Christina Rice, Joshua Adam Engle, Mark Forehand, Ron Loge, Vitalii Stepanchenko |  |  | Christina Rice, Ron Loge, Vitalii Stepanchenko |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | 200002700 | N/A | Not started | 0% | 17.65% | 188.35 | 156.6 | 0 | 4306.25 | 83.14% | 0 | 1.5 | 33.25 | 187.5 | 0 |  | 4306.25 |  | 217927.2 | 37933.6 | 33627.35 | 88.65%
02/17/25 |  | 08/29/25 | Open | Jason Esry | Aman Khan |  | Aman Khan, David D Tijerina, Ernesto Gonzalez, Jason Esry |  |  | Ernesto Gonzalez, Jason Esry, Michael Torres |  |  | David D Tijerina | TX-CEN | San Antonio ISD | 200002039 | N/A | Planning/Design/Staging | 15% | 80% | 30 | 6 | 0 | 2902.5 | 20% | 0 | 0 | 24 | 0 | 0 |  | 2902.5 |  | 96745.86 | 15087.8 | 12185.3 | 80.76%
03/19/25 |  | 08/29/25 | Open | Jason Esry | Aman Khan |  | Aman Khan, David D Tijerina, Jason Esry |  |  | Jason Esry, Michael Torres |  |  | David D Tijerina | TX-CEN | San Antonio ISD | 200002315 | N/A | Planning/Design/Staging | 0% | 6.15% | 252.02 | 236.52 | 0 | 1775 | 93.85% | 0 | 0 | 15.5 | 0 | 0 |  | 1775 |  | 0 | 24219.28 | 22444.28 | 92.67%
06/19/24 |  | 08/29/25 | Open | Jason Esry | Aman Khan |  | Aman Khan, David D Tijerina, Jason Esry, Larry Noble, Mohammed Almoola, Robert V Eubanks |  |  | An Le, Ben Crouch, Blake Nadler, Celso Lopez, Eric Straeter, Harley Garcia, Isaiah Rosales, Jason Esry, Jesus Escobedo, John Senkulics, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Michael Torres, Mohammed Almoola, Nathan Dao, Oscar Gonzalez, Paul Serres, Quinn Wieland, Robert Jones |  |  | David D Tijerina | TX-CEN | San Antonio ISD | J00018549 | Predictive Wireless Surveys (11 sites) | Implementation/Deployment | 75% | 71.19% | 1000.51 | 313.26 | 2195.99 | 62475 | 31.31% | 2195.99 | 25 | 712.25 | 21057.5 | 0 |  | 62475 |  | 641233.56 | 111014.4 | 48539.4 | 43.72%
05/15/24 |  | 08/29/25 | Open | Jason Esry | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Amy Martinez-Nagy, David D Tijerina, Jason Esry, Kurt Sell, Wyley Johnson |  |  | Jason Esry |  |  | David D Tijerina | TX-CEN | Travis County Central Health DBA: Central Health | J00018335 | ISE Implementation | Planning/Design/Staging | 50% | 26.79% | 140 | 102.5 | 17500 | 4687.5 | 73.21% | 17500 | 0 | 37.5 | 2562.5 | 0 |  | 4687.5 |  | 1420007.48 | 271134.16 | 266446.66 | 98.27%
03/31/25 |  | 08/29/25 | Open | Jennifer Soliz | Eduardo Chavez |  | Eduardo Chavez, Jennifer Soliz, Nicholas Viken Berghoudian |  |  | Jennifer Soliz |  |  | Nicholas Berghoudian | CA-LAX | County of Santa Clara | 200002554 | N/A | Planning/Design/Staging | 25% | 53.75% | 40 | 18.5 | 0 | 2687.5 | 46.25% | 0 | 0 | 21.5 | 0 | 0 |  | 2687.5 |  | 0 | 87477.6 | 84790.1 | 96.93%
02/25/25 |  | 08/29/25 | Open | Jim Blackwell | Ahmed Al-Zubaidi, Aman Khan, Wyley Johnson |  | Abdalsattar Albaghdadi, Ahmed Al-Zubaidi, Aleksei Lavrushenkov, Aman Khan, Ashley F Freeman, Brandon McMillan, Daniel Hernandez, Daniel R Hernandez, Jim Blackwell, Wyley Johnson |  |  | Abdalsattar Albaghdadi, Aleksei Lavrushenkov, Camrin Edwards, Craig St. Rose, Hector Rivera, Jaime Flores, James Adams, Jim Blackwell, Jose R. Duarte, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Paul Serres, Russell James Bugarin, Trenton Smith |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | 200002158 | N/A | Implementation/Deployment | 30% | 42.29% | 1837.36 | 1186.11 | 0 | 63708.75 | 64.56% | 0 | 125.75 | 777 | 9716.25 | 0 |  | 63708.75 |  | 8725829.12 | 275946.8 | 212238.05 | 76.91%
06/13/24 |  | 08/29/25 | Open | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Joanna Herrera, Steve J Rodriguez, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | IDEA FLORIDA INC. | J00018507 | JAX BOY 24 Projector Install | Implementation/Deployment | 95% | 98.5% | 66.5 | 1 | 8312.5 | 8187.5 | 1.504% | 8312.5 | 0 | 65.5 | 6375 | 0 |  | 8187.5 |  | 45887.1 | 49842.89 | 41655.39 | 83.57%
02/24/25 |  | 08/29/25 | Open | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Joanna Herrera, Xavier A Trevino |  |  | Carlos Carrillo, Felix Martinez, Francisco Hernandez, Joanna Herrera, Joaquin Garcia, Jorge Robert Rangel, Oscar Garcia, Rene Trejo, Roger Guerra |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002144 | N/A | Planning/Design/Staging | 20% | 34.59% | 577.5 | 401.25 | 0 | 14135 | 69.48% | 0 | 23.5 | 199.75 | 1410 | 0 |  | 14135 |  | 138266.8 | 67424.8 | 53289.8 | 79.04%
04/28/25 |  | 08/29/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Christopher Garcia, Conner MacDonnell, Joanna Herrera, Joshua Hubbard, Justin Mitchell, Michelle Bailey, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Alexander Chambless, An Le, Celso Lopez, Clinton Bennett Deason, Felix Martinez, Francisco Hernandez, Isaiah Rosales, James Danner, Jeremiah Solomon, Joanna Herrera, Joaquin Garcia, John Senkulics, Joshua Hubbard, Justin Mitchell, Michael Torres, Oscar Garcia, Rene Trejo, Wilangel Francis |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002892 | N/A | Implementation/Deployment | 30% | 48.72% | 700.5 | 412.75 | 0 | 23680 | 58.92% | 0 | 53.5 | 341.25 | 3210 | 0 |  | 23680 |  | 184702.58 | 83604.4 | 59924.4 | 71.68%
06/16/25 |  | 08/29/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003092 | N/A | Planning/Design/Staging | 5% | 8.418% | 11.88 | 10.88 | 0 | 125 | 91.58% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 2872.54 | 3397.6 | 3272.6 | 96.32%
06/04/24 |  | 08/29/25 | Open | Joanna Herrera | Bryan Brown |  | Christopher Garcia, James Danner, Joanna Herrera, Karyn Hubbard, Steve J Rodriguez, Xavier A Trevino |  |  | An Le, Angel Alicea, Angel Alicea-Torres, Blake Nadler, Celso Lopez, Isaiah Rosales, James Danner, Joanna Herrera, John Senkulics, Jorge Robert Rangel, Michael Torres, Rene Trejo, Trevor Galloso |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018461 | SA BOY 2024 - Classroom Projectors | Implementation/Deployment | 90% | 61.34% | 4573.5 | 1811.75 | 408709.62 | 216471.25 | 39.61% | 408709.62 | 43.5 | 2805.25 | 107547.5 | 0 |  | 216471.25 |  | 771065.14 | 583840.72 | 367369.47 | 62.92%
06/13/24 |  | 08/29/25 | Open | Joanna Herrera | Bryan Brown |  | Christopher Garcia, Joanna Herrera, Joshua Hubbard, Remi Martinez-Montenegro, Rene Trejo, Robert Lavender, Samuel Gonzalez, Steve J Rodriguez, Xavier A Trevino |  |  | Austen Howard, Dante Torres, Devin Moreno, Dylan Pittsinger, Jacob Hill, Joanna Herrera, Joshua Hubbard, Noah Castleberry, Noah Trump, Robert Lavender, Samuel Gonzalez, Sean Cowhey |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | J00018506 | TACO BOY 24 - Classroom Projector Install | Implementation/Deployment | 95% | 76.9% | 280.5 | 90.5 | 27165.78 | 17739.5 | 32.26% | 27165.78 | 25.7 | 215.7 | 12632.5 | 0 |  | 17739.5 |  | 45957.36 | 35324.8 | 17585.3 | 49.78%
12/09/22 |  | 08/29/25 | Open | Joanna Herrera | N/A |  | Christopher Brown, Christopher Brown, David Avila, Diana Berger, Joanna Herrera |  |  | Christopher Brown, Joanna Herrera |  |  | David Avila | TX-SOUT | RGV College | J00014493 | Quick WORK ORDER - MSWindows Server Domain Upgrade | Training/Knowledge Transfer/Documentation | 0% | 0% | 0 | -77 | 0 | 10335 | 0% | 0 | 0 | 77 | 10335 | 0 |  | 10335 |  | 0 | 0 | -10335 | 0%
12/09/22 |  | 08/29/25 | Open | Joanna Herrera | N/A |  | Christopher Brown, Christopher Brown, David Avila, Diana Berger, Joanna Herrera |  |  | Christopher Brown, Joanna Herrera |  |  | N/A | N/A | RGV College | J00014493 | Quick WORK ORDER - MSWindows Server Domain Upgrade | Training/Knowledge Transfer/Documentation | 90% | 15.24% | 39.38 | 33.38 | 5272.5 | 810 | 84.76% | 5272.5 | 0 | 6 | 0 | 0 |  | 810 |  | 0 | 0 | -810 | 0%
06/16/25 |  | 08/29/25 | Closed | Joaquin Marroquin | Bryan Brown, Christopher Garcia |  | Bryan Brown, Christopher Garcia, Joaquin Marroquin, Xavier A Trevino |  |  | N/A |  |  | Xavier A Trevino | TX-SOUT | Del Mar College | 200003063 | N/A | Not started | 0% | 0% | 85.63 | 85.63 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 21037.59 | 14992.8 | 14992.8 | 100%
06/20/25 |  | 08/29/25 | Open | Joaquin Marroquin | David D Tijerina |  | Christopher Puyear, Daniel Snyder, David D Tijerina, Joaquin Marroquin |  |  | N/A |  |  | David D Tijerina | TX-CEN | Leander ISD | 200003111 | N/A | Not started | 0% | 0% | 176.91 | 176.91 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 259638.23 | 29293.2 | 29293.2 | 100%
10/25/24 |  | 08/29/25 | Open | Joaquin Marroquin | Bryan Brown |  | Amy Martinez-Nagy, Brian Newman, Brian Newman, Christopher Garcia, David D Tijerina, Joaquin Marroquin, Larry Noble |  |  | Brian Newman, Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | J00019315 | CPHS Phase 1-3 - IP Paging Endpoint Installation | Implementation/Deployment | 90% | 45.27% | 166.76 | 91.26 | 22533 | 9700 | 54.73% | 22533 | 0 | 75.5 | 702.5 | 0 |  | 9700 |  | 414739.18 | 296350.57 | 286650.57 | 96.73%
10/25/24 |  | 08/29/25 | Open | Joaquin Marroquin | Bryan Brown |  | Amy Martinez-Nagy, Brian Newman, Brian Newman, Bryan Brown, Christopher Garcia, David D Tijerina, Joaquin Marroquin, Larry Noble |  |  | Brian Newman, Joaquin Marroquin |  |  | David D Tijerina | TX-CEN | Leander ISD | J00019316 | VRHS Phase 1-3 - IP Paging Endpoint Install | Implementation/Deployment | 90% | 20.63% | 395.06 | 313.56 | 18022.5 | 10502.5 | 79.37% | 18022.5 | 0 | 81.5 | 452.5 | 0 |  | 10502.5 |  | 480904.89 | 340856.62 | 330354.12 | 96.92%
10/25/24 |  | 08/29/25 | Open | Joaquin Marroquin | N/A |  | Amy Martinez-Nagy, Brian Newman, Brian Newman, Bryan Brown, Christopher Garcia, David D Tijerina, Joaquin Marroquin, Larry Noble |  |  | Alexander Chambless, Brian Newman, Clinton Bennett Deason, Jeremiah Solomon, Joaquin Marroquin, Joel Hubbard, Oscar Gonzalez, Rene Trejo, Steven Shipmon |  |  | David D Tijerina | TX-CEN | Leander ISD | J00019317 | RBMS Phase 1-3 - IP Paging Endpoint Installation | Implementation/Deployment | 90% | 72.91% | 248.25 | 103.25 | 9171.7 | 17797.5 | 41.59% | 9171.7 | 36 | 181 | 3027.5 | 0 |  | 17797.5 |  | 0 | 0 | -17797.5 | 0%
03/03/25 |  | 08/29/25 | Open | LaQisha Marshall | Bryan Brown |  | Christi D Hubbard, Christopher Garcia, LaQisha Marshall, Lori Endsley |  |  | LaQisha Marshall, Rene Trejo |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200002235 | N/A | Implementation/Deployment | 50% | 27.92% | 145.94 | 108.19 | 0 | 4643.75 | 74.13% | 0 | 3 | 40.75 | 225 | 0 |  | 4643.75 |  | 2669.6 | 24061.6 | 19417.85 | 80.7%
04/16/25 |  | 08/29/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, LaQisha Marshall |  |  | LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200002688 | N/A | Planning/Design/Staging | 5% | 3.982% | 125.55 | 120.55 | 0 | 625 | 96.02% | 0 | 0 | 5 | 0 | 0 |  | 625 |  | 36900 | 13223.6 | 12598.6 | 95.27%
05/08/24 |  | 08/29/25 | Open | LaQisha Marshall | Bryan Geoghan, David Watkins |  | Alexander Gutman, Beau C. Devillier, Bryan Geoghan, Conner MacDonnell, David Watkins, John Stephen Kurkjian, LaQisha Marshall, Matthew Veach |  |  | Gena Robbins, John Stephen Kurkjian, Joshua Hubbard, LaQisha Marshall, Matthew Veach, Noah Trump, Tavis Jackson |  |  | Alex Gutman | TX-DAL | Cadence McShane | J00017330 | Mountain View ECC | Planning/Design/Staging | 40% | 58.23% | 156.71 | 66.46 | 16079.6 | 11403.75 | 42.41% | 16079.6 | 1 | 91.25 | 2028.75 | 0 |  | 11403.75 |  | 262569.44 | 21811.2 | 10407.45 | 47.72%
01/24/24 |  | 08/29/25 | Open | LaQisha Marshall | N/A |  | Christi D Hubbard, Christopher Puyear, David Watkins, Juan Saenz, LaQisha Marshall, Larry Noble, Matthew Duncan |  |  | Juan Saenz, LaQisha Marshall, Ron Loge |  |  | Christi D Hubbard | TX-CEN | City of Austin - Aviation Dept | J00017491 | AWS Backup & Restore | On HOLD | 60% | 53.08% | 223.25 | 104.75 | 29638.75 | 16147.5 | 46.92% | 29638.75 | 0 | 118.5 | 13265 | 0 |  | 16147.5 |  | 0 | 0 | -16147.5 | 0%
05/21/24 |  | 08/29/25 | Open | LaQisha Marshall | George Edwin Jacob |  | Alexander Gutman, Beau C. Devillier, George Edwin Jacob, Jeffery Giles, LaQisha Marshall, Luis Ovalles |  |  | LaQisha Marshall, Luis Ovalles |  |  | Alex Gutman | TX-DAL | Dallas College | J00018375 | UCS FI Migration | On HOLD | 20% | 23.68% | 57 | 43.5 | 6868.5 | 1747.5 | 76.32% | 6868.5 | 0 | 13.5 | 1747.5 | 0 |  | 1747.5 |  | 4530.18 | 11332.8 | 9585.3 | 84.58%
02/03/25 |  | 08/29/25 | Open | LaQisha Marshall | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, LaQisha Marshall |  |  | Grayson McClanahan, LaQisha Marshall, Ming Chiu |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | 200001707 | N/A | Planning/Design/Staging | 25% | 10.16% | 1373.13 | 1233.63 | 0 | 18040 | 89.84% | 0 | 0 | 139.5 | 0 | 0 |  | 18040 |  | 537228.5 | 194634.4 | 176594.4 | 90.73%
06/14/24 |  | 08/29/25 | Open | LaQisha Marshall | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, LaQisha Marshall, Larry Noble, Lori Endsley, Raul Velazquez, Robert Kelly, Robert Kelly |  |  | Adam Felix, Alexander Chambless, Briliance Johnson, Bryan Mullen, Grayson McClanahan, Grayson Rigsby, Kevin Curtis, Kolawole Ayeni, LaQisha Marshall, LaTaveon Champ, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Raul Velazquez, Robert Kelly, Robert Jones, Shannan Thomas, Steven Shipmon, Tommy Percivill, Wilangel Francis |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | J00018515 | LAN switching and wireless - RFP 240005155 | Implementation/Deployment | 60% | 75.84% | 2152.94 | 555.69 | 187046.58 | 134733.75 | 25.81% | 187046.58 | 35.5 | 1632.75 | 3885 | 0 |  | 134733.75 |  | 3976803.7 | 255007.6 | 120273.85 | 47.16%
07/16/24 |  | 08/29/25 | Open | LaQisha Marshall | Daniel Snyder |  | Adam Felix, Christi D Hubbard, Daniel Snyder, LaQisha Marshall, Larry Noble, Lori Endsley, Robert Kelly, Robert Kelly |  |  | Adam Felix, Briliance Johnson, Grayson McClanahan, LaQisha Marshall, Oscar Gonzalez, Robert Kelly |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | J00018671 | Complete Wireless Site Surveys | Implementation/Deployment | 50% | 52.3% | 565 | 273.5 | 57023.15 | 26772.5 | 48.41% | 57023.15 | 4 | 295.5 | 22617.5 | 0 |  | 26772.5 |  | 0 | 74956 | 48183.5 | 64.28%
10/01/24 |  | 08/29/25 | Open | LaQisha Marshall | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, LaQisha Marshall, Larry Noble, Lori Endsley, Raul Velazquez, Robert Kelly, Robert Kelly |  |  | Adam Felix, James Robertson, Jorge Ramirez, Kevin Curtis, LaQisha Marshall, Matthew D'Ambrosio, Paul Serres, Raul Velazquez, Robert Kelly, Robert Jones, Steven Shipmon |  |  | Christi D Hubbard | TX-CEN | Lake Travis ISD | J00019123 | Switches and Wireless Upgrade Admin Buildings | Implementation/Deployment | 60% | 39.55% | 405.16 | 247.91 | 40437.6 | 17830 | 61.19% | 40437.6 | 3 | 160.25 | 6235 | 0 |  | 17830 |  | 280118.1 | 53856 | 36026 | 66.89%
12/19/24 |  | 08/29/25 | Open | LaQisha Marshall | Ahmed Al-Zubaidi |  | Ahmed Al-Zubaidi, David Monasmith, David Monasmith, Ibrahim Altaweel, Jerome Tanyag Mara, LaQisha Marshall, Mohammad Arman, Rogelio Morgado-Perez, Tom Magboo |  |  | Ibrahim Altaweel, Jerome Tanyag Mara, LaQisha Marshall, Mohammad Arman, Rogelio Morgado-Perez, Tom Magboo |  |  | David Monasmith | TX-HOU | Texas A&M System | 200000558 | N/A | Training/Knowledge Transfer/Documentation | 85% | 98.75% | 321 | 4 | 48050 | 44500 | 1.246% | 48050 | 0 | 317 | 0 | 0 |  | 44500 |  | 0 | 29995 | -14505 | -48.36%
03/27/25 |  | 08/29/25 | Open | LaQisha Marshall | Mark J Chambliss |  | David Monasmith, David Monasmith, LaQisha Marshall, Mark J Chambliss, Ming Chiu |  |  | LaQisha Marshall |  |  | David Monasmith | TX-HOU | Texas A&M University | 200002479 | N/A | Planning/Design/Staging | 10% | 2.486% | 261.5 | 255 | 0 | 812.5 | 97.51% | 0 | 0 | 6.5 | 0 | 0 |  | 812.5 |  | 43930.4 | 47500 | 46687.5 | 98.29%
05/14/25 |  | 08/29/25 | Open | LaQisha Marshall | N/A |  | David Monasmith, David Monasmith, LaQisha Marshall, Mark J Chambliss, Ming Chiu |  |  | N/A |  |  | David Monasmith | TX-HOU | Texas A&M University | 200002975 | N/A | Planning/Design/Staging | 5% | 0% | 7.5 | 7.5 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 1450 | 1450 | 100%
12/19/24 |  | 08/29/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Carlos Montalvo, Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah |  |  | Carlos Montalvo, Lauren Lanzini Coffey, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200000344 | N/A | Planning/Design/Staging | 25% | 21.39% | 104 | 81.75 | 14600 | 2886.25 | 78.61% | 14600 | 0 | 22.25 | 0 | 0 |  | 2886.25 |  | 54475 | 22994.8 | 20108.55 | 87.45%
06/02/25 |  | 08/29/25 | Open | Marco Lish | N/A |  | Marco Lish, Neel Shah |  |  | Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Finance Department | 200003026 | N/A | Planning/Design/Staging | 0% | 1.356% | 18.44 | 18.19 | 0 | 31.25 | 98.64% | 0 | 0 | 0.25 | 0 | 0 |  | 31.25 |  | 16587 | 3150.8 | 3119.55 | 99.01%
04/05/22 |  | 08/29/25 | Open | Marco Lish | Hugh Miller, Pradeep Tyagi , Wyley Johnson |  | Jason Espino, Larry Noble, Marco Lish, Neel Shah |  |  | Eric Firestone, Jason Espino, Lauren Lanzini Coffey, Marco Lish, Saif Qaissi |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | J00012799 | Azure East/West Traffic Services | Implementation/Deployment | 90% | 85.48% | 263.93 | 38.33 | 37728.75 | 32937.5 | 14.52% | 37728.75 | 0 | 225.6 | 31631.25 | 53.99 |  | 32937.5 |  | 67770.2 | 57175.2 | 24183.71 | 42.3%
02/28/25 |  | 08/29/25 | Open | Marshall Chuck Pugh | George Edwin Jacob |  | George Edwin Jacob, Lauren J Kennewell, Marshall Chuck Pugh , Ron Loge |  |  | Marshall Chuck Pugh, Ron Loge |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | 200002216 | N/A | Implementation/Deployment | 75% | 71.5% | 50 | 14.25 | 0 | 6106.25 | 28.5% | 0 | 0 | 35.75 | 0 | 0 |  | 6106.25 |  | 0 | 10458 | 4351.75 | 41.61%
06/03/25 |  | 08/29/25 | Open | Richard Keith Arnst | N/A |  | Christopher Garcia, Joel Hubbard, Lauren J Kennewell, Remi Martinez-Montenegro, Richard Keith Arnst, Robert Lavender |  |  | Richard Keith Arnst |  |  | Lauren J Kennewell | TX-DAL | Denton Regional Medical Center | 200003044 | N/A | Planning/Design/Staging | 30% | 15.44% | 35.63 | 30.13 | 0 | 687.5 | 84.56% | 0 | 0 | 5.5 | 0 | 0 |  | 687.5 |  | 15116.85 | 6414.2 | 5726.7 | 89.28%
06/16/25 |  | 08/29/25 | Open | Richard Keith Arnst | Bryan Brown, Christopher Garcia, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Lauren J Kennewell, Remi Martinez-Montenegro, Richard Keith Arnst, Robert Lavender |  |  | Richard Keith Arnst |  |  | Lauren J Kennewell | TX-DAL | Las Colinas Medical Center | 200003084 | N/A | Planning/Design/Staging | 15% | 25% | 20 | 15 | 0 | 625 | 75% | 0 | 0 | 5 | 0 | 0 |  | 625 |  | 9461.03 | 3342.96 | 2717.96 | 81.3%
06/17/25 |  | 08/29/25 | Open | Richard Keith Arnst | N/A |  | Arcangelo Fanelli, Bryan Geoghan, Joel Hubbard, Richard Keith Arnst |  |  | Richard Keith Arnst |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200003097 | N/A | Planning/Design/Staging | 15% | 4.605% | 76 | 72.5 | 0 | 437.5 | 95.39% | 0 | 0 | 3.5 | 0 | 0 |  | 437.5 |  | 41562 | 13980 | 13542.5 | 96.87%
04/14/25 |  | 08/29/25 | Open | Robert McIver | Christopher Ceykovsky |  | Christopher Ceykovsky, Robert McIver, Samuel Newland, Xavier A Trevino |  |  | Ahmed Alfayli, Camrin Edwards, Francisco Hernandez, James Danner, Jarshawn Newsome, Justin Cornish, Kevin Curtis, Matthew D'Ambrosio, Mohammed Al-Shaikhli, Paul Serres, Robert McIver, Samuel Newland, Trenton Smith, Younus Alabbood |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200002628 | N/A | Planning/Design/Staging | 40% | 3.315% | 4781.75 | 4623.25 | 0 | 15045 | 96.69% | 0 | 0 | 158.5 | 0 | 0 |  | 15045 |  | 1983337.23 | 612844.4 | 597799.4 | 97.55%
01/21/25 |  | 08/29/25 | Open | Ryan Scott | David Watkins |  | Arcangelo Fanelli, Bryan Mullen, David Watkins, Jonathan Weir, Jonathan Weir, Ryan Scott, Samuel Newland, Taylor Leger |  |  | Bryan Mullen, Ryan Scott, Samuel Newland |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200001676 | N/A | Implementation/Deployment | 55% | 29.22% | 765.7 | 541.95 | 86963.83 | 27991.25 | 70.78% | 86963.83 | 0 | 223.75 | 0 | 0 |  | 27991.25 |  | 0 | 155112 | 127120.75 | 81.95%
01/21/25 |  | 08/29/25 | Closed | Ryan Scott | David Watkins |  | Arcangelo Fanelli, Bryan Mullen, David Watkins, Jonathan Weir, Jonathan Weir, Ryan Scott |  |  | N/A |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200001677 | N/A | On HOLD | 15% | 0% | 621.4 | 621.4 | 71135 | 0 | 100% | 71135 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 126975.6 | 126975.6 | 100%
09/12/23 |  | 08/29/25 | Open | Ryan Scott | Christopher Puyear |  | Christopher Puyear, Karen Grant-Dennison, Rusty Bryan, Ryan Scott |  |  | Christopher Ceykovsky, Dante Torres, Henry Pugsley, John Stephen Kurkjian, Joshua Hubbard, Ryan Scott, Samuel Newland |  |  | Rusty Bryan | TX-DAL | Randall County Sheriff | J00016354 | Webex Calling Revision 2 - CAPX | Implementation/Deployment | 70% | 103.1% | 280.53 | 3.28 | 45660.65 | 36986.25 | 1.169% | 45660.65 | 12 | 289.25 | 32873.75 | 1160.39 |  | 36986.25 |  | 49316.64 | 47718 | 9571.36 | 20.06%
06/09/25 |  | 08/29/25 | Open | Ryan Scott | David Watkins |  | David Watkins, David Neal Gravatt, Mario Sanchez, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Mario Sanchez, Ryan Scott |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200002997 | N/A | Planning/Design/Staging | 5% | 6.35% | 141.73 | 132.73 | 0 | 1165 | 93.65% | 0 | 0 | 9 | 0 | 0 |  | 1165 |  | 54994.9 | 22178 | 21013 | 94.75%
07/17/24 |  | 08/29/25 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Beau C. Devillier, Bryan Geoghan, Shannon Marie Alvarado, Taylor Leger |  |  | Austen Howard, Carlo Enriquez, Dante Torres, Devin Moreno, Jacob Hill, Noah Castleberry, Ryan Frankeberger, Samuel Newland, Shannon Marie Alvarado, Yonathan Fadel |  |  | Taylor Leger | TX-DAL | Baylor Scott & White Surgical Hospital Fort Worth | J00018674 | Collaboration Upgrade and Refresh | Implementation/Deployment | 70% | 56.21% | 288.21 | 140.21 | 33980 | 17985 | 48.65% | 33980 | 14 | 162 | 4280 | 0 |  | 17985 |  | 78777.6 | 30204.8 | 12219.8 | 40.46%
06/02/25 |  | 08/29/25 | Open | Shannon Marie Alvarado | Christopher Puyear |  | Christopher Puyear, Shannon Marie Alvarado, Thomas McClanahan |  |  | Shannon Marie Alvarado |  |  | Thomas McClanahan | TX-CEN | City of Killeen | 200003027 | N/A | Planning/Design/Staging | 10% | 1.86% | 107.5 | 105.5 | 0 | 250 | 98.14% | 0 | 0 | 2 | 0 | 0 |  | 250 |  | 0 | 24509.6 | 24259.6 | 98.98%
06/16/25 |  | 08/29/25 | Open | Shannon Marie Alvarado | Jacob Parks, Jeffrey Holman |  | Dhulfiqar Al Hashimi, Edward Padron, Jacob Parks, Jason Osuna, Jeffrey Holman, Shannon Marie Alvarado |  |  | Dhulfiqar Al Hashimi, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | City of Las Cruces | 200003088 | N/A | Planning/Design/Staging | 5% | 8.237% | 72.84 | 66.84 | 0 | 825 | 91.76% | 0 | 0 | 6 | 0 | 0 |  | 825 |  | 177638.51 | 16890.4 | 16065.4 | 95.12%
04/30/25 |  | 08/29/25 | Open | Shannon Marie Alvarado | Jacob Parks, Jeffrey Holman, William Birdsong |  | Jacob Parks, Jeffrey Holman, Shannon Marie Alvarado, Taylor Leger, William Birdsong |  |  | Jonathan Weir, Joshua Osgood, Shannon Marie Alvarado |  |  | Taylor Leger | TX-DAL | Cleburne ISD | 200002917 | N/A | Planning/Design/Staging | 20% | 29.14% | 135.55 | 98.55 | 0 | 4710 | 72.7% | 0 | 2.5 | 39.5 | 150 | 0 |  | 4710 |  | 49208.2 | 23580.4 | 18870.4 | 80.03%
11/01/24 |  | 08/29/25 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Arcangelo Fanelli, Beau C. Devillier, Christopher Ceykovsky, Cory E Hopf, Cory Hopf, Miguel Reed, Nathan Dao, Shannon Marie Alvarado |  |  | Andy Pham, Christopher Ceykovsky, Gena Robbins, Jaime Flores, Jay Daniel De Leon, John Stephen Kurkjian, Justin Cornish, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Miguel Reed, Nathan Dao, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Huntsville Memorial Hospital | J00013743 | Collab refresh - UCS & Voice | Implementation/Deployment | 95% | 285.3% | 339.25 | -622.5 | 44716.4 | 131307.5 | -183.5% | 44716.4 | 6 | 967.75 | 123977.5 | 91.92 |  | 131307.5 |  | 98156.3 | 48057.6 | -83341.82 | -173.4%
07/29/24 |  | 08/29/25 | Open | Shannon Marie Alvarado | Aman Khan, Bryan Geoghan, Christopher Ceykovsky |  | Aman Khan, Bryan Geoghan, Christopher Ceykovsky, Garrett Curran, Shannon Marie Alvarado, Yong Kim |  |  | Hamzeh Tahat, Henry Pugsley, Shannon Marie Alvarado |  |  | Garrett Curran | CA-LAX | San Bernardino County Sheriff’s Department | J00018730 | Video Systems for Secured Visitation Booths | Implementation/Deployment | 70% | 21.16% | 128.75 | 101.5 | 18153.75 | 3043.75 | 78.83% | 18153.75 | 0 | 27.25 | 0 | 2357.5 |  | 3043.75 |  | 528972.26 | 38122.84 | 32721.59 | 85.83%
03/10/25 |  | 08/29/25 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Daniel Snyder, Jason Osuna, Shannon Marie Alvarado |  |  | Jesus Escobedo, Nathan Dao, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | 200002360 | N/A | On HOLD | 50% | 34.56% | 50.63 | 34.13 | 0 | 2035 | 67.41% | 0 | 1 | 17.5 | 60 | 0 |  | 2035 |  | 0 | 9207.2 | 7172.2 | 77.9%
04/15/25 |  | 08/29/25 | Open | Shannon Marie Alvarado | Daniel Snyder |  | Daniel Snyder, Jason Osuna, Shannon Marie Alvarado |  |  | Jesus Escobedo, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | Tokio Marine HCC | 200002681 | N/A | On HOLD | 50% | 26.27% | 41.88 | 30.88 | 0 | 1420 | 73.73% | 0 | 0 | 11 | 0 | 0 |  | 1420 |  | 0 | 9833.52 | 8413.52 | 85.56%
06/18/25 |  | 08/29/25 | Open | Summer Abunaja | N/A |  | Mark J Chambliss, Neel Shah, Summer Abunaja |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200003098 | N/A | Planning/Design/Staging | 10% | 0% | 21.26 | 21.26 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 9209.76 | 3588 | 3588 | 100%
06/18/25 |  | 08/29/25 | Open | Summer Abunaja | N/A |  | Mark J Chambliss, Neel Shah, Summer Abunaja |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200003099 | N/A | Planning/Design/Staging | 10% | 0% | 38.13 | 38.13 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 23023.8 | 5826.6 | 5826.6 | 100%
03/21/24 |  | 08/29/25 | Open | Summer Abunaja | David Watkins |  | Briliance Johnson, Christine A Hupe, David Watkins, Ernesto Gonzalez, Matthew Veach, Nathan Dao, Neel Shah, Nick Varga, Shiraz Humayun, Summer Abunaja, Tabais Prater |  |  | Aleksei Lavrushenkov, Briliance Johnson, Ernesto Gonzalez, Jesus Escobedo, Lauren Lanzini Coffey, Matthew Veach, Moises Rodriguez, Nathan Dao, Nick Varga, Ruben Cantu, Saravanan Lakshmanan, Summer Abunaja |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00017558 | TCP Wireless Post-Install Validation Surveys | Implementation/Deployment | 90% | 78.54% | 633.75 | 182.5 | 64411.98 | 51121.25 | 28.8% | 64411.98 | 46.5 | 497.75 | 34950 | 0 |  | 51121.25 |  | 0 | 105787.6 | 54666.35 | 51.68%
08/31/23 |  | 08/29/25 | Open | Summer Abunaja | Jacob Parks, Jeffrey Holman |  | Jason Espino, Jeff Barker, Summer Abunaja |  |  | Jason Espino |  |  | Ryan Wilson | TX-DAL | TPG Global | J00016452 | F5 Resource T&E - PROJECT CODE#64635 | Closed | 0% | 0% | 0 | -39.25 | 0 | 5887.5 | 0% | 0 | 0 | 39.25 | 5887.5 | 0 |  | 5887.5 |  | 0 | 8225 | 2337.5 | 28.42%
10/10/24 |  | 08/29/25 | Open | Tray Giddens | Chad Hart |  | Chad Hart, Christopher Kutalek, John Randall Bailey, Jr., Tray Giddens |  |  | Daniel Hernandez, Jesus Gonzalez, Jose R. Duarte, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Paul Serres, Tray Giddens |  |  | Christopher Kutalek | TX-HOU | TGS | J00019182 | Switching & Wireless – Clay Road | Planning/Design/Staging | 20% | 74.25% | 74.75 | 22.25 | 5456.75 | 4110 | 29.77% | 5456.75 | 3 | 55.5 | 2550 | 0 |  | 4110 |  | 0 | 7855.6 | 3745.6 | 47.68%
07/01/25 |  | 08/29/25 | Open | Walter Clay Knight | N/A |  | Aaron Christopher Pfeifer, Jamie Lewis, Jeremy Hoffpauir, Walter Clay Knight |  |  | Walter Clay Knight |  |  | Jamie Lewis | US-SP | NineStar Connect | 200003074 | N/A | Planning/Design/Staging | 5% | 1% | 100 | 99 | 0 | 125 | 99% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 0 | 22344 | 22219 | 99.44%
05/01/25 |  | 09/01/25 | Open | Jim Blackwell | Collin Mazzeno |  | Ahmed Al-Zubaidi, Ali Al-Haddad, Aman Khan, Ashley F Freeman, Christopher Brown, Christopher Brown, Collin Mazzeno, Cory Bradfield, Cory Bradfield, Daniel Hernandez, Daniel R Hernandez, David Escamilla, Henry Pugsley, Jesus Escobedo, Jim Blackwell, Jorge Ortiz Cardozo, Michelle Duenes, Michelle Moncayo, Moe Izaks, Steven Walker |  |  | Christopher Brown, Cory Bradfield, Deonte Terrell, Eric Firestone, Jesus Escobedo, Jesus Guadian, Jim Blackwell, Jorge Ortiz Cardozo |  |  | Ashley F Freeman | TX-HOU | Fort Bend County | 200002921 | N/A | Planning/Design/Staging | 5% | 12.51% | 1061.46 | 932.71 | 0 | 15950 | 87.87% | 0 | 4 | 132.75 | 562.5 | 0 |  | 15950 |  | 793670.5 | 355312.88 | 339362.88 | 95.51%
11/20/23 |  | 09/03/25 | Open | Abiodun David Babasola | Jacob Parks, Jeffrey Holman |  | Abiodun David Babasola, David Babasola, Garrett Curran, Jacob Parks, Jeffrey Holman, Sophia Quinter, Yong Kim |  |  | Abiodun David Babasola, Eric Firestone, Sophia Quinter |  |  | Garrett Curran | CA-LAX | Westside Union School District | J00016736 | WUSD Cisco ISE MDM Integration | Implementation/Deployment | 70% | 83.61% | 110.63 | 18.13 | 16041.25 | 13375 | 16.39% | 16041.25 | 0 | 92.5 | 8350 | 0 |  | 13375 |  | 16155 | 28071.08 | 14696.08 | 52.35%
09/06/24 |  | 09/05/25 | Open | Shannon Marie Alvarado | N/A |  | Christi D Hubbard, Jacob Sennett, Larry Noble, Shannon Marie Alvarado, Timothy Ramsey |  |  | Jacob Sennett, Shannon Marie Alvarado |  |  | Christi D Hubbard | TX-CEN | City of Austin - Aviation Dept | J00019008 | VPN, Duo & Site to Site tunnel | On HOLD | 0% | 0% | 0 | -19.25 | 0 | 2662.5 | 0% | 0 | 0 | 19.25 | 1425 | 0 |  | 2662.5 |  | 0 | 0 | -2662.5 | 0%
06/02/25 |  | 09/05/25 | Closed | Shannon Marie Alvarado | Christopher Puyear |  | Shannon Marie Alvarado, Thomas McClanahan |  |  | N/A |  |  | Thomas McClanahan | TX-CEN | City of Killeen | 200003028 | N/A | On HOLD | 0% | 0% | 20 | 20 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 3037.86 | 8940.2 | 8940.2 | 100%
05/15/25 |  | 09/05/25 | Open | Tray Giddens | Chad Hart |  | Chad Hart, Dustin Huffman, Tray Giddens |  |  | Craig St. Rose, Jaime Flores, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200002972 | N/A | Planning/Design/Staging | 5% | 9.901% | 313.1 | 286.1 | 0 | 2445 | 91.38% | 0 | 4 | 31 | 240 | 0 |  | 2445 |  | 0 | 56484.39 | 54039.39 | 95.67%
12/09/24 |  | 09/09/25 | Open | Marco Lish | Ahmed Al-Zubaidi, Wyley Johnson |  | Abdulrahman Farhan, Ahmed Al-Zubaidi, Dhulfiqar Al Hashimi, Marco Lish, Neel Shah, Wyley Johnson |  |  | Abdulrahman Farhan, Dhulfiqar Al Hashimi, Marco Lish |  |  | Neel Shah | TX-HOU | City of Houston Info Tech Services | 200000262 | N/A | Implementation/Deployment | 55% | 45.44% | 942.5 | 514.25 | 136662.5 | 62156.25 | 54.56% | 136662.5 | 0 | 428.25 | 0 | 0 |  | 62156.25 |  | 395456.18 | 272585.2 | 210428.95 | 77.2%
05/15/25 |  | 09/10/25 | Open | Abiodun David Babasola | Jeremy Hoffpauir |  | Aaron Christopher Pfeifer, Abiodun David Babasola, David Babasola, Jeremy Hoffpauir, Zachary Short, Zachary Short |  |  | Aaron Christopher Pfeifer, Abiodun David Babasola |  |  | Zachary Short | US-SP | Securus Technologies, Inc. | 200002943 | N/A | Planning/Design/Staging | 5% | 8.938% | 282.5 | 257.25 | 0 | 3308.75 | 91.06% | 0 | 0 | 25.25 | 0 | 0 |  | 3308.75 |  | 299443.75 | 53860.9 | 50552.15 | 93.86%
02/10/25 |  | 09/10/25 | Open | Ryan Scott | David Watkins |  | Christopher Prado, David Watkins, Karen Grant-Dennison, Mario Sanchez, Matthew Veach, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Devin Moreno, Jesus Escobedo, Matthew Veach, Mohammed Almoola, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200000259 | N/A | Planning/Design/Staging | 20% | 12.43% | 975.16 | 853.91 | 100887.7 | 14662.5 | 87.57% | 100887.7 | 0 | 121.25 | 0 | 0 |  | 14662.5 |  | 288487.3 | 163848 | 149185.5 | 91.05%
05/06/25 |  | 09/11/25 | Open | Abiodun David Babasola | William Birdsong |  | Abiodun David Babasola, David Babasola, Jonathan Weir, Jonathan Weir, Kristy L Dice, William Birdsong |  |  | Abiodun David Babasola, Jonathan Weir |  |  | Kristy L Dice | TX-DAL | Wichita Falls ISD | 200002566 | N/A | Planning/Design/Staging | 25% | 25.98% | 157.8 | 116.8 | 0 | 5125 | 74.02% | 0 | 0 | 41 | 0 | 0 |  | 5125 |  | 91929.24 | 27218 | 22093 | 81.17%
06/04/25 |  | 09/12/25 | Closed | Brian Willery | Jacob Parks, Jeffrey Holman |  | Brian Willery, Jacob Parks, Jeffrey Holman, Lauren J Kennewell |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | 200003049 | N/A | Not started | 0% | 0% | 192.7 | 192.7 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 296202.54 | 42694 | 42694 | 100%
04/17/24 |  | 09/12/25 | Open | Marco Lish | Bryan Geoghan |  | Beau C. Devillier, Bryan Geoghan, Hamzeh Tahat, Joshua Parker, Marco Lish, Michael Brett Beggs, Ming Chiu, Timothy Fain |  |  | Eric Firestone, Hamzeh Tahat, Jacob Hill, Marco Lish, Ming Chiu, Tambrey Ariel Davis |  |  | Joshua Parker | TX-DAL | Richardson ISD | J00018223 | Telephony Refresh | Implementation/Deployment | 70% | 81.13% | 852.69 | 161.44 | 90160.5 | 56976.25 | 18.93% | 90160.5 | 0.5 | 691.75 | 34147.5 | 5232.5 |  | 56976.25 |  | 2473843.95 | 119191.2 | 56982.45 | 47.81%
07/07/25 |  | 09/12/25 | Closed | Ryan Scott | N/A |  | David Watkins, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | N/A |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200003002 | N/A | Planning/Design/Staging | 5% | 0% | 4 | 4 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 166397.8 | 156.6 | 156.6 | 100%
10/28/24 |  | 09/17/25 | Open | Abiodun David Babasola | William Birdsong |  | Abiodun David Babasola, David Babasola, Jeff Barker, William Birdsong, William Davenport |  |  | Abiodun David Babasola, Caleb Henry, Calvin Darby, Conner MacDonnell, Dante Torres, Gabriel Lantigua, Jacob Hill, Noah Trump, Phillip Ma Lim, Tavis Jackson |  |  | N/A | N/A | Hurst Euless Bedford ISD | J00019308 | UPS Refresh | Implementation/Deployment | 100% | 76.11% | 878.7 | 269.45 | 63470.16 | 45585 | 30.66% | 63470.16 | 59.5 | 668.75 | 3570 | 0 |  | 45585 |  | 1470575 | 93166.4 | 47581.4 | 51.07%
10/28/24 |  | 09/17/25 | Open | Abiodun David Babasola | William Birdsong |  | Abiodun David Babasola, David Babasola, Jeff Barker, William Birdsong, William Davenport |  |  | Abiodun David Babasola, Caleb Henry, Calvin Darby, Conner MacDonnell, Dante Torres, Gabriel Lantigua, Jacob Hill, Noah Trump, Phillip Ma Lim, Tavis Jackson |  |  | William Davenport | TX-DAL | Hurst Euless Bedford ISD | J00019308 | UPS Refresh | Implementation/Deployment | 0% | 0% | 0 | -1 | 0 | 125 | 0% | 0 | 0 | 1 | 125 | 0 |  | 125 |  | 1470575 | 93166.4 | 93041.4 | 99.87%
05/22/25 |  | 09/18/25 | Open | Abiodun David Babasola | Steven Walker |  | Abiodun David Babasola, Christopher Brown, Christopher Brown, David Babasola, Kristy L Dice, Steven Walker |  |  | Abiodun David Babasola, Christopher Brown |  |  | Kristy L Dice | TX-DAL | Prestonwood Baptist Church | 200002988 | N/A | Planning/Design/Staging | 5% | 13.33% | 37.5 | 32.5 | 0 | 665 | 86.67% | 0 | 0 | 5 | 0 | 0 |  | 665 |  | 0 | 7470 | 6805 | 91.1%
07/01/24 |  | 09/19/25 | Open | Jennifer Soliz | Daniel Snyder |  | Daniel Snyder, Hannah Paul, Jennifer Soliz, Larry Noble, Lori Endsley, Sattar Mohseni |  |  | Jennifer Soliz, Sattar Mohseni |  |  | Hannah Edmunds | TX-CEN | Texas Water Development Board | J00018581 | 3rd Floor Equipment Install | On HOLD | 55% | 51.6% | 75.1 | 36.35 | 8017.3 | 4438.75 | 48.4% | 8017.3 | 0 | 38.75 | 3655 | 0 |  | 4438.75 |  | 0 | 11993.6 | 7554.85 | 62.99%
08/20/24 |  | 09/19/25 | Open | Marshall Chuck Pugh | Majid Shirzadeh, William Birdsong |  | Beau C. Devillier, Fadi Ashour, Jeffrey Holman, Lauren J Kennewell, Majid Shirzadeh, Marshall Chuck Pugh , William Birdsong |  |  | Austen Howard, Joan Brito, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | J00018863 | Cisco ISE Wireless Implementation | Implementation/Deployment | 75% | 92.55% | 47 | 7.5 | 4520 | 5047.5 | 15.96% | 4520 | 4 | 43.5 | 1651.25 | 0 |  | 5047.5 |  | 0 | 76414 | 71366.5 | 93.39%
11/04/24 |  | 09/19/25 | Open | Ryan Scott | David Watkins |  | Arcangelo Fanelli, Beau C. Devillier, Conner MacDonnell, Dante Torres, David Watkins, Devin Moreno, Erick Sanchez, John Johnson, Noah Castleberry, Quan Tran, Ryan Scott, Taylor Leger |  |  | Austen Howard, Caleb Baik, Caleb Henry, Devin Moreno, Jacob Hill, Jalen Vecchitto, John Johnson, Justin Mitchell, Noah Castleberry, Noah Trump, Phillip Ma Lim, Remijio Hernandez, Ryan Frankeberger, Ryan Scott |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00018810 | NPH Refresh - Phase 4 - WISH, RJA, NPH | Implementation/Deployment | 60% | 76.4% | 1846.13 | 450.63 | 172426.64 | 91633.75 | 24.41% | 172426.64 | 15 | 1410.5 | 1303.75 | 0 |  | 91633.75 |  | 2766309.6 | 376567.6 | 284933.85 | 75.67%
06/23/25 |  | 09/22/25 | Closed | Walter Clay Knight | N/A |  | Christopher Puyear, David D Tijerina, Patrick Joseph Palermo, Walter Clay Knight |  |  | N/A |  |  | David D Tijerina | TX-CEN | Williamson County | 200003110 | N/A | Planning/Design/Staging | 0% | 0% | 78.75 | 78.75 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 17500 | 17500 | 100%
06/13/22 |  | 09/26/25 | Open | Christina Rice | N/A |  | Beau C. Devillier, Christina Rice, Christina Rice, Henry Pugsley, Karyn Hubbard, Shawn Sutton |  |  | Christina Rice, Henry Pugsley, Karyn Hubbard |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00012832 | Denton ISD: Dial Plan Redesign | Planning/Design/Staging | 10% | 18.45% | 306.25 | 251.25 | 1156.25 | 8975 | 82.04% | 1156.25 | 1.5 | 56.5 | 2162.5 | 0 |  | 8975 |  | 0 | 0 | -8975 | 0%
04/14/25 |  | 09/26/25 | Open | Christina Rice | David Watkins, Jacob Parks, Jeffrey Holman |  | Beau C. Devillier, Christina Rice, Christina Rice, David Watkins, Jacob Parks, Jeffrey Holman, Shawn Sutton, Zachary Neal Newman, Zachary Newman |  |  | Christina Rice, Joan Brito, John Johnson, Juan Pomares, Zachary Neal Newman |  |  | Shawn Sutton | TX-DAL | Denton ISD | J00019250 | Denton ISD: Middle Schools - Erate Switch Refresh | Planning/Design/Staging | 10% | 15.36% | 802.55 | 679.3 | 64501.15 | 12611.25 | 84.64% | 64501.15 | 0 | 123.25 | 625 | 0 |  | 12611.25 |  | 1692897.06 | 145522.5 | 132911.25 | 91.33%
06/26/25 |  | 09/26/25 | Closed | Jason Esry | William Birdsong |  | Alexander Gutman, Jason Esry, William Birdsong |  |  | N/A |  |  | Alex Gutman | TX-DAL | Dallas ISD | 200003133 | N/A | Not started | 0% | 0% | 99.6 | 99.6 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 20262 | 20262 | 100%
05/28/25 |  | 09/26/25 | Open | Jason Matthew Davis | Christopher Puyear |  | Christopher Puyear, David D Tijerina, Jason Matthew Davis |  |  | Jason Matthew Davis, Kristian Martell, Patrick Joseph Palermo, Thomas Francis LoMonaco |  |  | David D Tijerina | TX-CEN | Williamson County | 200002970 | N/A | Not started | 20% | 11.38% | 175.75 | 155.75 | 0 | 3475 | 88.62% | 0 | 0 | 20 | 0 | 0 |  | 3475 |  | 3541.33 | 34000 | 30525 | 89.78%
07/28/23 |  | 09/26/25 | Open | Jennifer Soliz | Emilio Carrillo |  | Aldo Cortes, David D Tijerina, Jason Espino, Jennifer Soliz, Larry Noble, Lonnie Owens, Nelson Garcia, Raul Velazquez |  |  | Aldo Cortes, James Danner, Jason Espino, Jennifer Soliz, Jillian Townson, Nelson Garcia, Raul Velazquez |  |  | Lonnie Owens | TX-CEN | City of San Antonio | J00009651 | COSA DC Relocation Echo | Implementation/Deployment | 0% | 0% | 0 | -355 | 0 | 47516.25 | 0% | 0 | 19.5 | 374.5 | 45078.75 | 844.55 |  | 47516.25 |  | 570196.7 | 36244.8 | -12116 | -33.43%
07/28/23 |  | 09/26/25 | Open | Jennifer Soliz | Emilio Carrillo |  | Aldo Cortes, David D Tijerina, Jason Espino, Jennifer Soliz, Larry Noble, Lonnie Owens, Nelson Garcia, Raul Velazquez |  |  | Aldo Cortes, James Danner, Jason Espino, Jennifer Soliz, Jillian Townson, Nelson Garcia, Raul Velazquez |  |  | N/A | N/A | City of San Antonio | J00009651 | COSA DC Relocation Echo | Implementation/Deployment | 75% | 1.31% | 286.3 | 282.55 | 23799.2 | 543.75 | 98.69% | 23799.2 | 0 | 3.75 | 0 | 844.55 |  | 543.75 |  | 570196.7 | 36244.8 | 34856.5 | 96.17%
01/06/25 |  | 09/26/25 | Open | Jennifer Soliz | David Goss, Matthew Duncan |  | Carmen Isela Brandt, David Goss, Jennifer Soliz, Matthew Duncan |  |  | Jennifer Soliz |  |  | Carmen Brandt | CA-LAX | Marin County | 200000552 | N/A | Planning/Design/Staging | 40% | 47.5% | 20 | 10.5 | 2500 | 1187.5 | 52.5% | 2500 | 0 | 9.5 | 0 | 0 |  | 1187.5 |  | 0 | 176468.22 | 175280.72 | 99.33%
05/31/23 |  | 09/26/25 | Open | Jim Blackwell | William Birdsong |  | Ali Al-Haddad, Brandon McMillan, Camille Elizabeth Taber, Carlo Enriquez, Daniel Hernandez, Daniel R Hernandez, Dionisio Oscar Medina-Marcelin, Dionisio Oscar Medina-Marcelino, Edgar Ibarra, Ernesto Arturo Fernandez, Jaime B Flores, Jaime Flores, James Espinosa, Jeff Barker, Jim Blackwell, Joseph Macer, Justin Cornish, Karyn Hubbard, Kreshnik Memaj, Lauren Lanzini Coffey, Maria De Kanter, Mohammad Jilani, Paul Frank Attilio, Phillip Capozzi, Quy Le, Robert V Eubanks, Sattar Mohseni, William Bi |  |  | Abdalsattar Albaghdadi, Akeem Berrien, Alberto Demarquez, Bodie Schmidt, Carlo Enriquez, Conner MacDonnell, Daniel Hernandez, David Thomas, Diego Asencio, Dionisio Oscar Medina-Marcelino, Edgar Ibarra, Emily Wilson, Erick Sanchez, Ernesto Arturo Fernandez, Henry Pugsley, James Espinosa, Jesus Gonzalez, Jim Blackwell, Jonathan Weir, Jonathan Rubio, Jose R. Duarte, Josue Morales, Julio C Montoya, Justin Cornish, Kebret Eshetu, Kendall Walls, Kevin Curtis, Kolawole Ayeni, Kreshnik Memaj, LaCraig |  |  | Camille Taber | FL | Hillsborough County Public Schools | J00015708 | HCPS CAT Two Erate Project | Implementation/Deployment | 85% | 485.3% | 4919.41 | -18663.84 | 429133.83 | 1926970 | -379.4% | 429133.83 | 292.5 | 23875.75 | 691755 | 40758.97 |  | 1926970 |  | 17364921.01 | 0 | -1967728.97 | 0%
03/25/25 |  | 09/26/25 | Open | Marco Lish | David Escamilla |  | Dennis Odneal, Marco Lish |  |  | Juan Saenz, Marco Lish |  |  | Dennis Odneal | TX-HOU | University of Nevada Las Vegas | 200002508 | N/A | Planning/Design/Staging | 45% | 40.95% | 99.5 | 58.75 | 0 | 5353.75 | 59.05% | 0 | 0 | 40.75 | 0 | 0 |  | 5353.75 |  | 0 | 18200 | 12846.25 | 70.58%
01/20/25 |  | 09/26/25 | Open | Tray Giddens | Ahmed Al-Zubaidi, David Escamilla, Mark J Chambliss, Saif Qaissi, Wyley Johnson |  | Abdulrahman Farhan, Ahmed Al-Zubaidi, Cory E Hopf, Cory Hopf, David Escamilla, Haley Glasscock, Ibrahim Altaweel, Lindie Lorraine Lamar, Mark J Chambliss, Rogelio Morgado-Perez, Romar Roca, Saif Qaissi, Tray Giddens, Wyley Johnson |  |  | Abdalsattar Albaghdadi, Abdulrahman Farhan, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Stafford MSD | 200001658 | N/A | Planning/Design/Staging | 5% | 9.578% | 485.5 | 439 | 69717.5 | 6525 | 90.42% | 69717.5 | 0 | 46.5 | 0 | 0 |  | 6525 |  | 0 | 92047.48 | 85522.48 | 92.91%
01/27/25 |  | 09/26/25 | Open | Tray Giddens | Ahmed Al-Zubaidi, David Escamilla, Mark J Chambliss, Saif Qaissi, Wyley Johnson |  | Ahmed Al-Zubaidi, Cory Bradfield, Cory Bradfield, David Escamilla, Lindie Lorraine Lamar, Mark J Chambliss, Saif Qaissi, Tray Giddens, Wyley Johnson |  |  | Cory Bradfield, Tray Giddens |  |  | Lindie Lamar | TX-HOU | Stafford MSD | 200001723 | N/A | Planning/Design/Staging | 5% | 2.042% | 146.88 | 143.88 | 18485 | 380 | 97.96% | 18485 | 0 | 3 | 0 | 0 |  | 380 |  | 0 | 24280.2 | 23900.2 | 98.43%
06/30/25 |  | 09/30/25 | Closed | Abiodun David Babasola | Jeremy Williams |  | Abiodun David Babasola, David Babasola, Ismael Velazquez, Jeremy Williams |  |  | N/A |  |  | Ismael Velazquez | FL | City of Pembroke Pines | 200003138 | N/A | Not started | 0% | 0% | 110 | 110 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 24780 | 24780 | 100%
05/05/25 |  | 09/30/25 | Open | Brian Willery | Jacob Parks, Jeffrey Holman |  | Brian Willery, Eric Firestone, Jacob Parks, Jeffrey Holman, Lauren J Kennewell |  |  | Brian Willery, Eric Firestone |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | 200002938 | N/A | Planning/Design/Staging | 5% | 37.5% | 188 | 117.5 | 0 | 10493.75 | 62.5% | 0 | 0 | 70.5 | 0 | 0 |  | 10493.75 |  | 0 | 44343.6 | 33849.85 | 76.34%
05/08/25 |  | 09/30/25 | Open | Christina Rice | David Watkins, Jacob Parks, Jeffrey Holman |  | Christina Rice, Christina Rice, David Watkins, Jacob Parks, Jeffrey Holman, Shawn Sutton |  |  | Christina Rice |  |  | Shawn Sutton | TX-DAL | Denton ISD | 200002813 | N/A | Not started | 0% | 0.1036% | 1205.6 | 1204.35 | 0 | 156.25 | 99.9% | 0 | 0 | 1.25 | 0 | 0 |  | 156.25 |  | 542366.85 | 49464.2 | 49307.95 | 99.68%
06/25/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003118 | N/A | Planning/Design/Staging | 5% | 0.3402% | 1175.7 | 1171.7 | 0 | 500 | 99.66% | 0 | 0 | 4 | 0 | 0 |  | 500 |  | 262961.28 | 154858.2 | 154358.2 | 99.68%
06/25/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003120 | N/A | Planning/Design/Staging | 5% | 0.5387% | 371.25 | 369.25 | 0 | 250 | 99.46% | 0 | 0 | 2 | 0 | 0 |  | 250 |  | 83367.45 | 52997.5 | 52747.5 | 99.53%
06/25/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003121 | N/A | Planning/Design/Staging | 5% | 0.5709% | 700.6 | 696.6 | 0 | 500 | 99.43% | 0 | 0 | 4 | 0 | 0 |  | 500 |  | 159258.24 | 93787.4 | 93287.4 | 99.47%
06/25/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003127 | N/A | Planning/Design/Staging | 5% | 0.4199% | 714.3 | 711.3 | 0 | 375 | 99.58% | 0 | 0 | 3 | 0 | 0 |  | 375 |  | 162961.92 | 95968.5 | 95593.5 | 99.61%
06/25/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | N/A |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003128 | N/A | Planning/Design/Staging | 5% | 0% | 193.55 | 193.55 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 42592.32 | 27434 | 27434 | 100%
06/25/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003129 | N/A | Planning/Design/Staging | 5% | 6% | 25 | 23.5 | 0 | 187.5 | 94% | 0 | 0 | 1.5 | 0 | 0 |  | 187.5 |  | 62194.67 | 3896.8 | 3709.3 | 95.19%
06/26/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | Joanna Herrera |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003130 | N/A | Planning/Design/Staging | 5% | 4.054% | 37 | 35.5 | 0 | 187.5 | 95.95% | 0 | 0 | 1.5 | 0 | 0 |  | 187.5 |  | 90899.91 | 5767.3 | 5579.8 | 96.75%
06/30/25 |  | 09/30/25 | Open | Joanna Herrera | Bryan Brown, Remi Martinez-Montenegro |  | Bryan Brown, Christopher Garcia, Joanna Herrera, Remi Martinez-Montenegro, Xavier A Trevino |  |  | N/A |  |  | Xavier A Trevino | TX-SOUT | Idea Public Schools | 200003139 | N/A | Planning/Design/Staging | 5% | 0% | 384 | 384 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 45815.04 | 37920.8 | 37920.8 | 100%
06/16/25 |  | 09/30/25 | Open | LaQisha Marshall | Ahmed Al-Zubaidi, Steven Walker |  | Ahmed Al-Zubaidi, David Monasmith, David Monasmith, LaQisha Marshall, Steven Walker |  |  | LaQisha Marshall |  |  | David Monasmith | TX-HOU | College Station ISD | 200003091 | N/A | Not started | 0% | 0.322% | 155.25 | 154.75 | 0 | 62.5 | 99.68% | 0 | 0 | 0.5 | 0 | 0 |  | 62.5 |  | 0 | 29995 | 29932.5 | 99.79%
06/19/25 |  | 09/30/25 | Open | Marshall Chuck Pugh | N/A |  | Kristy L Dice, Marshall Chuck Pugh |  |  | N/A |  |  | Kristy L Dice | TX-DAL | Highland Park ISD | 200003105 | N/A | Planning/Design/Staging | 5% | 0% | 60 | 60 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 13446 | 13446 | 100%
10/14/24 |  | 09/30/25 | Open | Marshall Chuck Pugh | Christopher Pheonix Preddy, Warren Wilson |  | Beau C. Devillier, Christopher Pheonix Preddy, Conner MacDonnell, Lauren J Kennewell, Marshall Chuck Pugh , Timothy Fain, Warren Wilson |  |  | Christopher Pheonix Preddy, Marshall Chuck Pugh |  |  | Lauren J Kennewell | TX-DAL | Midlothian ISD | J00019211 | Transportation - Avigilon Unity Video and ACM | On HOLD | 20% | 21.07% | 32.04 | 25.29 | 3624.55 | 1043.75 | 78.93% | 3624.55 | 0 | 6.75 | 918.75 | 0 |  | 1043.75 |  | 0 | 6440.4 | 5396.65 | 83.79%
08/16/24 |  | 09/30/25 | Closed | Marshall Chuck Pugh | N/A |  | Beau C. Devillier, Lauren J Kennewell, Majid Shirzadeh, Marshall Chuck Pugh , William Birdsong |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | J00018849 | Plano ISD 140473 C2 2024 SW AP UPS | Cancelled | 0% | 0% | 9940.79 | 9940.79 | 775084 | 0 | 100% | 775084 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
06/29/23 |  | 09/30/25 | Open | Ryan Scott | Jacob Parks, Jeffrey Holman, Timothy Rosser, William Birdsong |  | Dhulfiqar Al Hashimi, Jorge Ortiz Cardozo, Karen Grant-Dennison, Rusty Bryan, Ryan Scott |  |  | Dhulfiqar Al Hashimi, Jean Pierre Obenda, Jorge Ortiz Cardozo, Marco Lish, Ryan Scott |  |  | Rusty Bryan | TX-DAL | Randall County | J00014449 | July 2023 - WAN Migration | On HOLD | 70% | 25.34% | 247.65 | 184.9 | 32006.25 | 8493.75 | 74.66% | 32006.25 | 0 | 62.75 | 8337.5 | 0 |  | 8493.75 |  | 713835.7 | 34950.4 | 26456.65 | 75.7%
04/17/25 |  | 09/30/25 | Open | Shannon Marie Alvarado | Jeffrey Holman |  | Jason Osuna, Jeffrey Holman, Shannon Marie Alvarado |  |  | Romar Roca, Shannon Marie Alvarado |  |  | Jason Osuna | TX-CEN | City of Artesia | 200002719 | N/A | Planning/Design/Staging | 5% | 9.896% | 212.2 | 191.2 | 0 | 2975 | 90.1% | 0 | 0 | 21 | 0 | 0 |  | 2975 |  | 6946 | 37421.24 | 34446.24 | 92.05%
05/27/25 |  | 09/30/25 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Bryan Geoghan, Shannon Marie Alvarado, Taylor Leger |  |  | George McGann, Shannon Marie Alvarado |  |  | Taylor Leger | TX-DAL | Corsicana ISD | 200003008 | N/A | Planning/Design/Staging | 5% | 3.21% | 93.45 | 90.45 | 0 | 390 | 96.79% | 0 | 0 | 3 | 0 | 0 |  | 390 |  | 75852 | 19682.8 | 19292.8 | 98.02%
04/01/25 |  | 09/30/25 | Open | Shannon Marie Alvarado | Bryan Geoghan |  | Bryan Geoghan, Mark Forehand, Shannon Marie Alvarado |  |  | Henry Pugsley, Shannon Marie Alvarado |  |  | Mark Forehand | TX-DAL | Grapevine-Colleyville ISD | 200002562 | N/A | Implementation/Deployment | 70% | 27.82% | 230.94 | 166.69 | 0 | 10443.75 | 72.18% | 0 | 0 | 64.25 | 0 | 0 |  | 10443.75 |  | 147511.57 | 49434.76 | 38991.01 | 78.87%
06/18/25 |  | 09/30/25 | Closed | Shannon Marie Alvarado | Christopher Pheonix Preddy |  | Alexander Gutman, Christopher Pheonix Preddy, Shannon Marie Alvarado |  |  | N/A |  |  | Alex Gutman | TX-DAL | TXO Energy Partners | 200003104 | N/A | Not started | 0% | 0% | 7.5 | 7.5 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2073.6 | 884.8 | 884.8 | 100%
02/26/24 |  | 09/30/25 | Closed | Summer Abunaja | Michael Brett Beggs |  | Beau C. Devillier, Kristy L Dice, Luis Ovalles, Summer Abunaja |  |  | Henry Pugsley, Luis Ovalles |  |  | Kristy L Dice | TX-DAL | Aledo ISD | J00017666 | T&E - VMWare Support | Implementation/Deployment | 0% | 0% | 0 | -61.25 | 0 | 8478.75 | 0% | 0 | 0 | 61.25 | 6318.75 | 0 |  | 8478.75 |  | 0 | 2457 | -6021.75 | -245.1%
03/20/24 |  | 09/30/25 | Open | Summer Abunaja | N/A |  | Kristian Martell, Larry Noble, Neel Shah, Patrick Joseph Palermo, Summer Abunaja, Thomas Francis LoMonaco |  |  | Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00017867 | Contact Center - T&E Loews Hotels | Implementation/Deployment | 0% | 0% | 0 | -155 | 0 | 29450 | 0% | 0 | 0 | 155 | 19285 | 0 |  | 29450 |  | 0 | 0 | -29450 | 0%
03/25/24 |  | 09/30/25 | Open | Summer Abunaja | N/A |  | Kristian Martell, Larry Noble, Neel Shah, Patrick Joseph Palermo, Summer Abunaja, Thomas Francis LoMonaco |  |  | Kristian Martell, Patrick Joseph Palermo |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00017868 | TCI Reliant Medical T&E | Implementation/Deployment | 0% | 0% | 0 | -92 | 0 | 17480 | 0% | 0 | 0 | 92 | 14440 | 0 |  | 17480 |  | 0 | 0 | -17480 | 0%
05/17/24 |  | 09/30/25 | Open | Summer Abunaja | N/A |  | Kristian Martell, Larry Noble, Neel Shah, Summer Abunaja |  |  | Justin Smallwood, Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00018390 | Boston Children's Hospital Physicians T&E | Implementation/Deployment | 0% | 0% | 0 | -64.5 | 0 | 12125 | 0% | 0 | 0 | 64.5 | 10640 | 0 |  | 12125 |  | 0 | 0 | -12125 | 0%
05/01/24 |  | 09/30/25 | Open | Summer Abunaja | N/A |  | Beau C. Devillier, Joshua Adam Engle, Mark Forehand, Nazario Armenta Barraza, Summer Abunaja |  |  | Nazario Armenta Barraza, Ron Loge, Samuel Newland |  |  | Mark Forehand | TX-DAL | DR Horton | J00018280 | Wireless Consultant T&E | Implementation/Deployment | 0% | 0% | 0 | -31.5 | 0 | 4827.5 | 0% | 0 | 2 | 33.5 | 3217.5 | 0 |  | 4827.5 |  | 0 | 0 | -4827.5 | 0%
05/07/24 |  | 09/30/25 | Open | Summer Abunaja | N/A |  | Aaron Christopher Pfeifer, Jessica Anderson, Summer Abunaja, William Isaac Sears |  |  | Summer Abunaja, Trey Stanford |  |  | Jessica Anderson | US-SP | Summit Broadband | J00018306 | Network WAN Consultant T&E | Implementation/Deployment | 0% | 0% | 0 | -3.5 | 0 | 455 | 0% | 0 | 0 | 3.5 | 455 | 0 |  | 455 |  | 0 | 0 | -455 | 0%
04/15/25 |  | 10/01/25 | Open | Marco Lish | David Watkins |  | David Watkins, Jonathan Weir, Jonathan Weir, Kristy L Dice, Marco Lish, Saravanan Lakshmanan, Sophia Quinter |  |  | Marco Lish, Marshall Chuck Pugh, Saravanan Lakshmanan, Sophia Quinter |  |  | Kristy L Dice | TX-DAL | Lewisville ISD | 200002662 | N/A | Planning/Design/Staging | 10% | 3.879% | 1185.83 | 1139.83 | 0 | 5860 | 96.12% | 0 | 0 | 46 | 0 | 0 |  | 5860 |  | 434211.66 | 239922.9 | 234062.9 | 97.56%
10/02/24 |  | 10/01/25 | Open | Summer Abunaja | N/A |  | Daniel Saenz, Diana Berger, Erick Nunez , Summer Abunaja |  |  | Erick Nunez |  |  | Daniel Saenz | TX-SOUT | Valley View ISD | J00019128 | T&E - Internet Latency Troubleshooting | Implementation/Deployment | 0% | 0% | 0 | -7 | 0 | 875 | 0% | 0 | 0 | 7 | 875 | 0 |  | 875 |  | 0 | 0 | -875 | 0%
06/20/25 |  | 10/02/25 | Open | Tray Giddens | Mark J Chambliss |  | Anthony Towsley, Dustin Huffman, Mark J Chambliss, Tray Giddens |  |  | Anthony Towsley, Tray Giddens |  |  | Dustin Huffman | TX-HOU | Golden Nugget Biloxi | 200003032 | N/A | Planning/Design/Staging | 5% | 1.55% | 258 | 254 | 0 | 530 | 98.45% | 0 | 0 | 4 | 0 | 0 |  | 530 |  | 28325.94 | 50929.16 | 50399.16 | 98.96%
06/05/25 |  | 10/03/25 | Closed | Brian Willery | Jacob Parks, Jeffrey Holman |  | Brian Willery, Jacob Parks, Jeffrey Holman, Lauren J Kennewell |  |  | N/A |  |  | Lauren J Kennewell | TX-DAL | City of Frisco | 200003055 | N/A | Not started | 0% | 0% | 290.53 | 290.53 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 39087.6 | 66232.8 | 66232.8 | 100%
06/09/25 |  | 10/03/25 | Open | Christina Rice | Christopher Ceykovsky |  | Brian Newman, Brian Newman, Christina Rice, Christina Rice, Christopher Ceykovsky, Joshua Parker |  |  | Brian Newman, Christina Rice |  |  | Joshua Parker | TX-DAL | Richardson ISD | 200003062 | N/A | Planning/Design/Staging | 0% | 3.062% | 130.63 | 126.63 | 0 | 515 | 96.94% | 0 | 0 | 4 | 0 | 0 |  | 515 |  | 87919.92 | 17643.2 | 17128.2 | 97.08%
06/04/25 |  | 10/03/25 | Open | Joaquin Marroquin | Ahmed Al-Zubaidi, David Escamilla, Steven Walker, Wyley Johnson |  | Ahmed Al-Zubaidi, Christopher Brown, Christopher Brown, Cory Bradfield, Cory Bradfield, David Escamilla, Joaquin Marroquin, Steven Walker, Wyley Johnson, Xavier A Trevino |  |  | Cory Bradfield, Joaquin Marroquin |  |  | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | 200003048 | N/A | Planning/Design/Staging | 5% | 3.981% | 351.66 | 337.66 | 0 | 1840 | 96.02% | 0 | 0 | 14 | 0 | 0 |  | 1840 |  | 2515824.14 | 94653.6 | 92813.6 | 98.06%
07/01/25 |  | 10/03/25 | Open | LaQisha Marshall | Bryan Geoghan |  | Alexander Gutman, Bryan Geoghan, LaQisha Marshall |  |  | N/A |  |  | Alex Gutman | TX-DAL | Dallas College | 200003152 | N/A | Planning/Design/Staging | 0% | 0% | 162.5 | 162.5 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 40898.8 | 40898.8 | 100%
06/06/25 |  | 10/06/25 | Open | Marshall Chuck Pugh | Christopher Puyear |  | Anthony Towsley, Christopher Puyear, Henry Pugsley, Kristy L Dice, Marshall Chuck Pugh |  |  | Anthony Towsley, Henry Pugsley, Marshall Chuck Pugh |  |  | Kristy L Dice | TX-DAL | Highland Park ISD | 200003065 | N/A | Planning/Design/Staging | 20% | 2.912% | 326.25 | 316.75 | 0 | 1310 | 97.09% | 0 | 0 | 9.5 | 0 | 0 |  | 1310 |  | 470170.8 | 75213.6 | 73903.6 | 98.26%
06/05/25 |  | 10/10/25 | Open | Abiodun David Babasola | Jacob Parks, Jeffrey Holman |  | Abiodun David Babasola, David Babasola, Dhulfiqar Al Hashimi, Jacob Parks, Jeffrey Holman, Kristy L Dice |  |  | Abiodun David Babasola |  |  | Kristy L Dice | TX-DAL | Wichita Falls ISD | 200002990 | N/A | Planning/Design/Staging | 5% | 1.142% | 87.54 | 86.54 | 0 | 125 | 98.86% | 0 | 0 | 1 | 0 | 0 |  | 125 |  | 0 | 9626.84 | 9501.84 | 98.7%
08/07/23 |  | 10/17/25 | Open | Marco Lish | Bryan Geoghan |  | Bryan Geoghan, Camille Elizabeth Taber, George McGann, Jeff Barker, Marco Lish |  |  | George McGann, Marco Lish |  |  | Camille Taber | FL | Hillsborough County Sheriff Office | J00015965 | Avaya to Cisco Phase 2-Emailed SA | Implementation/Deployment | 70% | 52.04% | 1999.31 | 958.81 | 255442.9 | 141372.5 | 47.96% | 255442.9 | 0 | 1040.5 | 99488.75 | 0 |  | 141372.5 |  | 859046.89 | 429566.57 | 288194.07 | 67.09%
10/21/24 |  | 10/23/25 | Open | Jennifer Soliz | Shannon Rico |  | Eric Firestone, Jason Espino, Jeffrey Holman, Jennifer Soliz, Larry Noble, Lonnie Owens, Shannon Rico |  |  | Eric Firestone, Jason Espino, Jennifer Soliz |  |  | Lonnie Owens | TX-CEN | CPS Energy | J00019253 | DCT Phase II Optimization | Implementation/Deployment | 55% | 35.64% | 211.83 | 136.33 | 0 | 10881.25 | 64.36% | 0 | 0 | 75.5 | 0 | 0 |  | 10881.25 |  | 0 | 27806.3 | 16925.05 | 60.87%
12/13/23 |  | 10/30/25 | Open | Ali Al-Haddad | Mark J Chambliss |  | Ali Al-Haddad, Khalid Abunaja, Mark J Chambliss, Meredith A Richardson |  |  | Ahmed Alfayli, Ali Al-Haddad, Andy Pham, Baq Alsaedi, Bryant Bush, Camrin Edwards, Daniel Hernandez, David Dobbs, Devon LeMoine, Dueart Barton, Hector Rivera, Jaime Flores, James Adams, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Julio C Montoya, Justin Cornish, Justin Smallwood, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Nathan Dao, Nicolas Garakani, Paul Serres, Robert Brim, Russell J |  |  | N/A | N/A | Houston ISD | J00018391 | E-Rate 2021-22-23 combined-not deploying | Planning/Design/Staging | 20% | 0% | 0 | -10053.72 | 1351.39 | 907038.85 | 0% | 1351.39 | 911.24 | 10964.96 | 237586.95 | 0 |  | 907038.85 |  | 2032607.16 | 480977.5 | -426061.35 | -88.58%
07/07/25 |  | 10/30/25 | Closed | Ryan Scott | David Watkins |  | Ahmed Jameel, David Watkins, Mario Sanchez, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | N/A |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200002998 | N/A | Planning/Design/Staging | 5% | 0% | 349.2 | 349.2 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 239924.7 | 55192.4 | 55192.4 | 100%
06/10/25 |  | 10/31/25 | Closed | Jason Esry | Daniel Snyder |  | Daniel Snyder, David D Tijerina, Jason Esry |  |  | N/A |  |  | David D Tijerina | TX-CEN | Travis County | 200003070 | N/A | Not started | 0% | 0% | 329.63 | 329.63 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 49700 | 49700 | 100%
05/08/25 |  | 10/31/25 | Open | Jason Matthew Davis | Bryan Geoghan |  | Arcangelo Fanelli, Bryan Geoghan, Jason Matthew Davis, Patrick Joseph Palermo |  |  | Jason Matthew Davis, Patrick Joseph Palermo |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200002623 | N/A | Not started | 20% | 4.928% | 436.25 | 414.75 | 0 | 3955 | 95.07% | 0 | 0 | 21.5 | 0 | 0 |  | 3955 |  | 0 | 109797.2 | 105842.2 | 96.4%
05/08/25 |  | 10/31/25 | Open | Jason Matthew Davis | Bryan Geoghan |  | Arcangelo Fanelli, Bryan Geoghan, Jason Matthew Davis, Patrick Joseph Palermo |  |  | Jason Matthew Davis, Kristian Martell, Patrick Joseph Palermo |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200002793 | N/A | Not started | 20% | 11.08% | 225.63 | 200.63 | 0 | 4587.5 | 88.92% | 0 | 0 | 25 | 0 | 0 |  | 4587.5 |  | 0 | 64537.6 | 59950.1 | 92.89%
06/24/25 |  | 10/31/25 | Closed | Jason Matthew Davis | Bryan Geoghan |  | Arcangelo Fanelli, Bryan Geoghan, Jason Matthew Davis |  |  | N/A |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200002952 | N/A | On HOLD | 0% | 0% | 215.63 | 215.63 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 60110.8 | 60110.8 | 100%
06/24/25 |  | 10/31/25 | Closed | Jason Matthew Davis | N/A |  | Arcangelo Fanelli, Bryan Geoghan, Jason Matthew Davis |  |  | N/A |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | 200002953 | N/A | Not started | 0% | 0% | 65 | 65 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 21744.4 | 21744.4 | 100%
05/08/24 |  | 10/31/25 | Open | LaQisha Marshall | Bryan Geoghan, David Watkins |  | Alexander Gutman, Beau C. Devillier, Christopher Ceykovsky, Jeffery Giles, LaQisha Marshall, Matthew Veach |  |  | Gena Robbins, John Stephen Kurkjian, Karyn Hubbard, LaQisha Marshall, Matthew Veach |  |  | Alex Gutman | TX-DAL | Con-Real Construction | J00015172 | Mountain View Welcome Ctr Network HW Installs | Planning/Design/Staging | 5% | 36.27% | 139.49 | 88.89 | 15204.25 | 6332.5 | 63.72% | 15204.25 | 0 | 50.6 | 5801.25 | 0 |  | 6332.5 |  | 134804.41 | 21195.2 | 14862.7 | 70.12%
03/27/25 |  | 10/31/25 | Open | LaQisha Marshall | Christopher Puyear, Daniel Snyder |  | Christi D Hubbard, Christopher Puyear, Daniel Snyder, George McGann, LaQisha Marshall, Raul Velazquez, Robert Kelly, Robert Kelly |  |  | George McGann, Kevin Curtis, Kolawole Ayeni, LaQisha Marshall, Matthew D'Ambrosio, Paul Serres, Raul Velazquez, Robert Kelly |  |  | Christi D Hubbard | TX-CEN | Manor ISD | 200002483 | N/A | Implementation/Deployment | 50% | 6.671% | 2383.3 | 2224.3 | 0 | 21396.25 | 93.33% | 0 | 0 | 159 | 0 | 0 |  | 21396.25 |  | 506431.2 | 231480.8 | 210084.55 | 90.76%
05/05/25 |  | 10/31/25 | Open | Marco Lish | N/A |  | Jonathan Pendrich, Marco Lish |  |  | N/A |  |  | Jonathan Pendrich | TX-DAL | Oncor Electric Delivery Company LLC | 200002930 | N/A | Cancelled | 0% | 0% | 560.05 | 560.05 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
06/09/25 |  | 10/31/25 | Open | Marshall Chuck Pugh | N/A |  | Christopher Puyear, George McGann, Kristy L Dice, Marshall Chuck Pugh |  |  | N/A |  |  | Kristy L Dice | TX-DAL | Trinity River Authority | 200003069 | N/A | Planning/Design/Staging | 5% | 0% | 33.01 | 33.01 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 7291.92 | 7291.92 | 100%
06/27/25 |  | 10/31/25 | Closed | Walter Clay Knight | N/A |  | Hannah Paul, Walter Clay Knight, Wyley Johnson |  |  | N/A |  |  | Hannah Edmunds | TX-CEN | Texas Parks and Wildlife | 200003134 | N/A | Planning/Design/Staging | 5% | 0% | 103.05 | 103.05 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 20981.6 | 20981.6 | 100%
02/14/25 |  | 10/31/25 | Open | William Chris Roome | George Edwin Jacob |  | Gearld Stanley McNiel, George Edwin Jacob, Jonathan Pendrich, Katharine McCarley, Katherine McCarley, Ron Loge, Stan McNiel, William Chris Roome, William Roome |  |  | Bradley Buchanan, Carlo Enriquez, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jalen Vecchitto, Joshua Hubbard, Joshua Osgood, Justin Mitchell, Lauren Lanzini Coffey, Noah Castleberry, Remijio Hernandez, Ron Loge, William Chris Roome |  |  | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | 200001912 | N/A | Planning/Design/Staging | 10% | 40.1% | 740 | 443.25 | 66900 | 24858.75 | 59.9% | 66900 | 0 | 296.75 | 0 | 0 |  | 24858.75 |  | 1636787.76 | 953120 | 928261.25 | 97.39%
05/19/25 |  | 11/07/25 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Lauren Lanzini Coffey, Mark J Chambliss, Neel Shah, Shiraz Humayun |  |  | Lauren Lanzini Coffey, Ming Chiu |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | J00017209 | FUTURE- Ribbon for Phase 5 locations | On HOLD | 0% | 10% | 400 | 360 | 54800 | 5555 | 90% | 54800 | 0 | 40 | 31.25 | 0 |  | 5555 |  | 169670.5 | 88830 | 83275 | 93.75%
11/08/23 |  | 11/07/25 | Open | Summer Abunaja | Jeremy Hoffpauir |  | Jessica Anderson, Summer Abunaja, William Isaac Sears |  |  | Aaron Christopher Pfeifer |  |  | Jessica Anderson | US-SP | City of Valparaiso | J00016891 | WAN T&E | Not started | 0% | 0% | 0 | -23.75 | 0 | 3206.25 | 0% | 0 | 0 | 23.75 | 3206.25 | 0 |  | 3206.25 |  | 0 | 4115 | 908.75 | 22.08%
05/03/24 |  | 11/13/25 | Open | Abiodun David Babasola | David Watkins, Jacob Parks, Jeffrey Holman |  | Abiodun David Babasola, David Watkins, David Babasola, Eric Firestone, Jacob Parks, Jeffrey Holman, Kristy L Dice, Saravanan Lakshmanan |  |  | Abiodun David Babasola, Eric Firestone, Saravanan Lakshmanan |  |  | Kristy L Dice | TX-DAL | Prestonwood Baptist Church | J00018069 | Wireless and ISE Upgrade and Authentication | On HOLD | 65% | 87.14% | 206 | 26.5 | 28455 | 24525 | 12.86% | 28455 | 0 | 179.5 | 22145 | 0 |  | 24525 |  | 35562.2 | 45614.4 | 21089.4 | 46.23%
11/14/24 |  | 11/13/25 | Open | Summer Abunaja | Mark J Chambliss |  | Mark J Chambliss |  |  | Jordan Johnson, Ming Chiu |  |  | David Monasmith | TX-HOU | Texas A&M University | 200000122 | N/A | Implementation/Deployment | 0% | 0% | 0 | -9.25 | 0 | 1272.5 | 0% | 0 | 0 | 9.25 | 0 | 0 |  | 1272.5 |  | 0 | 612.5 | -660 | -107.8%
07/08/25 |  | 11/14/25 | Closed | Abiodun David Babasola | Bryan Brown, Christopher Puyear |  | Abiodun David Babasola, Anthony Towsley, Bryan Brown, Christopher Garcia, Christopher Puyear, David Babasola, Kristy L Dice |  |  | N/A |  |  | Kristy L Dice | TX-DAL | Prestonwood Christian Academy | 200003081 | N/A | Planning/Design/Staging | 5% | 0% | 733.81 | 733.81 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 220534.45 | 98987.48 | 98987.48 | 100%
11/26/24 |  | 11/25/25 | Open | Summer Abunaja | Wyley Johnson |  | Eric Firestone, Jacob Sennett, Jay David Carothers, Summer Abunaja, Wyley Johnson |  |  | Eric Firestone |  |  | N/A | N/A | Transworld Network, Corp | 200000209 | N/A | Implementation/Deployment | 0% | 0% | 0 | -73.25 | 0 | 10987.5 | 0% | 0 | 0 | 73.25 | 0 | 0 |  | 10987.5 |  | 0 | 15337.5 | 4350 | 28.36%
04/09/25 |  | 11/28/25 | Open | Christina Rice | Jacob Parks, Jeffrey Holman, Joshua Adam Engle |  | Caleb Henry, Christina Rice, Christina Rice, Frank Jaimes, Jacob Parks, Jeffrey Holman, Joshua Adam Engle, Mark Forehand, Ryan Frankeberger |  |  | Caleb Henry, Christina Rice, Dante Torres, Frank Jaimes, Gabriel Lantigua, Jacob Hill, Jalen Vecchitto, John Johnson, Noah Castleberry, Noah Trump, Ryan Frankeberger |  |  | Mark Forehand | TX-DAL | UT Southwestern Medical Center | 200002634 | N/A | Not started | 0% | 21.58% | 363.75 | 293.5 | 0 | 5733.75 | 80.69% | 0 | 8.25 | 78.5 | 495 | 0 |  | 5733.75 |  | 1354176.14 | 59263.8 | 53530.05 | 90.33%
01/29/24 |  | 11/28/25 | Open | Ryan Scott | Michael Brett Beggs |  | Arcangelo Fanelli, Beau C. Devillier, Bryan Mullen, Michael Brett Beggs, Ron Loge, Ryan Scott, Taylor Leger, Tony Dean Skipworth |  |  | Bryan Mullen, Ron Loge, Ryan Scott |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00017306 | 2023 DC Core ACI Optimization | Implementation/Deployment | 60% | 78.15% | 541.25 | 118.25 | 71986.25 | 53125 | 21.85% | 71986.25 | 0 | 423 | 28000 | 0 |  | 53125 |  | 0 | 168369.6 | 115244.6 | 68.45%
04/09/25 |  | 11/28/25 | Open | Shannon Marie Alvarado | David Watkins, Michael Brett Beggs |  | Arcangelo Fanelli, David Watkins, Michael Brett Beggs, Shannon Marie Alvarado |  |  | Jeffery Alan Jorzig, Jorge Ortiz Cardozo, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Baptist Hospitals of Southeast Texas | 200002598 | N/A | Planning/Design/Staging | 30% | 5.721% | 1669.25 | 1577.25 | 0 | 11937.5 | 94.49% | 0 | 3.5 | 95.5 | 437.5 | 0 |  | 11937.5 |  | 1393666.9 | 366314.8 | 354377.3 | 96.74%
12/03/24 |  | 12/02/25 | Closed | Summer Abunaja | Christopher Ceykovsky |  | Brian Newman, Brian Newman, Christopher Ceykovsky, Eric Rodriguez, Summer Abunaja |  |  | Brian Newman, Erick Nunez |  |  | N/A | N/A | Harlingen CISD | 200000272 | N/A | Not started | 0% | 0% | 0 | -11.5 | 0 | 1550 | 0% | 0 | 0 | 11.5 | 0 | 0 |  | 1550 |  | 0 | 175 | -1375 | -785.7%
12/06/24 |  | 12/05/25 | Open | Shannon Marie Alvarado | Emilio Carrillo |  | David Neal Gravatt, Emilio Carrillo, Joseph Boglino, Shannon Marie Alvarado |  |  | David Neal Gravatt, Shannon Marie Alvarado |  |  | Joseph Boglino | US-FED | U.S. Peace Corps | 200000270 | N/A | Closed | 0% | 0% | 0 | -8.5 | 0 | 1062.5 | 0% | 0 | 0 | 8.5 | 0 | 0 |  | 1062.5 |  | 0 | 3382.5 | 2320 | 68.59%
06/25/25 |  | 12/05/25 | Open | Walter Clay Knight | Wyley Johnson |  | Hannah Paul, Timothy Sean Marcyes, Walter Clay Knight, Wyley Johnson |  |  | Walter Clay Knight |  |  | Hannah Edmunds | TX-CEN | Texas Water Development Board | 200003117 | N/A | Planning/Design/Staging | 5% | 0.5246% | 381.18 | 379.18 | 0 | 250 | 99.48% | 0 | 0 | 2 | 0 | 0 |  | 250 |  | 0 | 79189.6 | 78939.6 | 99.68%
12/10/24 |  | 12/09/25 | Open | Summer Abunaja | Mark J Chambliss |  | George McGann, Monica Johnson, Summer Abunaja |  |  | George McGann |  |  | N/A | N/A | Dickinson ISD | 200000347 | N/A | Implementation/Deployment | 0% | 0% | 0 | -1 | 0 | 140 | 0% | 0 | 0 | 1 | 0 | 0 |  | 140 |  | 0 | 188.5 | 48.5 | 25.73%
12/13/24 |  | 12/12/25 | Open | Jason Esry | Jacob Parks, Jeffrey Holman, Joshua Adam Engle, Majid Shirzadeh, William Birdsong |  | Alexander Gutman, Beau C. Devillier, Jacob Parks, Jalen Vecchitto, Jason Esry, Jeffrey Holman, Joshua Adam Engle, Joshua Osgood, Justin Mitchell, Justin Thompson, Majid Shirzadeh, Sean Cowhey, Shannon Mobley, William Birdsong |  |  | Bradley Buchanan, Caleb Henry, Calvin Darby, Carlo Enriquez, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jalen Vecchitto, Jason Esry, Jayden Colon, Jeffery Giles, Jesus Escobedo, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Mitchell, Justin Thompson, Kebret Eshetu, Kendall Walls, Kirk O'Guinn, Nazario Armenta Barraza, Noah Castleberry, Patrick Shea Thompson, Phillip Ma Lim, Quy Le, Remijio Hernandez, Ryan Frankeberger, Samuel Gonzalez, Sean Cowhey, Thai Truo |  |  | Alex Gutman | TX-DAL | Dallas ISD | J00018682 | 2024 New Construction | Implementation/Deployment | 20% | 113.3% | 3963.52 | -356.23 | 362682.15 | 416230 | -8.988% | 362682.15 | 171.75 | 4491.5 | 113380 | 0 |  | 416230 |  | 5851903.72 | 736621.6 | 320391.6 | 43.49%
12/14/23 |  | 12/12/25 | Open | Summer Abunaja | N/A |  | Jamie Lewis, Jeff Barker, Summer Abunaja |  |  | Aaron Christopher Pfeifer |  |  | Jamie Lewis | US-SP | Stupp Bros | J00017145 | T&E - SFL-081123-JBR | Implementation/Deployment | 0% | 0% | 0 | -95.75 | 0 | 12926.25 | 0% | 0 | 0 | 95.75 | 12352.5 | 0 |  | 12926.25 |  | 0 | 0 | -12926.25 | 0%
01/15/25 |  | 12/16/25 | Open | Walter Clay Knight | David Watkins, George Delp |  | Alexander Gutman, David Watkins, George Delp, Rafael Rodriguez-Vargas |  |  | Rafael Rodriguez-Vargas, Walter Clay Knight |  |  | Alex Gutman | TX-DAL | Dallas County of Texas | 200001632 | N/A | Planning/Design/Staging | 25% | 3.837% | 1264 | 1215.5 | 0 | 6092.5 | 96.16% | 0 | 0 | 48.5 | 0 | 0 |  | 6092.5 |  | 260248.96 | 0 | -6092.5 | 0%
12/18/24 |  | 12/17/25 | Closed | Summer Abunaja | Jacob Parks, Jeffrey Holman |  | Jacob Parks, Jeffrey Holman, Kristy L Dice, Summer Abunaja |  |  | Abdulrahman Farhan, Christopher Brown, Eric Firestone, Erick Sanchez, Henry Pugsley, Jacob Sennett, Jonathan Weir, Luis Ovalles, Moises Rodriguez, Saravanan Lakshmanan |  |  | Kristy L Dice | TX-DAL | Highland Park ISD | 200000882 | N/A | Not started | 50% | 0% | 0 | -192.25 | 195.26 | 28306.25 | 0% | 195.26 | 6 | 198.25 | 810 | 0 |  | 28306.25 |  | 0 | 55151.25 | 26845 | 48.68%
08/24/23 |  | 12/19/25 | Open | Christina Rice | Bryan Geoghan |  | Beau C. Devillier, Bryan Geoghan, Christina Rice, Christina Rice, Conner MacDonnell, Henry Pugsley, Karyn Hubbard, Shawn Sutton |  |  | Brian Newman, Christina Rice, Clinton Bennett Deason, Conner MacDonnell, Dante Torres, Dylan Pittsinger, Henry Pugsley, Jacob Hill, Joel Hubbard, Joshua Hubbard, Ming Chiu |  |  | Shawn Sutton | TX-DAL | Northwest ISD | J00016307 | NISD: District-Wide Olympus Deployment | Implementation/Deployment | 30% | 25.92% | 5275.31 | 4001.91 | 440085.14 | 156786.25 | 75.86% | 440085.14 | 94 | 1367.4 | 81090 | 53.02 |  | 156786.25 |  | 1430536.4 | 495754.4 | 338915.13 | 68.36%
07/01/25 |  | 12/19/25 | Closed | Summer Abunaja | N/A |  | Neel Shah, Summer Abunaja |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200003147 | N/A | Not started | 0% | 0% | 583.63 | 583.63 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 75862.2 | 78984.8 | 78984.8 | 100%
07/01/25 |  | 12/19/25 | Closed | Summer Abunaja | Ahmed Al-Zubaidi, David Watkins |  | Ahmed Al-Zubaidi, David Watkins, Neel Shah, Summer Abunaja, Wyley Johnson |  |  | N/A |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200003148 | N/A | Not started | 0% | 0% | 521.53 | 521.53 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 236161.63 | 66343.2 | 66343.2 | 100%
12/21/23 |  | 12/22/25 | Closed | Karyn Hubbard | David Watkins |  | Alexander Gutman, Beau C. Devillier, Jonathan Weir, Jonathan Weir, Karyn Hubbard |  |  | Gena Robbins, Jonathan Weir, Sophia Quinter |  |  | Alex Gutman | TX-DAL | Dallas College | J00017208 | Eng Help - New Construction T&E - PO-000009312 | Cancelled | 0% | 0% | 0 | -4.5 | 0 | 600 | 0% | 0 | 0 | 4.5 | 600 | 0 |  | 600 |  | 0 | 48000 | 47400 | 98.75%
01/04/23 |  | 12/26/25 | Open | Ryan Scott | David Watkins |  | Arcangelo Fanelli, David Watkins, Erick Sanchez, Ryan Scott, Taylor Leger |  |  | Carlo Enriquez, Joshua Hubbard, Justin Thompson, Ryan Scott |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00013266 | Utility Plant Ruggedized Switch Installs | On HOLD | 45% | 23.29% | 90.16 | 70.66 | 7463.87 | 2105 | 78.37% | 7463.87 | 1.5 | 21 | 1886.25 | 187.51 |  | 2105 |  | 138787.64 | 13613.2 | 11320.69 | 83.16%
12/30/22 |  | 12/30/25 | Open | Walter Clay Knight | Amanda Barney, George Delp, Tom Haag |  | Amanda Barney, Andrew G Wagenhofer, Cory E Hopf, Cory Hopf, Craig St. Rose, Craig St. Rose, Daniel Hernandez, Daniel R Hernandez, David Irek, David Dobbs, David James Irek, Elizabeth Diaz, George Delp, Jerry Rocco, Jorge Ortiz Cardozo, Jose E. Duarte Jr, Jose R Duarte, Jose R. Duarte, Kinton Connelly, Larry Noble, Thomas Haag, Timothy Rosser, Tom Haag |  |  | Aaron Abshire, Aaron Christopher Pfeifer, Andrew G Wagenhofer, Carlo Enriquez, Craig St. Rose, Daniel Hernandez, Darrell Walton, Darrell Walton, David Dobbs, Dionisio Oscar Medina-Marcelin, Dionisio Oscar Medina-Marcelino, Elizabeth Diaz, Jorge Ortiz Cardozo, Jose Gutierrez, Jose R. Duarte, Julian M Rodriguez-Yunes, Kebret Eshetu, Kendall Walls, Quy Le, Rafael Rodriguez-Vargas, Walter Clay Knight, William Chris Roome, Yasmeen Darawshah, Yonathan Fadel |  |  | Jason Osuna | TX-CEN | Chicago Public Schools | J00010100 | Cisco WAN HW Deployment YR1 | Implementation/Deployment | 55% | 106.1% | 6657.01 | -100.49 | 751018.81 | 646257.5 | -1.51% | 751018.81 | 302.5 | 7060 | 535593.75 | 76706.95 |  | 646257.5 |  | 10759919.25 | 1124830.6 | 401866.15 | 35.73%
03/03/25 |  | 12/31/25 | Open | Jason Matthew Davis | Amanda Barney, Chad Hart, David Watkins, Kristian Martell, Mark J Chambliss |  | Amanda Barney, Christine A Hupe, David Laurence Fine, Jason Matthew Davis, Kristian Martell, Lauren Lanzini Coffey, Neel Shah, Taylar Hansen, Tim Losee |  |  | Carlos Montalvo, David Laurence Fine, Jason Matthew Davis, Kristian Martell, Lauren Lanzini Coffey, Thomas Francis LoMonaco, Tim Losee |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200002160 | N/A | Planning/Design/Staging | 10% | 4.738% | 14801.65 | 14100.4 | 0 | 118813.75 | 95.26% | 0 | 0 | 701.25 | 0 | 0 |  | 118813.75 |  | 0 | 4006141.2 | 3887327.45 | 97.03%
06/24/24 |  | 12/31/25 | Open | Marshall Chuck Pugh | Majid Shirzadeh, William Birdsong |  | Austen Howard, Beau C. Devillier, Conner MacDonnell, Dante Torres, Jeffery Alan Jorzig, Jeffery Jorzig, Joshua Hubbard, Lauren J Kennewell, Majid Shirzadeh, Marshall Chuck Pugh , Remijio Hernandez, Ryan Frankeberger, Timothy Fain, Vitalii Stepanchenko, William Birdsong |  |  | Austen Howard, Bryce Evans, Carlo Enriquez, Dante Torres, Jalen Vecchitto, Jeffery Alan Jorzig, Jeffery Giles, Joshua Hubbard, Justin Mitchell, Kendall Walls, Marshall Chuck Pugh, Noah Trump, Phillip Ma Lim, Quy Le, Remijio Hernandez, Ryan Frankeberger, Vitalii Stepanchenko, William Chris Roome, Yonathan Fadel |  |  | Lauren J Kennewell | TX-DAL | Plano ISD | J00018578 | Phase 2 - C2 2024 SW AP UPS | Planning/Design/Staging | 30% | 19.16% | 9940.79 | 8154.54 | 776104.14 | 160696.25 | 82.03% | 776104.14 | 118.25 | 1904.5 | 28706.25 | 0 |  | 160696.25 |  | 0 | 1295683.36 | 1134987.11 | 87.6%
02/03/25 |  | 12/31/25 | Open | Ryan Scott | David Watkins |  | David Watkins, Jesus Escobedo, Karen Grant-Dennison, Mohammed Almoola, Rusty Bryan, Ryan Scott, William Chris Roome |  |  | Ahmed Jameel, Devin Moreno, Ryan Scott, William Chris Roome |  |  | Rusty Bryan | TX-DAL | Tenet Health Care | 200000261 | N/A | Planning/Design/Staging | 5% | 3.2% | 3461.33 | 3350.58 | 340363.85 | 12985 | 96.8% | 340363.85 | 0 | 110.75 | 0 | 0 |  | 12985 |  | 3177814.04 | 543934.8 | 530949.8 | 97.61%
02/05/25 |  | 12/31/25 | Open | Shannon Marie Alvarado | Steven Walker |  | Arcangelo Fanelli, Christopher Brown, Christopher Brown, Shannon Marie Alvarado, Steven Walker |  |  | Christopher Brown, Shannon Marie Alvarado |  |  | Arcangelo Fanelli | TX-DAL | Arlington ISD | 200001852 | N/A | On HOLD | 75% | 55.68% | 46.25 | 20.5 | 6151.25 | 3416.25 | 44.32% | 6151.25 | 0 | 25.75 | 0 | 0 |  | 3416.25 |  | 0 | 9042 | 5625.75 | 62.22%
12/04/24 |  | 12/31/25 | Open | Shannon Marie Alvarado | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, Shannon Marie Alvarado |  |  | Henry Pugsley, Shannon Marie Alvarado |  |  | Christi D Hubbard | TX-CEN | City of Austin - Aviation Dept | 200000233 | N/A | Planning/Design/Staging | 10% | 11.93% | 136.25 | 120 | 19211.25 | 2643.75 | 88.07% | 19211.25 | 0 | 16.25 | 0 | 0 |  | 2643.75 |  | 22212 | 26120.48 | 23476.73 | 89.88%
04/07/25 |  | 12/31/25 | Open | Shannon Marie Alvarado | Christopher Puyear |  | Christi D Hubbard, Christopher Puyear, Shannon Marie Alvarado |  |  | Henry Pugsley, Shannon Marie Alvarado |  |  | Christi D Hubbard | TX-CEN | City of Austin - Aviation Dept | 200002555 | N/A | Planning/Design/Staging | 10% | 21.36% | 55 | 43.25 | 0 | 1956.25 | 78.64% | 0 | 0 | 11.75 | 0 | 0 |  | 1956.25 |  | 0 | 10585.2 | 8628.95 | 81.52%
01/13/25 |  | 12/31/25 | Open | Shannon Marie Alvarado | Ahmed Al-Zubaidi, Wyley Johnson |  | Ahmed Al-Zubaidi, Eric Firestone, Jessica Anderson, Shannon Marie Alvarado, Wyley Johnson |  |  | Eric Firestone, Shannon Marie Alvarado |  |  | Jessica Anderson | US-SP | Louisiana Energy & Power Authority | 200001602 | N/A | Closed | 100% | 57.8% | 74.4 | 36.65 | 11897.6 | 6350 | 49.26% | 11897.6 | 5.25 | 43 | 787.5 | 0 |  | 6350 |  | 0 | 17803.2 | 11453.2 | 64.33%
03/25/24 |  | 12/31/25 | Open | Summer Abunaja | N/A |  | Kristian Martell, Larry Noble, Neel Shah, Patrick Joseph Palermo, Summer Abunaja, Thomas Francis LoMonaco |  |  | Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00017869 | Americo T&E | Implementation/Deployment | 0% | 0% | 0 | -327 | 0 | 62130 | 0% | 0 | 0 | 327 | 43415 | 0 |  | 62130 |  | 0 | 0 | -62130 | 0%
03/29/24 |  | 12/31/25 | Open | Summer Abunaja | Daniel Snyder |  | Amy Martinez-Nagy, Daniel Snyder, David D Tijerina, Jeffrey Charles Primeaux, Jeffrey Primeaux, Larry Noble, Summer Abunaja, Taylor Poole |  |  | Anthony Onyeka Madubike, Brian David Malone, Dustin Randall Legg, James Cobb, Jeffrey Charles Primeaux, Julio Perez |  |  | David D Tijerina | TX-CEN | University of Texas - Austin | J00017993 | Tech & Consultant Staffing T&E | Implementation/Deployment | 0% | 0% | 0 | -6639.4 | 0 | 419653 | 0% | 0 | 1.75 | 6641.15 | 203813 | 139973.53 |  | 419653 |  | 455715 | 226100 | -333526.53 | -147.5%
04/16/24 |  | 01/01/26 | Open | Ryan Scott | N/A |  | Arcangelo Fanelli, Beau C. Devillier, Ryan Scott, Taylor Leger |  |  | Devin Moreno, Kristian Martell, Ming Chiu, Noah Castleberry, Patrick Joseph Palermo, Prince Owusu, Ron Loge, Ryan Scott, Samuel Newland, Tony Dean Skipworth |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00018108 | T&E - 1591988-CAP- Phase 3 | Implementation/Deployment | 0% | 0% | 0 | -409.75 | 0 | 66648.75 | 0% | 0 | 0 | 409.75 | 59558.75 | 0 |  | 66648.75 |  | 0 | 0 | -66648.75 | 0%
12/05/24 |  | 01/02/26 | Open | Lauren Lanzini Coffey | Mark J Chambliss |  | Andrew Longcor, Andrew Nguyen Longcor, Carlos Montalvo, Christine A Hupe, Jason Matthew Davis, Lauren Lanzini Coffey, Mark J Chambliss, Ming Chiu, Neel Shah, Taylar Hansen |  |  | Andrew Nguyen Longcor, Andy Pham, Bryant Bush, Carlos Montalvo, David Dobbs, Devon LeMoine, James Adams, Jason Matthew Davis, Jerald Garner, Jesus Gonzalez, John Scott Fletcher , Jose R. Duarte, Justin Cornish, Justin Smallwood, Kenneth Stevenson, Kevin Roderick, Kolawole Ayeni, Kord Mullins, Lauren Lanzini Coffey, Luis Alvarez, Ming Chiu, Mohammed Al-Shaikhli, Nicolas Garakani, Patrick Joseph Palermo, Russell James Bugarin, Summer Abunaja, Trenton Smith, Younus Alabbood |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200000238 | N/A | Implementation/Deployment | 25% | 19.32% | 29279.73 | 24320.48 | 2523.25 | 590661.25 | 83.06% | 2523.25 | 698.25 | 5657.5 | 65055 | 24765 |  | 590661.25 |  | 1399658.9 | 5115326 | 4499899.75 | 87.97%
01/24/24 |  | 01/23/26 | Closed | Shannon Marie Alvarado | N/A |  | Christi D Hubbard, Christopher Puyear, David Watkins, Hamzeh Tahat, Larry Noble, Matthew Duncan, Shannon Marie Alvarado |  |  | Shannon Marie Alvarado |  |  | Christi D Hubbard | TX-CEN | City of Austin - Aviation Dept | J00017494 | CANCELLED | Cancelled | 0% | 0% | 0 | -0.5 | 0 | 62.5 | 0% | 0 | 0 | 0.5 | 62.5 | 0 |  | 62.5 |  | 0 | 0 | -62.5 | 0%
01/29/24 |  | 01/28/26 | Closed | Ryan Scott | N/A |  | George Delp, Jeff Barker, Jessica Anderson, Rafael Rodriguez-Vargas, Ryan Scott |  |  | Eric Firestone, Rafael Rodriguez-Vargas, Ryan Scott |  |  | Jessica Anderson | US-SP | Bluegrass Network | J00017438 | Time & Expense - WAN Consultant - 1149 | Not started | 0% | 0% | 0 | -45.5 | 0 | 6158.75 | 0% | 0 | 0 | 45.5 | 1651.25 | 0 |  | 6158.75 |  | 0 | 0 | -6158.75 | 0%
05/12/25 |  | 01/30/26 | Open | Brittney Antoinette Hickman | David Watkins, Michael Brett Beggs |  | Alexander Liu, Arcangelo Fanelli, Bradley Buchanan, Brittney Antoinette Hickman, Bryan Mullen, Brycen Dimas, Caleb Henry, Conner MacDonnell, David Watkins, Devin Moreno, Erick Sanchez, Frank Jaimes, Jalen Vecchitto, Jayden Colon, John Johnson, Joshua Osgood, Michael Brett Beggs, Noah Castleberry, Noah Trump, Quan Tran, Riley Jezek, Sean Cowhey, Tavis Jackson, Taylor Poole |  |  | Abiodun David Babasola, Alexander Liu, Bradley Buchanan, Brittney Antoinette Hickman, Bryan Mullen, Brycen Dimas, Caleb Henry, Carlo Enriquez, Conner MacDonnell, Devin Moreno, Erick Sanchez, Frank Jaimes, Gabriel Lantigua, Jacob Hill, Jalen Vecchitto, Jayden Colon, John Johnson, Jonathan Weir, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Mitchell, Justin Thompson, Kendall Walls, Matthew Veach, Noah Castleberry, Noah Trump, Quy Le, Remijio Hernandez, Ryan Frankeberger, Samuel Gonzalez, |  |  | Arcangelo Fanelli | TX-DAL | Fort Worth ISD | 200002923 | N/A | Implementation/Deployment | 55% | 62.96% | 4965.41 | 1983.66 | 0 | 237640 | 39.95% | 0 | 144.5 | 3126.25 | 9060 | 0 |  | 237640 |  | 6571428.53 | 417179.5 | 179539.5 | 43.04%
02/07/24 |  | 02/06/26 | Open | Richard Keith Arnst | Bryan Geoghan |  | Bryan Geoghan, Christopher Butler, Ming Chiu, Randy Schamberger, Richard Keith Arnst |  |  | Ming Chiu, Richard Keith Arnst |  |  | Randy Schamberger | FL | Collier County Board of County Commissioners | J00017482 | Collaboration Upgrade | Closed | 0% | 0% | 0 | -123.75 | 0 | 17163.75 | 0% | 0 | 0 | 123.75 | 17163.75 | 0 |  | 17163.75 |  | 0 | 28725 | 11561.25 | 40.25%
02/16/24 |  | 02/16/26 | Open | Summer Abunaja | Timothy Ramsey |  | Daniel Saenz, Diana Berger, Sophia Quinter, Summer Abunaja, Timothy Ramsey |  |  | Sophia Quinter |  |  | Daniel Saenz | TX-SOUT | Texas A&M International University | J00017626 | ISE Support T&E | Not started | 0% | 0% | 0 | -77 | 0 | 11550 | 0% | 0 | 0 | 77 | 6300 | 0 |  | 11550 |  | 0 | 8025 | -3525 | -43.93%
03/06/25 |  | 03/05/26 | Open | Summer Abunaja | Mark J Chambliss |  | Jason Osuna, Mark J Chambliss, Summer Abunaja |  |  | Anthony Towsley |  |  | Jason Osuna | TX-CEN | Cobre Consolidated School District | 200002345 | N/A | Implementation/Deployment | 0% | 0% | 0 | -16.5 | 0 | 2310 | 0% | 0 | 0 | 16.5 | 0 | 0 |  | 2310 |  | 0 | 11300 | 8990 | 79.56%
03/19/24 |  | 03/18/26 | Open | Summer Abunaja | N/A |  | Kristian Martell, Larry Noble, Michael B Griffin, Neel Shah, Patrick Joseph Palermo, Summer Abunaja, Thomas Francis LoMonaco |  |  | Patrick Joseph Palermo, Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00017863 | ATSG, Montefiore Medical Center WxCCE T&E | Not started | 0% | 0% | 0 | -93.5 | 0 | 17765 | 0% | 0 | 0 | 93.5 | 15010 | 0 |  | 17765 |  | 0 | 0 | -17765 | 0%
07/05/24 |  | 03/24/26 | Open | Marco Lish | Ahmed Al-Zubaidi, Saif Qaissi |  | Abdalsattar Albaghdadi, Ahmed Al-Zubaidi, Dhulfiqar Al Hashimi, Larry Noble, Marco Lish, Neel Shah, Saif Qaissi |  |  | Abdalsattar Albaghdadi, Abdulrahman Farhan, Dhulfiqar Al Hashimi, Marco Lish, Marshall Chuck Pugh |  |  | Neel Shah | TX-HOU | City of Houston Police Dept | J00017828 | HPD Site to Site VPN | Implementation/Deployment | 80% | 102% | 166.25 | -3.25 | 23791.25 | 24712.5 | -1.955% | 23791.25 | 0 | 169.5 | 23600 | 0 |  | 24712.5 |  | 0 | 39255.2 | 14542.7 | 37.05%
12/22/22 |  | 04/17/26 | Open | Robert McIver | Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Hugh Miller, Michael Brett Beggs, Wyley Johnson |  | Abdalsattar Albaghdadi, Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Cory Bradfield, Cory Bradfield, Daniel Hernandez, Daniel R Hernandez, David Monasmith, David Monasmith, Dhulfiqar Al Hashimi, Ernesto Gonzalez, Fadi Ashour, Mark Lynd, Michael Brett Beggs, Mohammed Almoola, Quoc Nguyen, Robert McIver, Romar Roca, Timothy Sean Marcyes, Wyley Johnson |  |  | Abdalsattar Albaghdadi, Albert Bernal, Cory Bradfield, Craig St. Rose, David Dobbs, Dhulfiqar Al Hashimi, Erick Nunez , Ernesto Gonzalez, James Adams, Jose R. Duarte, Justin Smallwood, Kendric Mamou, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Mohammed Almoola, Mohaymen Sodi, Moises Rodriguez, Mustafa Al-Tamimi, Paul Serres, Rafael Rodriguez-Vargas, Robert McIver, Timothy Sean Marcyes |  |  | David Monasmith | TX-HOU | Texas A&M System | J00014492 | Rellis Campus - Core Network Refresh | Planning/Design/Staging | 40% | 73.68% | 2440.44 | 742.61 | 279798.13 | 235074.25 | 30.43% | 279798.13 | 100.25 | 1798.08 | 133933 | 1154.69 |  | 235074.25 |  | 4123249.95 | 632171.96 | 395943.02 | 62.63%
02/20/25 |  | 04/30/26 | Closed | Robert McIver | N/A |  | Daniel Saenz, Edward Padron, Robert McIver |  |  | N/A |  |  | Daniel Saenz | TX-SOUT | South Texas ISD | 200001974 | N/A | Closed | 0% | 0% | 172.5 | 172.5 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
05/02/24 |  | 05/01/26 | Closed | Summer Abunaja | N/A |  | Beau C. Devillier, Katharine McCarley, Katherine McCarley, Luis Ovalles, Michael Brett Beggs, Summer Abunaja |  |  | Luis Ovalles, Summer Abunaja |  |  | Katie McCarley | TX-DAL | Coblentz Patch Duffy & Bass LLP | J00018301 | UCS Fabric Interconnect Replacement Support T&E | Closed | 0% | 0% | 0 | -6 | 0 | 740 | 0% | 0 | 0 | 6 | 740 | 0 |  | 740 |  | 0 | 0 | -740 | 0%
05/02/24 |  | 05/01/26 | Closed | Summer Abunaja | N/A |  | Beau C. Devillier, Katharine McCarley, Katherine McCarley, Luis Ovalles, Michael Brett Beggs, Summer Abunaja |  |  | Luis Ovalles, Summer Abunaja |  |  | N/A | N/A | Coblentz Patch Duffy & Bass LLP | J00018301 | UCS Fabric Interconnect Replacement Support T&E | Closed | 100% | 0% | 26.4 | 26.4 | 3410 | 0 | 100% | 3410 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0%
05/21/25 |  | 05/20/26 | Open | Karyn Hubbard | N/A |  | Karyn Hubbard, Neel Shah |  |  | Jennifer Galvan |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200003005 | N/A | Not started | 0% | 0% | 0 | -232 | 0 | 23200 | 0% | 0 | 0 | 232 | 0 | 0 |  | 23200 |  | 0 | 0 | -23200 | 0%
05/23/24 |  | 05/22/26 | Open | Summer Abunaja | N/A |  | Larry Noble, Neel Shah, Summer Abunaja |  |  | Patrick Joseph Palermo, Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00018436 | Yale New Haven Health | Not started | 0% | 0% | 0 | -6.5 | 0 | 1235 | 0% | 0 | 0 | 6.5 | 1235 | 0 |  | 1235 |  | 0 | 0 | -1235 | 0%
07/24/24 |  | 07/23/26 | Open | Summer Abunaja | Christopher Puyear |  | Christi D Hubbard, George McGann, Larry Noble, Summer Abunaja |  |  | George McGann |  |  | Christi D Hubbard | TX-CEN | Manor ISD | J00018714 | T&E - Dial Plan Assistance for Police Department | Not started | 0% | 0% | 0 | -6 | 0 | 840 | 0% | 0 | 0 | 6 | 420 | 0 |  | 840 |  | 0 | 1050 | 210 | 20%
10/11/24 |  | 07/29/26 | Closed | Walter Clay Knight | George Delp |  | George Delp, Jessica Anderson, William Isaac Sears |  |  | Aaron Christopher Pfeifer, Walter Clay Knight |  |  | Jessica Anderson | US-SP | Celito Communications, LLC | J00019226 | T&E - 2946600 | Closed | 0% | 0% | 0 | -74.25 | 0 | 9973.75 | 0% | 0 | 0 | 74.25 | 0 | 0 |  | 9973.75 |  | 0 | 4230 | -5743.75 | -135.8%
08/29/24 |  | 08/28/26 | Closed | Summer Abunaja | N/A |  | Beau C. Devillier, Juan Pomares, Mark Forehand, Summer Abunaja, William Birdsong |  |  | Conner MacDonnell, Jhon Genao, Kenneth Stevenson, Nathan Dao, Ryan Frankeberger, Summer Abunaja |  |  | Mark Forehand | TX-DAL | Sixth Street | J00018905 | Dallas and Houston Office Expansion T&E | Closed | 100% | 0% | 0 | -17 | 20.25 | 1250 | 0% | 20.25 | 1.5 | 18.5 | 1160 | 0 |  | 1250 |  | 0 | 0 | -1250 | 0%
09/18/24 |  | 09/17/26 | Open | Summer Abunaja | N/A |  | Aaron Christopher Pfeifer, Jessica Anderson, Summer Abunaja |  |  | Aaron Christopher Pfeifer, Rafael Rodriguez-Vargas |  |  | Jessica Anderson | US-SP | LTC Connect | J00019074 | LTC Time and Expense | Not started | 0% | 0% | 0 | -17.5 | 0 | 2362.5 | 0% | 0 | 0 | 17.5 | 202.5 | 0 |  | 2362.5 |  | 0 | 0 | -2362.5 | 0%
04/29/24 |  | 09/30/26 | Open | Summer Abunaja | N/A |  | Kristian Martell, Larry Noble, Neel Shah, Summer Abunaja |  |  | Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00018270 | Veritiv MACD Support T&E | Implementation/Deployment | 0% | 0% | 0 | -9.5 | 0 | 1805 | 0% | 0 | 0 | 9.5 | 1805 | 0 |  | 1805 |  | 0 | 0 | -1805 | 0%
04/30/24 |  | 09/30/26 | Open | Summer Abunaja | N/A |  | Larry Noble, Neel Shah, Summer Abunaja |  |  | Thomas Francis LoMonaco |  |  | Neel Shah | TX-HOU | ATSG, Inc | J00018271 | Lakeland Bank Remote MACD Support T&E | Implementation/Deployment | 0% | 0% | 0 | -30 | 0 | 5700 | 0% | 0 | 0 | 30 | 5510 | 0 |  | 5700 |  | 0 | 0 | -5700 | 0%
10/08/24 |  | 10/07/26 | Closed | Joaquin Marroquin | N/A |  | Christopher Ceykovsky, Daniel Saenz, Diana Berger, Joaquin Marroquin |  |  | Joaquin Marroquin, Samuel Newland |  |  | Daniel Saenz | TX-SOUT | Donna ISD | J00019198 | UC T&E | Closed | 100% | 62.5% | 4 | 1.5 | 400 | 335 | 37.5% | 400 | 0 | 2.5 | 335 | 0 |  | 335 |  | 0 | 0 | -335 | 0%
04/10/25 |  | 11/27/26 | Open | LaQisha Marshall | Daniel Snyder |  | Christi D Hubbard, Daniel Snyder, Ernesto Gonzalez, LaQisha Marshall |  |  | LaQisha Marshall |  |  | Christi D Hubbard | TX-CEN | Austin ISD | 200002637 | N/A | Planning/Design/Staging | 5% | 0.0408% | 12842.19 | 12836.94 | 0 | 656.25 | 99.96% | 0 | 0 | 5.25 | 0 | 0 |  | 656.25 |  | 0 | 0 | -656.25 | 0%
04/02/25 |  | 12/31/26 | Open | Christina Rice | N/A |  | Bryan Mullen, Christina Rice, Christina Rice, David Watkins, Jonathan Pendrich, Katharine McCarley, Katherine McCarley |  |  | Bryan Mullen, Christina Rice, Jeffery Alan Jorzig |  |  | Jonathan Pendrich | TX-DAL | Winstead PC | 200001932 | N/A | Not started | 5% | 62% | 37.5 | 14.25 | 0 | 2906.25 | 38% | 0 | 0 | 23.25 | 0 | 0 |  | 2906.25 |  | 0 | 0 | -2906.25 | 0%
06/25/25 |  | 12/31/26 | Open | Jennifer Soliz | N/A |  | Eric Firestone, Jacob Parks, Jeffrey Holman, Jennifer Soliz, Lonnie Owens |  |  | Eric Firestone |  |  | Lonnie Owens | TX-CEN | CPS Energy | 200003131 | N/A | Implementation/Deployment | 0% | 0% | 0 | -2 | 0 | 300 | 0% | 0 | 0 | 2 | 0 | 0 |  | 300 |  | 0 | 40540 | 40240 | 99.26%
01/31/25 |  | 12/31/26 | Open | Lauren Lanzini Coffey | N/A |  | Lauren Lanzini Coffey, Neel Shah |  |  | Jason Espino |  |  | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200001825 | N/A | Implementation/Deployment | 0% | 0% | 0 | -95 | 0 | 14250 | 0% | 0 | 0 | 95 | 0 | 0 |  | 14250 |  | 0 | 19000 | 4750 | 25%
06/12/25 |  | 12/31/26 | Open | Marshall Chuck Pugh | Christopher Pheonix Preddy |  | Christopher Pheonix Preddy, Marshall Chuck Pugh , Taylor Leger |  |  | Christopher Pheonix Preddy, Marshall Chuck Pugh |  |  | Taylor Leger | TX-DAL | Rockwall ISD | 200003090 | N/A | Not started | 0% | 0% | 0 | -30.25 | 0 | 5181.25 | 0% | 0 | 0 | 30.25 | 0 | 0 |  | 5181.25 |  | 0 | 24895 | 19713.75 | 79.19%
01/12/24 |  | 12/31/26 | Open | Ryan Scott | N/A |  | Arcangelo Fanelli, Beau C. Devillier, Ryan Scott |  |  | Fadi Ashour |  |  | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00017298 | No SOW-1591988-CAP- T&E-INETGenie ISE Support | Implementation/Deployment | 0% | 0% | 0 | -35 | 0 | 3500 | 0% | 0 | 0 | 35 | 3500 | 5250 |  | 3500 |  | 0 | 0 | -8750 | 0%
03/26/25 |  | 12/31/26 | Open | Shannon Marie Alvarado | William Birdsong |  | Jonathan Pendrich, Shannon Marie Alvarado, William Birdsong |  |  | Shannon Marie Alvarado |  |  | Jonathan Pendrich | TX-DAL | LENNOX INTERNATIONAL INC | 200002513 | N/A | Not started | 0% | 0% | 0 | -5.5 | 0 | 687.5 | 0% | 0 | 0 | 5.5 | 0 | 0 |  | 687.5 |  | 0 | 0 | -687.5 | 0%
05/22/25 |  | 12/31/26 | Open | Summer Abunaja | N/A |  | Christopher Puyear, Shawn Sutton, Summer Abunaja |  |  | Henry Pugsley |  |  | Shawn Sutton | TX-DAL | City of North Richland Hills (TX) | 200003009 | N/A | Not started | 0% | 0% | 0 | -6.5 | 0 | 1137.5 | 0% | 0 | 0 | 6.5 | 0 | 0 |  | 1137.5 |  | 0 | 0 | -1137.5 | 0%
02/04/25 |  | 12/31/26 | Open | Summer Abunaja | Joshua Adam Engle |  | Joshua Adam Engle, Mark Forehand, Nazario Armenta Barraza, Summer Abunaja |  |  | Jeffery Alan Jorzig, Nazario Armenta Barraza, Samuel Newland |  |  | Mark Forehand | TX-DAL | DR Horton | 200001845 | N/A | Implementation/Deployment | 0% | 0% | 0 | -123 | 0 | 15895 | 0% | 0 | 0 | 123 | 0 | 0 |  | 15895 |  | 0 | 14705 | -1190 | -8.092%
02/28/25 |  | 12/31/26 | Open | Summer Abunaja | Saif Qaissi |  | Dennis Odneal, Saif Qaissi, Summer Abunaja |  |  | Samuel Newland |  |  | Dennis Odneal | TX-HOU | Harris Health System | 200002250 | N/A | Not started | 0% | 0% | 0 | -4 | 0 | 560 | 0% | 0 | 0 | 4 | 0 | 0 |  | 560 |  | 254705.75 | 28435 | 27875 | 98.03%
05/12/25 |  | 12/31/26 | Open | Summer Abunaja | N/A |  | Mark Forehand, Michael Brett Beggs, Summer Abunaja |  |  | Luis Ovalles, Summer Abunaja |  |  | Mark Forehand | TX-DAL | Hyosung America | 200002964 | N/A | Not started | 0% | 0% | 0 | -9 | 0 | 1180 | 0% | 0 | 0 | 9 | 0 | 0 |  | 1180 |  | 0 | 390 | -790 | -202.6%
01/14/25 |  | 12/31/26 | Open | Summer Abunaja | N/A |  | John Stephen Kurkjian, Monica Johnson, Summer Abunaja |  |  | Thomas Francis LoMonaco |  |  | Monica Johnson | TX-HOU | Port of Houston Authority | 200001645 | N/A | Implementation/Deployment | 0% | 0% | 0 | -4.5 | 0 | 855 | 0% | 0 | 0 | 4.5 | 0 | 0 |  | 855 |  | 0 | 0 | -855 | 0%
05/27/25 |  | 12/31/26 | Open | Summer Abunaja | N/A |  | Lindie Lorraine Lamar, Samuel Newland, Summer Abunaja |  |  | Henry Pugsley |  |  | Lindie Lamar | TX-HOU | Westlake Corporation | 200003024 | N/A | Not started | 0% | 0% | 0 | -2.75 | 0 | 481.25 | 0% | 0 | 0 | 2.75 | 0 | 0 |  | 481.25 |  | 0 | 175 | -306.25 | -175%
03/24/25 |  | 12/31/26 | Open | Walter Clay Knight | Joshua Adam Engle |  | Dennis Odneal, Joshua Adam Engle, Walter Clay Knight, Warren Llewellyn Flynn |  |  | Jeffery Alan Jorzig, Walter Clay Knight |  |  | Dennis Odneal | TX-HOU | Ochsner Health | 200002523 | N/A | Implementation/Deployment | 0% | 0% | 0 | -105 | 0 | 13125 | 0% | 0 | 0 | 105 | 0 | 0 |  | 13125 |  | 0 | 0 | -13125 | 0%
[21 empty] | 548435.1409 | 130499.4509 | 35510064.83 | 37712121.1 | 23.79% | 35510064.83 | 22545.24 | 440480.93 | 23710877.4 | 1467701.6446 |  | 37712121.1 |  | 476175531.77 | 90123500.79 | 50943678.0454 | 56.53%