## Summary_Explanations
Description | Value
ADVANCED ANALYTICS SUMMARY & EXPLANATIONS
OVERVIEW
This report analyzes projects involving tracked consultants and solution architects only.
All calculations exclude company-wide projects without tracked team members.
PREDICTIVE ANALYTICS
Projects are categorized by budget size to predict success rates:
• Small Projects: <100 hours budgeted
• Medium Projects: 100-500 hours budgeted
• Large Projects: >500 hours budgeted
Success Rate = % of projects within 30% of budget
ANOMALY DETECTION
Statistical analysis identifies projects with unusual performance:
• Uses standard deviation to find outliers
• Deviation Score >2.0 = Anomaly (configurable)
• Higher deviation = more unusual performance
RISK ASSESSMENT
Projects scored based on risk factors:
Risk Score 3+ = High Risk Project
Risk Factors & Points:
• Large Budget (>500 hrs): +2 points
• High Overrun (>50% over budget): +3 points
• Complex Resourcing (>3 people): +1 point
Risk Score Meanings:
• Score 3: Moderate Risk - Monitor closely
• Score 4: High Risk - Requires intervention
• Score 5: Critical Risk - Immediate action needed
• Score 6: Extreme Risk - Escalate to management
VARIANCE EXPLANATIONS
Variance shows how much actual hours differ from budget:
Example: "+289.0% variance (36→141 hrs)"
• Budgeted: 36 hours
• Actual: 141 hours
• Variance: +289% (project took 3.9x longer than planned)
• This indicates major scope creep or estimation issues
Variance Interpretation:
• 0% = Exactly on budget (rare)
• +10% = 10% over budget (acceptable)
• +30% = 30% over budget (concerning)
• +50% = 50% over budget (problematic)
• +100% = Double the budget (major issue)
• +200%+ = Triple+ the budget (critical failure)
• -10% = 10% under budget (good efficiency)
• -20% = 20% under budget (excellent efficiency)
• -50% = 50% under budget (possible under-scoping)
SUCCESS CRITERIA
• Efficiency Threshold: 15% over budget
• Success Threshold: 30% over budget
• Projects >30% over = Failed projects
• Projects ≤30% over = Successful projects
COLOR CODING (in project tabs)
• Green: >10% under budget (excellent)
• Yellow: 10-30% over budget (acceptable)
• Red: >30% over budget (failed)
RECOMMENDATIONS
• Review all Red projects for lessons learned
• Investigate Anomaly projects for root causes
• Monitor High Risk projects closely
• Celebrate Green projects and share best practices
• Use predictive data for better project planning

## Analytics_Report
Metric | Value
ADVANCED ANALYTICS REPORT
Generated from tracked projects only
PREDICTIVE ANALYTICS
Success Rate Predictions by Project Size:
Small Projects (<100 hrs) | 76.3% (38 projects)
Medium Projects (100-500) | 86.8% (38 projects)
Large Projects (>500 hrs) | 88.9% (9 projects)
Key Insight: | Larger projects tend to have lower success rates
ANOMALY DETECTION
Detected 4 anomalous projects:
J00007932 | +950.0% variance (1→10 hrs)
J00014358 | +473.1% variance (52→298 hrs)
J00019133 | +316.6% variance (36→151 hrs)
J00017378 | +316.0% variance (346→1440 hrs)
RISK ASSESSMENT
Identified 14 high-risk projects:
J00007932 | Risk Score 4 (High Overrun, Complex Resourcing)
J00010667 | Risk Score 4 (High Overrun, Complex Resourcing)
J00017378 | Risk Score 4 (High Overrun, Complex Resourcing)
200000177 | Risk Score 3 (Large Budget, Complex Resourcing)
200001912 | Risk Score 3 (Large Budget, Complex Resourcing)
RECOMMENDATIONS
• Review anomalous projects for root causes
• Monitor high-risk projects closely
• Use predictive data for project planning
• Focus on improving large project success rates

## Small_Projects
Job_Number | Budget_Hrs | Actual_Hrs | Variance_% | Success | Resources_Engaged | Solution_Architect | Account_Manager
200000552 | 20 | 9.5 | -52.5 | TRUE | Jennifer Soliz | David Goss, Matthew Duncan | Carmen Brandt
200001544 | 36.56 | 1.5 | -95.8972 | TRUE | Richard Keith Arnst | David Escamilla | Ashley F Freeman
200001852 | 46.25 | 25.75 | -44.3243 | TRUE | Christopher Brown, Shannon Marie Alvarado | Steven Walker | Arcangelo Fanelli
200002088 | 27.5 | 30.75 | 11.8182 | TRUE | Christopher Brown, Tray Giddens | Steven Walker | Dustin Huffman
200002157 | 17.5 | 23.5 | 34.2857 | FALSE | Christina Rice, Joshua Osgood, Luis Ovalles, Sophia Quinter | Jacob Parks, Jeffrey Holman, Michael Brett Beggs | Shawn Sutton
200002216 | 50 | 35.75 | -28.5 | TRUE | Marshall Chuck Pugh, Ron Loge | George Edwin Jacob | Lauren J Kennewell
200002270 | 5 | 5.75 | 15 | TRUE | Jennifer Soliz | Steven Walker | Garrett Curran
200002327 | 98.55 | 84.25 | -14.5104 | TRUE | Caleb Henry, Cory Bradfield, Craig St. Rose, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio, Noah Trump, Paul Serres, Tray Giddens | Aman Khan, David Escamilla | Dustin Huffman
200002359 | 18.4 | 9 | -51.087 | TRUE | Tony Dean Skipworth, Walter Clay Knight | Jeremy Williams | Camille Taber
200002361 | 66.25 | 41.5 | -37.3585 | TRUE | Brian Willery, Cory Bradfield | David Escamilla | Jaclyn Pias
200002434 | 43.75 | 51 | 16.5714 | FALSE | Christopher Brown, Richard Keith Arnst | Steven Walker | Daniel Saenz
200002508 | 99.5 | 40.75 | -59.0452 | TRUE | Juan Saenz, Marco Lish | David Escamilla | Dennis Odneal
200002593 | 33 | 5 | -84.8485 | TRUE | LaQisha Marshall, Tony Dean Skipworth | David D Tijerina, David Goss | David D Tijerina
200002600 | 55 | 25 | -54.5455 | TRUE | Christopher Brown, Tray Giddens | Steven Walker | Dustin Huffman
200002613 | 75 | 30.5 | -59.3333 | TRUE | Christopher Brown, Joanna Herrera | Steven Walker | Jason Osuna
200002653 | 84 | 0 | -100 | TRUE |  | George Edwin Jacob | Jonathan Pendrich
200002887 | 77.5 | 13.75 | -82.2581 | TRUE | Luis Ovalles, Marco Lish | Michael Brett Beggs | Jonathan Pendrich
200002958 | 46.78 | 0 | -100 | TRUE |  | David Goss, Steven Walker | Jason Osuna
200002987 | 79.35 | 11 | -86.1374 | TRUE | Cory Bradfield, Jim Blackwell | Firas Abood
200002988 | 37.5 | 5 | -86.6667 | TRUE | Abiodun David Babasola, Christopher Brown | Steven Walker | Kristy L Dice
200003014 | 64.63 | 2 | -96.9055 | TRUE | Tony Dean Skipworth, Walter Clay Knight | David Goss | David D Tijerina
200003046 | 10.55 | 12 | 13.7441 | TRUE | Joanna Herrera, Juan Saenz | Michael Brett Beggs | Arcangelo Fanelli
200003066 | 43.75 | 17.5 | -60 | TRUE | Brian Willery, Frank Jaimes, Jalen Vecchitto, Ron Loge | David Escamilla | Jaclyn Pias
J00007932 | 1 | 10.5 | 950 | FALSE | Darrell Walton, Joel Hubbard, Moises Rodriguez, Vitalii Stepanchenko, William Chris Roome | Bryan Geoghan, Christopher Garcia, David Watkins, Jacob Parks, Jeffrey Holman, Joshua Adam Engle, Michael Brett Beggs, Pedro Cantu | Arcangelo Fanelli
J00010667 | 38.8 | 86.5 | 122.9381 | FALSE | Aaron Abshire, Cory Bradfield, Felipe Waterwall, Luis Alvarez, Victor Estrada | Billy Pearson, Firas Abood, Wyley Johnson | Susan Richardson
J00012888 | 96.6 | 177.75 | 84.0062 | FALSE | Gena Robbins, Luis Ovalles, Ron Loge | Michael Brett Beggs | Arcangelo Fanelli
J00012890 | 38.78 | 76.25 | 96.622 | FALSE | Gena Robbins, Luis Ovalles, Ron Loge | Michael Brett Beggs | Arcangelo Fanelli
J00014358 | 52 | 298 | 473.0769 | FALSE | Marco Lish | Michael Brett Beggs | Jonathan Pendrich
J00014741 | 41.88 | 15.75 | -62.3926 | TRUE | Brian Willery, Juan Saenz | David Escamilla | Garrett Curran
J00014746 | 24.06 | 6.25 | -74.0233 | TRUE | Brian Willery, Juan Saenz | David Escamilla | Garrett Curran
J00014805 | 46.13 | 53.75 | 16.5185 | FALSE | Christopher Brown, Marshall Chuck Pugh | Steven Walker | Lauren J Kennewell
J00018290 | 30 | 23 | -23.3333 | TRUE | Summer Abunaja, Tony Dean Skipworth | George Edwin Jacob | Joseph Boglino
J00018375 | 57 | 13.5 | -76.3158 | TRUE | LaQisha Marshall, Luis Ovalles | George Edwin Jacob | Alex Gutman
J00018667 | 77.63 | 27 | -65.2196 | TRUE | Joaquin Marroquin, Juan Saenz | David Escamilla | David D Tijerina
J00019060 | 56.25 | 30.75 | -45.3333 | TRUE | Darrell Walton, Devin Moreno, Jose Gutierrez, Noah Castleberry, Ryan Scott | Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs | Arcangelo Fanelli
J00019061 | 67.5 | 29.25 | -56.6667 | TRUE | Bryan Mullen, Devin Moreno, Noah Castleberry, Ryan Scott, Tony Dean Skipworth | Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs | Arcangelo Fanelli
J00019133 | 36.25 | 151 | 316.5517 | FALSE | Jason Esry, Luis Ovalles | Steven Walker | William Davenport
J00019243 | 10 | 10.5 | 5 | TRUE | Jennifer Soliz | Steven Walker | Hannah Edmunds

## Medium_Projects
Job_Number | Budget_Hrs | Actual_Hrs | Variance_% | Success | Resources_Engaged | Solution_Architect | Account_Manager
200000304 | 207.13 | 100 | -51.7211 | TRUE | Cory Bradfield, Diego Asencio, Shannon Marie Alvarado | George Edwin Jacob, Michael Brett Beggs | Camille Taber
200001587 | 197.8 | 231.25 | 16.911 | FALSE | Brittney Antoinette Hickman, David Goss, Jacob Hill, Luis Ovalles, Noah Trump | David Goss | Rusty Bryan
200001640 | 144.58 | 26.5 | -81.671 | TRUE | Cory Bradfield, Francisco Hernandez, Jonathan Pina, Robert McIver, Roger Guerra | Firas Abood | Eric Rodriguez
200001658 | 485.5 | 46.5 | -90.4222 | TRUE | Abdalsattar Albaghdadi, Abdulrahman Farhan, Tray Giddens | Ahmed Al-Zubaidi, David Escamilla, Mark J Chambliss, Saif Qaissi, Wyley Johnson | Lindie Lamar
200001723 | 146.88 | 3 | -97.9575 | TRUE | Cory Bradfield, Tray Giddens | Ahmed Al-Zubaidi, David Escamilla, Mark J Chambliss, Saif Qaissi, Wyley Johnson | Lindie Lamar
200001737 | 140 | 162.5 | 16.0714 | FALSE | Brittney Antoinette Hickman, Christopher Brown, Luis Ovalles | Steven Walker | Mark Forehand
200001810 | 202.4 | 40.75 | -79.8666 | TRUE | Richard Keith Arnst | Steven Walker | Susan Richardson
200001831 | 218.13 | 159.5 | -26.8785 | TRUE | Cory Bradfield, Craig St. Rose, James Adams, Jose R. Duarte, Kord Mullins, Miguel Reed, Tray Giddens | David Escamilla | Dustin Huffman
200002286 | 161.85 | 82.5 | -49.0269 | TRUE | Erick Nunez , Juan Saenz, Marco Lish | Matthew Duncan | Neel Shah
200002407 | 130.63 | 24.5 | -81.2447 | TRUE | Cory Bradfield, Jason Esry | David Goss | David D Tijerina
200002471 | 242.97 | 75.75 | -68.8233 | TRUE | Abiodun David Babasola, Austen Howard, Brycen Dimas, Dante Torres, Remijio Hernandez, Ron Loge | George Edwin Jacob | Lauren J Kennewell
200002488 | 296.94 | 148.5 | -49.9899 | TRUE | Cory Bradfield, Craig St. Rose, Justin Cornish, Walter Clay Knight | David Escamilla | Ashley F Freeman
200002580 | 188.88 | 0 | -100 | TRUE |  | Jeremy Williams, Michael Brett Beggs | Camille Taber
200002612 | 151.25 | 32.75 | -78.3471 | TRUE | Christina Rice, Juan Saenz | Matthew Duncan, Michael Brett Beggs | Shawn Sutton
200002640 | 109.25 | 37 | -66.1327 | TRUE | Brittney Antoinette Hickman, Juan Saenz, Osazee Eweka | Matthew Duncan | Garrett Curran
200002778 | 144.12 | 4 | -97.2245 | TRUE | Juan Saenz, Summer Abunaja | Jeremy Williams | Garrett Curran
200002941 | 127.5 | 65.25 | -48.8235 | TRUE | Juan Saenz, Robert McIver, Ron Loge | David Escamilla | Daniel Saenz
200002979 | 106.2 | 3.5 | -96.7043 | TRUE | Brian Willery | David Goss, Steven Walker | Jason Osuna
200002989 | 263 | 29.5 | -88.7833 | TRUE | Ashutosh Patel, Ibrahim Altaweel, Jerome Tanyag Mara, LaQisha Marshall, Tom Magboo | Ahmed Al-Zubaidi, Steven Walker | David Monasmith
200003048 | 351.66 | 14 | -96.0189 | TRUE | Cory Bradfield, Joaquin Marroquin | Ahmed Al-Zubaidi, David Escamilla, Steven Walker, Wyley Johnson | Xavier A Trevino
200003058 | 123.75 | 0 | -100 | TRUE |  | Amanda Barney, George Edwin Jacob, Majid Shirzadeh | Lauren J Kennewell
200003091 | 155.25 | 0.5 | -99.6779 | TRUE | LaQisha Marshall | Ahmed Al-Zubaidi, Steven Walker | David Monasmith
J00009890 | 398.42 | 193 | -51.5587 | TRUE | Andrew G Wagenhofer, Christopher Knipe, Jennifer Soliz, Michael Hilton, Ron Loge, Sarah Beatrice Williamson | Kenneth Dieter | Lonnie Owens
J00011651 | 288.56 | 299.1 | 3.6526 | TRUE | Andy Pham, Devon LeMoine, Justin Cornish, Lauren Lanzini Coffey, Michael Hilton, Ron Loge, Tony Dean Skipworth | Billy Pearson, Firas Abood | Neel Shah
J00013237 | 474.48 | 411.5 | -13.2735 | TRUE | Abdulrahman Farhan, Eric Firestone, Ernesto Gonzalez, Isaiah Covington, Jaime Cortez, James Danner, Jason Esry, Jeffrey Charles Primeaux, Kyle Linder, Micah Rendon, Mohammed Almoola, Ron Loge, Tony Dean Skipworth, Trevor Youngman | Emilio Carrillo, Firas Abood, Kenneth Dieter, Mark J Chambliss, Timothy Ramsey | David D Tijerina
J00014807 | 105.75 | 43.5 | -58.8652 | TRUE | Christopher Brown, Marshall Chuck Pugh | Steven Walker | Lauren J Kennewell
J00016147 | 373.4 | 488.75 | 30.8918 | FALSE | Austen Howard, Carlo Enriquez, Devin Moreno, Jhon Genao, Justin Mitchell, Kanoa Parman, Kebret Eshetu, Kevin Curtis, Kirk O'Guinn, Kolawole Ayeni, Matthew D'Ambrosio, Mohaymen Sodi, Nicolas Garakani, Noah Trump, Patrick Shea Thompson, Phillip Ma Lim, Quy Le, Ron Loge, Sean Cowhey, Tabais Prater, Tray Giddens, William Chris Roome, Yonathan Fadel | David Escamilla | Dustin Huffman
J00016590 | 409.89 | 420.75 | 2.6495 | TRUE | Austen Howard, Christina Rice, Conner MacDonnell, Cory Bradfield, Devin Moreno, Gena Robbins, Jackory Nash, Jeffery Giles, Jhon Genao, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Tony Dean Skipworth | Michael Brett Beggs | Shawn Sutton
J00017214 | 474.88 | 155.5 | -67.2549 | TRUE | Cory Bradfield, Jason Esry, Ron Loge | David Escamilla, Michael Brett Beggs | David D Tijerina
J00017378 | 346.13 | 1439.88 | 315.994 | FALSE | Abdalsattar Albaghdadi, Anthony Lange, Brian Willery, Bryant Bush, Cory Bradfield, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Luis Ovalles, Matthew D'Ambrosio, Mohaymen Sodi, Nathan Dao, Nicolas Garakani, Paul Serres | David Escamilla | Susan Richardson
J00017474 | 238.75 | 171 | -28.377 | TRUE | Christopher Brown, Luis Ovalles, Tray Giddens | Steven Walker | Dustin Huffman
J00018235 | 105.2 | 68 | -35.3612 | TRUE | Andy Pham, Cory Bradfield, Jim Blackwell | David Escamilla, Firas Abood | Ashley F Freeman
J00018637 | 148.8 | 197.25 | 32.5605 | FALSE | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja | Matthew Duncan | Neel Shah
J00018726 | 305.23 | 221.5 | -27.4318 | TRUE | Carlo Enriquez, Jason Esry, Jay Daniel De Leon, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Kendall Walls, Luis Ovalles, Phillip Ma Lim, Quy Le, Tavis Jackson, Yonathan Fadel | Michael Brett Beggs | William Davenport
J00018897 | 109.25 | 12.25 | -88.7872 | TRUE | Juan Saenz, Osazee Eweka, Walter Clay Knight | George Edwin Jacob | Joseph Boglino
J00018949 | 109.25 | 4.5 | -95.881 | TRUE | Brittney Antoinette Hickman | Matthew Duncan | Carmen Brandt
J00019097 | 106.25 | 82.5 | -22.3529 | TRUE | Cory Bradfield, Tray Giddens | David Escamilla | Dustin Huffman
J00019153 | 198.15 | 139 | -29.8511 | TRUE | Luis Ovalles, Nick Varga, Walter Clay Knight | Aman Khan, David Escamilla, Eduardo Chavez, Jacob Parks, Jeffrey Holman | Carmen Brandt

## Large_Projects
Job_Number | Budget_Hrs | Actual_Hrs | Variance_% | Success | Resources_Engaged | Solution_Architect | Account_Manager
200000177 | 593.75 | 174.75 | -70.5684 | TRUE | Cory Bradfield, Joaquin Marroquin, Kevin Curtis, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Sophia Quinter, Timothy Sean Marcyes | Daniel Snyder, David Goss, Wyley Johnson | David D Tijerina
200001912 | 740 | 296.75 | -59.8986 | TRUE | Bradley Buchanan, Carlo Enriquez, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jalen Vecchitto, Joshua Hubbard, Joshua Osgood, Justin Mitchell, Lauren Lanzini Coffey, Noah Castleberry, Remijio Hernandez, Ron Loge, William Chris Roome | George Edwin Jacob | Jonathan Pendrich
200002598 | 1669.25 | 95.5 | -94.2789 | TRUE | Jeffery Alan Jorzig, Jorge Ortiz Cardozo, Shannon Marie Alvarado | David Watkins, Michael Brett Beggs | Arcangelo Fanelli
200002923 | 4965.41 | 3126.25 | -37.0394 | TRUE | Abiodun David Babasola, Alexander Liu, Bradley Buchanan, Brittney Antoinette Hickman, Bryan Mullen, Brycen Dimas, Caleb Henry, Carlo Enriquez, Conner MacDonnell, Devin Moreno, Erick Sanchez, Frank Jaimes, Gabriel Lantigua, Jacob Hill, Jalen Vecchitto, Jayden Colon, John Johnson, Jonathan Weir, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Mitchell, Justin Thompson, Kendall Walls, Matthew Veach, Noah Castleberry, Noah Trump, Quy Le, Remijio Hernandez, Ryan Frankeberger, Samuel Gonzalez, | David Watkins, Michael Brett Beggs | Arcangelo Fanelli
J00014229 | 880.08 | 491.75 | -44.1244 | TRUE | Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge | David Escamilla | Shawn Sutton
J00014492 | 2440.44 | 1798.08 | -26.3215 | TRUE | Abdalsattar Albaghdadi, Albert Bernal, Cory Bradfield, Craig St. Rose, David Dobbs, Dhulfiqar Al Hashimi, Erick Nunez , Ernesto Gonzalez, James Adams, Jose R. Duarte, Justin Smallwood, Kendric Mamou, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Mohammed Almoola, Mohaymen Sodi, Moises Rodriguez, Mustafa Al-Tamimi, Paul Serres, Rafael Rodriguez-Vargas, Robert McIver, Timothy Sean Marcyes | Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Hugh Miller, Michael Brett Beggs, Wyley Johnson | David Monasmith
J00014845 | 548.85 | 662.25 | 20.6614 | FALSE | Ashutosh Patel, Kreshnik Memaj, Raul Velazquez, Richard Keith Arnst, Romar Roca, Tony Dean Skipworth | Ahmed Al-Zubaidi, David Escamilla, Joshua Adam Engle, Wyley Johnson | Randy Schamberger
J00017292 | 592.25 | 340 | -42.5918 | TRUE | Cory Bradfield, Hamzeh Tahat, Michael Garcia, Osazee Eweka, Samuel Newland, Shannon Marie Alvarado | Firas Abood, Mark J Chambliss | Ashley F Freeman
J00017306 | 541.25 | 423 | -21.8476 | TRUE | Bryan Mullen, Ron Loge, Ryan Scott | Michael Brett Beggs | Arcangelo Fanelli

## Anomaly_Projects
Job_Number | Customer | Job_Description | Budget_Hrs | Actual_Hrs | Variance_% | Deviation_Score | Resources_Engaged | Solution_Architect | Account_Manager | Project_Description
J00007932 | Parkland Health & Hospital System | 1045085 | 1 | 10.5 | 950 | 6.7601 | Darrell Walton, Joel Hubbard, Moises Rodriguez, Vitalii Stepanchenko, William Chris Roome | Bryan Geoghan, Christopher Garcia, David Watkins, Jacob Parks, Jeffrey Holman, Joshua Adam Engle, Michael Brett Beggs, Pedro Cantu | Arcangelo Fanelli
J00014358 | Wells Fargo Financial Services | Staff Aug Backlog | 52 | 298 | 473.0769 | 3.2116 | Marco Lish | Michael Brett Beggs | Jonathan Pendrich
J00017378 | Klein ISD | Datacenter Compute, Storage & Network Electronics | 346.13 | 1439.88 | 315.994 | 2.275 | Abdalsattar Albaghdadi, Anthony Lange, Brian Willery, Bryant Bush, Cory Bradfield, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Luis Ovalles, Matthew D'Ambrosio, Mohaymen Sodi, Nathan Dao, Nicolas Garakani, Paul Serres | David Escamilla | Susan Richardson
J00019133 | Hurst Euless Bedford ISD | SQL Physical to Virtual Migration | 36.25 | 151 | 316.5517 | 2.3767 | Jason Esry, Luis Ovalles | Steven Walker | William Davenport

## High_Risk_Projects
Job_Number | Risk_Score | Customer | Job_Description | Risk_Factors | Budget_Hrs | Actual_Hrs | Variance_% | Resources_Engaged | Solution_Architect | Account_Manager | Project_Description
J00010667 | 4 | Klein ISD | UCS and FortiSiem (Fortinet third party) | High Overrun, Complex Resourcing | 38.8 | 86.5 | 122.9381 | Aaron Abshire, Cory Bradfield, Felipe Waterwall, Luis Alvarez, Victor Estrada | Billy Pearson, Firas Abood, Wyley Johnson | Susan Richardson
J00007932 | 4 | Parkland Health & Hospital System | 1045085 | High Overrun, Complex Resourcing | 1 | 10.5 | 950 | Darrell Walton, Joel Hubbard, Moises Rodriguez, Vitalii Stepanchenko, William Chris Roome | Bryan Geoghan, Christopher Garcia, David Watkins, Jacob Parks, Jeffrey Holman, Joshua Adam Engle, Michael Brett Beggs, Pedro Cantu | Arcangelo Fanelli
J00017378 | 4 | Klein ISD | Datacenter Compute, Storage & Network Electronics | High Overrun, Complex Resourcing | 346.13 | 1439.88 | 315.994 | Abdalsattar Albaghdadi, Anthony Lange, Brian Willery, Bryant Bush, Cory Bradfield, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Luis Ovalles, Matthew D'Ambrosio, Mohaymen Sodi, Nathan Dao, Nicolas Garakani, Paul Serres | David Escamilla | Susan Richardson
200001912 | 3 | Wells Fargo Financial Services |  | Large Budget, Complex Resourcing | 740 | 296.75 | -59.8986 | Bradley Buchanan, Carlo Enriquez, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jalen Vecchitto, Joshua Hubbard, Joshua Osgood, Justin Mitchell, Lauren Lanzini Coffey, Noah Castleberry, Remijio Hernandez, Ron Loge, William Chris Roome | George Edwin Jacob | Jonathan Pendrich
200002923 | 3 | Fort Worth ISD |  | Large Budget, Complex Resourcing | 4965.41 | 3126.25 | -37.0394 | Abiodun David Babasola, Alexander Liu, Bradley Buchanan, Brittney Antoinette Hickman, Bryan Mullen, Brycen Dimas, Caleb Henry, Carlo Enriquez, Conner MacDonnell, Devin Moreno, Erick Sanchez, Frank Jaimes, Gabriel Lantigua, Jacob Hill, Jalen Vecchitto, Jayden Colon, John Johnson, Jonathan Weir, Joshua Hubbard, Joshua Osgood, Juan Pomares, Justin Mitchell, Justin Thompson, Kendall Walls, Matthew Veach, Noah Castleberry, Noah Trump, Quy Le, Remijio Hernandez, Ryan Frankeberger, Samuel Gonzalez, | David Watkins, Michael Brett Beggs | Arcangelo Fanelli
200000177 | 3 | Leander ISD |  | Large Budget, Complex Resourcing | 593.75 | 174.75 | -70.5684 | Cory Bradfield, Joaquin Marroquin, Kevin Curtis, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Sophia Quinter, Timothy Sean Marcyes | Daniel Snyder, David Goss, Wyley Johnson | David D Tijerina
J00012888 | 3 | DFW International Airport | SaaS/Parking NO HDWR - AAAQ361562 | High Overrun | 96.6 | 177.75 | 84.0062 | Gena Robbins, Luis Ovalles, Ron Loge | Michael Brett Beggs | Arcangelo Fanelli
J00012890 | 3 | DFW International Airport | HX Nodes for SAAB - AAAQ361558 | High Overrun | 38.78 | 76.25 | 96.622 | Gena Robbins, Luis Ovalles, Ron Loge | Michael Brett Beggs | Arcangelo Fanelli
J00014358 | 3 | Wells Fargo Financial Services | Staff Aug Backlog | High Overrun | 52 | 298 | 473.0769 | Marco Lish | Michael Brett Beggs | Jonathan Pendrich
J00014229 | 3 | City of Dallas | AWS - DRaaS Implementation | Large Budget, Complex Resourcing | 880.08 | 491.75 | -44.1244 | Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge | David Escamilla | Shawn Sutton
J00014492 | 3 | Texas A&M System | Rellis Campus - Core Network Refresh | Large Budget, Complex Resourcing | 2440.44 | 1798.08 | -26.3215 | Abdalsattar Albaghdadi, Albert Bernal, Cory Bradfield, Craig St. Rose, David Dobbs, Dhulfiqar Al Hashimi, Erick Nunez , Ernesto Gonzalez, James Adams, Jose R. Duarte, Justin Smallwood, Kendric Mamou, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Mohammed Almoola, Mohaymen Sodi, Moises Rodriguez, Mustafa Al-Tamimi, Paul Serres, Rafael Rodriguez-Vargas, Robert McIver, Timothy Sean Marcyes | Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Hugh Miller, Michael Brett Beggs, Wyley Johnson | David Monasmith
J00014845 | 3 | Charlotte County Clerk of the Circuit Court | Core Upgrade & Net-Pro-3rd Party Srvcs | Large Budget, Complex Resourcing | 548.85 | 662.25 | 20.6614 | Ashutosh Patel, Kreshnik Memaj, Raul Velazquez, Richard Keith Arnst, Romar Roca, Tony Dean Skipworth | Ahmed Al-Zubaidi, David Escamilla, Joshua Adam Engle, Wyley Johnson | Randy Schamberger
J00017292 | 3 | Harris County Hospital District | UC Infra Installation & Apps Upgrade | Large Budget, Complex Resourcing | 592.25 | 340 | -42.5918 | Cory Bradfield, Hamzeh Tahat, Michael Garcia, Osazee Eweka, Samuel Newland, Shannon Marie Alvarado | Firas Abood, Mark J Chambliss | Ashley F Freeman
J00019133 | 3 | Hurst Euless Bedford ISD | SQL Physical to Virtual Migration | High Overrun | 36.25 | 151 | 316.5517 | Jason Esry, Luis Ovalles | Steven Walker | William Davenport