## Summary
Consultant | Unique_Projects | Total_Hours | Efficiency_Score | Success_Ratio | Projects_Within_Budget | Projects_Over_Budget
Cory Bradfield | 19 | 5178.71 | 89.4737 | 89.4737 | 17 | 2
Tony Dean Skipworth | 9 | 1861.85 | 88.8889 | 88.8889 | 8 | 1
Juan Saenz | 12 | 1012.25 | 83.3333 | 91.6667 | 11 | 1
Ron Loge | 14 | 3211.85 | 71.4286 | 71.4286 | 10 | 4
Osazee Eweka | 3 | 574.25 | 66.6667 | 66.6667 | 2 | 1
Christopher Brown | 10 | 598.75 | 60 | 70 | 7 | 3
Luis Ovalles | 12 | 1801.75 | 50 | 50 | 6 | 6

## Christopher Brown
Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | Variance_%
01/30/25 | 07/31/25 | Open | Brittney Antoinette Hickman | Steven Walker | Brittney Antoinette Hickman, Christopher Brown, Christopher Brown, Luis Ovalles, Mark Forehand, Steven Walker | Brittney Antoinette Hickman, Christopher Brown, Luis Ovalles | Mark Forehand | TX-DAL | City of Richardson | 200001737 |  | Planning/Design/Staging | 0.55 | 1.1607 | 140 | -22.5 | 18620 | 21637.5 | -0.16071 | 18620 | 0 | 162.5 | 0 | 0 | 21637.5 | 19743.14 | 30078.44 | 8440.94 | 0.28063 | 16.0714
02/05/25 | 12/31/25 | Open | Shannon Marie Alvarado | Steven Walker | Arcangelo Fanelli, Christopher Brown, Christopher Brown, Shannon Marie Alvarado, Steven Walker | Christopher Brown, Shannon Marie Alvarado | Arcangelo Fanelli | TX-DAL | Arlington ISD | 200001852 |  | On HOLD | 0.75 | 0.55676 | 46.25 | 20.5 | 6151.25 | 3416.25 | 0.44324 | 6151.25 | 0 | 25.75 | 0 | 0 | 3416.25 | 0 | 9042 | 5625.75 | 0.62218 | -44.3243
02/19/25 | 04/29/25 | Open | Tray Giddens | Steven Walker | Christopher Brown, Christopher Brown, Dustin Huffman, Steven Walker, Tray Giddens | Christopher Brown, Tray Giddens | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | 200002088 |  | Closed | 1 | 1.1182 | 27.5 | -3.25 | 0 | 4101.25 | -0.11818 | 0 | 0 | 30.75 | 0 | 0 | 4101.25 | 0 | 5760.4 | 1659.15 | 0.28803 | 11.8182
03/18/25 | 07/18/25 | Open | Richard Keith Arnst | Steven Walker | Daniel Saenz, Eric Rodriguez, Richard Keith Arnst, Steven Walker | Christopher Brown, Richard Keith Arnst | Daniel Saenz | TX-SOUT | Great Hearts Texas | 200002434 |  | Planning/Design/Staging | 0.75 | 1.1657 | 43.75 | -7.25 | 0 | 6770 | -0.16571 | 0 | 0 | 51 | 0 | 0 | 6770 | 473 | 7187.84 | 417.84 | 0.058132 | 16.5714
04/04/25 | 08/22/25 | Open | Tray Giddens | Steven Walker | Christopher Brown, Christopher Brown, Dustin Huffman, Steven Walker, Tray Giddens | Christopher Brown, Tray Giddens | Dustin Huffman | TX-HOU | City of League City | 200002600 |  | Planning/Design/Staging | 0.05 | 0.45454 | 55 | 30 | 0 | 3295 | 0.54545 | 0 | 0 | 25 | 0 | 0 | 3295 | 0 | 11520.8 | 8225.8 | 0.714 | -54.5455
04/09/25 | 08/01/25 | Open | Joanna Herrera | Steven Walker | Jason Osuna, Joanna Herrera, Steven Walker | Christopher Brown, Joanna Herrera | Jason Osuna | TX-CEN | Cobre Consolidated School District | 200002613 |  | Implementation/Deployment | 0.75 | 0.40667 | 75 | 44.5 | 0 | 4027.5 | 0.59333 | 0 | 0 | 30.5 | 0 | 0 | 4027.5 | 0 | 14663.2 | 10635.7 | 0.72533 | -59.3333
05/22/25 | 09/18/25 | Open | Abiodun David Babasola | Steven Walker | Abiodun David Babasola, Christopher Brown, Christopher Brown, David Babasola, Kristy L Dice, Steven Walker | Abiodun David Babasola, Christopher Brown | Kristy L Dice | TX-DAL | Prestonwood Baptist Church | 200002988 |  | Planning/Design/Staging | 0.05 | 0.13333 | 37.5 | 32.5 | 0 | 665 | 0.86667 | 0 | 0 | 5 | 0 | 0 | 665 | 0 | 7470 | 6805 | 0.91098 | -86.6667
08/25/23 | 07/01/25 | Closed | Marshall Chuck Pugh | Steven Walker | Beau C. Devillier, Christopher Brown, Christopher Brown, Lauren J Kennewell, Lee McChesney, Marshall Chuck Pugh , Steven Walker | Christopher Brown, Marshall Chuck Pugh | Lauren J Kennewell | TX-DAL | Carroll ISD | J00014805 | Microsoft Office 365 Migration | Closed | 0.85 | 1.1652 | 46.13 | -7.62 | 6022.35 | 7208.75 | -0.16519 | 6022.35 | 0 | 53.75 | 7208.75 | 0 | 7208.75 | 0 | 8128 | 919.25 | 0.1131 | 16.5185
08/25/23 | 07/01/25 | Open | Marshall Chuck Pugh | Steven Walker | Beau C. Devillier, Christopher Brown, Christopher Brown, Lauren J Kennewell, Lee McChesney, Marshall Chuck Pugh, Steven Walker | Christopher Brown, Marshall Chuck Pugh | Lauren J Kennewell | TX-DAL | Carroll ISD | J00014807 | Microsoft Office 365 Migration | Closed | 1 | 0.41135 | 105.75 | 62.25 | 13806.25 | 5762.5 | 0.58865 | 13806.25 | 0 | 43.5 | 1375 | 0 | 5762.5 | 0 | 18635 | 12872.5 | 0.69077 | -58.8652
02/12/24 | 07/25/25 | Open | Tray Giddens | Steven Walker | Christopher Brown, Christopher Brown, Dustin Huffman, Kurt Sell, Luis Ovalles, Steven Walker, Tray Giddens | Christopher Brown, Luis Ovalles, Tray Giddens | Dustin Huffman | TX-HOU | Houston Federal Credit Union | J00017474 | Domain Upgrade & O365 Migration | Implementation/Deployment | 0 | 0 | 238.75 | -139 | 0 | 18570 | 0 | 0 | 0 | 171 | 18570 | 0 | 18570 | 0 | 47282.8 | 28712.8 | 0.60726 | -28.377

## Cory Bradfield
Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | Variance_%
12/09/24 | 07/31/25 | Open | Joaquin Marroquin | Daniel Snyder, David Goss, Wyley Johnson | Amy Martinez-Nagy, Daniel Snyder, David D Tijerina, David Goss, Joaquin Marroquin, Sophia Quinter, Wyley Johnson | Cory Bradfield, Joaquin Marroquin, Kevin Curtis, Matthew D'Ambrosio, Oscar Gonzalez, Paul Serres, Sophia Quinter, Timothy Sean Marcyes | David D Tijerina | TX-CEN | Leander ISD | 200000177 |  | Implementation/Deployment | 0.5 | 0.29431 | 593.75 | 419 | 84633.75 | 23146.25 | 0.70568 | 84633.75 | 0 | 174.75 | 0 | 0 | 23146.25 | 239314.87 | 135009.72 | 111863.47 | 0.82856 | -70.5684
01/06/25 | 04/18/25 | Open | Shannon Marie Alvarado | George Edwin Jacob, Michael Brett Beggs | Camille Elizabeth Taber, Cory Bradfield, Cory Bradfield, George Edwin Jacob, Michael Brett Beggs, Shannon Marie Alvarado | Cory Bradfield, Diego Asencio, Shannon Marie Alvarado | Camille Taber | FL | Hillsborough County Public Schools | 200000304 |  | Closed | 1 | 0.48279 | 207.13 | 135.13 | 27051.05 | 12560 | 0.65239 | 27051.05 | 28 | 100 | 3780 | 0 | 12560 | 1212759 | 44171.24 | 31611.24 | 0.71565 | -51.7211
01/15/25 | 07/25/25 | Open | Robert McIver | Firas Abood | Cory Bradfield, Cory Bradfield, Firas Abood, Robert McIver, Xavier A Trevino | Cory Bradfield, Francisco Hernandez, Jonathan Pina, Robert McIver, Roger Guerra | Eric Rodriguez | TX-SOUT | McAllen ISD | 200001640 |  | Implementation/Deployment | 0.65 | 0.18329 | 144.58 | 119.33 | 18622.04 | 2887.5 | 0.82536 | 18622.04 | 1.25 | 26.5 | 75 | 0 | 2887.5 | 205113.02 | 25656.4 | 22768.9 | 0.88745 | -81.671
01/27/25 | 09/26/25 | Open | Tray Giddens | Ahmed Al-Zubaidi, David Escamilla, Mark J Chambliss, Saif Qaissi, Wyley Johnson | Ahmed Al-Zubaidi, Cory Bradfield, Cory Bradfield, David Escamilla, Lindie Lorraine Lamar, Mark J Chambliss, Saif Qaissi, Tray Giddens, Wyley Johnson | Cory Bradfield, Tray Giddens | Lindie Lamar | TX-HOU | Stafford MSD | 200001723 |  | Planning/Design/Staging | 0.05 | 0.020424 | 146.88 | 143.88 | 18485 | 380 | 0.97958 | 18485 | 0 | 3 | 0 | 0 | 380 | 0 | 24280.2 | 23900.2 | 0.98435 | -97.9575
02/10/25 | 06/18/25 | Open | Tray Giddens | David Escamilla | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Tray Giddens | Cory Bradfield, Craig St. Rose, James Adams, Jose R. Duarte, Kord Mullins, Miguel Reed, Tray Giddens | Dustin Huffman | TX-HOU | Galveston County | 200001831 |  | Closed | 1 | 0.73121 | 218.13 | 98.63 | 23386.25 | 12895 | 0.45216 | 23386.25 | 40 | 159.5 | 2400 | 0 | 12895 | 0 | 30708 | 17813 | 0.58008 | -26.8785
03/12/25 | 06/30/25 | Open | Tray Giddens | Aman Khan, David Escamilla | Aman Khan, Dustin Huffman, Tray Giddens | Caleb Henry, Cory Bradfield, Craig St. Rose, Justin Smallwood, Kevin Curtis, Kolawole Ayeni, Luis Alvarez, Matthew D'Ambrosio, Noah Trump, Paul Serres, Tray Giddens | Dustin Huffman | TX-HOU | Gulf Capital Bank | 200002327 |  | Closed | 1 | 0.85489 | 98.55 | 29.55 | 0 | 9661.25 | 0.29985 | 0 | 15.25 | 84.25 | 1721.25 | 0 | 9661.25 | 527907.68 | 15272 | 5610.75 | 0.36739 | -14.5104
03/10/25 | 06/13/25 | Open | Brian Willery | David Escamilla | Brian Willery, David Escamilla, Jaclyn Pias | Brian Willery, Cory Bradfield | Jaclyn Pias | TX-HOU | US Legal Support | 200002361 |  | Implementation/Deployment | 0.95 | 0.62642 | 66.25 | 24.75 | 0 | 5467.5 | 0.37358 | 0 | 0 | 41.5 | 0 | 0 | 5467.5 | 0 | 13856.84 | 8389.34 | 0.60543 | -37.3585
03/14/25 | 07/25/25 | Open | Jason Esry | David Goss | David D Tijerina, David Goss, Jason Esry | Cory Bradfield, Jason Esry | David D Tijerina | TX-CEN | Leander ISD | 200002407 |  | Planning/Design/Staging | 0.25 | 0.18755 | 130.63 | 106.13 | 0 | 3172.5 | 0.81245 | 0 | 0 | 24.5 | 0 | 0 | 3172.5 | 547590.15 | 29141.2 | 25968.7 | 0.89113 | -81.2447
03/24/25 | 08/08/25 | Open | Walter Clay Knight | David Escamilla | Ashley F Freeman, Cory Bradfield, Cory Bradfield, David Escamilla, Moe Izaks, Walter Clay Knight | Cory Bradfield, Craig St. Rose, Justin Cornish, Walter Clay Knight | Ashley F Freeman | TX-HOU | Harris County Toll Road Authority | 200002488 |  | Implementation/Deployment | 0.85 | 0.5001 | 296.94 | 164.94 | 0 | 17115 | 0.55547 | 0 | 16.5 | 148.5 | 1852.5 | 0 | 17115 | 2498811.16 | 61174 | 44059 | 0.72022 | -49.9899
05/23/25 | 06/27/25 | Open | Jim Blackwell | Firas Abood | Cory Bradfield, Cory Bradfield, Firas Abood, Jeremy R Freeman, Jim Blackwell, Meredith A Richardson | Cory Bradfield, Jim Blackwell |  |  | Houston ISD | 200002987 |  | Implementation/Deployment | 0.5 | 0.13863 | 79.35 | 68.35 | 0 | 1445 | 0.86137 | 0 | 0 | 11 | 0 | 0 | 1445 | 0 | 11000 | 9555 | 0.86864 | -86.1374
06/04/25 | 10/03/25 | Open | Joaquin Marroquin | Ahmed Al-Zubaidi, David Escamilla, Steven Walker, Wyley Johnson | Ahmed Al-Zubaidi, Christopher Brown, Christopher Brown, Cory Bradfield, Cory Bradfield, David Escamilla, Joaquin Marroquin, Steven Walker, Wyley Johnson, Xavier A Trevino | Cory Bradfield, Joaquin Marroquin | Xavier A Trevino | TX-SOUT | Corpus Christi ISD | 200003048 |  | Planning/Design/Staging | 0.05 | 0.039811 | 351.66 | 337.66 | 0 | 1840 | 0.96019 | 0 | 0 | 14 | 0 | 0 | 1840 | 2515824.14 | 94653.6 | 92813.6 | 0.98056 | -96.0189
05/24/21 | 09/30/22 | Open | Brian Willery | Billy Pearson, Firas Abood, Wyley Johnson | Brian Willery, Larry Noble, Susan Richardson | Aaron Abshire, Cory Bradfield, Felipe Waterwall, Luis Alvarez, Victor Estrada | Susan Richardson | TX-HOU | Klein ISD | J00010667 | UCS and FortiSiem (Fortinet third party) | Training/Knowledge Transfer/Documentation | 0.95 | 2.2294 | 38.8 | -37.7 | 4017.7 | 7522 | -0.97165 | 4017.7 | 10 | 86.5 | 6638 | 0 | 7522 | 437100.6 | 5547.2 | -1974.8 | -0.356 | 122.9381
12/22/22 | 04/17/26 | Open | Robert McIver | Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Hugh Miller, Michael Brett Beggs, Wyley Johnson | Abdalsattar Albaghdadi, Ahmed Al-Zubaidi, Amanda Barney, Chad Hart, Cory Bradfield, Cory Bradfield, Daniel Hernandez, Daniel R Hernandez, David Monasmith, David Monasmith, Dhulfiqar Al Hashimi, Ernesto Gonzalez, Fadi Ashour, Mark Lynd, Michael Brett Beggs, Mohammed Almoola, Quoc Nguyen, Robert McIver, Romar Roca, Timothy Sean Marcyes, Wyley Johnson | Abdalsattar Albaghdadi, Albert Bernal, Cory Bradfield, Craig St. Rose, David Dobbs, Dhulfiqar Al Hashimi, Erick Nunez , Ernesto Gonzalez, James Adams, Jose R. Duarte, Justin Smallwood, Kendric Mamou, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Miguel Reed, Mohammed Al-Shaikhli, Mohammed Almoola, Mohaymen Sodi, Moises Rodriguez, Mustafa Al-Tamimi, Paul Serres, Rafael Rodriguez-Vargas, Robert McIver, Timothy Sean Marcyes | David Monasmith | TX-HOU | Texas A&M System | J00014492 | Rellis Campus - Core Network Refresh | Planning/Design/Staging | 0.4 | 0.73679 | 2440.44 | 742.61 | 279798.13 | 235074.25 | 0.30429 | 279798.13 | 100.25 | 1798.08 | 133933 | 1154.69 | 235074.25 | 4123249.95 | 632171.96 | 395943.02 | 0.62632 | -26.3215
10/04/23 | 04/07/25 | Open | Christina Rice | Michael Brett Beggs | Austen New LN: Howard Cockerham, Beau C. Devillier, Christina Rice, Christina Rice, Cory Bradfield, Cory Bradfield, Devin Moreno, Gena Robbins, Jeffery Giles, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Michael Brett Beggs, Shawn Sutton | Austen Howard, Christina Rice, Conner MacDonnell, Cory Bradfield, Devin Moreno, Gena Robbins, Jackory Nash, Jeffery Giles, Jhon Genao, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Tony Dean Skipworth | Shawn Sutton | TX-DAL | Denton ISD | J00016590 | Denton ISD: UCS-X & Dell - DC Refresh | Training/Knowledge Transfer/Documentation | 0.9 | 1.0265 | 409.89 | 9.64 | 50465.25 | 51603.75 | 0.023519 | 50465.25 | 20.5 | 420.75 | 46758.75 | 0 | 51603.75 | 727494.38 | 66283.56 | 14679.81 | 0.22147 | 2.6495
02/26/24 | 07/25/25 | Open | Jason Esry | David Escamilla, Michael Brett Beggs | Cory Bradfield, Cory Bradfield, David D Tijerina, David Escamilla, Jason Esry, Larry Noble, Michael Brett Beggs, Ron Loge | Cory Bradfield, Jason Esry, Ron Loge | David D Tijerina | TX-CEN | University of Texas - Austin | J00017214 | UT Austin VXRail Apex DC Refresh | Implementation/Deployment | 0.65 | 0.32745 | 474.88 | 327.38 | 65336.87 | 23597.5 | 0.6894 | 65336.87 | 8 | 155.5 | 15172.5 | 0 | 23597.5 | 2059242.16 | 110000 | 86402.5 | 0.78548 | -67.2549
05/02/24 | 05/01/25 | Open | Shannon Marie Alvarado | Firas Abood, Mark J Chambliss | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Hamzeh Tahat, Karyn Hubbard, Leonid G Kamenker, Leonid Kamenker, Samuel Newland, Shannon Marie Alvarado | Cory Bradfield, Hamzeh Tahat, Michael Garcia, Osazee Eweka, Samuel Newland, Shannon Marie Alvarado | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00017292 | UC Infra Installation & Apps Upgrade | Closed | 1 | 0.57408 | 592.25 | 260.25 | 81565.25 | 45447.5 | 0.43943 | 81565.25 | 8 | 340 | 25967.5 | 3277.5 | 45447.5 | 387306.6 | 73499.4 | 24774.4 | 0.33707 | -42.5918
02/16/24 | 06/30/25 | Open | Brian Willery | David Escamilla | Brian Willery, Cory Bradfield, Cory Bradfield, Jaime B Flores, Jaime Flores, Larry Noble, Maria De Kanter, Mohaymen Sodi, Susan Richardson | Abdalsattar Albaghdadi, Anthony Lange, Brian Willery, Bryant Bush, Cory Bradfield, David Dobbs, Devon LeMoine, Hector Rivera, Jaime Flores, Jerald Garner, Jesus Gonzalez, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kenneth Stevenson, Kevin Curtis, Kolawole Ayeni, Luis Ovalles, Matthew D'Ambrosio, Mohaymen Sodi, Nathan Dao, Nicolas Garakani, Paul Serres | Susan Richardson | TX-HOU | Klein ISD | J00017378 | Datacenter Compute, Storage & Network Electronics | Training/Knowledge Transfer/Documentation | 0.95 | 4.1599 | 346.13 | -986.17 | 46690.64 | 176731.55 | -2.8491 | 46690.64 | 107.58 | 1439.88 | 103574.25 | 32.5 | 176731.55 | 6806687.42 | 164198.28 | -12565.77 | -0.076528 | 315.994
04/29/24 | 06/30/25 | Open | Jim Blackwell | David Escamilla, Firas Abood | Ashley F Freeman, Cory Bradfield, Cory Bradfield, David Escamilla, Firas Abood, Jim Blackwell, Larry Noble, Luis A Alvarez, Luis Alvarez | Andy Pham, Cory Bradfield, Jim Blackwell | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00018235 | UCSC Server Implementation | Closed | 1 | 0.64639 | 105.2 | 49.45 | 1387.5 | 8605 | 0.47006 | 1387.5 | 12.25 | 68 | 2718.75 | 0 | 8605 | 167484.44 | 19506.8 | 10901.8 | 0.55887 | -35.3612
09/26/24 | 08/01/25 | Open | Tray Giddens | David Escamilla | Cory Bradfield, Cory Bradfield, David Escamilla, Dustin Huffman, Kurt Sell, Tray Giddens | Cory Bradfield, Tray Giddens | Dustin Huffman | TX-HOU | Galveston County | J00019097 | VMware Services | Implementation/Deployment | 0.5 | 0.77647 | 106.25 | 23.75 | 14981.25 | 10987.5 | 0.22353 | 14981.25 | 0 | 82.5 | 800 | 0 | 10987.5 | 0 | 23711.6 | 12724.1 | 0.53662 | -22.3529

## Juan Saenz
Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | Variance_%
03/04/25 | 08/01/25 | Open | Marco Lish | Matthew Duncan | Marco Lish, Matthew Duncan, Neel Shah | Erick Nunez , Juan Saenz, Marco Lish | Neel Shah | TX-HOU | City of Houston Public Works | 200002286 |  | Implementation/Deployment | 0.55 | 0.50973 | 161.85 | 79.35 | 0 | 10910 | 0.49027 | 0 | 0 | 82.5 | 0 | 0 | 10910 | 0 | 33830.4 | 22920.4 | 0.67751 | -49.0269
03/25/25 | 09/26/25 | Open | Marco Lish | David Escamilla | Dennis Odneal, Marco Lish | Juan Saenz, Marco Lish | Dennis Odneal | TX-HOU | University of Nevada Las Vegas | 200002508 |  | Planning/Design/Staging | 0.45 | 0.40955 | 99.5 | 58.75 | 0 | 5353.75 | 0.59045 | 0 | 0 | 40.75 | 0 | 0 | 5353.75 | 0 | 18200 | 12846.25 | 0.70584 | -59.0452
04/04/25 | 07/31/25 | Open | Christina Rice | Matthew Duncan, Michael Brett Beggs | Christina Rice, Christina Rice, Juan Saenz, Matthew Duncan, Michael Brett Beggs, Shawn Sutton | Christina Rice, Juan Saenz | Shawn Sutton | TX-DAL | Denton ISD | 200002612 |  | Not started | 0 | 0.21653 | 151.25 | 118.5 | 0 | 4326.25 | 0.78347 | 0 | 0 | 32.75 | 0 | 0 | 4326.25 | 0 | 24667.24 | 20340.99 | 0.82462 | -78.3471
04/25/25 | 08/01/25 | Open | Brittney Antoinette Hickman | Matthew Duncan | Brittney Antoinette Hickman, Carmen Isela Brandt, Garrett Curran, Juan Saenz, Matthew Duncan, Osazee Eweka | Brittney Antoinette Hickman, Juan Saenz, Osazee Eweka | Garrett Curran | CA-LAX | Los Angeles Community College District | 200002640 |  | Implementation/Deployment | 0.5 | 0.33867 | 109.25 | 72.25 | 0 | 4840 | 0.66133 | 0 | 0 | 37 | 0 | 0 | 4840 | 0 | 22598.8 | 17758.8 | 0.78583 | -66.1327
04/22/25 | 07/18/25 | Open | Summer Abunaja | Jeremy Williams | Garrett Curran, Jeremy Williams, Summer Abunaja | Juan Saenz, Summer Abunaja | Garrett Curran | CA-LAX | Santa Ana Unified School District | 200002778 |  | On HOLD | 0.15 | 0.027754 | 144.12 | 140.12 | 0 | 435 | 0.97225 | 0 | 0 | 4 | 0 | 0 | 435 | 0 | 33348 | 32913 | 0.98696 | -97.2245
05/05/25 | 07/31/25 | Open | Robert McIver | David Escamilla | Arpine Ramirez, Daniel Saenz, David Escamilla, Juan Saenz, Robert McIver, Ron Loge | Juan Saenz, Robert McIver, Ron Loge | Daniel Saenz | TX-SOUT | City of Mission | 200002941 |  | Implementation/Deployment | 0.6 | 0.51176 | 127.5 | 62.25 | 0 | 9808.75 | 0.48824 | 0 | 0 | 65.25 | 0 | 0 | 9808.75 | 0 | 11672.56 | 1863.81 | 0.15967 | -48.8235
05/09/25 | 06/30/25 | Open | Jim Blackwell | Firas Abood | Firas Abood, Jesus Escobedo, Jim Blackwell, Juan Saenz, Meredith A Richardson | Jim Blackwell, Juan Saenz |  |  | Houston ISD | 200002956 |  | Closed | 0 | 0 | 0 | -20.5 | 0 | 2747.5 | 0 | 0 | 0 | 20.5 | 0 | 0 | 2747.5 | 0 | 4500 | 1752.5 | 0.38944 | 0
06/03/25 | 07/03/25 | Open | Joanna Herrera | Michael Brett Beggs | Arcangelo Fanelli, Joanna Herrera, Juan Saenz, Michael Brett Beggs | Joanna Herrera, Juan Saenz | Arcangelo Fanelli | TX-DAL | Cook Children's Health Care System | 200003046 |  | Training/Knowledge Transfer/Documentation | 0.95 | 1.1374 | 10.55 | -1.45 | 0 | 1605 | -0.13744 | 0 | 0 | 12 | 0 | 0 | 1605 | 0 | 1585 | -20 | -0.012618 | 13.7441
11/07/22 | 07/25/25 | Open | Richard Keith Arnst | David Escamilla | Alexander Gutman, Beau C. Devillier, Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge, Shawn Sutton | Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge | Shawn Sutton | TX-DAL | City of Dallas | J00014229 | AWS - DRaaS Implementation | Implementation/Deployment | 0.75 | 0.55876 | 880.08 | 388.33 | 101771 | 66506.25 | 0.44124 | 101771 | 0 | 491.75 | 59935 | 1005.53 | 66506.25 | 0 | 225027.68 | 157515.9 | 0.69998 | -44.1244
01/30/23 | 06/30/25 | Open | Brian Willery | David Escamilla | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim | Brian Willery, Juan Saenz | Garrett Curran | CA-LAX | Amazon Web Services | J00014741 | AWS Funded - Control Tower Setup | Training/Knowledge Transfer/Documentation | 0 | 0 | 41.88 | -14 | 0 | 1890 | 0 | 0 | 0 | 15.75 | 1890 | 0 | 1890 | 0 | 10000 | 8110 | 0.811 | -62.3926
01/30/23 | 06/30/25 | Open | Brian Willery | David Escamilla | Brian Willery, Garrett Curran, Juan Saenz, Yong Kim | Brian Willery, Juan Saenz | Garrett Curran | CA-LAX | Amazon Web Services | J00014746 | WORK ORDER - AWS Funded Migration Evaluator | Training/Knowledge Transfer/Documentation | 0 | 0 | 24.06 | -4 | 0 | 540 | 0 | 0 | 0 | 6.25 | 540 | 0 | 540 | 0 | 4800 | 4260 | 0.8875 | -74.0233
07/11/24 | 06/26/25 | Closed | Summer Abunaja | Matthew Duncan | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja | Neel Shah |  | Amazon Web Services | J00018637 | AWS AppStream POC | Closed | 1 | 0.72077 | 148.8 | 41.55 | 19660.5 | 13988.75 | 0.27923 | 19660.5 | 0 | 197.25 | 0 | 0 | 13988.75 | 0 | 31024 | 17035.25 | 0.5491 | 32.5605
07/16/24 | 08/01/25 | Open | Joaquin Marroquin | David Escamilla | David D Tijerina, David Escamilla, Joaquin Marroquin, Juan Saenz, Larry Noble | Joaquin Marroquin, Juan Saenz | David D Tijerina | TX-CEN | Amazon Web Services | J00018667 | AWS DRS Migration & Control Tower Deployment | Implementation/Deployment | 0 | 0 | 77.63 | -16.5 | 0 | 2147.5 | 0 | 0 | 0 | 27 | 2147.5 | 0 | 2147.5 | 0 | 15710.4 | 13562.9 | 0.86331 | -65.2196
08/28/24 | 10/31/24 | Open | Walter Clay Knight | George Edwin Jacob | Jeff Barker, Joseph Boglino | Juan Saenz, Osazee Eweka, Walter Clay Knight | Joseph Boglino | US-FED | Amazon Web Services | J00018897 | AWS POC | Cancelled | 0 | 0 | 109.25 | -12.25 | 0 | 1591.25 | 0 | 0 | 0 | 12.25 | 1591.25 | 0 | 1591.25 | 0 | 23584.9 | 21993.65 | 0.93253 | -88.7872

## Luis Ovalles
Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | Variance_%
01/10/25 | 07/31/25 | Open | Brittney Antoinette Hickman | David Goss | Brittney Antoinette Hickman, David Goss, Luis Ovalles, Rusty Bryan | Brittney Antoinette Hickman, David Goss, Jacob Hill, Luis Ovalles, Noah Trump | Rusty Bryan | TX-DAL | Region 17 Education Service Center | 200001587 |  | Planning/Design/Staging | 0.85 | 1.1691 | 197.8 | -7.45 | 23159.04 | 28383.75 | -0.037664 | 23159.04 | 26 | 231.25 | 1560 | 0 | 28383.75 | 732573.72 | 0 | -28383.75 | 0 | 16.911
01/30/25 | 07/31/25 | Open | Brittney Antoinette Hickman | Steven Walker | Brittney Antoinette Hickman, Christopher Brown, Christopher Brown, Luis Ovalles, Mark Forehand, Steven Walker | Brittney Antoinette Hickman, Christopher Brown, Luis Ovalles | Mark Forehand | TX-DAL | City of Richardson | 200001737 |  | Planning/Design/Staging | 0.55 | 1.1607 | 140 | -22.5 | 18620 | 21637.5 | -0.16071 | 18620 | 0 | 162.5 | 0 | 0 | 21637.5 | 19743.14 | 30078.44 | 8440.94 | 0.28063 | 16.0714
03/27/25 | 05/09/25 | Open | Christina Rice | Jacob Parks, Jeffrey Holman, Michael Brett Beggs | Christina Rice, Christina Rice, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Shawn Sutton, Sophia Quinter | Christina Rice, Joshua Osgood, Luis Ovalles, Sophia Quinter | Shawn Sutton | TX-DAL | Denton ISD | 200002157 |  | Training/Knowledge Transfer/Documentation | 0.95 | 1.3429 | 17.5 | -4 | 0 | 2970 | -0.22857 | 0 | 2 | 23.5 | 120 | 0 | 2970 | 138843.78 | 3660.32 | 690.32 | 0.1886 | 34.2857
04/24/25 | 07/11/25 | Open | Marco Lish | Michael Brett Beggs | Jonathan Pendrich, Marco Lish, Michael Brett Beggs | Luis Ovalles, Marco Lish | Jonathan Pendrich | TX-DAL | Coblentz Patch Duffy & Bass LLP | 200002887 |  | Planning/Design/Staging | 0.2 | 0.17742 | 77.5 | 63.75 | 0 | 1808.75 | 0.82258 | 0 | 0 | 13.75 | 0 | 0 | 1808.75 | 0 | 16209.92 | 14401.17 | 0.88842 | -82.2581
08/23/22 | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs | Arcangelo Fanelli, Beau C. Devillier, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs | Gena Robbins, Luis Ovalles, Ron Loge | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012888 | SaaS/Parking NO HDWR - AAAQ361562 | Closed | 1 | 1.8401 | 96.6 | -81.15 | 12915 | 24048.75 | -0.84006 | 12915 | 0 | 177.75 | 24048.75 | 64.29 | 24048.75 | 0 | 0 | -24113.04 | 0 | 84.0062
07/11/22 | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs | Arcangelo Fanelli, Beau C. Devillier, Cory E Hopf, Cory Hopf, Joshua Adam Engle, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs | Gena Robbins, Luis Ovalles, Ron Loge | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012890 | HX Nodes for SAAB - AAAQ361558 | Closed | 1 | 1.9662 | 38.78 | -35.47 | 4752.5 | 10301.25 | -0.91465 | 4752.5 | 2 | 76.25 | 8681.25 | 0 | 10301.25 | 67944 | 0 | -10301.25 | 0 | 96.622
10/04/23 | 04/07/25 | Open | Christina Rice | Michael Brett Beggs | Austen New LN: Howard Cockerham, Beau C. Devillier, Christina Rice, Christina Rice, Cory Bradfield, Cory Bradfield, Devin Moreno, Gena Robbins, Jeffery Giles, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Michael Brett Beggs, Shawn Sutton | Austen Howard, Christina Rice, Conner MacDonnell, Cory Bradfield, Devin Moreno, Gena Robbins, Jackory Nash, Jeffery Giles, Jhon Genao, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Tony Dean Skipworth | Shawn Sutton | TX-DAL | Denton ISD | J00016590 | Denton ISD: UCS-X & Dell - DC Refresh | Training/Knowledge Transfer/Documentation | 0.9 | 1.0265 | 409.89 | 9.64 | 50465.25 | 51603.75 | 0.023519 | 50465.25 | 20.5 | 420.75 | 46758.75 | 0 | 51603.75 | 727494.38 | 66283.56 | 14679.81 | 0.22147 | 2.6495
02/12/24 | 07/25/25 | Open | Tray Giddens | Steven Walker | Christopher Brown, Christopher Brown, Dustin Huffman, Kurt Sell, Luis Ovalles, Steven Walker, Tray Giddens | Christopher Brown, Luis Ovalles, Tray Giddens | Dustin Huffman | TX-HOU | Houston Federal Credit Union | J00017474 | Domain Upgrade & O365 Migration | Implementation/Deployment | 0 | 0 | 238.75 | -139 | 0 | 18570 | 0 | 0 | 0 | 171 | 18570 | 0 | 18570 | 0 | 47282.8 | 28712.8 | 0.60726 | -28.377
02/26/24 | 09/30/25 | Closed | Summer Abunaja | Michael Brett Beggs | Beau C. Devillier, Kristy L Dice, Luis Ovalles, Summer Abunaja | Henry Pugsley, Luis Ovalles | Kristy L Dice | TX-DAL | Aledo ISD | J00017666 | T&E - VMWare Support | Implementation/Deployment | 0 | 0 | 0 | -61.25 | 0 | 8478.75 | 0 | 0 | 0 | 61.25 | 6318.75 | 0 | 8478.75 | 0 | 2457 | -6021.75 | -2.4509 | 0
05/21/24 | 08/29/25 | Open | LaQisha Marshall | George Edwin Jacob | Alexander Gutman, Beau C. Devillier, George Edwin Jacob, Jeffery Giles, LaQisha Marshall, Luis Ovalles | LaQisha Marshall, Luis Ovalles | Alex Gutman | TX-DAL | Dallas College | J00018375 | UCS FI Migration | On HOLD | 0.2 | 0.23684 | 57 | 43.5 | 6868.5 | 1747.5 | 0.76316 | 6868.5 | 0 | 13.5 | 1747.5 | 0 | 1747.5 | 4530.18 | 11332.8 | 9585.3 | 0.8458 | -76.3158
07/29/24 | 06/05/25 | Closed | Jason Esry | Michael Brett Beggs | Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Michael Brett Beggs, Phillip Ma Lim, Tavis Jackson , William Davenport | Carlo Enriquez, Jason Esry, Jay Daniel De Leon, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Kendall Walls, Luis Ovalles, Phillip Ma Lim, Quy Le, Tavis Jackson, Yonathan Fadel | William Davenport |  | Hurst Euless Bedford ISD | J00018726 | Data Center Network Refresh | Closed | 1 | 0.48324 | 305.23 | 157.73 | 36770.62 | 16992.5 | 0.51676 | 36770.62 | 0 | 221.5 | 0 | 0 | 16992.5 | 570092.93 | 42659.36 | 25666.86 | 0.60167 | -27.4318
10/02/24 | 05/02/25 | Open | Jason Esry | Steven Walker | Jason Esry, Jeff Barker, Steven Walker, William Davenport | Jason Esry, Luis Ovalles | William Davenport |  | Hurst Euless Bedford ISD | J00019133 | SQL Physical to Virtual Migration | Closed | 1 | 3.8897 | 36.25 | -104.75 | 4821.25 | 18975 | -2.8897 | 4821.25 | 0 | 151 | 0 | 0 | 18975 | 0 | 7087.2 | -11887.8 | -1.6774 | 316.5517
10/07/24 | 06/16/25 | Open | Walter Clay Knight | Aman Khan, David Escamilla, Eduardo Chavez, Jacob Parks, Jeffrey Holman | Aman Khan, Carmen Isela Brandt, David Escamilla, Eduardo Chavez, Jacob Parks, Jeffrey Holman, Yong Kim | Luis Ovalles, Nick Varga, Walter Clay Knight | Carmen Brandt | CA-LAX | City of Manhattan Beach | J00019153 | Network Refresh and NetApp | Implementation/Deployment | 0.65 | 0.70149 | 198.15 | 59.15 | 29446.73 | 17395 | 0.29851 | 29446.73 | 0 | 139 | 125 | 0 | 17395 | 0 | 45340.08 | 27945.08 | 0.61634 | -29.8511

## Osazee Eweka
Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | Variance_%
04/25/25 | 08/01/25 | Open | Brittney Antoinette Hickman | Matthew Duncan | Brittney Antoinette Hickman, Carmen Isela Brandt, Garrett Curran, Juan Saenz, Matthew Duncan, Osazee Eweka | Brittney Antoinette Hickman, Juan Saenz, Osazee Eweka | Garrett Curran | CA-LAX | Los Angeles Community College District | 200002640 |  | Implementation/Deployment | 0.5 | 0.33867 | 109.25 | 72.25 | 0 | 4840 | 0.66133 | 0 | 0 | 37 | 0 | 0 | 4840 | 0 | 22598.8 | 17758.8 | 0.78583 | -66.1327
05/02/24 | 05/01/25 | Open | Shannon Marie Alvarado | Firas Abood, Mark J Chambliss | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Hamzeh Tahat, Karyn Hubbard, Leonid G Kamenker, Leonid Kamenker, Samuel Newland, Shannon Marie Alvarado | Cory Bradfield, Hamzeh Tahat, Michael Garcia, Osazee Eweka, Samuel Newland, Shannon Marie Alvarado | Ashley F Freeman | TX-HOU | Harris County Hospital District | J00017292 | UC Infra Installation & Apps Upgrade | Closed | 1 | 0.57408 | 592.25 | 260.25 | 81565.25 | 45447.5 | 0.43943 | 81565.25 | 8 | 340 | 25967.5 | 3277.5 | 45447.5 | 387306.6 | 73499.4 | 24774.4 | 0.33707 | -42.5918
07/11/24 | 06/26/25 | Closed | Summer Abunaja | Matthew Duncan | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja | Neel Shah |  | Amazon Web Services | J00018637 | AWS AppStream POC | Closed | 1 | 0.72077 | 148.8 | 41.55 | 19660.5 | 13988.75 | 0.27923 | 19660.5 | 0 | 197.25 | 0 | 0 | 13988.75 | 0 | 31024 | 17035.25 | 0.5491 | 32.5605
08/28/24 | 10/31/24 | Open | Walter Clay Knight | George Edwin Jacob | Jeff Barker, Joseph Boglino | Juan Saenz, Osazee Eweka, Walter Clay Knight | Joseph Boglino | US-FED | Amazon Web Services | J00018897 | AWS POC | Cancelled | 0 | 0 | 109.25 | -12.25 | 0 | 1591.25 | 0 | 0 | 0 | 12.25 | 1591.25 | 0 | 1591.25 | 0 | 23584.9 | 21993.65 | 0.93253 | -88.7872

## Ron Loge
Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | Variance_%
02/14/25 | 10/31/25 | Open | William Chris Roome | George Edwin Jacob | Gearld Stanley McNiel, George Edwin Jacob, Jonathan Pendrich, Katharine McCarley, Katherine McCarley, Ron Loge, Stan McNiel, William Chris Roome, William Roome | Bradley Buchanan, Carlo Enriquez, Conner MacDonnell, Dante Torres, Devin Moreno, Frank Jaimes, Jacob Hill, Jalen Vecchitto, Joshua Hubbard, Joshua Osgood, Justin Mitchell, Lauren Lanzini Coffey, Noah Castleberry, Remijio Hernandez, Ron Loge, William Chris Roome | Jonathan Pendrich | TX-DAL | Wells Fargo Financial Services | 200001912 |  | Planning/Design/Staging | 0.1 | 0.40101 | 740 | 443.25 | 66900 | 24858.75 | 0.59899 | 66900 | 0 | 296.75 | 0 | 0 | 24858.75 | 1636787.76 | 953120 | 928261.25 | 0.97392 | -59.8986
02/28/25 | 08/29/25 | Open | Marshall Chuck Pugh | George Edwin Jacob | George Edwin Jacob, Lauren J Kennewell, Marshall Chuck Pugh , Ron Loge | Marshall Chuck Pugh, Ron Loge | Lauren J Kennewell | TX-DAL | Plano ISD | 200002216 |  | Implementation/Deployment | 0.75 | 0.715 | 50 | 14.25 | 0 | 6106.25 | 0.285 | 0 | 0 | 35.75 | 0 | 0 | 6106.25 | 0 | 10458 | 4351.75 | 0.41612 | -28.5
04/03/25 | 08/21/25 | Open | Abiodun David Babasola | George Edwin Jacob | Abiodun David Babasola, David Babasola, George Edwin Jacob, Lauren J Kennewell, Ron Loge, Timothy Fain | Abiodun David Babasola, Austen Howard, Brycen Dimas, Dante Torres, Remijio Hernandez, Ron Loge | Lauren J Kennewell | TX-DAL | Duncanville ISD | 200002471 |  | Planning/Design/Staging | 0.5 | 0.31177 | 242.97 | 171.72 | 0 | 9826.25 | 0.70675 | 0 | 4.5 | 75.75 | 442.5 | 0 | 9826.25 | 992618.73 | 50096.3 | 40270.05 | 0.80385 | -68.8233
05/05/25 | 07/31/25 | Open | Robert McIver | David Escamilla | Arpine Ramirez, Daniel Saenz, David Escamilla, Juan Saenz, Robert McIver, Ron Loge | Juan Saenz, Robert McIver, Ron Loge | Daniel Saenz | TX-SOUT | City of Mission | 200002941 |  | Implementation/Deployment | 0.6 | 0.51176 | 127.5 | 62.25 | 0 | 9808.75 | 0.48824 | 0 | 0 | 65.25 | 0 | 0 | 9808.75 | 0 | 11672.56 | 1863.81 | 0.15967 | -48.8235
06/09/25 | 08/08/25 | Open | Brian Willery | David Escamilla | Brian Willery, David Escamilla, Jaclyn Pias | Brian Willery, Frank Jaimes, Jalen Vecchitto, Ron Loge | Jaclyn Pias | TX-HOU | AIS Portfolio Services | 200003066 |  | Planning/Design/Staging | 0.05 | 0.4 | 43.75 | 30.25 | 0 | 1901.25 | 0.69143 | 0 | 4 | 17.5 | 470 | 0 | 1901.25 | 251413.55 | 11000 | 9098.75 | 0.82716 | -60
12/29/23 | 12/20/24 | Open | Jennifer Soliz | Kenneth Dieter | Jennifer Soliz, Larry Noble, Lonnie Owens | Andrew G Wagenhofer, Christopher Knipe, Jennifer Soliz, Michael Hilton, Ron Loge, Sarah Beatrice Williamson | Lonnie Owens | TX-CEN | CPS Energy | J00009890 | 2194850 - ACI NERC | Cancelled | 0.95 | 0.48441 | 398.42 | 215.42 | 45052.12 | 32855 | 0.54069 | 45052.12 | 10 | 193 | 31105 | 279.63 | 32855 | 860337.8 | 74726 | 41591.37 | 0.55658 | -51.5587
01/24/22 | 05/16/25 | Open | Lauren Lanzini Coffey | Billy Pearson, Firas Abood | Firas Abood, Lauren Lanzini Coffey, Michael Hilton, Neel Shah, Ron Loge, Tony Dean Skipworth | Andy Pham, Devon LeMoine, Justin Cornish, Lauren Lanzini Coffey, Michael Hilton, Ron Loge, Tony Dean Skipworth | Neel Shah |  | Sam Houston State University | J00011651 | ACI Deployment | Training/Knowledge Transfer/Documentation | 0.95 | 0.029456 | 288.56 | 280.06 | 32286.7 | 980.5 | 0.97054 | 32286.7 | 0 | 299.1 | 0 | 643.98 | 980.5 | 956677.52 | 94815.2 | 93190.72 | 0.98287 | 3.6526
08/23/22 | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs | Arcangelo Fanelli, Beau C. Devillier, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs | Gena Robbins, Luis Ovalles, Ron Loge | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012888 | SaaS/Parking NO HDWR - AAAQ361562 | Closed | 1 | 1.8401 | 96.6 | -81.15 | 12915 | 24048.75 | -0.84006 | 12915 | 0 | 177.75 | 24048.75 | 64.29 | 24048.75 | 0 | 0 | -24113.04 | 0 | 84.0062
07/11/22 | 05/30/25 | Open | Karyn Hubbard | Michael Brett Beggs | Arcangelo Fanelli, Beau C. Devillier, Cory E Hopf, Cory Hopf, Joshua Adam Engle, Karyn Hubbard, Luis Ovalles, Michael Brett Beggs | Gena Robbins, Luis Ovalles, Ron Loge | Arcangelo Fanelli | TX-DAL | DFW International Airport | J00012890 | HX Nodes for SAAB - AAAQ361558 | Closed | 1 | 1.9662 | 38.78 | -35.47 | 4752.5 | 10301.25 | -0.91465 | 4752.5 | 2 | 76.25 | 8681.25 | 0 | 10301.25 | 67944 | 0 | -10301.25 | 0 | 96.622
06/20/22 | 06/20/25 | Open | Jason Esry | Emilio Carrillo, Firas Abood, Kenneth Dieter, Mark J Chambliss, Timothy Ramsey | David D Tijerina, Jaime Cortez, Jason Esry, Larry Noble, Robert Kelly, Robert Kelly, Timothy Ramsey, Tony Dean Skipworth | Abdulrahman Farhan, Eric Firestone, Ernesto Gonzalez, Isaiah Covington, Jaime Cortez, James Danner, Jason Esry, Jeffrey Charles Primeaux, Kyle Linder, Micah Rendon, Mohammed Almoola, Ron Loge, Tony Dean Skipworth, Trevor Youngman | David D Tijerina | TX-CEN | San Antonio ISD | J00013237 | DC \ ACI \ Core Router and FW Work | Implementation/Deployment | 0.95 | 0.86726 | 474.48 | 82.98 | 58472.5 | 50840 | 0.17489 | 58472.5 | 20 | 411.5 | 43967.5 | 473.32 | 50840 | 637580.65 | 83092 | 31778.68 | 0.38245 | -13.2735
11/07/22 | 07/25/25 | Open | Richard Keith Arnst | David Escamilla | Alexander Gutman, Beau C. Devillier, Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge, Shawn Sutton | Charles Brown, Juan Saenz, Richard Keith Arnst, Ron Loge | Shawn Sutton | TX-DAL | City of Dallas | J00014229 | AWS - DRaaS Implementation | Implementation/Deployment | 0.75 | 0.55876 | 880.08 | 388.33 | 101771 | 66506.25 | 0.44124 | 101771 | 0 | 491.75 | 59935 | 1005.53 | 66506.25 | 0 | 225027.68 | 157515.9 | 0.69998 | -44.1244
08/01/23 | 08/01/25 | Open | Tray Giddens | David Escamilla | Aman Khan, Austen New LN: Howard Cockerham, Bradley Buchanan, Conner MacDonnell, Dante Torres, David Escamilla, Devin Moreno, Dustin Huffman, Frank Jaimes, Jeffery Giles, Jhon Genao, Juan Pomares, Kirk O'Guinn, Kurt Sell, Mohaymen Sodi, Noah Castleberry, Noah Trump, Patrick Shea Thompson, Patrick Thompson, Phillip Ma Lim, Ron Loge, Sean Cowhey, Tabais Prater, Tavis Jackson, Tray Giddens | Austen Howard, Carlo Enriquez, Devin Moreno, Jhon Genao, Justin Mitchell, Kanoa Parman, Kebret Eshetu, Kevin Curtis, Kirk O'Guinn, Kolawole Ayeni, Matthew D'Ambrosio, Mohaymen Sodi, Nicolas Garakani, Noah Trump, Patrick Shea Thompson, Phillip Ma Lim, Quy Le, Ron Loge, Sean Cowhey, Tabais Prater, Tray Giddens, William Chris Roome, Yonathan Fadel | Dustin Huffman | TX-HOU | Apache Corporation | J00016147 | Nexus Refresh | Implementation/Deployment | 0.5 | 1.3089 | 373.4 | -95.85 | 49610.75 | 58927.5 | -0.2567 | 49610.75 | 19.5 | 488.75 | 47760 | 20 | 58927.5 | 866896 | 78495 | 19547.5 | 0.24903 | 30.8918
02/26/24 | 07/25/25 | Open | Jason Esry | David Escamilla, Michael Brett Beggs | Cory Bradfield, Cory Bradfield, David D Tijerina, David Escamilla, Jason Esry, Larry Noble, Michael Brett Beggs, Ron Loge | Cory Bradfield, Jason Esry, Ron Loge | David D Tijerina | TX-CEN | University of Texas - Austin | J00017214 | UT Austin VXRail Apex DC Refresh | Implementation/Deployment | 0.65 | 0.32745 | 474.88 | 327.38 | 65336.87 | 23597.5 | 0.6894 | 65336.87 | 8 | 155.5 | 15172.5 | 0 | 23597.5 | 2059242.16 | 110000 | 86402.5 | 0.78548 | -67.2549
01/29/24 | 11/28/25 | Open | Ryan Scott | Michael Brett Beggs | Arcangelo Fanelli, Beau C. Devillier, Bryan Mullen, Michael Brett Beggs, Ron Loge, Ryan Scott, Taylor Leger, Tony Dean Skipworth | Bryan Mullen, Ron Loge, Ryan Scott | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00017306 | 2023 DC Core ACI Optimization | Implementation/Deployment | 0.6 | 0.78152 | 541.25 | 118.25 | 71986.25 | 53125 | 0.21848 | 71986.25 | 0 | 423 | 28000 | 0 | 53125 | 0 | 168369.6 | 115244.6 | 0.68447 | -21.8476
07/11/24 | 06/26/25 | Closed | Summer Abunaja | Matthew Duncan | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja | Neel Shah |  | Amazon Web Services | J00018637 | AWS AppStream POC | Closed | 1 | 0.72077 | 148.8 | 41.55 | 19660.5 | 13988.75 | 0.27923 | 19660.5 | 0 | 197.25 | 0 | 0 | 13988.75 | 0 | 31024 | 17035.25 | 0.5491 | 32.5605

## Tony Dean Skipworth
Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | Variance_%
03/11/25 | 05/02/25 | Closed | Walter Clay Knight | Jeremy Williams | Camille Elizabeth Taber, Jeremy Williams, Walter Clay Knight | Tony Dean Skipworth, Walter Clay Knight | Camille Taber | FL | Mainline | 200002359 |  | Closed | 1 | 0.48913 | 18.4 | 9.4 | 0 | 1190 | 0.51087 | 0 | 0 | 9 | 0 | 0 | 1190 | 0 | 4254.1 | 3064.1 | 0.72027 | -51.087
04/25/25 | 07/31/25 | Open | LaQisha Marshall | David D Tijerina, David Goss | David D Tijerina, David Escamilla, David Goss, LaQisha Marshall, Tony Dean Skipworth | LaQisha Marshall, Tony Dean Skipworth | David D Tijerina | TX-CEN | Travis County | 200002593 |  | Planning/Design/Staging | 0.05 | 0.15152 | 33 | 28 | 0 | 635 | 0.84848 | 0 | 0 | 5 | 0 | 0 | 635 | 89560.52 | 19724 | 19089 | 0.96781 | -84.8485
05/27/25 | 07/31/25 | Open | Walter Clay Knight | David Goss | David D Tijerina, David Goss, Tony Dean Skipworth, Walter Clay Knight | Tony Dean Skipworth, Walter Clay Knight | David D Tijerina | TX-CEN | Williamson County | 200003014 |  | Planning/Design/Staging | 0.05 | 0.030945 | 64.63 | 62.63 | 0 | 260 | 0.96905 | 0 | 0 | 2 | 0 | 0 | 260 | 59519.92 | 8772.88 | 8512.88 | 0.97036 | -96.9055
01/24/22 | 05/16/25 | Open | Lauren Lanzini Coffey | Billy Pearson, Firas Abood | Firas Abood, Lauren Lanzini Coffey, Michael Hilton, Neel Shah, Ron Loge, Tony Dean Skipworth | Andy Pham, Devon LeMoine, Justin Cornish, Lauren Lanzini Coffey, Michael Hilton, Ron Loge, Tony Dean Skipworth | Neel Shah |  | Sam Houston State University | J00011651 | ACI Deployment | Training/Knowledge Transfer/Documentation | 0.95 | 0.029456 | 288.56 | 280.06 | 32286.7 | 980.5 | 0.97054 | 32286.7 | 0 | 299.1 | 0 | 643.98 | 980.5 | 956677.52 | 94815.2 | 93190.72 | 0.98287 | 3.6526
06/20/22 | 06/20/25 | Open | Jason Esry | Emilio Carrillo, Firas Abood, Kenneth Dieter, Mark J Chambliss, Timothy Ramsey | David D Tijerina, Jaime Cortez, Jason Esry, Larry Noble, Robert Kelly, Robert Kelly, Timothy Ramsey, Tony Dean Skipworth | Abdulrahman Farhan, Eric Firestone, Ernesto Gonzalez, Isaiah Covington, Jaime Cortez, James Danner, Jason Esry, Jeffrey Charles Primeaux, Kyle Linder, Micah Rendon, Mohammed Almoola, Ron Loge, Tony Dean Skipworth, Trevor Youngman | David D Tijerina | TX-CEN | San Antonio ISD | J00013237 | DC \ ACI \ Core Router and FW Work | Implementation/Deployment | 0.95 | 0.86726 | 474.48 | 82.98 | 58472.5 | 50840 | 0.17489 | 58472.5 | 20 | 411.5 | 43967.5 | 473.32 | 50840 | 637580.65 | 83092 | 31778.68 | 0.38245 | -13.2735
05/31/24 | 07/11/25 | Open | Richard Keith Arnst | Ahmed Al-Zubaidi, David Escamilla, Joshua Adam Engle, Wyley Johnson | Ashutosh Patel, Christopher Butler, Maria De Kanter, Randy Schamberger, Raul Velazquez, Richard Keith Arnst, Tony Dean Skipworth | Ashutosh Patel, Kreshnik Memaj, Raul Velazquez, Richard Keith Arnst, Romar Roca, Tony Dean Skipworth | Randy Schamberger | FL | Charlotte County Clerk of the Circuit Court | J00014845 | Core Upgrade & Net-Pro-3rd Party Srvcs | Implementation/Deployment | 0.85 | 1.2066 | 548.85 | -81.4 | 87146.41 | 89143.75 | -0.14831 | 87146.41 | 32 | 662.25 | 65992.5 | 50 | 89143.75 | 271377.04 | 112684.24 | 23490.49 | 0.20846 | 20.6614
10/04/23 | 04/07/25 | Open | Christina Rice | Michael Brett Beggs | Austen New LN: Howard Cockerham, Beau C. Devillier, Christina Rice, Christina Rice, Cory Bradfield, Cory Bradfield, Devin Moreno, Gena Robbins, Jeffery Giles, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Michael Brett Beggs, Shawn Sutton | Austen Howard, Christina Rice, Conner MacDonnell, Cory Bradfield, Devin Moreno, Gena Robbins, Jackory Nash, Jeffery Giles, Jhon Genao, Joshua Osgood, Juan Pomares, Kirk O'Guinn, Luis Ovalles, Tony Dean Skipworth | Shawn Sutton | TX-DAL | Denton ISD | J00016590 | Denton ISD: UCS-X & Dell - DC Refresh | Training/Knowledge Transfer/Documentation | 0.9 | 1.0265 | 409.89 | 9.64 | 50465.25 | 51603.75 | 0.023519 | 50465.25 | 20.5 | 420.75 | 46758.75 | 0 | 51603.75 | 727494.38 | 66283.56 | 14679.81 | 0.22147 | 2.6495
05/09/24 | 06/30/25 | Open | Summer Abunaja | George Edwin Jacob | Joseph Boglino, Larry Noble, Summer Abunaja, Tony Dean Skipworth | Summer Abunaja, Tony Dean Skipworth | Joseph Boglino | US-FED | U.S. Peace Corps | J00018290 | APIC Cluster Project | Implementation/Deployment | 0.2 | 0.76667 | 30 | 7 | 4050 | 3070 | 0.23333 | 4050 | 0 | 23 | 3070 | 0 | 3070 | 140008.68 | 6075 | 3005 | 0.49465 | -23.3333
10/23/24 | 08/11/25 | Open | Ryan Scott | Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs | Arcangelo Fanelli, Beau C. Devillier, Bryan Geoghan, David Watkins, David Pena, Jacob Parks, Jeffrey Holman, Michael Brett Beggs, Ryan Scott, Tony Dean Skipworth | Bryan Mullen, Devin Moreno, Noah Castleberry, Ryan Scott, Tony Dean Skipworth | Arcangelo Fanelli | TX-DAL | Parkland Health & Hospital System | J00019061 | DC: ACI - APIC Refresh | On HOLD | 0.2 | 0.43333 | 67.5 | 39.25 | 7575.69 | 3676.25 | 0.58148 | 7575.69 | 1 | 29.25 | 247.5 | 0 | 3676.25 | 0 | 16532.8 | 12856.55 | 0.77764 | -56.6667