## Problem_Projects
Issue_Type | Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP %
Old Closed Project | 09/07/18 | 10/05/18 | Open | Ben Reyes |  |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00001078 | 0000338105 | Closed | 1 | 0 | 1 | 1 | 30 | 0 | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 381 | 20 | 20 | 1
Old Closed Project | 01/21/19 | 02/21/19 | Open | Ben Reyes |  |  | John Velez |  |  | Houston ISD | J00003362 | NET-PRO-EU | Closed | 0 | 0 | 0 | -1 | 0 | 35 | 0 | 0 | 0 | 1 | 35 | 0 | 35 | 96.9 | 50 | 15 | 0.3
Old Closed Project | 02/05/19 | 02/05/20 | Open | Ben Reyes |  |  | John Velez |  |  | Houston ISD | J00003493 | NET-PRO-EU | Closed | 1 | 1 | 1 | 0 | 30 | 35 | 0 | 30 | 0 | 1 | 35 | 2.32 | 35 | 153.44 | 50 | 12.68 | 0.2536
Old Closed Project | 02/05/19 | 02/05/20 | Open | Ben Reyes |  |  | John Velez |  |  | Houston ISD | J00003501 | NET-PRO-EU | Closed | 0 | 0 | 0 | -1 | 0 | 35 | 0 | 0 | 0 | 1 | 35 | 0 | 35 | 379.31 | 100 | 65 | 0.65
Old Closed Project | 03/07/19 | 03/09/20 | Open | Ben Reyes |  |  | John Velez |  |  | Houston ISD | J00003789 | 8000288890 | Closed | 1 | 2 | 1 | -1 | 30 | 70 | -1 | 30 | 0 | 2 | 70 | 0 | 70 | 146.55 | 50 | -20 | -0.4
Old Closed Project | 03/07/19 | 03/09/20 | Open | Ben Reyes | [5 empty] | Houston ISD | J00003790 | 8000289032 | Closed | 1 | 0 | 1 | 1 | 30 | 0 | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 348.22 | 75 | 75 | 1
Old Closed Project | 03/07/19 | 03/09/20 | Open | Ben Reyes | [5 empty] | Houston ISD | J00003791 | 8000289314 | Closed | 1 | 0 | 1 | 1 | 30 | 0 | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 89.91 | 50 | 50 | 1
Old Closed Project | 03/25/19 | 03/25/20 | Open | Ben Reyes |  |  | John Velez |  |  | Houston ISD | J00003876 | AAAQ65674 | Closed | 1 | 1 | 1 | 0 | 30 | 35 | 0 | 30 | 0 | 1 | 35 | 0 | 35 | 328.42 | 50 | 15 | 0.3
Old Closed Project | 03/26/19 | 03/26/20 | Open | Ben Reyes |  |  | Thai Hong |  |  | Houston ISD | J00003888 | NET-PRO-EU | Closed | 1 | 9.3333 | 6 | -50 | 0 | 1960 | -8.3333 | 0 | 0 | 56 | 1960 | 62 | 1960 | 0 | 0 | -2022 | 0
Old Closed Project | 03/27/19 | 03/27/20 | Open | Ben Reyes | [5 empty] | Houston ISD | J00003899 | AAAQ67912 | Closed | 1 | 0 | 1 | 1 | 30 | 0 | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 130.13 | 50 | 50 | 1
Old Closed Project | 03/28/19 | 03/30/20 | Open | Ben Reyes | [5 empty] | Houston ISD | J00003913 | AAAQ65561 | Closed | 1 | 0 | 1 | 1 | 30 | 0 | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 90.6 | 0 | 0 | 0
Old Closed Project | 10/30/20 | 10/30/20 | Open | Tray Giddens |  |  | Abel Abraham, Aboobiada Aliabdalla, Adeline Tidjon, Ahmed Alkutel, Ahmed Hamad, Aide Guadian, Ana Morales, Brianna Johnson, Darrick Bonner, David Gonzalez, Desmond Thomas, Ekpenyong Otu, Eleazar Guzman, Eliana Guzman, Felipe Ajche, Gerardo Guzman, Gregory Clark, Gregory Posey, Harold Mauricio Gomez, Hugo Gutierrez, Jaylen Morgan, Jennifer Mares, Jesus Guadian, Joan Elmore, John Silva, Jose E. Duarte Jr, Joseph Eneremadu, Juan Mendoza, Kai Rose , Kenia Dimas, Miguel Campos, Moses Mwamba | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00008064 | 0000391611 - Student 14000 | Closed | 1 | 0.35249 | 14000 | 9065.08 | 420000 | 163067.6 | 0.64751 | 420000 | 0 | 4934.92 | 163067.6 | 3246.38 | 163067.6 | 8223180 | 458260 | 291946.02 | 0.63708
Old Closed Project | 09/24/21 | 07/28/23 | Open | Jim Blackwell | Christine A Hupe | Ahmed Jameel, Aleksei Lavrushenkov, Christine A Hupe, Craig St. Rose, Craig St. Rose, Jim Blackwell, Mustafa Al-Tamimi | Ahmed Jameel, Aleksei Lavrushenkov, Andy Alvarenga, Andy Pham, Bobby Fontenot, Craig St. Rose, Daniel Hernandez, David Dobbs, Hector Rivera, Jaime Flores, Jim Blackwell, Justin Higgins, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mustafa Al-Tamimi, Paul Serres, Victor Estrada | Neel Shah |  | Dickinson ISD | J00011303 | PO 21003551 - ERATE21 - Meraki | Closed | 1 | 0 | 537.71 | 537.71 | 31832.8 | 0 | 1 | 31832.8 | 0 | 945.25 | 0 | 2831.258 | 0 | 979744.4 | 59016.2 | 56184.942 | 0.95203
Old Closed Project | 12/08/21 | 05/31/23 | Open | Jim Blackwell | Albert H Nguyen | Albert H Nguyen, Aleksei Lavrushenkov, Jim Blackwell, Mustafa Al-Tamimi, Truong Nguyen | Aaron Johns, Ahmed Jameel, Andy Alvarenga, Andy Pham, Craig St. Rose, David Dobbs, Hector Rivera, Jeff Ogbor, Jim Blackwell, Justin Higgins, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kord Mullins, Luis Alvarez, Matthew D'Ambrosio, Mustafa Al-Tamimi, Nathan Dao, Syed Zaidi, Victor Estrada | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00011620 | Fine Arts x8 Site Network & Wireless Upgrades | Closed | 0 | 0 | 0 | -530.25 | 0 | 31895 | 0 | 0 | 28 | 558.25 | 30495 | 1710.2628 | 31895 | 462660.4 | 41683.1 | 8077.8372 | 0.19379
Old Closed Project | 06/13/22 | 02/17/23 | Open | Brian Willery | Wyley Johnson |  | Brian Willery | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00012044 | ASA Refresh | Closed | 1 | 0.051869 | 365.34 | 346.39 | 45748.8 | 2368.75 | 0.94813 | 45748.8 | 0 | 18.95 | 2368.75 | 0 | 2368.75 | 44540.58 | 68440.4 | 66071.65 | 0.96539
Old Closed Project | 02/25/22 | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Tray Giddens | Ana Morales, Antonio Acosta, Dedric Bowens, Delilah Davis, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Mauricio Gomez, Hussein Majeed, Ishmeal Vaughn, Jesus Guadian, Kai Rose , Lorenzo Hernandez, Maria Rivera, Monica Cavazos, Oscar Nunez, Safa Abdallah, Samsoni Jean Claude, William Van der Voort | Monica Johnson | TX-HOU | Harmony Public Schools Sugarland | J00012155 | 22081022 houston west | Closed | 1 | 0.49548 | 646.85 | 326.35 | 22639.75 | 9705 | 0.50452 | 22639.75 | 0 | 320.5 | 9705 | 231.32 | 9705 | 4843.68 | 37500 | 27563.68 | 0.73503
Old Closed Project | 03/07/22 | 06/01/23 | Open | Tray Giddens | Mark J Chambliss | Mark J Chambliss, Tray Giddens | Isaac Brown, Alexander Sanchez, Ana Morales, Andrew Comeaux, Anthony Balogun, Antonio Acosta, Axel Zavala, Brendacia Morgan, Brianna Mosqueda, Darrick Bonner, David Gonzalez, David Lenihan, Dedric Bowens, Devante Humphrey, Devin Bradford, Diana Cabrera, Eleazar Guzman, Eliana Guzman, Elliot Henriquez, Enrique Valdes, Felipe Ajche, Gregory Posey, Harold Gomez, Harold Mauricio Gomez, Ishmeal Vaughn, Jarshawn Newsome, Jaylen Morgan, Jesus Guadian, John Silva, Josias Ajche , Justin Jefferson, |  |  | Houston ISD | J00012230 | Esser Computer Lab 6690 | Closed | 1 | 0.86062 | 6690 | 932.47 | 234150 | 201735.9 | 0.13938 | 234150 | 0 | 5757.53 | 201735.9 | 7322.76 | 201735.9 | 6201880 | 0 | -209058.66 | 0
Old Closed Project | 06/27/22 | 02/10/23 | Open | Brian Willery |  | Abdulrahman Farhan, Brian Willery, Jason Osuna, Larry Noble, Romar Roca | Abdulrahman Farhan, Brian Willery, Romar Roca | Jason Osuna | TX-CEN | Buc-ee's, LTD | J00012741 | ASA Refresh | Closed | 1 | 0.89232 | 365.34 | 57.34 | 53786.25 | 48637.5 | 0.15695 | 53786.25 | 18 | 326 | 45937.5 | 112.01 | 48637.5 | 0 | 0 | -48749.51 | 0
Old Closed Project | 10/24/22 | 04/21/23 | Open | Joanna Herrera | Edward Padron, Rogelio Dominguez | Joanna Herrera, Ruben Cantu, Steve J Rodriguez, Xavier A Trevino | Felix Martinez, Francisco Medrano, Joanna Herrera, Jose Salazar, Marisela Contreras, Ruben Cantu | Xavier A Trevino | TX-SOUT | City of Brownsville | J00012772 | Work Order – IDF Closet @ IS Bldg B | Closed | 1 | 0.89904 | 52 | 12.75 | 4908.5 | 4945 | 0.24519 | 4908.5 | 7.5 | 46.75 | 4375 | 35.83 | 4945 | 25065.12 | 21160.32 | 16179.49 | 0.76461
Old Closed Project | 04/18/22 | 04/28/23 | Open | Brian Willery | Charles Brown, David Escamilla | Osazee Eweka | Brian Willery, Charles Brown, Osazee Eweka | Susan Richardson |  | Amazon Web Services | J00012911 | AWS Migration Evaluator - Work Order | Closed | 1 | 0 | 24.75 | 24.75 | 2895.75 | 0 | 1 | 2895.75 | 0 | 43 | 0 | 0 | 0 | 0 | 3958.8 | 3958.8 | 1
Old Closed Project | 05/09/22 | 09/09/22 | Open | Brian Willery | Joshua Adam Engle | Beau C. Devillier, Brian Willery, Jean Pierre Obenda, Lauren J Kennewell, Vitalii Stepanchenko | Brian Willery, Carlo Enriquez, Chase Davis, Conner MacDonnell, Daniel Hernandez, Dante Torres, Devin Moreno, Dionisio Oscar Medina-Marcelin, Dylan Pittsinger, Jean Pierre Obenda, Jhon Genao, Joel Fleming, Joel Hubbard, Jordan Newman, Juan Pomares, Kanoa Parman, Luis Hernandez, Orlando Francis, Patrick Thompson, Sean Cowhey, Taylor Poole, Thai Truong, Timothy Mitchell, Vitalii Stepanchenko | Lauren J Kennewell | TX-DAL | McKinney ISD | J00012957 | Burks-Webb-Johnson Schools - Network PS | Closed | 1 | 2.1411 | 486.34 | -517.96 | 38892.5 | 89975 | -1.065 | 38892.5 | 37 | 1041.3 | 86877.5 | 2790.53 | 89975 | 0 | 58797 | -33968.53 | -0.57773
Old Closed Project | 06/20/22 | 05/19/23 | Open | Brian Willery | Bryan Geoghan | Anthony Towsley, Brian Willery, Bryan Mullen, Lauren J Kennewell, Shiraz Humayun | Abdulrahman Farhan, Brian Willery, Bryan Mullen, Mohaymen Sodi | Lauren J Kennewell | TX-DAL | City of Frisco | J00013293 | Library - Network Infrastructure Install | Closed | 1 | 0.59422 | 369.39 | 149.89 | 40794.75 | 27637.5 | 0.40578 | 40794.75 | 0 | 219.5 | 27637.5 | 219.72 | 27637.5 | 1053772.05 | 61491.68 | 33634.46 | 0.54698
Old Closed Project | 03/03/23 | 06/22/23 | Open | Brian Willery |  | Brian Willery, Felipe D. Waterwall, Felipe Waterwall, Larry Noble, Susan Richardson | Aaron Johns, Andy Alvarenga, Felipe Waterwall | Susan Richardson | TX-HOU | Klein ISD | J00013316 | WebEx Room Kit | Closed | 1 | 1.0161 | 11.81 | -0.19 | 1003.75 | 750 | -0.016088 | 1003.75 | 0 | 12 | 750 | 38.22 | 750 | 4739.4 | 1219.96 | 431.74 | 0.3539
Old Closed Project | 08/15/22 | 05/26/23 | Open | Brian Willery | Matthew Duncan | Brian Willery, Charles Brown, Matthew Duncan, Steve J Rodriguez, Xavier A Trevino | Brian Willery, Charles Brown, Juan Saenz, Osazee Eweka | Xavier A Trevino |  | Amazon Web Services | J00013506 | AWS Cybersecurity Migration | Closed | 1 | 0 | 114.4 | 114.4 | 13156 | 0 | 1 | 13156 | 0 | 181 | 0 | 0 | 0 | 0 | 21218 | 21218 | 1
Old Closed Project | 08/31/22 | 03/31/23 | Open | Tray Giddens |  | Ashley F Freeman, Larry Noble, Tray Giddens | Isaac Brown, Andrew Comeaux, David Gonzalez, David Lenihan, Dedric Bowens, Devante Humphrey, Eliana Guzman, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, John Silva, Kaustuv Ghosh, Oscar Nunez, Samsoni Jean Claude, Tray Giddens | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00013827 | FBISD AV classroom and carts | Closed | 1 | 0.85405 | 606.99 | 88.59 | 27314.25 | 21442 | 0.14595 | 27314.25 | 0 | 518.4 | 21442 | 0 | 21442 | 1500931.7 | 39150 | 17708 | 0.45231
Old Closed Project | 11/09/22 | 03/31/23 | Open | Brian Willery | Bryan Geoghan | Brian Newman, Brian Newman, Brian Willery, Lauren J Kennewell, Shiraz Humayun | Brian Newman | Lauren J Kennewell | TX-DAL | City of Frisco | J00014067 | Collaboration Upgrade to 14 | Closed | 1 | 0.83951 | 101.25 | 16.25 | 14006.25 | 11900 | 0.16049 | 14006.25 | 0 | 85 | 11900 | 0 | 11900 | 0 | 13726.4 | 1826.4 | 0.13306
Old Closed Project | 10/14/22 | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014148 | 23111694 | Closed | 1 | 0.125 | 8 | 7 | 314.2 | 125 | 0.875 | 314.2 | 0 | 1 | 125 | 0 | 125 | 0 | 607.48 | 482.48 | 0.79423
Old Closed Project | 10/14/22 | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014163 | 23111721 | Closed | 1 | 0.69444 | 1.44 | 0.44 | 64.8 | 125 | 0.30556 | 64.8 | 0 | 1 | 125 | 0 | 125 | 0 | 104.4 | -20.6 | -0.19732
Old Closed Project | 11/04/22 | 12/30/22 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools - Laredo | J00014180 | 23011002 | Closed | 1 | 0.049309 | 10.14 | 9.64 | 398.1 | 62.5 | 0.95069 | 398.1 | 0 | 0.5 | 62.5 | 0 | 62.5 | 0 | 579.6 | 517.1 | 0.89217
Old Closed Project | 11/04/22 | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens |  | Monica Johnson | TX-HOU | Harmony Public Schools - Laredo | J00014181 | 23011059 | Closed | 1 | 0 | 1.05 | 1.05 | 41.25 | 0 | 1 | 41.25 | 0 | 0 | 0 | 0 | 0 | 0 | 55.12 | 55.12 | 1
Old Closed Project | 11/04/22 | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Eleazar Guzman, Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools - Odessa | J00014182 | 23041034 | Closed | 1 | 0.5102 | 2.94 | 1.44 | 115.5 | 92.5 | 0.4898 | 115.5 | 0 | 1.5 | 92.5 | 0 | 92.5 | 0 | 277.8 | 185.3 | 0.66703
Old Closed Project | 11/04/22 | 03/29/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Lorenzo Hernandez | Monica Johnson | TX-HOU | Harmony Public Schools Sugarland | J00014183 | 23080891 | Closed | 1 | 2.0833 | 0.48 | -0.52 | 18.6 | 30 | -1.0833 | 18.6 | 0 | 1 | 30 | 0 | 30 | 0 | 29.92 | -0.08 | -0.0026738
Old Closed Project | 11/04/22 | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Dedric Bowens, Jesus Guadian, Samsoni Jean Claude, Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools - Katy | J00014184 | 23080892 | Closed | 1 | 1.3423 | 8.94 | -3.06 | 351.6 | 455 | -0.34228 | 351.6 | 0 | 12 | 455 | 0 | 455 | 0 | 871.92 | 416.92 | 0.47816
Old Closed Project | 11/04/22 | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Eleazar Guzman, Eliana Guzman, Oscar Nunez, Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools Houston | J00014186 | 23080907 | Closed | 1 | 3.0387 | 1.81 | -3.69 | 71.45 | 212.5 | -2.0387 | 71.45 | 0 | 5.5 | 212.5 | 0 | 212.5 | 0 | 144.2 | -68.3 | -0.47365
Old Closed Project | 11/04/22 | 12/30/22 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014187 | 23111782 | Closed | 1 | 0.12755 | 3.92 | 3.42 | 154.3 | 62.5 | 0.87245 | 154.3 | 0 | 0.5 | 62.5 | 0 | 62.5 | 0 | 237.84 | 175.34 | 0.73722
Old Closed Project | 11/04/22 | 01/27/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools Austin | J00014188 | 23130658 | Closed | 1 | 0.47619 | 2.1 | 1.1 | 82.5 | 125 | 0.52381 | 82.5 | 0 | 1 | 125 | 0 | 125 | 0 | 110.24 | -14.76 | -0.13389
Old Closed Project | 11/04/22 | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools Austin | J00014189 | 23130698 | Closed | 1 | 0.074404 | 13.44 | 12.44 | 528 | 125 | 0.9256 | 528 | 0 | 1 | 125 | 0 | 125 | 0 | 790 | 665 | 0.84177
Old Closed Project | 11/14/22 | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014379 | 23111961 | Closed | 1 | 2.0833 | 0.48 | -0.52 | 18.6 | 125 | -1.0833 | 18.6 | 0 | 1 | 125 | 0 | 125 | 0 | 29.92 | -95.08 | -3.1778
Old Closed Project | 11/14/22 | 05/29/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014380 | 23111847-001 | Closed | 1 | 0 | 2.1 | 2.1 | 82.5 | 0 | 1 | 82.5 | 0 | 0 | 0 | 0 | 0 | 0 | 110.24 | 110.24 | 1
Old Closed Project | 12/19/22 | 03/31/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens |  | Monica Johnson | TX-HOU | Harmony Public Schools - DFW Cluster | J00014385 | 23112109 | Closed | 1 | 0 | 2.84 | 2.84 | 112 | 0 | 1 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 334.04 | 334.04 | 1
Old Closed Project | 12/19/22 | 04/28/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens | Tray Giddens | Monica Johnson | TX-HOU | Harmony Public Schools El Paso | J00014387 | 23041098 | Closed | 1 | 0.15873 | 6.3 | 5.3 | 247.5 | 125 | 0.84127 | 247.5 | 0 | 1 | 125 | 0 | 125 | 0 | 544.28 | 419.28 | 0.77034
Old Closed Project | 12/19/22 | 03/31/23 | Open | Tray Giddens | Albert H Nguyen, Andrew Wells, Warren Wilson | Larry Noble, Monica Johnson, Tray Giddens |  | Monica Johnson | TX-HOU | Harmony Public Schools San Antonio | J00014390 | 23011107 | Closed | 1 | 0 | 1.05 | 1.05 | 41.25 | 0 | 1 | 41.25 | 0 | 0 | 0 | 0 | 0 | 0 | 55.12 | 55.12 | 1
Old Closed Project | 02/28/23 | 04/13/23 | Open | Abiodun David Babasola | Bryan Brown | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker | Adam Ko, David Gonzalez, Enrique Medina Valdes, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, Joel Hubbard, Samsoni Jean Claude | Joshua Parker | TX-DAL | Richardson ISD | J00014429 | 02308971 | Closed | 1 | 0.616 | 125 | 48 | 4375 | 2910 | 0.384 | 4375 | 0 | 77 | 2910 | 121.66 | 2910 | 250476.25 | 30000 | 26968.34 | 0.89894
Old Closed Project | 02/28/23 | 03/24/23 | Open | Abiodun David Babasola | Bryan Brown | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker | Adam Ko, Chase Davis, David Gonzalez, Enrique Medina Valdes, Gregory Posey, Harold Gomez, Joel Hubbard, Pablo Bernal, Zachary Newman | Joshua Parker | TX-DAL | Richardson ISD | J00014430 | 02309382 | Closed | 1 | 0.3192 | 250 | 170.2 | 8750 | 3378 | 0.6808 | 8750 | 0 | 79.8 | 3378 | 21.84 | 3378 | 494313.12 | 60000 | 56600.16 | 0.94334
Old Closed Project | 02/28/23 | 03/28/23 | Open | Abiodun David Babasola | Bryan Brown | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker | Adam Ko, Anthony Balogun, Chase Davis, David Gonzalez, David Lenihan, Enrique Medina Valdes, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, Joel Hubbard, Oscar Nunez, Pablo Bernal, Samsoni Jean Claude, Zachary Newman | Joshua Parker | TX-DAL | Richardson ISD | J00014432 | 02308970 | Closed | 1 | 0.34686 | 670 | 437.6 | 23450 | 9084 | 0.65313 | 23450 | 0 | 232.4 | 9084 | 0 | 9084 | 532234.6 | 160800 | 151716 | 0.94351
Old Closed Project | 12/21/22 | 03/28/23 | Open | Abiodun David Babasola | Bryan Brown | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker | Abiodun David Babasola, Adam Ko, Chase Davis, Felipe Ajche, Gregory Posey, Harold Gomez, Ishmeal Vaughn, Joel Hubbard, Juan Pomares, Pablo Bernal, Samsoni Jean Claude, Zachary Newman | Joshua Parker | TX-DAL | Richardson ISD | J00014442 | 02309383 | Closed | 1 | 0.23691 | 359 | 273.95 | 12565 | 4460.5 | 0.76309 | 12565 | 0 | 85.05 | 4460.5 | 0 | 4460.5 | 350664.57 | 86640 | 82179.5 | 0.94852
Old Closed Project | 01/18/23 | 04/14/23 | Open | Brian Willery | Jacob Parks, Jeffrey Holman | Beau C. Devillier, Brian Willery, Cristino Vega, Jacob Sennett, James Elmore, James Elmore, Lauren J Kennewell, Sophia Quinter | Brian Willery, Cristino Vega, Prince Owusu, Ron Loge, Sophia Quinter | Lauren J Kennewell | TX-DAL | McKinney ISD | J00014561 | Remote ISE Nodes Installation and Config | Closed | 1 | 1.2761 | 138.94 | -38.36 | 20455 | 24312.5 | -0.27609 | 20455 | 0 | 177.3 | 23862.5 | 0 | 24312.5 | 28911.2 | 33750.4 | 9437.9 | 0.27964
Old Closed Project | 01/13/23 | 03/23/23 | Open | Abiodun David Babasola | Bryan Brown | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker | Isaac Brown, Abiodun David Babasola, Aboobiada Ali Abdalla, Andrew Comeaux, Anthony Balogun, David Lenihan, Dedric Bowens, Devante Humphrey, Eliana Guzman, Enrique Valdes, Gregory Posey, Kai Rose , Kaustuv Ghosh | Joshua Parker | TX-DAL | Richardson ISD | J00014580 | Chromebook Install | Closed | 0 | 0 | 0 | -483.75 | 0 | 14702.5 | 0 | 0 | 0 | 483.75 | 14702.5 | 952.99 | 14702.5 | 1083000 | 234000 | 218344.51 | 0.9331
Old Closed Project | 06/16/23 | 07/14/23 | Open | Tray Giddens | Robert Berken | Camille Elizabeth Taber, Jeff Barker, Tray Giddens | James Adams, Tray Giddens | Camille Taber | FL | Mainline | J00015193 | NSK Santa Fe AP\Switch Install | Closed | 1 | 1.1739 | 34.5 | 9 | 2362.5 | 2852.5 | 0.26087 | 2362.5 | 15 | 40.5 | 1952.5 | 1359.03 | 2852.5 | 0 | 3723.32 | -488.21 | -0.13112
Old Closed Project | 04/24/23 | 06/02/23 | Open | Jim Blackwell | Albert H Nguyen | Ashley F Freeman, Jim Blackwell, Larry Noble | Ben Crouch, Moises Rodriguez | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00015332 | T&E - Wireless Controller Debug | Closed | 0 | 0 | 0 | -22 | 0 | 3017.5 | 0 | 0 | 0 | 22 | 3017.5 | 0 | 3017.5 | 0 | 2700 | -317.5 | -0.11759
Old Closed Project | 05/22/23 | 05/22/23 | Open | Jim Blackwell | Firas Abood | Firas Abood, Jim Blackwell, Khalid Abunaja, Meredith A Richardson | Andy Pham, Jaime Flores, Jim Blackwell, Joshua Hubbard, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio |  |  | Houston ISD | J00015369 | Synology Video Storage | Closed | 1 | 0.4 | 43.75 | 29 | 5781.25 | 1505 | 0.66286 | 5781.25 | 2.75 | 17.5 | 1340 | 10.4 | 1505 | 48323.52 | 4950 | 3434.6 | 0.69386
Old Closed Project | 07/05/23 | 07/05/23 | Open | Abiodun David Babasola |  | Abiodun David Babasola, Beau C. Devillier, David Babasola, Joshua Parker | Adiel Alvarez, Felipe Ajche, Gregory Posey, Harold Gomez, Jarshawn Newsome, Jesus Guadian, Josias Ajche, Josue Iglesias, Nathanael Morales, Samsoni Jean Claude | Joshua Parker | TX-DAL | Universal Service Administrative Company | J00015697 | ECF2290007795-SLD | Closed | 0 | 0 | 3000 | -349.5 | 0 | 10485 | 0 | 0 | 0 | 349.5 | 10485 | 373.84 | 10485 | 1200000 | 0 | -10858.84 | 0
Old Closed Project | 07/18/23 | 07/25/23 | Open | Tray Giddens | Mark J Chambliss | Dustin Huffman, Larry Noble, Tray Giddens | Jaime Flores, Tray Giddens | Dustin Huffman | TX-HOU | Cypress-Fairbanks ISD | J00016071 | Deploy 90 Phones at ES 58 | Closed | 1 | 0.98462 | 16.25 | 1.25 | 1506.25 | 1090 | 0.076923 | 1506.25 | 1 | 16 | 1030 | 0 | 1090 | 0 | 2428.8 | 1338.8 | 0.55122
Old Closed Project | 01/05/16 | 01/04/17 | Open | Crystal Gentry | [5 empty] | Houston ISD | J002287 | 8000106462 | Closed | 1 | 0 | 2 | 2 | 70 | 0 | 1 | 70 | 0 | 0 | 0 | 0 | 0 | 1406 | 0 | 0 | 0
Old Closed Project | 01/05/16 | 01/04/17 | Open | Crystal Gentry | [5 empty] | Houston ISD | J002288 | AAAQ12399 | Closed | 1 | 0 | 1 | 1 | 35 | 0 | 1 | 35 | 0 | 0 | 0 | 0 | 0 | 608.94 | 225 | 225 | 1
Old Closed Project | 01/05/16 | 01/04/17 | Open | Crystal Gentry | [5 empty] | Houston ISD | J002289 | AAAQ12458 | Closed | 1 | 0 | 1 | 1 | 35 | 0 | 1 | 35 | 0 | 0 | 0 | 0 | 0 | 164.25 | 50 | 50 | 1
Old Closed Project | 12/01/16 | 11/30/17 | Open | Crystal Gentry |  |  |  | Ashley F Freeman | TX-HOU | Fort Bend ISD | J004781 | 0000285912 | Closed | 1 | 0 | 1 | 1 | 35 | 0 | 1 | 35 | 0 | 0 | 0 | 0 | 0 | 528.37 | 20 | 20 | 1