## Sheet1
Consultants | Start Date | End Date | Job Status | Project Manager | Solution Architect | Resources Assigned | Resources Engaged | Account Manager | AM Region | Customer | Job Number | Job Description | Project Status | Project Complete % | Project Used % | Budget Hrs | Hrs Remaining | Budget Dollars | Actual Dollars | Hrs Remaining % | PSE Budget Amt | Travel Hrs Posted | Total Hrs Posted | Travel Amt Posted | Misc Exp Amt | Total Amt Posted | Hardware Rev | Services Rev | Services GP | Services GP % | DAS_Plus
Juan Saenz | 01/08/25 | 05/30/25 | Open | Lauren Lanzini Coffey |  | Juan Saenz, Lauren Lanzini Coffey, Matthew Duncan, Neel Shah | Juan Saenz | Neel Shah | TX-HOU | Texas Children's Hospital - VID#0000773548 | 200001600 |  | Implementation/Deployment | 0.35 | 0.53773 | 106 | 49 | 14020 | 7695 | 0.46226 | 14020 | 0 | 57 | 0 | 0 | 7695 | 0 | 0 | -7695 | 0 | 0.4658
Juan Saenz | 07/11/24 | 06/26/25 | Closed | Summer Abunaja | Matthew Duncan | Juan Saenz, Larry Noble, Matthew Duncan, Neel Shah, Osazee Eweka, Summer Abunaja | Juan Saenz, Lauren Lanzini Coffey, Osazee Eweka, Ron Loge, Summer Abunaja | Neel Shah |  | Amazon Web Services | J00018637 | AWS AppStream POC | Closed | 1 | 0.72077 | 148.8 | 41.55 | 19660.5 | 13988.75 | 0.27923 | 19660.5 | 0 | 197.25 | 0 | 0 | 13988.75 | 0 | 31024 | 17035.25 | 0.5491 | 0.6744
Cory Bradfield | 10/21/24 | 03/31/25 | Closed | Jim Blackwell | Firas Abood | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Firas Abood, Jim Blackwell, Larry Noble, Moe Izaks | Bryant Bush, Cory Bradfield, David Dobbs, Hector Rivera, Jaime Flores, Jim Blackwell, Luis Alvarez | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00019249 | Compute Infrastructure for VMS i-Pro Video Servers | Closed | 1 | 0.34069 | 296.46 | 223.46 | 37625.29 | 10257.5 | 0.75376 | 37625.29 | 28 | 101 | 3837.5 | 0 | 10257.5 | 2366146.96 | 75597.52 | 65340.02 | 0.86431 | 0.3407
Cory Bradfield | 12/08/23 | 01/31/25 | Open | Jim Blackwell | Firas Abood | Ashley F Freeman, Cory Bradfield, Cory Bradfield, Firas Abood, Jim Blackwell, Larry Noble | Ali Al-Haddad, Andy Pham, Anthony Lange, Bryant Bush, Cory Bradfield, David Dobbs, Hector Rivera, Jerald Garner, Jim Blackwell, Justin Cornish, Kevin Curtis, Kolawole Ayeni, Matthew D'Ambrosio, Nicolas Garakani, Paul Serres | Ashley F Freeman | TX-HOU | Fort Bend ISD | J00016827 | Dell Powerscale Deployment | Closed | 1 | 0.87086 | 182.2 | 70.03 | 21839.6 | 15891.45 | 0.38436 | 21839.6 | 46.5 | 158.67 | 9928.95 | 136.5 | 15891.45 | 2758826.44 | 35341.2 | 19313.25 | 0.54648 | 0.8709
Christopher Brown | 08/25/23 | 07/01/25 | Closed | Marshall Chuck Pugh | Steven Walker | Beau C. Devillier, Christopher Brown, Christopher Brown, Lauren J Kennewell, Lee McChesney, Marshall Chuck Pugh , Steven Walker | Christopher Brown, Marshall Chuck Pugh | Lauren J Kennewell | TX-DAL | Carroll ISD | J00014805 | Microsoft Office 365 Migration | Closed | 0.85 | 1.1652 | 46.13 | -7.62 | 6022.35 | 7208.75 | -0.16519 | 6022.35 | 0 | 53.75 | 7208.75 | 0 | 7208.75 | 0 | 8128 | 919.25 | 0.1131 | 0.8348
Christopher Brown | 09/06/24 | 09/06/24 | Open | Richard Keith Arnst | Steven Walker | Christopher Brown, Christopher Brown, Diana Berger, Eric Rodriguez, Richard Keith Arnst | Christopher Brown, Richard Keith Arnst, Ron Loge | Eric Rodriguez | TX-SOUT | Great Hearts Texas | J00015293 | MS O365 & AD Migration | Closed | 0 | 0 | 316.25 | -472 | 0 | 63455 | 0 | 0 | 0 | 472 | 63455 | 99.74 | 63455 | 14700 | 55249.2 | -8305.54 | -0.15033 | 0.5075
Tony Dean Skipworth | 05/08/23 | 03/13/25 | Closed | LaQisha Marshall | David Escamilla | Chad Hart, Christopher Kutalek, David Escamilla, Jennifer Huie, John Randall Bailey, Jr., LaQisha Marshall, Ron Loge, Tony Dean Skipworth | Bryan Mullen, Bryant Bush, Craig St. Rose, David Dobbs, Hector Rivera, Jaime Flores, Jorge Ortiz Cardozo, Jose R. Duarte, Justin Cornish, Karrar Al-Azzawi, Kevin Curtis, Kolawole Ayeni, Kyle Linder, LaQisha Marshall, Matthew D'Ambrosio, Nathan Dao, Paul Serres, Ron Loge, Sajjad Abo Dbs, Tony Dean Skipworth | Christopher Kutalek | TX-HOU | AlliantGroup | J00014081 | ACI Implementation | Closed | 1 | 1.4354 | 410.51 | -117.24 | 52391.25 | 65877.5 | -0.2856 | 52391.25 | 61.5 | 589.25 | 56372.5 | 1103.42 | 65877.5 | 1049545.84 | 62092.96 | -4887.96 | -0.07872 | 0.5646
Tony Dean Skipworth | 03/11/25 | 05/02/25 | Closed | Walter Clay Knight | Jeremy Williams | Camille Elizabeth Taber, Jeremy Williams, Walter Clay Knight | Tony Dean Skipworth, Walter Clay Knight | Camille Taber | FL | Mainline | 200002359 |  | Closed | 1 | 0.48913 | 18.4 | 9.4 | 0 | 1190 | 0.51087 | 0 | 0 | 9 | 0 | 0 | 1190 | 0 | 4254.1 | 3064.1 | 0.72027 | 0.4891
Osazee Eweka | 04/25/25 | 08/01/25 | Open | Brittney Antoinette Hickman | Matthew Duncan | Brittney Antoinette Hickman, Carmen Isela Brandt, Garrett Curran, Juan Saenz, Matthew Duncan, Osazee Eweka | Brittney Antoinette Hickman, Juan Saenz, Osazee Eweka | Garrett Curran | CA-LAX | Los Angeles Community College District | 200002640 |  | Implementation/Deployment | 0.5 | 0.33867 | 109.25 | 72.25 | 0 | 4840 | 0.66133 | 0 | 0 | 37 | 0 | 0 | 4840 | 0 | 22598.8 | 17758.8 | 0.78583 | 0.6663
Osazee Eweka | 08/15/22 | 05/26/23 | Open | Brian Willery | Matthew Duncan | Brian Willery, Charles Brown, Matthew Duncan, Steve J Rodriguez, Xavier A Trevino | Brian Willery, Charles Brown, Juan Saenz, Osazee Eweka | Xavier A Trevino |  | Amazon Web Services | J00013506 | AWS Cybersecurity Migration | Closed | 1 | 0 | 114.4 | 114.4 | 13156 | 0 | 1 | 13156 | 0 | 181 | 0 | 0 | 0 | 0 | 21218 | 21218 | 1 | 0.4178
Ron Loge | 06/27/22 | 03/21/24 | Open | Brian Willery | Jacob Parks, Jeffrey Holman, Kenneth Dieter | Beau C. Devillier, Brian Willery, Lauren J Kennewell | Brian Willery, James Elmore, Juan Saenz, Mohaymen Sodi, Ron Loge, Tony Dean Skipworth | Lauren J Kennewell | TX-DAL | McKinney ISD | J00013362 | Net-Pro-Srvc - ACI Configurations | Closed | 1 | 0.56599 | 1133.13 | 516.79 | 151009.25 | 85975 | 0.45607 | 151009.25 | 25 | 641.34 | 72023.75 | 258.81 | 85975 | 0 | 49989 | -36244.81 | -0.72506 | 0.566
Ron Loge | 08/14/23 | 05/15/24 | Open | LaQisha Marshall | David Watkins, Firas Abood, Michael Brett Beggs | David Watkins, Firas Abood, Kurt Sell, LaQisha Marshall, Lori Endsley, Michael Brett Beggs, Romar Roca, Ron Loge, Thomas McClanahan, Tony Dean Skipworth | LaQisha Marshall, Ron Loge, Tony Dean Skipworth | Thomas McClanahan | TX-CEN | Samsung Austin Semiconductor, LLC (SAS) | J00016213 | ACI Network refresh | Closed | 1 | 0.7372 | 648.74 | 188.49 | 84856.2 | 74426.25 | 0.29055 | 84856.2 | 18 | 478.25 | 71676.25 | 310.41 | 74426.25 | 0 | 127285 | 52548.34 | 0.41284 | 0.7372
Luis Ovalles | 05/01/24 | 12/13/24 | Open | Jason Esry | Michael Brett Beggs | Jason Esry, Jeff Barker, Karen Grant-Dennison, Michael Brett Beggs, William Davenport | Austen Howard, Carlo Enriquez, Cason Spencer, Jason Esry, Joan Brito, Joshua Osgood, Kebret Eshetu, Luis Ovalles, Patrick Shea Thompson, Quy Le, Remijio Hernandez, William Chris Roome | William Davenport |  | Hurst Euless Bedford ISD | J00018256 | Data Centers Modernization Project | Closed | 1 | 0 | 418.38 | 418.38 | 47059.1 | 0 | 1 | 47059.1 | 0 | 310.5 | 0 | 0 | 0 | 1538061.88 | 72866 | 72866 | 1 | 0.7421
Luis Ovalles | 07/29/24 | 06/05/25 | Closed | Jason Esry | Michael Brett Beggs | Jason Esry, Jeff Barker, Jeffery Alan Jorzig, Jeffery Jorzig, Michael Brett Beggs, Phillip Ma Lim, Tavis Jackson , William Davenport | Carlo Enriquez, Jason Esry, Jay Daniel De Leon, Jayden Colon, Jeffery Alan Jorzig, Jhon Genao, Kendall Walls, Luis Ovalles, Phillip Ma Lim, Quy Le, Tavis Jackson, Yonathan Fadel | William Davenport |  | Hurst Euless Bedford ISD | J00018726 | Data Center Network Refresh | Closed | 1 | 0.48324 | 305.23 | 157.73 | 36770.62 | 16992.5 | 0.51676 | 36770.62 | 0 | 221.5 | 0 | 0 | 16992.5 | 570092.93 | 42659.36 | 25666.86 | 0.60167 | 0.7257